## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
acc7b2b3-9b0d-4728-bde9-d8c15415da85 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
db22a2e3-fcec-4497-b9ce-acf1a1000fab | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
2a0bdfcd-d071-45d9-91d7-59fc5d291bdd | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
29dc5989-ab7c-4d89-88c9-3b4c9fea92b9 | checkpoint | site has been cleaned in advance of our arrival on site
3438b9dc-c5f7-49dd-b4a2-2a5fac5eef0a | checkpoint | Walls are plumb and level
a68bdc9e-f2e1-578d-9207-20ecebddb735 | note | IMPORTANT
3a52a44d-a222-4776-86a4-1d7b1cd916d8 | checkpoint | Tiling works running to programme - prior trades completed
4f3be667-fafa-44fb-bf2a-3199db934788 | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
11b378c9-8473-4cff-bba7-6c4560969765 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
f06a5d6f-b98f-4f8d-b8ec-beeaf3cbbf74 | checkpoint | Data sheets, of products, are supplied on site with TA's
83a84f92-b17c-47b6-a986-0ecd05efb568 | checkpoint | Inductions completed & Site Inspection checklist has been completed
ce31c036-9ab8-454b-b25b-2b26a66b77d9 | checkpoint | All tools tagged and tested - (photo's required)
26624961-0a0c-45bf-8d78-11bc1537092f | checkpoint | Tiler has current site safe - Input number and expiry
fa39fbce-b864-48a9-a6b3-fc7a48467318 | checkpoint | Tiler has correct PPE relevant to project.
7e850b8e-45cf-4acf-a1b0-89f54d4beda4 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
02b053a7-2d9a-41b8-91b8-c2ba679fdca2 | checklist | QA - Wall Tiling |  | QA - Wall Tiling
e64748b1-98f6-4a75-bf5a-7c7488f23f82 | section | Wall tiling installation
5f20b30f-3d63-4257-94cb-acb85ad5a3fa | checkpoint | Wall primed prior to installation - details added
75cac63b-e54c-4aa5-a8ca-7b5baacef2a7 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
47003a42-e76b-4354-ad2e-ecaffabd1854 | checkpoint | Mitre tiles at vertical corners
3258b4dc-2d41-4283-810c-c4249df36e74 | checkpoint | Installation of tiles to walls and as per drawings (full tile from the bottom)
33c15040-be2c-481e-814e-e38dd6423e98 | checkpoint | Grouting is consistent, neat and cleaned from surface.
7d917e6e-7c46-4721-ab30-fd6e46bd17bc | checkpoint | Tiling is completed, checked and supervisor to sign on
09e78dbd-79ce-4590-a8f1-41b2696ac2d6 | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
5f117086-a58a-4cf7-98d0-9e9b02041e6a | checkpoint | Correct tiles trim is supplied and installed as per drawings
852f6eb7-ea3e-4fed-8541-7d4017e32fdf | checkpoint | Area left clean & tidy
01be214f-0e80-4cb5-9421-c658d02bfb92 | checkpoint | Builders clean completed
4558dfde-8b22-4f95-b11d-a7a4c5d2131a | checklist | QA-Other Information |  | QA-Other Information
2457fcfa-70f5-4106-92ad-ec68e1d5bf84 | section | Other Information
6e3979d9-7d4a-40a2-aaad-830fb3a1514a | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
35c294ee-9d29-4c72-bf3e-ec50006a2fa8 | checkpoint | change of details and or instructions
7202602c-4829-4526-b824-c24dae4bbc6b | checkpoint | Site specific details to be added
daaea0f6-bf65-4c7a-8d98-82674a7df917 | checkpoint | Material Details - Notes to be added of materials used on site