## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
23a64eb6-e6af-48be-896d-5e27197e2d75 | checklist | Floor Preparation - FL2 |  | Floor Preparation - FL2
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
dc5e3c99-2a27-45ce-852e-3e7ce148dbfb | checkpoint | Is the area clean, and cleared, ready for necessary preparation
68125c47-64f1-41e7-b6c2-fce2729486b5 | checkpoint | Grinding, - completed before works (photo required) after works (photo required)
e8d3892f-9f74-49b3-9f2d-8e7a0b6dfd27 | checkpoint | Apply Mapei eco prim grip to floor prior to levelling (after grinding)
6ceb9a8b-29ec-40b8-a11e-6050b6c759a2 | checkpoint | Level Floor with Mapei Nivorapid (15mm at tile edge to 5mm finish at BOH)
c691634d-b0a7-4574-a383-e8ef5ca8c407 | checkpoint | Apply water based polyurethane to top of completed levelling.
3803254a-fe17-4872-a728-a485e6107ce5 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
71ab7e83-4827-417d-b991-54215fb79bc9 | checkpoint | site has been cleaned in advance of our arrival on site
93ac801b-bebd-4b56-af9c-3537cea1080a | checkpoint | Walls are plumb and level
65447ad8-4ad2-5aff-b819-98f749c162a5 | note | IMPORTANT
57049d64-f15a-43c9-90c6-8932a2598328 | checkpoint | Tiling works running to programme - prior trades completed
55417a1f-f0cb-4587-9d23-2c5409dc748b | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
2f8814f0-b8df-4e99-9333-fa21c25d7c11 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
b4e61fae-4c2f-438e-b64a-85d78506035b | checkpoint | Data sheets, of products, are supplied on site with TA's
8d3f9647-2669-4526-baab-573bae9e24a6 | checkpoint | Inductions completed & Site Inspection checklist has been completed
3e4575bb-d6d0-4728-ade3-90b143a43e68 | checkpoint | All tools tagged and tested - (photo's required)
1887fe74-562d-4a62-ac55-f7ea60782b9a | checkpoint | Tiler has current site safe - Input number and expiry
e0dda98c-98d1-422c-a4eb-329616c84ba7 | checkpoint | Tiler has correct PPE relevant to project.
b46aa76d-a065-4a0e-bb28-ae29c85d4e8a | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
06a0b0f7-dd55-474a-b175-2416bc1149c6 | checklist | QA - Other Information |  | QA - Other Information
19e81259-7ad8-48fc-98a4-dd23deb89731 | section | Other Information
48354e05-3520-4194-950c-0cea07c07a15 | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
f8d81299-935f-4f58-a6f9-8b7134bd2fe6 | checkpoint | change of details and or instructions
51f45ac1-2a7e-413e-8394-3935e40ec0db | checkpoint | Site specific details to be added
24f65ef7-4942-4c0d-b206-831336b4d629 | checkpoint | Material Details - Notes to be added of materials used on site
165fc902-21b7-4bd5-90c4-feb574b22c07 | checkpoint | SSSP/TA forms attached
e089ce8d-b156-498a-b479-6b20bdfcb262 | checklist | QA - Tiling Installation |  | QA - Tiling Installation
ecf45921-1991-4580-a3ae-283d5c9d69dc | section | Tiling to floors and walls
b4b05e3a-1b99-4473-a61e-4490a49aefbf | checkpoint | Prime floor substrate prior to installation
92fa0149-bbc6-465a-9f8d-4c863e5d6a10 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
a47a9672-85da-453a-9386-a45481a2cfc9 | checkpoint | Specified product used with notched trowel or required product
e47d517b-9acd-44ec-a6fa-4923b62a57e0 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
87cef766-6aa0-4798-8e2d-318cd8592b56 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
265dfe5c-46a9-459d-85e7-53b6453a908b | checkpoint | Install tiles to shopfront entry and along shopfront to mall floor
d26d2fca-f413-4400-b828-ef3fbfaaa7f9 | checkpoint | Install tiles along shopfront to mall floor
e208cf1f-53ac-417e-bdae-5196bbea056b | checkpoint | Install tiles to walls as per drawings
6d81cdaf-0cd4-45d8-865e-b3babfd6ad1d | checkpoint | Trim - Install Black trim to both sides of floor tiles
38581287-1903-4565-bd6d-aaf8ad4d698d | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
e8825e25-2ea8-404d-ab2b-ae23742e0a22 | checkpoint | Grout is consistent throughout and no missing grout.
124656af-9b91-497c-a778-826a30402f13 | checkpoint | Tiling completed, checked and Supervisor sign off
88c7845b-653a-4f5e-9baf-be39554770cb | checkpoint | Silicone is completed to all tile junctions where required
5ecb89df-4a2c-47b3-b34a-32d7bd028852 | checkpoint | Area left clean & tidy
9dba425f-9157-44cf-ac89-7ef38bd54e69 | checkpoint | Builders clean completed