## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f6049ff5-e051-4ca4-9331-101f1a2e0b49 | checklist | Other Information |  | Other Information
d1c28dc1-33d1-4087-aa2e-007010295f4f | section | Other Information
ff31f3a9-de2f-4ac0-8b81-5f22de22b4a1 | checkpoint | Variations or extra works added into folder - all works and materials noted
5f4f1c66-7d41-4061-9dde-084192f5b394 | checkpoint | change of details and or instructions
2d5658b9-6e96-4f6b-ad3c-7d50a4cc57de | checkpoint | Site specific details to be added
0dbe1321-c9c5-4bbc-b2e0-407f2bf3c3ba | checkpoint | Material Details - Notes to be added of materials used on site
845e61b3-ecb9-4d2f-ba04-6ed7251ca818 | checkpoint | SSSP/TA forms attached
2280337f-fc03-4661-aea0-b15602cdcb24 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8cb0bda6-c87e-4fe7-a64a-158ed17d9dc1 | checkpoint | site has been cleaned in advance of our arrival on site
80708e4f-eb3e-4d3a-9ec3-a58e7aae3c09 | checkpoint | Walls are plumb and level
24c81cb3-bd84-58f1-b4dd-18452dc1e099 | note | IMPORTANT
b334601f-6146-4a67-ae85-aa75ce17f73e | checkpoint | Tiling works running to programme - prior trades completed
9e28d640-bb6c-43a1-99b7-054088eab18f | checkpoint | Has prior trades QA been signed off by main contractor
76bdcaaa-1c83-410f-a46d-6ced15c3326b | checkpoint | Gib compound and sanding cleaned up from rooms
b775e9ee-f2be-4746-8df9-67c9ce41d289 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
9edc5e97-ae7a-4764-bfd4-ffcd4b3ba0c5 | checkpoint | Inductions completed
7d1d3039-9a04-41ec-8b90-68665d621d31 | checkpoint | Site Inspection checklist has been completed
76f5e7e6-8f76-40db-96f2-6b2e44e498a7 | checkpoint | All tools tagged and tested - (photo's required)
19502769-ec82-465e-87c6-70827802d454 | checkpoint | Tiler has current site safe - Input number and expiry
07a8f96b-e292-4e18-aa42-32e83c038b31 | checkpoint | Tiler has correct PPE
6b6de35c-7daf-465f-87e4-ddbcbcbadc54 | checkpoint | Correct drawings supplied as per onsite
41ca2986-c91c-4341-8cfc-e01f108f9bce | checklist | QA - Floor Prep Bathroom |  | QA - Floor Prep Bathroom
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ba15aa48-ee80-46b5-878e-f8b3f1dbd642 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
4ed16472-a4f5-4e1a-8651-b6a938c8333c | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
c410e123-dec5-4476-b7c2-f4e248fbe7a4 | checkpoint | Screeding to shower to create base (take photos)
9cf1ef90-62a5-4703-9b4d-868ca473f9a4 | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
495151c3-6bce-43ae-aa7b-93e6c1d30580 | checkpoint | Grinding completed before works (photo required) after works (photo required)
e43f8d25-b59b-4753-b9f5-3552d63e6c24 | checkpoint | Floor levelling completed - hours and bags used to be recorded
2f9a726b-7571-487c-8693-7096ea13225d | checklist | QA - Tiling Installation |  | QA - Tiling Installation
f3194011-0e1d-45df-971d-df447eacdf38 | section | Tiling bathroom floor and walls
4424a115-e8d3-4e23-8558-b1b2f62a9379 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
dda68317-c157-44ed-937a-80b3d598ae63 | checkpoint | Specified product used with notched trowel or required product
1a3cd669-e8e3-4afb-87f5-0be1eaf51f08 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
e933f705-0475-4060-99e8-901bf8a900bb | checkpoint | Install tiles to floors including cuts to shower falls
31c9d976-8b0d-43d5-9340-cc28df9c7d89 | checkpoint | Install tiles 2400 high to shower walls
87b8e3b7-d6c5-4576-9730-bde5bb37f028 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
ec1b8811-07b6-40a4-b405-76f779a33f88 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings
fdf0e5de-ac85-444b-8a29-72581316e713 | checkpoint | Install tiles to walls - 1200mm high
c40901e0-6f9d-4bf8-98c9-bcf5f4ebf100 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
7d5880e9-8b1d-43ae-95e5-269986c25c4b | checkpoint | Grout is consistent throughout and no missing grout.
b0057d9a-57db-461e-a294-b8dff480a736 | checkpoint | Tiling completed, checked and Supervisor sign off
36e54abe-ad6b-4e68-b687-e5221fa61df0 | checkpoint | Silicone is completed to all tile junctions where required
4ba2eb8f-7516-4fc1-ad54-0a18c2e1d578 | checkpoint | Area left clean & tidy
761fc5d7-7a2c-462d-8f28-950dfdb36f21 | checkpoint | Builders clean completed
54191080-fb16-48f3-8a8f-28a712bdd026 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d75548c9-bcab-4c95-adcc-cc198af9b4c6 | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
2c7d2bbd-d134-4ff9-98a9-edb24b2eeb26 | checkpoint | Waterproofing coat # 1 applied to floors and walls (take photos)
6a9dd251-cff8-4fa1-af55-713959d86957 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
43dad42d-838c-49d0-b4a2-963f0a77157f | checkpoint | Flood tests, if required, undertaken and photos provided.