## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
694a3921-68b9-4176-abaa-8f588909af1c | checklist | Balcony Tiling |  | Balcony Tiling
54eda78d-c4fa-4579-b3c7-18feff30edc5 | section | Tiling to Balconys
fc678ec9-9d21-49b9-be55-15b096322fa5 | checkpoint | tiles set out according to latest drawing - always check revisions on site
5d355c7a-1c05-4d9c-9568-76e61b1c1a38 | checkpoint | substrate straight, aigned off by MC
1bdbebdb-b01a-4968-92c4-09e05b742b14 | checkpoint | Install tiles on nurajack system
0ebd258f-973d-4240-aec9-86979ad9c619 | checkpoint | area left clean & tidy
7c66ac99-f3de-458c-a1d4-50aef46a1a29 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
708b0205-1dda-4da1-8c09-96e9c3c2945e | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
c6182091-c23a-4733-a669-8440f87e8bb2 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3a5f450f-68fc-4db3-aa10-593ee0cb4094 | checkpoint | site has been cleaned in advance of our arrival on site
f9a2599f-6048-4290-8708-2c544bc2121f | checkpoint | Walls are plumb and level
3e4b4b4f-5254-52f8-8633-1265f9d3602c | note | IMPORTANT
372270bd-f007-4adf-b4a9-a36786e576d8 | checkpoint | Tiling works running to programme - prior trades completed
bcaa0886-b786-43eb-aba8-0d5c6e63b3bc | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
b6f060e8-90ba-4a9b-afe0-0e3510455274 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
29354567-87d8-456f-9114-78404f82c34e | checkpoint | Data sheets, of products, are supplied on site with TA's
d1d4adae-ca61-435f-9a03-aa823de7d037 | checkpoint | Inductions completed & Site Inspection checklist has been completed
f1b2310b-834b-4a4c-a94b-21d7bd13bada | checkpoint | All tools tagged and tested - (photo's required)
8b5532ce-8400-44a0-ba20-522796a78e86 | checkpoint | Tiler has current site safe - Input number and expiry
1ee8db57-81aa-44d8-863d-65d5d48b34e8 | checkpoint | Tiler has correct PPE relevant to project.
40d02a8d-b4ab-42e5-bcb4-8e4e7a7467eb | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
df06304f-b59c-4241-9c42-98fbcd341aaf | checklist | QA - Laundry Installation |  | QA - Laundry Installation
98d774b9-f66c-4f83-aeab-74c0579223bf | section | Laundry Installation
33d4e3ae-28a0-4546-9fc4-b66bfbefa43d | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
a0a37820-41b4-4d05-aac2-453dd51c879a | checkpoint | Installation of tiles to splashback and as per drawings
b65f6c13-7a73-45b5-b15b-81642a122f31 | checkpoint | Grouting is consistent, neat and cleaned from surface.
25c61e18-9c8f-4b49-b8d9-b0d5541025a2 | checkpoint | Tiling is completed, checked and supervisor to sign on
9d902a4e-9b7f-4c00-9b9a-a0a01c665da4 | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
bc5fdac8-39c2-4364-bd0d-a583b799c843 | checkpoint | Correct tiles trim is supplied and installed as per drawings
13ef0412-f4fa-404c-ae04-0afbf45219fc | checkpoint | Area left clean & tidy
71b75a1d-85cb-45cb-86ca-449086ee37a3 | checkpoint | Builders clean completed
f1fc61ee-e025-42f6-ad44-4f49b6c5d713 | checklist | QA - Splashback Installation |  | QA - Splashback Installation
5c58c081-3292-47bf-9100-c1359555a130 | section | Splashback Installation
880a82fe-af23-43ea-a93c-e29c361c9af8 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
d10fdd1a-971c-4b2b-bccf-de74ae548341 | checkpoint | Installation of tiles to splashback and as per drawings
76fd14da-ba9f-4285-b6e3-e6c859ad4fce | checkpoint | Grouting is consistent, neat and cleaned from surface.
95409b86-2f4f-49c4-a95a-80f2edf62199 | checkpoint | Tiling is completed, checked and supervisor to sign on
095803ca-6f76-43de-8e00-4cc6d16f7cd1 | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
9d62d84a-d4cb-43fa-b089-034e303365d8 | checkpoint | Correct tiles trim is supplied and installed as per drawings
958fd730-90de-453f-bd10-23e48fd9437c | checkpoint | Area left clean & tidy
85e587d8-7c84-44f7-887a-304915449b32 | checkpoint | Builders clean completed
4d030f56-93c7-4958-95e2-4c97490d37e1 | checklist | QA - Tiling Installation - Bathrooms |  | QA - Tiling Installation - Bathrooms
0c2c7ba1-bcfb-462b-ad43-62f5f0f96e2d | section | Tiling to floors and walls
9841e851-7fce-40ad-bc6c-b843ae668f5c | checkpoint | Tiles set out according to latest drawing - always check revisions on site
5fc75671-5116-49f0-8c81-3038cd521fce | checkpoint | Specified product used with notched trowel or required product
3151a358-ca81-4b84-9d76-035641406ccc | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
a28faa93-4fbe-4501-a3bd-66ccc7fe1bc0 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
74d81d14-6521-457e-be58-d9bee77766fa | checkpoint | Install tiles to floors as per drawings - Keraflexmaxi SG1
a4319509-f16d-4506-bdb9-f68f872acd63 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
a18b8e6b-cf05-4670-959c-2501ca99c8cf | checkpoint | Install tiles to walls as per drawings - keraflex maxi SG1
28f81e7b-bf3d-4a41-a398-62bebcc2949a | checkpoint | Grout nominated is the correct colour and applied evenly and correctly -
10e42cfa-e86d-4ac2-ad71-8ed077db1760 | checkpoint | Grout is consistent throughout and no missing grout.
90543090-bf1d-4715-88aa-87eb20ee1564 | checkpoint | Tiling completed, checked and Supervisor sign off
07425edf-954f-4522-9a84-07758baa5049 | checkpoint | Silicone is completed to all tile junctions where required
12b85e64-79bd-4b7c-afcd-11c97d8d2328 | checkpoint | Area left clean & tidy
32ec4c02-ce74-416e-ad21-67c838cbeb46 | checkpoint | Builders clean completed
0739cf50-a674-4e90-a4a8-a4c5707a9984 | checklist | QA - Tiling Installation - Toilet |  | QA - Tiling Installation - Toilet
f8f375e8-3c11-414c-ac40-8acd7026ab2b | section | Tiling to floors and walls
ba3338b3-a96e-4d8f-8cb5-b73fa1f307fb | checkpoint | Tiles set out according to latest drawing - always check revisions on site
1d84c9e0-4678-490d-aa22-6398cfd56a80 | checkpoint | Specified product used with notched trowel or required product
8d5b7e7c-807d-4a6c-a5db-c57e5c43060d | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
15eaecf4-4f94-4761-851c-5a8410559fbc | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
a2e2bff7-9936-458b-a218-c96373e189b3 | checkpoint | Install tiles to floors as per drawings - Keraflexmaxi SG1
e3891bcc-f6be-4f01-9260-28f0bc343ff9 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
1a3f6fd2-1568-4a23-86af-1c120c4fbd46 | checkpoint | Install tiles to walls as per drawings - keraflex maxi SG1
a2307b44-5a12-40f2-813c-a4954a0b06ce | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
74e95f52-8e46-4691-85ab-c3fdd06b6940 | checkpoint | Grout is consistent throughout and no missing grout.
35975b67-30a1-4a10-98f7-9900f8964211 | checkpoint | Tiling completed, checked and Supervisor sign off
ad7e9943-3418-4c7b-8425-925504bcfdf1 | checkpoint | Silicone is completed to all tile junctions where required
02e8e7dd-58f7-40db-bd69-1dc17fc56a7b | checkpoint | Area left clean & tidy
171d0633-ea99-47a7-954b-2e8953418c8e | checkpoint | Builders clean completed
e998c571-754f-4521-b14f-f13c24a32dd6 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b1bff358-bf72-42d8-b780-aef69a556709 | checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
e77bc8ce-769f-4aa3-a74c-b03a0e87230f | checkpoint | Gaskets have been installed to floor flange and wall plumbing fittings
9624cbfa-dcdb-45da-a515-681a0531c474 | checkpoint | Correct waterproofing is supplied as per project specification.
005c867a-e065-4497-84e5-3596d61f3bb6 | checkpoint | Waterproofing coat # 1 applied to floors, upstand and walls (take photos) Ardex Superflex WPM002
8283cf4d-be97-42da-a45f-3b31e4645caa | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos) Ardex Superflex WPM002
35d1c72d-32ba-41b5-beb1-347c3ac7f6be | checkpoint | Flood tests, if required, undertaken and photos provided.
1c0f8de0-f1bd-49a0-9c8a-1ea24c90b1ea | checklist | QA-Other Information |  | QA-Other Information
134fde3f-2df4-44f6-b79c-57690b02043f | section | Other Information
0f754ac7-daeb-4858-b6ef-8fe50b667c4f | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
63d98138-f3dc-42d1-b1f0-c4dc4e4514ef | checkpoint | change of details and or instructions
241a3295-9b14-4592-b344-a88a395149ac | checkpoint | Site specific details to be added
ad3b4aa2-77ab-4226-90fd-459cff4fb831 | checkpoint | Material Details - Notes to be added of materials used on site
4b952cf6-27e1-46fc-99fb-69a3c9969a29 | checkpoint | SSSP/TA forms attached
714bf9f4-3206-45ff-8938-8a87b4a448aa | checklist | Wall/Floor Preparation |  | Wall/Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4f6406a2-50a8-4243-a06e-c55dfb3d6e8e | checkpoint | Is the area clean, and cleared, ready for necessary preparation
11173cd2-9e5a-4024-93d2-ebd202aaafea | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
b737c1c4-246c-401d-af68-ddd42e4d3340 | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
8b5ac221-7a90-4a46-beca-5eb7960028c5 | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
16d710ab-f05d-4c19-bfc7-720d665bca76 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
4db4271b-7118-4af4-a841-b810303398c7 | checkpoint | acoustic underlay Ardex DX 70 installed as per drawings
524a5538-2d68-4de5-93c7-23dbc8893db1 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
de60529f-92bf-427b-b480-e2eaf9531c21 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)