## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d7bcc60a-d45f-421b-b234-6afde2511c58 | checklist | Other Information |  | Other Information
2fd48154-f1d9-4019-b7af-e06beb38bceb | section | Other Information
478bb5da-20d2-46d5-8d63-b7dc6aa02657 | checkpoint | Variations or extra works added into folder - all works and materials noted
bc3fb7db-ae00-4d30-b916-4b213533404e | checkpoint | change of details and or instructions
49bcaaba-f127-4d02-8458-f291903c0dc6 | checkpoint | Site specific details to be added
2ddfa87a-f734-424d-8023-f12ae8a24b04 | checkpoint | Material Details - Notes to be added of materials used on site
b63179ae-9438-4dc3-9b6a-6cf2cf82320e | checkpoint | SSSP/TA forms attached
d3b561df-ec84-4d56-a4c7-69a28d2eb37b | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fcd2e640-a32e-4f0e-8d50-26e3ea5dab74 | checkpoint | site has been cleaned in advance of our arrival on site
1ab93f05-49d9-4e7d-8d24-42e4a019d505 | checkpoint | Walls are plumb and level
7f1c360c-59a6-548a-8708-e8ace0ca833d | note | IMPORTANT
b0496ff0-f252-409c-958a-31eecc9baf4f | checkpoint | Tiling works running to programme - prior trades completed
a8dbdb0c-0dbe-4a54-baec-6d62646478b1 | checkpoint | Has prior trades QA been signed off by main contractor
a05b77c4-2751-453e-896a-75862dea048c | checkpoint | Gib compound and sanding cleaned up from rooms
8b358c4c-7f3f-4fe9-b2a1-f6edc5c79a3b | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
9e485079-4b2c-4c95-8bef-1eedc012db67 | checkpoint | Inductions completed
761bc76d-ea1c-4860-906f-a94a1c2a8e38 | checkpoint | Site Inspection checklist has been completed
aaf21a85-f6d0-4cda-9824-73c52ae473ff | checkpoint | All tools tagged and tested - (photo's required)
00fc2b8d-ce2f-47e7-86b6-c17852865f92 | checkpoint | Tiler has current site safe - Input number and expiry
334492df-f079-4759-8a82-7c3c07cc990c | checkpoint | Tiler has correct PPE
4b3aadff-5522-4525-a7ee-10abe90c4554 | checkpoint | Correct drawings supplied as per onsite
2eef665c-e350-412b-b4c3-77b41d5580aa | checklist | QA - Splashback Installation |  | QA - Splashback Installation
26fa3fd7-759f-40d7-91b6-ec2f96b7c783 | section | Splashback Installation
b71e897f-8d63-4959-a569-34b575a7c90f | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
66e1c86f-dafa-44c9-b5b1-a589eab22e16 | checkpoint | Splashback Tiles set out as per drawings
89c9d771-2e0b-4c2f-9c72-3a9a6399d919 | checkpoint | Tiles to walls
39461e87-7000-44d9-8b90-2de6bb67b40c | checkpoint | Tiling is completed, checked and supervisor to sign on
027cdf18-7745-4fa8-a4b0-ee1d0568855f | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
07f68831-6181-4a36-bc1c-8c67c05fbd50 | checkpoint | correct tiles trim is supplied and installed as per drawings
77ca0747-a98e-433d-a068-15c39594cc3e | checkpoint | Area left clean & tidy
54c65532-1193-439b-98e5-624a27b7baf9 | checkpoint | Builders clean completed
b358d11f-7929-4573-a4b2-79f56e53b79e | checkpoint | QA Kitchen Island
dca1cc78-bff5-4c96-af53-8e25283ad920 | section | Kitchen Island Tiling
7404fddc-fca5-4451-b62a-791df9d70737 | checkpoint | Substrate straight, signed off by MC, and ready for installation (insert notes for remediation if required)
309e72c2-2450-40ce-a7f9-7414b300913e | checkpoint | Set out tiles and install as per drawings
92734e3d-efcc-4214-847a-efa69501aa6c | checkpoint | Tiling is completed, checked and supervisor to sign on
ab06eaf5-0c8e-4828-98a5-5e7540850012 | checkpoint | correct tile trim is supplied and installed as per drawings
36a60b31-03d5-49b9-a3a2-f7a62fd51d08 | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
20b74259-cfb6-4170-9405-ca620dccdc37 | checkpoint | Area left clean & tidy
e4de6a9c-6af0-4e09-ac18-e1f5d9c3eea4 | checkpoint | Builders clean completed
2a12f08d-1827-4df6-a005-2c9a120496d1 | checkpoint | QA Joinery Unit
5feb45c8-cf1d-432f-be00-419388cb61da | section | Joinery Unit
616a7a8d-58d4-4f73-bcc8-f94731330152 | checkpoint | Substrate straight, signed off by MC, and ready for installation (insert notes for remediation if required)
2d947ef8-456d-42f4-be06-541157489447 | checkpoint | Set out tiles and install as per drawings
15c7ca75-e162-4b13-b591-432537443222 | checkpoint | Tiling is completed, checked and supervisor to sign on
857fe79f-fd87-4408-bbb3-ab14d761d865 | checkpoint | correct tile trim is supplied and installed as per drawings
f16cdd16-a7db-4869-811f-22ae163c2207 | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
8ba404dd-8335-41dd-9a65-bfa62139e8b4 | checkpoint | Area left clean & tidy
dbaa9fcc-3bc7-4fc6-9419-75bd3ffe8a42 | checkpoint | Builders clean completed
66970d5f-e535-4973-92e8-192b07ac1128 | checklist | QA Joinery Unit |  | QA Joinery Unit
bce4b36d-3319-4808-a808-37527452e40b | section | Joinery Unit
d229b76c-be6d-46aa-8e05-0df47c0eacdc | checkpoint | Substrate straight, signed off by MC, and ready for installation (insert notes for remediation if required)
03f69c7b-f96e-4d8d-98d2-85c5593e5439 | checkpoint | Set out tiles and install as per drawings
c358c86f-55c6-4c26-8bfa-2d970df397a5 | checkpoint | Tiling is completed, checked and supervisor to sign on
b358b716-b1af-4a42-ad33-08c1bab10085 | checkpoint | correct tile trim is supplied and installed as per drawings
dd0d1828-7916-4940-ab2d-95a980633724 | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
3eb32c87-0529-4ef5-ac68-b6ceff3cb56c | checkpoint | Area left clean & tidy
3bee8b04-d54c-400e-bc61-a4149da6e9a1 | checkpoint | Builders clean completed
2f051a85-6476-4496-ac89-84fd01bb68fb | checklist | QA Kitchen Island |  | QA Kitchen Island
2fddf84a-5cc8-4ba7-8453-13994f0492f9 | section | Kitchen Island Tiling
b748719c-1a87-47d9-87e6-fccfe5d8ce42 | checkpoint | Substrate straight, signed off by MC, and ready for installation (insert notes for remediation if required)
4e7e40ea-88d6-4a46-a8a4-3d0e01836a30 | checkpoint | Set out tiles and install as per drawings
8675923f-6b0a-49c0-abb4-9b2a67095cad | checkpoint | Tiling is completed, checked and supervisor to sign on
8b51036e-48ae-4930-b125-8f5262fb5204 | checkpoint | correct tile trim is supplied and installed as per drawings
838135e0-f81e-473c-894d-49dc62aec7fd | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
7fcd9c01-952d-4d1b-aff3-7abfaa2c1c4e | checkpoint | Area left clean & tidy
1ce2d512-43d7-40e5-8d80-fec6dfc3bae0 | checkpoint | Builders clean completed