## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c95a5f07-d8da-43ca-93c8-4e0511f6d09b | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
119507d1-6689-4481-91c9-9d9814fbe14c | checkpoint | site has been cleaned in advance of our arrival on site
5835cbe9-300c-43bb-a271-053dcd764eeb | checkpoint | Walls are plumb and level
055c84d2-5d3e-5bfb-8dd3-6dfe951c4d26 | note | IMPORTANT
5c1b4cbf-ea1b-465e-9ac8-24ecf9e17460 | checkpoint | Tiling works running to programme - prior trades completed
6a8cb9b2-6b89-4269-87ab-cb53b77ca774 | checkpoint | Has prior trades QA been signed off by main contractor
613f9f95-f81f-4bce-abaf-8833632459f4 | checkpoint | Gib compound and sanding cleaned up from rooms
0c2a06f3-97a6-47c5-a55d-208b2e20deb6 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor
710f4966-67a3-4ab0-8cf8-d7f70b493d5b | checkpoint | Inductions completed
2cdc4caa-a54e-46bf-a811-0eac1d3d0439 | checkpoint | Site Inspection checklist has been completed
b91c2182-0dbe-4443-82c8-434beed688ea | checkpoint | All tools tagged and tested - (photo's required)
b5eb3fb6-d26c-4855-b1f8-efbad49265ac | checkpoint | Dust control tent has been set up and tested
7654d1e1-5e51-4984-a9be-02cac981a326 | checklist | QA - Acoustics |  | QA - Acoustics
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8b3bcd41-1dfe-459c-b1af-056061861312 | checkpoint | Floors lasered and fall within BRANZ tolerance over stated distance
f70b6a2f-0bb6-4b58-99e6-e6be9517207d | checkpoint | Floors are clean of debris on arrival
0c68bc1f-7dc0-4410-a5b1-4e6b55f99c6c | checkpoint | Install Mapesonic CR 4mm acoustics to floors (ID 1802)
077f0bc0-92b5-4b76-af71-bec9123941e7 | checkpoint | Joints are tight and flush
ff9dd56b-1726-4570-bacb-d806ae9be9cc | checkpoint | Perimeter 6mm silicone installed flush and neat
758483b1-a8df-4396-aff8-3432d55d2349 | checklist | QA - Floor Prep Bathrooms |  | QA - Floor Prep Bathrooms
336d53cb-4509-48ee-8dff-6e85088b864f | section | Floor Preparation
e18bae2e-3f4e-4238-ab72-b00f9027038a | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
04da2540-ca65-4c0e-99e0-8a5b3ec48be1 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
0919f3ba-6f24-4c63-9c24-3bce9da58a9b | checkpoint | Has screeding been completed to shower at correct height and falls - R4 screed
0a7947ee-929b-4bb0-a62b-c9b7587628d6 | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
998800d1-a2e3-4979-aa97-c3ae70586395 | checklist | QA - Floor/wall Prep Bathrooms |  | QA - Floor/wall Prep Bathrooms
4ede9756-be15-44df-b423-0a842caaf1d3 | section | Floor/Wall Preparation
713d8cc6-07dd-482d-93d9-118cb4c9b267 | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
4fc5064e-a5fd-4c57-971e-ca5c7878d456 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
1ed47150-03d7-4ba9-b581-aaf11fbbeee9 | checkpoint | Has screeding been completed to shower at correct height and falls - if required
71a03e2a-69b6-4615-93bf-b4590bc706af | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
f5b30fc5-6460-41ca-ae15-987b70047f09 | checkpoint | Grinding completed, and signed off by Slava, to areas as per markup
8788a58f-3ce2-4214-94a2-279324574136 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
93e8556c-4682-4347-ba32-60b15502d75d | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
7157c0e6-3c08-4071-84c1-962fb2e9a495 | checkpoint | Waterproofing coat # 1 applied to floors and walls (take photos)
8318bb4a-0c37-471a-86fe-68432fd06f71 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
299254f4-f901-4a51-8c85-54d53829f9b6 | checkpoint | Flood tests, if required, undertaken and photos provided within conqa
d39e87a3-6ade-45b5-b7c9-b5073eebee15 | checklist | QA Tiling Installation |  | QA Tiling Installation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d540c9ad-f256-410d-8ea3-78a8a897246b | checkpoint | Floor Tiles set out according to latest drawing - PROCURE drawings required
d0b5f0f3-64b6-4f7f-b3c4-776818ff6498 | checkpoint | Wall tiles set our according to latest drawing - PROCURE drawings required
f18a45bb-9d83-4092-8ffd-a5ee1be8ec7f | checkpoint | Specified product used with notched trowel or required product
ac19871d-278f-48d6-b67d-8681ff47ac92 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
5102ef95-1b82-480c-b776-d67c442dd143 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
24ef394f-7ec0-4e83-af8e-6f82bf688c83 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings
182b8491-b564-44f8-ac1d-26bb15b11779 | checkpoint | Tiles to shower niche are tidy including trim installation
db840b90-dcfd-4731-a481-76a9fde13f63 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
24cdad5b-9338-45c7-bb0c-98ddc4bcf8d2 | checkpoint | Grout is consistent throughout and no missing grout.
16740bb0-777d-4642-b35e-b71c195ce410 | checkpoint | Tiling completed, checked and Supervisor sign off
473c9cab-b82d-4b66-90a6-b7968b9fe680 | checkpoint | Silicone is completed to all tile junctions where required
a5476f18-b5bd-4bc5-888e-b70f9e20f66c | checkpoint | After grouting, a final clean to remove all grout haze to floors & walls in completed by TAL Tiling
0f33a8a9-a2f4-4241-8ed2-ee3d0cdfdb27 | checkpoint | Area left clean & Tidy by TAL Tiling
69262dc4-3019-4ec0-98de-0a245aef401e | checkpoint | Builders clean completed
2ea24b6f-a472-4cec-b581-fa4354928860 | checklist | Tile Supply |  | Tile Supply
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ff4bf067-2187-407d-a0f8-e01522229109 | checkpoint | Tile photos on arrival to site (before unloading)
491aa3af-512e-4d71-ae65-76b0965eb53e | checkpoint | Tile photos inside site once loaded into site
8cec42a3-03a2-4231-ac15-003b2e66e4b6 | checkpoint | Input numbers of pallets total upon delivery - Grey Matt Impact 300x500
ac356a45-3127-45e1-819c-da7b3e1d3e4c | checkpoint | Input numbers of pallets total upon delivery - Scripter Rebel 300x600
15bc35d5-03cc-4021-bf8e-e1407e9481be | checkpoint | Input numbers of pallets total upon delivery - Willow Waters Mosaics
a7c5785a-d154-4469-b001-5aa2bc1e50be | checkpoint | Imput numbers of pallets total upon delivery - Wooden Grey Hexagon