## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
52134683-9b52-4540-ad07-c39b072a054b | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c4bf5599-68a8-4ad2-97ae-9ae18c49880c | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
4fcf343f-700c-410b-9860-3463851154d3 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
34b9ed51-e3fe-4f7d-ac33-2c82fd76ea24 | checkpoint | site has been cleaned in advance of our arrival on site
fc4cbfa1-c53f-4933-be7f-732a013566c4 | checkpoint | Walls are plumb and level
fa0084a0-ffc2-5283-a36c-db56c3027e06 | note | IMPORTANT
df02793b-561e-4e3f-bb37-0350efc6364e | checkpoint | Tiling works running to programme - prior trades completed
c3641f1f-bbb2-44ff-b1c6-ee0a952a1bda | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
94ce6af3-c53d-4c11-9318-46ac3a443b3a | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
750a065c-aa07-4d20-b4be-eb61d006646d | checkpoint | Data sheets, of products, are supplied on site with TA's
b94934d9-d260-43c4-8e7e-1bbbb85f37f0 | checkpoint | Inductions completed & Site Inspection checklist has been completed
0cac5072-45ef-4099-bb58-a3818ce4783e | checkpoint | All tools tagged and tested - (photo's required)
fdf953b3-03ae-43f8-9455-2e18daed7d2f | checkpoint | Tiler has current site safe - Input number and expiry
0070b1a7-de05-4f5a-a96c-ae634829b8e4 | checkpoint | Tiler has correct PPE relevant to project.
45b016b0-f9e6-4b7d-91ae-4324f9c8b892 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
795d43fb-0204-4ba2-80d0-c8bfdf6971b0 | checklist | QA - Tiling Installation |  | QA - Tiling Installation
f6ebdc20-6829-467e-b514-95af9203d9a0 | section | Tiling to floors and walls
6b3e9aad-6732-4cdc-becf-d44dd925d053 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
76545614-a5ba-4894-b210-4d2e90d4bff0 | checkpoint | Specified product used with notched trowel or required product
b2096f26-e4ac-4499-ac58-c5102c67c7f0 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
73fd5eab-c061-4e8f-9104-60f4a45e9ad0 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
13d1f173-5059-48bd-b8fe-db8ae3be8150 | checkpoint | Install tiles to floors as per drawings
5764b6b4-c22c-4d2e-a627-50a4d721183b | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
ecb83b3c-5f13-4737-97a1-d31e185c3d4b | checkpoint | Install tiles to walls as per drawings
a1276dc1-66a4-4fe2-8da9-65eecc080b24 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
8777c817-97d2-43c3-b00d-bc183ae2fc5e | checkpoint | Grout is consistent throughout and no missing grout.
81d49d33-1996-410e-8160-81ad8f4a61f7 | checkpoint | Tiling completed, checked and Supervisor sign off
eff2033a-2a26-4387-88db-558b09b18249 | checkpoint | Silicone is completed to all tile junctions where required
83ed6351-7a69-4de7-89ec-af45de7e0dc7 | checkpoint | Area left clean & tidy
eb54fa32-a530-42e6-972e-f7a3c4b803b3 | checkpoint | Builders clean completed
bf4936ab-8387-4c71-8d73-f84b06104317 | checklist | QA-Other Information |  | QA-Other Information
24e7b90a-4ad7-4628-92d8-baf8be331403 | section | Other Information
9a2669b5-19b7-4e03-b486-d5cb5bb2a77f | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
d10f6e8b-95c3-4db5-8e62-7f968a5c1bc1 | checkpoint | change of details and or instructions
71fc3915-3084-4285-8bdf-0a0a4cb12e82 | checkpoint | Site specific details to be added
38a78b3b-50b0-415c-9377-407e77882254 | checkpoint | Material Details - Notes to be added of materials used on site
0ef125c7-762a-4361-86e6-a4fd57f39052 | checklist | Wall/Floor Preparation |  | Wall/Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8d6913e7-4a49-47e0-9f2c-c44f9d2d63ed | checkpoint | Is the area clean, and cleared, ready for necessary preparation
8d4db05c-99c5-4f1a-9035-1e6eaffcf076 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
f6c11000-98ac-4687-9292-755fc5a1b066 | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
51207946-0d66-4419-8152-93d72a6ccd28 | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
9814cb47-5785-4446-8fc1-fd1cf84e55d7 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
a3f84d92-a1b7-42dc-a53f-383219d4161b | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
babfd6e1-2609-4eb8-9a23-3e9c1945da22 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)