## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Mamaku Passing Lane - Pavement Renewals - Unbound Granular Overlay | itp |  |  |  | Yes | ITP - Mamaku Passing Lane - Pavement Renewals - Unbound Granular Overlay Rev 0.02 | 0ddfc32c-b9e3-4548-ad2d-f99a93bc860f
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 08eaefeb-dfc6-52c8-9a9b-a26477f9d6e5 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 30c1c816-0e4c-5f86-81f7-d314e11ae544 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | e91d63f2-000b-5989-bfc1-cdee6f970211 |  | note | FREQUENCY - Before work commences
label | 7288fd11-9bd1-5694-b9b3-259f70bfd255 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date
label | 632daafa-5d91-5a9e-8d22-6fa57df0e66d |  | note | TYPE - V
label | 5ca02137-3240-590b-b05c-6432ba999ffd |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 8169f3ff-6f9b-59b0-847c-7ffc57e8d0f8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 89e67b19-5904-5c92-9f6f-aa1b526bd480 |  | note | METHODS OR REFERENCE - Contract Specification
label | 0300cc3a-e160-5543-9010-33b16da98854 |  | note | FREQUENCY - At least 24hrs before establishment or work commences
label | 4a778c12-94a6-5180-bd00-53bf95b31bc6 |  | note | ACCEPTANCE CRITERIA - Principal's Acceptance according to guidelines in Appendix 6.3
label | bbd8c70d-6933-5d04-b2b8-2e6b116c8d23 |  | note | TYPE - H
label | e6809c1d-c05b-5625-a624-015d0ba004e1 |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site.
label | ea16be77-fdbc-5503-a5ef-1c9c5cf4871d |  | note | RESPONSIBLE PERSON - Renewals Manager
label | cff3f26c-633d-53bf-a2b8-7d08880f7c12 |  | note | RECORDS / REMARKS - NZTA to approve.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Notification of Intention to Start Work
label | 97358566-dac4-5e80-ba4d-438c9187f3d1 |  | note | VERIFICATION ACTIVITY - Notification
label | 629b979c-1c76-55fd-98ed-eb04cec32b0f |  | note | FREQUENCY - Before work commences
label | fcebc2a4-2fc1-5ca2-b430-0886a8d41e66 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents
label | facf5a5e-1bda-5541-964b-cbc140fcc447 |  | note | TYPE - H
label | 46d382ee-ba2c-5797-ae4e-72d911fa9fd7 |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site.
label | a4c5300b-0278-583f-b029-f3e11f1b0c13 |  | note | RESPONSIBLE PERSON - Renewals PM
label | ce31f2e0-07e7-5633-b8f1-9fcd6754593c |  | note | RECORDS / REMARKS - NZTA to approve letter drop before distribution to residents.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Traffic Management / TMP
label | 835c312c-da59-55f5-a3d3-900e3b2d54e0 |  | note | VERIFICATION ACTIVITY - Visual check
label | ba413eac-9ace-5c47-891e-6172ab828e27 |  | note | METHODS OR REFERENCE - CoPTTM
label | ff5642c9-e8b9-5833-a96e-064f3d099afc |  | note | FREQUENCY - Before work commences
label | a2e9a371-8b54-59f4-85ba-a1c84ba84193 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved, Plans approved, Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely
label | f23471e1-8c46-5132-a6fa-386d3e4789fb |  | note | TYPE - H
label | 1683137a-d011-5e98-9eb4-10de4f6b4a67 |  | note | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | c3918d18-fd2c-5f1c-9fe9-9ec272378901 |  | note | RESPONSIBLE PERSON - Renewals PM / TMC
label | 0a347d3b-d800-58e7-8008-02d70aa0f907 |  | note | RECORDS / REMARKS - CAR No., TMP No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Design Report Approval
label | e51a308f-06be-5f87-bd92-266acdf2ffd1 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 981f9495-58a4-58b5-80c5-084e99f817bd |  | note | METHODS OR REFERENCE - NZTA NOC Rehab Catalogue Design & Treatment Approach
label | 09e7631f-580e-531f-9ddb-417344566598 |  | note | FREQUENCY - Before work commences
label | 3e7789f4-62a8-5076-979a-30cf94cf837a |  | note | ACCEPTANCE CRITERIA - Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document
label | 462c3761-ed9a-5c6b-a2b9-189e99b35635 |  | note | TYPE - H
label | 4b58aace-8cd1-50a0-a2a2-af9c79ec239a |  | note | DESCRIPTION - Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers
label | 885bea78-222d-5c0c-adb8-694cc1cea735 |  | note | RESPONSIBLE PERSON - NZTA Network Manager & Accreditied Designer
label | ec293ea9-d93c-574f-a607-e552916c21ee |  | note | RECORDS / REMARKS - NZTA Approval to Proceed NTC No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Seal Design Approval
label | 828de8dd-e37e-5a63-8ff2-f2dd274bb068 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 9b122875-6e4b-5e10-8c4d-72be7af56940 |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Regional Sealing Manager
label | a6c00c73-7a6e-58a2-902c-18d2bcced083 |  | note | FREQUENCY - Before work commences
label | a0df1cd4-e69b-56f6-8437-ec49dc78db46 |  | note | ACCEPTANCE CRITERIA - Downer Regional Sealing Manager reviews and signs off on Seal Design proposed.
label | 512d14e9-0787-58c8-b5ba-feb14bfdd15e |  | note | TYPE - H
label | eeb9f2de-1a4e-5ebe-aa2f-a71ba2392ddd |  | note | DESCRIPTION - Hold point - Review and approval of seal design completed
label | a2671dde-aaf9-5a54-9213-c68f24c92c36 |  | note | RESPONSIBLE PERSON - Regional Sealing Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Project Manager Handover
label | 21365e4b-e87e-53d6-a5af-500f5436a11d |  | note | VERIFICATION ACTIVITY - Confirmation
label | b5cda862-1e2d-5be6-a30e-0d2e081b02fe |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Designer to PM
label | d5db2b3a-90e9-5ac1-a981-f68e27518e94 |  | note | FREQUENCY - Before work commences
label | 238af437-27a5-561c-a27a-0fe580ce2d75 |  | note | ACCEPTANCE CRITERIA - Downer Technical Services Team Designer reviews and signs off on Handover.
label | 5530818c-a7e4-585f-b6cd-25dc1f11a91c |  | note | TYPE - H
label | 07942a50-b419-57a7-b0e6-c4f2f3d7ba18 |  | note | DESCRIPTION - Hold point - Handover completed
label | 9193e47a-e217-545f-87a6-4d79b2613ad8 |  | note | RESPONSIBLE PERSON - Regional Engineering Team Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Crew Pack
label | a1ea7db5-9b75-56d5-aa56-4ff2ef09f855 |  | note | METHODS OR REFERENCE - Items to be included:
label | db6d4f9d-bd61-5c08-a484-ff0470eeaed7 |  | note | FREQUENCY - Before work commences
label | 452c7b1f-f70b-5381-8b0b-f8b554cee2c9 |  | note | ACCEPTANCE CRITERIA - Approved TMP
label | 4fc9ce9d-9bff-5c8c-99f3-a63ba31c0b71 |  | note | ○ Services location plans / Marked out
label | d22df00e-d73f-5602-83d6-aca720674a30 |  | note | ○ Approved RQP
label | 06652813-6ed5-5eff-9176-055d187ffa60 |  | note | ○ Approved for Construction drawings & Pavement Design
label | 858170f0-75d3-58a6-94a4-8d6cf64e2562 |  | note | ○ Ramm data
label | a5f7425b-9983-5731-ad88-b1f4ec1213cc |  | note | ○ Approved ITP
label | 7ff917aa-6959-5428-a4db-f069c3895ddf |  | note | ○ Crew Briefing Plan
label | 83e7a8c6-2b4e-5169-abcb-ebab7483750b |  | note | TYPE - H
label | 3336da7a-808a-55a5-95b0-178c46d1fa53 |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Setout / Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Setout
label | 8031c041-e1d5-5ecf-b49c-02d1b69176b4 |  | note | VERIFICATION ACTIVITY - Survey
label | 52c4bcb8-375a-5520-b142-c017583ccc35 |  | note | METHODS OR REFERENCE - As per approved drawings
label | 66ffc71b-5f23-5c34-8255-6d5a4e16a7f2 |  | note | FREQUENCY - Per installation / Site
label | 7f503e80-8805-5dbc-8eb0-90bf9a91b578 |  | note | ACCEPTANCE CRITERIA - Design strings /design surface model loaded for machine control
label | bb19a3cd-23db-562c-82a9-97481634a940 |  | note | TYPE - V
label | 98a689ac-ec9c-5d95-88c3-1d603e28c51d |  | note | DESCRIPTION - Machine control requirement. Downer surveyor required for MC upload and verification of model operation
label | 7ff972cf-14fc-5913-9c4c-0441a012eb2b |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-status |  |  | checkpoint | 2.2 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | a8a6ed85-c0eb-53e1-ba17-25a0964f39c3 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 280f3019-dbc7-5b2a-914d-4eb7f6be0840 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 03a4f4fa-5f72-50d1-bfde-26cb8891f44a |  | note | FREQUENCY - Before work commences
label | fd906fcb-3554-5e96-8fa9-e21625bc88e6 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | cf2b66f0-2c37-5fef-89b4-6d6c53ca9611 |  | note | TYPE - H
label | 6f79d47c-8cb6-56f6-ad4f-9eeecc598e0c |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
label | 3c935f89-f0ce-556d-bb24-6d6c0d6c8d59 |  | note | RESPONSIBLE PERSON - Renewals PM / Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | 61219f07-032b-57f2-ae30-a8a691cb0cdc |  | note | VERIFICATION ACTIVITY - Notification
label | 0185a592-1dbd-553b-9ace-452df37d5167 |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | d4a063db-a647-5510-906e-30a9265e8e50 |  | note | FREQUENCY - Before work commences
label | be70b833-8038-55a2-9c37-ea92234b7404 |  | note | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | 06d82ee4-569e-51e1-bc55-b5f70cd108af |  | note | TYPE - H
label | fde7b47b-322b-5472-911b-a4b7eb11c1cd |  | note | DESCRIPTION - Where risk of cultural discovery
label | 1b0f383f-5cbf-5e24-b2c2-f5e321f7e7c0 |  | note | RESPONSIBLE PERSON - Renewals PM / Communications Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Archaeological Risk
label | 279a8a79-4336-5322-a2df-4abb3c79864f |  | note | VERIFICATION ACTIVITY - Toolbox meeting
label | dd1ff11d-4074-55c4-b5fb-6be807a2881f |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | 9da9e39c-4d12-5686-a7c9-76bf2ad0a5e7 |  | note | FREQUENCY - Before work commences
label | a5b7e3ec-3e3c-5dd2-bcfb-a727ec2f779c |  | note | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | a0dd72a9-1691-5701-bdd4-9363bd665168 |  | note | TYPE - H
label | ab2f100a-6c53-54ef-bbeb-eb78c5d51813 |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
label | 98bf9490-2d41-5509-a7ff-c7bd5072d4aa |  | note | RESPONSIBLE PERSON - Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Traffic Management / Signs Setup
label | a7c0f8e7-5a76-5c04-91cf-b295690292a1 |  | note | VERIFICATION ACTIVITY - Visual check
label | fe1635fa-bf59-579e-b4b8-b6e1306a0f96 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | e02aad0a-662f-52d0-9ae2-bb8cedbdd725 |  | note | FREQUENCY - Before work commences each day
label | 7ddd8f14-364e-530d-9292-26ad034f5cb4 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 64a41e72-7684-50a9-a0c4-e3a8cad6a900 |  | note | TYPE - H
label | 040d980a-a1a5-53c0-9142-12fe00a05209 |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | f41a7353-1ac6-5b73-9adc-ce7d59945915 |  | note | RESPONSIBLE PERSON - STMS
label | d220ac0b-3b04-53ef-91a4-1c88dbcff9d4 |  | note | RECORDS / REMARKS - Daily site record sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (1)
label | f8649302-7501-55d0-aa15-61d8c137e7ae |  | note | VERIFICATION ACTIVITY - Visual check
label | 2a178f29-f051-5067-9a43-4d11944b2fbc |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | 52d68592-88e9-534e-9d2a-2e2c1f661ed9 |  | note | FREQUENCY - Before work commences
label | f70d01b8-9c8e-5f5d-89e1-acc4c543cf46 |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | 36e9a1f5-1e9e-5ba2-b29c-952fa5131006 |  | note | TYPE - H
label | f1ef1482-2bdf-51e3-9ff0-ef3ddfd4b006 |  | note | DESCRIPTION - Hold point - Walkover required ahead of MS Civil establishment
label | 886c848f-c8ff-50d2-a409-9e50817c3adb |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | eaf22591-77fc-5a46-aceb-05b1c667c008 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (2)
label | 5ce4b1f9-ede2-5a92-afc1-20af5e0c0310 |  | note | VERIFICATION ACTIVITY - Visual check
label | cd075500-7627-5337-8de3-0426bfaf9463 |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | 6799d818-23f0-5408-b216-ca9adf8869b2 |  | note | FREQUENCY - Before work commences
label | 76bf11c6-7952-53cd-bd61-19fe1b86ad21 |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | 55f7414c-9a9f-51bc-ae33-88cb9b7c8fd0 |  | note | TYPE - H
label | 3c24e6b5-8e4d-5eb6-8a89-2f221e295f60 |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until walkover completed
label | c1ddc456-9699-59eb-abbd-8b7843e5f73e |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | 71ff0c6a-96f6-54ca-a246-f5c272c07d4e |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminary Works
checkpoint-status |  |  | checkpoint | 3.1 - Shoulder Stripping / Vegetation clearing
label | 3202f7de-607e-5f8c-955d-4b3ab9e36521 |  | note | VERIFICATION ACTIVITY - Visual check
label | b676e8f6-eb4b-5cfa-95a1-1bf4f50000a8 |  | note | METHODS OR REFERENCE - On site
label | ef1961e4-1b24-5a6c-b92e-c8ff1b3081b1 |  | note | ACCEPTANCE CRITERIA - Shoulder stripping as per drawings completed
label | 9ce2e7fa-7303-5241-ad8c-98557aed15a2 |  | note | TYPE - V
label | 7023ee7e-141f-59c8-b59c-856e5e45c76e |  | note | RESPONSIBLE PERSON - Site Foreman
label | 2f232092-80e7-58a3-8c92-b22bb4c29997 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
checkpoint-status |  |  | checkpoint | 3.1 - Site pavement A/C digouts
label | 474f47c4-fcc4-51c7-bd20-57d12697c741 |  | note | VERIFICATION ACTIVITY - Visual check
label | 1ff482a3-cab7-5b6b-9896-1c8be343c8f4 |  | note | METHODS OR REFERENCE - Check RAMM records for depths
label | c624b57a-3d21-5ad7-ba28-37e6dc210ae8 |  | note | FREQUENCY - Before Overlay work commences
label | 7059d898-9b8e-52ce-8a46-24099d0eaf5d |  | note | ACCEPTANCE CRITERIA - Work completed prior to overlay contractor onsite
label | b139917b-143d-5368-988f-63e7a7393f4c |  | note | TYPE - V
label | af2fe149-3f15-543a-aad6-b642c95453b7 |  | note | DESCRIPTION - A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed
label | ea924cd2-e989-59d1-8cd3-6782e3aa98c1 |  | note | RESPONSIBLE PERSON - Construction Supervisor / Site Foreman
checkpoint-group |  |  | section | 4 - Culvert extensions / Headwalls / Flumes
checkpoint-status |  |  | checkpoint | 4.1 - Excavation Inlet / Outlet Gradients
label | 03f9e1ae-8a06-55df-94f1-ce50ab31d743 |  | note | VERIFICATION ACTIVITY - Survey
label | 66ed3225-e0e8-53e2-a85e-e0b9c21b74b7 |  | note | METHODS OR REFERENCE - NZTA F/3
label | b534caa0-ecd0-5716-8501-bd64a1738960 |  | note | FREQUENCY - Once
label | 5c0834ce-2ff1-5ba2-96d3-087c7377c5ef |  | note | ACCEPTANCE CRITERIA - Consistent gradient in and out
label | c13e6796-523e-5a7e-b25a-3012aa38528c |  | note | TYPE - H
label | ae548e53-b9d9-5eac-9ad0-5c57663d7a1d |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | f9066c9c-d8cd-53e3-b6b5-005280e9946c |  | note | RESPONSIBLE PERSON - Site Foreman
label | f01d566c-f04d-5791-bb63-42d4838c12f9 |  | note | RECORDS / REMARKS - Required No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Pipe materials / class
label | c2abbe86-cfe8-510a-b27a-f2778e504082 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 3ae1f78b-000a-559e-8f9e-022a63eff572 |  | note | METHODS OR REFERENCE - NZTA F/3 2.1
label | fd62b97c-ecaf-5ec9-8267-41cd77a0356d |  | note | FREQUENCY - Once
label | 2742b5f0-be38-556e-9903-f80e7c62e8f2 |  | note | ACCEPTANCE CRITERIA - Meets appropriate AS/NZ standard reletive to specified type
label | f7d55f57-408d-5555-be93-b50118a58f6e |  | note | TYPE - V
label | be535f73-b0dc-5217-b9fd-7e0ef44eaac7 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 3399bf00-7028-5d00-a115-96fe772b61d1 |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-status |  |  | checkpoint | 4.3 - Bedding contact
label | efc2e78e-1da9-58d6-babe-ac1061489d0a |  | note | VERIFICATION ACTIVITY - Visual Check
label | 232eb424-701f-55a6-b8a2-603da807efa7 |  | note | METHODS OR REFERENCE - NZTA F/3 5.1
label | f65b8d0b-9c80-58d3-8152-aff05bc091dc |  | note | FREQUENCY - continuous
label | 08e40d56-bdba-5a48-90c6-67716456a1ef |  | note | ACCEPTANCE CRITERIA - uniform contact over full length of pipe
label | c8a733fd-7c5c-54cc-8352-ba8d500604e9 |  | note | TYPE - V
label | 8a2e0c16-239b-52aa-bab9-193e8b140fdd |  | note | RESPONSIBLE PERSON - Site Foreman
label | e452d08a-dae5-5ff6-8e30-5d45a9297683 |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-group |  |  | section | 5 - Subsoil drainage
checkpoint-status |  |  | checkpoint | 5.1 - Trench
label | b3963e02-0468-5062-98eb-fce1122978ea |  | note | VERIFICATION ACTIVITY - Visual
label | 414513b0-99a2-5af8-b202-262dcd5b750c |  | note | FREQUENCY - each site
label | 96313dea-360c-5ab4-ab9d-9c041a2a768b |  | note | ACCEPTANCE CRITERIA - Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm
label | d8667a73-b1dc-5b40-8502-c7ef9f42e527 |  | note | TYPE - H
label | 0005ea96-80f0-59d9-96ae-e5f68443d7b5 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | 5a850522-fec1-5bf9-a025-5c3f4e3a7a63 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 57f40306-c1b5-5e17-9a03-73b1387602f8 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Drainage material
label | 5f4f2561-030c-5b82-9091-2679efbf271e |  | note | VERIFICATION ACTIVITY - Visual
label | 74d7ad91-598c-5573-b6cb-97254e6b6e5a |  | note | FREQUENCY - each site
label | f81e3453-2372-55b6-a5ab-e2de801258fc |  | note | ACCEPTANCE CRITERIA - 7-12mm clean filter material ( grade 2 - 4 Sealing chip
label | 37d643e7-f52a-593a-825b-514101a91450 |  | note | TYPE - H
label | d10040ae-c1e6-5006-86c5-595f8ec83435 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | 21b585aa-197d-5872-859e-a02f92cac576 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 10c18a1d-08a5-5d6c-834f-5fa453f5b23b |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Pipe type (1)
label | dd1d7ac0-b112-5b9f-bd30-632607b26cfc |  | note | VERIFICATION ACTIVITY - Visual
label | 3e281363-beb1-54f3-9832-c7ae463cfe49 |  | note | METHODS OR REFERENCE - Diameter as per the design drawings
label | 0fe8dfcb-7615-5058-9060-dc55097b811d |  | note | FREQUENCY - Use outside traffic Lane
label | e0d20bee-fc6c-5bbc-89ba-4e4114ceabe7 |  | note | ACCEPTANCE CRITERIA - Docket to confirm
label | a4f2bfee-6845-52af-9557-93392b5fbda1 |  | note | TYPE - V
label | 740c9637-2188-5443-b61b-8eb3f36385ff |  | note | DESCRIPTION - "Nova flow"
label | d8f26d21-72cc-57c3-a331-797a9ad25443 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 76b1f0c4-171f-5c6a-b631-a34526bb799c |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-status |  |  | checkpoint | 5.3 - Pipe type (2)
label | 0e209fff-f84c-52da-9b45-fa9d20ec9903 |  | note | VERIFICATION ACTIVITY - Visual
label | 10228b13-1f6c-5402-849b-f101cd73495b |  | note | METHODS OR REFERENCE - Diameter as per the design drawings
label | 9fc772a0-a1b4-5558-9f87-1471ca52d25f |  | note | FREQUENCY - Under traffic lane
label | 7722c9bd-1211-547d-91a7-90cc2f9717b8 |  | note | ACCEPTANCE CRITERIA - Docket to confirm
label | 81ae50ec-3553-50f0-824e-373c4ebbb8e4 |  | note | TYPE - V
label | bbd634f9-a76d-562a-b736-e1a65352a2e6 |  | note | DESCRIPTION - Nexus
label | 547a4073-b360-5c05-aa7d-8cdb477eb0db |  | note | RESPONSIBLE PERSON - Site Foreman
label | 38278ecd-66a5-5fa1-ba56-3d8caa8bd0b0 |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-status |  |  | checkpoint | 5.4 - Filter Fabric
label | 86182b47-9a44-53e2-9fa0-00557b784595 |  | note | VERIFICATION ACTIVITY - Visual
label | 9ac70457-9e2b-51f7-af3d-31f0b03f7e08 |  | note | ACCEPTANCE CRITERIA - 150mm lap, top of fabric minimum 150mm below FSL
label | abb7136b-9b54-5c3a-bd78-087bf4925758 |  | note | TYPE - H
label | cc432739-fff8-5ebd-ac55-2f68c41baf2f |  | note | DESCRIPTION - Hold Point – Visual check prior to reinstatement
label | bfa775ed-7b53-5669-b0b3-cf5c5cbae902 |  | note | RESPONSIBLE PERSON - Site Foreman
label | c630b5b3-18ce-5147-b954-3664da2ecb0b |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Outlet
label | 01d12036-a49f-5e60-b145-a27f2268abd4 |  | note | VERIFICATION ACTIVITY - Visual
label | eb4ac5d1-4cdf-55df-b80d-66f07ae9a3fd |  | note | ACCEPTANCE CRITERIA - Connect to sump barrel, culvert of construct Concrete Apron
label | 1c2d8218-f06d-5620-af36-5cdd692d5c05 |  | note | TYPE - H
label | 08381d81-8144-5ca3-a49e-1b4007d1511f |  | note | DESCRIPTION - Hold Point – Visual check prior to reinstatement
label | 2976f839-4bea-5c26-92ed-dad3048e8eea |  | note | RESPONSIBLE PERSON - Site Foreman
label | 8b6c1d1f-04b6-5e83-bbcb-58b3139ee836 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Flushing / Cleaning eyes
label | 49f465ac-4b35-5b36-85f3-7365faaf8c02 |  | note | VERIFICATION ACTIVITY - Visual
label | 72a82aa5-bb74-5b13-9042-56368fc4c2e5 |  | note | METHODS OR REFERENCE - To be placed & constructed as per Approved Drawings
label | b3f991cb-6219-5af6-9672-b4417d8974ae |  | note | FREQUENCY - Each free end
label | f6420272-a283-5ce9-b186-d23c149fad3f |  | note | RESPONSIBLE PERSON - Site Foreman
label | 833a4165-10a2-5925-b673-cca46d13032f |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-status |  |  | checkpoint | 5.7 - Reinstatement (1)
label | f9daec86-319a-5287-888f-926014eb8519 |  | note | VERIFICATION ACTIVITY - Sealed Pavement
label | 31f77a88-91ff-5162-860b-63b2f5c8dc34 |  | note | ACCEPTANCE CRITERIA - Pavement matches surrounding, surface with AC or 3/5 chip
label | 6228ef8c-7668-50cd-a21d-f0fe3cee24b5 |  | note | TYPE - V
label | 617c218c-b13b-55aa-bb98-51beef6d3ded |  | note | RESPONSIBLE PERSON - Site Foreman
label | 08437fd7-9aae-5d2c-8e59-dce6af592f00 |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-status |  |  | checkpoint | 5.7 - Reinstatement (2)
label | 08fd2d41-c0e8-5813-8be2-d2d700c69d09 |  | note | VERIFICATION ACTIVITY - Berms and shoulder
label | f1c2b5c6-67a4-56e3-9f97-d07edb236f5c |  | note | ACCEPTANCE CRITERIA - Top min 150mm impermiable backfill
label | 3f9a6364-4a07-55c8-a3f0-1e6305090840 |  | note | TYPE - V
label | 3e5419fb-57b1-59aa-bacd-881977062e5d |  | note | RESPONSIBLE PERSON - Site Foreman
label | 15f8bd82-9579-5506-8ec8-bef7bdb4313e |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-group |  |  | section | 6 - Preteatment of Insitu Materials
checkpoint-status |  |  | checkpoint | 6.1 - Cut to Waste Existing Seal
label | 33847798-c3cd-5eab-896e-64e378d46795 |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | 594bffd5-09ac-5ab7-9544-569a51f456e0 |  | note | FREQUENCY - Prior to material import
label | 1bd23e85-9e40-5343-b9e8-8592e02b6b19 |  | note | ACCEPTANCE CRITERIA - No unsuitable material remaining
label | 47d251f5-0187-5fbb-93f5-72eb3e1267d7 |  | note | TYPE - V
label | 63f400fa-e731-5a66-9b6a-df63e75f786d |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 6.2 - Undercut unsuitable areas
label | e4b69a5d-49c1-5990-94b3-876958ca1ecf |  | note | VERIFICATION ACTIVITY - Visual Inspection/ measurements
label | 5520669b-822e-5102-a938-e2b65732a773 |  | note | METHODS OR REFERENCE - Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table
label | 134d7295-a23f-5d1e-8881-eded5334950b |  | note | FREQUENCY - Where required
label | b402ec1b-34f9-53e5-9c34-fb61928fea53 |  | note | ACCEPTANCE CRITERIA - All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to
label | 3af5f840-f6f8-5dbb-bc9d-fcbe75ef72be |  | note | TYPE - H
label | 69633272-b2e8-52f1-9c90-52434e1dbc9b |  | note | DESCRIPTION - Hold Point - Organise site walkover with NZTA MCM prior to dig outs commencing. Variation agreed.
label | 3d46f752-4e2f-5f5f-b130-1a53f604aa20 |  | note | RESPONSIBLE PERSON - Renewals Manager / Site Foreman / NZTA MCM
label | 0f1d0de3-d79e-5c4b-96b6-5952b7d4bf19 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Imported Basecourse Materials Testing
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (1)
label | b92612fb-a0e0-503a-a747-897925745717 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | 038b076b-30eb-5662-b6b3-1353491b0748 |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.10
label | 1e3391d4-6c6e-57c0-aae4-f71c991f34c7 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 6cd6375b-6684-590c-808c-63377b89d2e7 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 2b7947c8-c395-5d85-9c79-6b1f05cafcd4 |  | note | TYPE - V
label | 9bce6eed-3a56-55dc-b272-97382593e90b |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | ebea5518-d7cc-51f4-9ce0-9e00590ef26c |  | note | RESPONSIBLE PERSON - Renewals PM
label | ea2b86a5-293f-5428-91dc-1e8b9c206597 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (2)
label | 37c79ac9-9b07-5be1-aea5-6b52527e7b04 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | 272e73dc-f9f8-5cd3-a007-e17b663df7e9 |  | note | METHODS OR REFERENCE - NZTA M/4
label | 8683a944-cbef-5646-a309-e3db8211df1e |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 6ed7d969-d59b-5f2c-9223-8ed8a1b480b2 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 8e815717-bbec-5cf1-9634-04199964c63c |  | note | TYPE - H
label | 332163ce-fd60-5316-8f6c-a1715816b7b7 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 59bbe9ab-94e0-5836-9e51-cbaed077e0f3 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 5aed8f34-ec31-5218-a47b-71734f7540d9 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (1)
label | 2d998ae0-331f-570a-902b-d213cdd3b222 |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | e71c19f1-d873-5d75-8923-fa1bb7ba5b40 |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.11
label | 083a5bb8-bb02-5028-b2fc-7943d7266d8b |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 316d8945-d315-58bd-bed2-57da33ab5bee |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | b02168fd-0bef-56ca-83e6-6eff74fbada1 |  | note | TYPE - V
label | c4dfa7a2-bea2-530d-8794-dce6e240f598 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | ea877a04-61ac-556b-aa9b-9417308ab6f2 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 36a2f37c-e750-5d83-939e-3c4833a98690 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (2)
label | 4496fa59-d5a6-565b-9319-38398e3a69d5 |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | 139db919-57d1-5f18-b335-cc0996a74add |  | note | METHODS OR REFERENCE - NZTA M/4
label | cfe4c489-406c-562d-af95-4767f85dae5f |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | bc6176f7-32e6-5345-8590-1de64e7ef7ea |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | 1045afb4-b91b-562c-994f-b36fd7975d9e |  | note | TYPE - H
label | 77f7aa21-4180-5613-aa7d-ca9b71f3f92a |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 919b0fda-bd38-5d25-a72b-43c807c0d5e0 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 7a1a6e8f-a7aa-5f57-8d6f-e064e17fcb08 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (1)
label | 06bf98d2-833b-5986-a4af-570acd9d423f |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | 62456ce4-31e2-54b7-91ca-0e660454cc1c |  | note | METHODS OR REFERENCE - NZS 4407 T3.15, NZS 4402 T4.1.3
label | c7248626-5ee8-58bd-88e1-a553826971a1 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | e9c535ac-74bc-59ea-8956-3e55c13f447a |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | 270bde89-fad9-5e20-8145-dec6d93ad914 |  | note | TYPE - V
label | 28b162d2-bc3b-5502-b1da-4b993bff7a9c |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | bf505be8-8fcb-5544-a1dc-d290cc973e18 |  | note | RESPONSIBLE PERSON - Renewals PM
label | a227927e-ae98-54a6-8dbc-7d8c4d475a73 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (2)
label | 771bc895-1fe4-5d4f-b92c-8ad9d76481a1 |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | 59722964-ecba-5628-a196-c62cef34d6af |  | note | METHODS OR REFERENCE - NZTA M/4
label | 4f51889a-81cf-52bf-8fe8-f2ae58ff8443 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ef88c8f3-7d6d-5c38-9cf7-596d41dac7f6 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | dfee4671-d047-5b4b-ad8d-4143e69760c2 |  | note | TYPE - H
label | 4a4af47b-bd57-5439-9914-8a71ab7f9e19 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 84eacf31-0b16-587e-a439-da5a70bc0e0b |  | note | RESPONSIBLE PERSON - Renewals PM
label | 0287fb21-37cf-588a-a1fe-ec1b79005c09 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (1)
label | 63c7044a-1ad4-5c57-8cc1-48e0000e3d1e |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | 86c38ad5-c8f5-5d7f-8bdf-ecc23ba49656 |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | d174d48e-d12c-58b5-8d70-60b348379532 |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | 358f88e9-8358-5ccb-a2a3-6f722254ebe2 |  | note | ○ 400 - 1500m3 - 3 tests
label | 6c36647a-a2bc-5da8-b29c-e377d3ac3c4c |  | note | ○ 1500 - 4000m3 – 4 tests
label | b4293729-9ce2-5159-82d2-6f24d3d38c8b |  | note | ○ >4000m3 – 1 test per 1000m3
label | b2dc00ab-78fb-511b-ad84-1aa504c98873 |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | 0a8106d6-af1c-56ea-b832-490284555664 |  | note | TYPE - V
label | 16e384de-4cc4-5dd8-ab96-a006a8183ef5 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | ff79a8ce-de03-5375-b12a-4dfea8d50eee |  | note | RESPONSIBLE PERSON - Renewals PM
label | 2ef69b4e-727c-5bc6-8838-439c6c6660a2 |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (2)
label | e8819a87-399f-583a-b4f5-e248d2b377cc |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | 81fca59e-087c-56c4-9597-28f5e9139139 |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | 0cff1caa-1ef4-536c-a622-9fa29f78430b |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | 2e882fad-e2e0-533f-a175-958d0e9d4860 |  | note | ○ 400 - 1500m3 - 3 tests
label | 907513a5-1f0c-5ba4-b7ec-f0f195058ca0 |  | note | ○ 1500 - 4000m3 – 4 tests
label | f00c1ab3-33a0-50b3-9822-a416f3eec0c6 |  | note | ○ >4000m3 – 1 test per 1000m3
label | c0d8ae81-a368-5c11-9053-b53c0b31a68e |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | 7d241ae5-1551-5bbf-974c-eb59f75ddc4f |  | note | TYPE - H
label | 956be70b-e96d-5ccc-a0cd-7e0c46e17cd6 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | ec99e38b-5ace-5b95-a2af-0659c8e2917f |  | note | RESPONSIBLE PERSON - Renewals PM
label | 832f72a5-8747-5ef0-bd63-57f5141cfa03 |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5 - Imported Basecourse Materials Compaction Testing
label | ec83ad66-76f4-5915-a3ef-2e552716bcc1 |  | note | VERIFICATION ACTIVITY - Maximum Dry Density (MDD) at Optimum Water Content (OWC)
label | 40007aef-272f-5588-8c4c-8554b4ba5978 |  | note | METHODS OR REFERENCE - TNZ B/02 - 7.5
label | 16db7f29-40ac-5e60-92e0-1274dc1af3f3 |  | note | FREQUENCY - 1 MDD per 5000m² or if aggregate source or processing method changes
label | 25d041e1-9a3b-5231-a451-8055e580cf23 |  | note | ACCEPTANCE CRITERIA - Used to support results required in ITP section 8.4 - Compaction.
label | 7f6c39c2-30c4-59e4-b674-afbd0d43f9ed |  | note | TYPE - H
label | 3504a9b9-746b-5c51-9ef4-7822234c9c25 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | e078a30f-4fa3-5f7a-b891-386629feaca1 |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.6 - Nominal 150mm Make-up Metal
label | b29b4511-c332-5b3c-9226-11a4b4baeb2b |  | note | VERIFICATION ACTIVITY - Quantity of material used
label | 03f7a4e9-e07a-59c1-b4bb-6f44d8d42787 |  | note | METHODS OR REFERENCE - 150mm depth over high spots
label | 7d2c8f94-ae4f-5acc-9590-faa86a60b512 |  | note | FREQUENCY - Each Subsection
label | 76807c61-4d48-52c0-bdb0-b898827aeeaa |  | note | ACCEPTANCE CRITERIA - Correct amount of material used (M³Solid) as per geometric design / MC
label | 24f48f01-32c3-5490-922b-9b3d36a3cd92 |  | note | TYPE - V
label | 6d4d3f73-dfb2-5f87-9dc4-00144e993dfe |  | note | DESCRIPTION - Spot checks to be taken
label | 1196a40b-e96a-5fc7-ab7d-1323fbaef225 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 8 - Construction Quality Assurance (QA)
checkpoint-status |  |  | checkpoint | 8.1 - Tie in taper
label | 3ddf7e9e-90ae-52b1-929c-a83c467486da |  | note | VERIFICATION ACTIVITY - Visual Check and Stringlines/Lift Peg
label | 43f9d1e2-2bcd-594f-a60c-828c50d73f68 |  | note | METHODS OR REFERENCE - NZTA B/2
label | c6e9d60b-8df1-543e-bf85-c43f6682a933 |  | note | FREQUENCY - Per lane per tie in
label | 49fd00fc-bd9f-5c53-90c5-7d0a5777d0d9 |  | note | ACCEPTANCE CRITERIA - Minimum layer thickness as per B/2 section 7.3a at tie ins.
label | 451818a7-aee6-5567-8fc9-ff436946828b |  | note | TYPE - V
label | 72d2e7e5-906c-53da-8f13-8fe7b49d7962 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 9090ed50-c5f6-5901-8165-7e5bfe52eb91 |  | note | RECORDS / REMARKS - Stringlines recorded and supplied, Photographs
checkpoint-status |  |  | checkpoint | 8.2 - Uncompacted Layer Thickness
label | 10bff420-7418-5a49-9e5c-e8b943395001 |  | note | VERIFICATION ACTIVITY - Stringline/Lift Pegs
label | bf59858c-4792-5715-93de-70da24dc403e |  | note | METHODS OR REFERENCE - NZTA B/2
label | 369079ae-4ffb-5f07-8127-da6056114acf |  | note | FREQUENCY - Per layer imported
label | 0d9a1ecd-3e0d-539c-a806-b534fb8d9f44 |  | note | ACCEPTANCE CRITERIA - No imported layer > 200mm no less than 2.5x particle size ie 100mm AP40
label | 2755b96b-2e17-5ec2-993e-c9ce04cf2c5b |  | note | TYPE - V
label | 699e8802-41f0-5da3-98fd-df89f16d36a4 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 1ccc0b33-b1d4-514e-8925-edadbf70b2bb |  | note | RECORDS / REMARKS - Stringlines recorded and supplied
checkpoint-status |  |  | checkpoint | 8.3 - Field Compaction Target
label | dd1dc223-3313-5e16-89bc-669ecb960ec6 |  | note | VERIFICATION ACTIVITY - NDM - Plateau
label | acec32bc-bb79-5c8f-9572-c9c380b739d2 |  | note | METHODS OR REFERENCE - NZTA B/2
label | eafea9a7-55a1-519d-b005-5e4b541ed18e |  | note | FREQUENCY - 1 Every 3000m2
label | 966c18fb-6330-5df3-a2bc-c7bbb038daba |  | note | ACCEPTANCE CRITERIA - Plateau testing done as required depending on the material variability throughout the site to determine compaction pattern.
label | 139f0805-50f8-5479-9126-ddef47e434b4 |  | note | TYPE - H
label | 30e6e7cc-872f-53f4-b753-b88a55b31286 |  | note | DESCRIPTION - Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target
label | 257b7260-a8ea-5c14-8db2-707587dce7ac |  | note | RESPONSIBLE PERSON - Site Foreman
label | 31403b1d-cf14-570b-8a84-558f494f98e6 |  | note | RECORDS / REMARKS - Verified test results of plateau to be supplied
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (1)
label | ef83e09a-722c-5e57-8946-6ea50e3eff2d |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | 93e111aa-0a6b-5b79-8db2-44d73468ad95 |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | 5b36289e-421f-52bc-83ae-5af39868a219 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 56960bba-44f0-54b2-b546-75daebae960c |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | 71cb4563-68f9-5b1a-9790-f2bd760d2db5 |  | note | TYPE - V
label | e349dded-6a54-59f1-a1dd-accdc9dca869 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | f6a0b8ca-9305-5e85-9703-8fedca72177d |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 83f35b01-0c1b-501c-ae26-cfd5f1320c1c |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (2)
label | 0b9f07a1-1da1-52ab-99ef-67681c8c4941 |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | a39ff4e0-992f-5128-a3e4-5c35f02de4fa |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | 0fa12a24-b16f-50c7-beea-7f4a931c2a72 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | e56ae664-9452-5623-a3af-6f0112bee511 |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | f34ed147-86a9-564d-b813-8900201ba65c |  | note | TYPE - H
label | a0a1df4e-cc6c-529e-803b-fb628fd3745d |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | baed8b8a-737c-5272-874a-c1a90be89a65 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 4c64ec17-4173-54dc-a7d2-71f53c4157a9 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 - Degree of Saturation
label | 6c5b44ec-199e-5026-b14e-b3e33d821d91 |  | note | VERIFICATION ACTIVITY - NDM
label | 944e1f86-fc36-58ff-9fb9-a85e6b34537f |  | note | METHODS OR REFERENCE - NZTA B/2
label | d3023016-1ee3-52c1-a047-13827b040fc8 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | a0c7e17b-6a10-5866-8dde-108fe12844b4 |  | note | ACCEPTANCE CRITERIA - No tests higher than 80%
label | 38825cfc-b0fe-5e06-a347-adffd67bbf67 |  | note | TYPE - H
label | ccdc7abd-1b66-5af6-a722-97a0c940e310 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD
label | f0c66f30-d2aa-53a4-97b7-4c6020b6ae30 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | b56c4caf-0e3e-578a-8e49-b642445725c2 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (1)
label | e09f8043-5701-5445-a546-a33d79146457 |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | c1a436cc-c838-56ab-9136-9e6eeac2edbd |  | note | METHODS OR REFERENCE - Visual inspection
label | cea56268-ed2b-57bb-a02b-3b7fdc0ddaca |  | note | ○ Cut/fill tolerance check
label | a5dcd9ed-c896-51be-a828-78acf62e412b |  | note | ○ String records
label | 3568a00f-1898-556d-802e-23cd09823dfe |  | note | ○ Straight edge
label | ced59e15-9d59-53d4-8dc0-20c788fe4971 |  | note | FREQUENCY - 1 test per 20m
label | 857bafea-1251-56c6-9d0f-e47eb1379989 |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | 0b6ae882-c15f-53d1-aa79-d219ea674550 |  | note | ○ Gradual deviations
label | bb0cd4ae-4fbc-5ad3-b853-14f13b9dbaeb |  | note | ○ Crossfall > 1%
label | 3406912a-8d5a-5911-ba47-fa111d43fac2 |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | 06be5dc8-1fc8-525e-b2c2-e0288d76953d |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | 8f0170e4-2b00-59bd-932c-afc19855fa2d |  | note | TYPE - V
label | 9f46c98e-a9ee-57af-829d-5cb9ad804b19 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | d4bd29da-6c35-5e63-8d41-0e69d81a369b |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | 118f14ef-40af-5f9d-9739-accab087382a |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (2)
label | 89b01a72-15b0-5f19-952f-18559d21791e |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | aecb3304-bd68-544c-a05a-529662121683 |  | note | METHODS OR REFERENCE - Visual inspection
label | eba90f5e-07e1-55d1-b489-b013a7c36566 |  | note | ○ Cut/fill tolerance check
label | e9a2b494-ab99-5ebe-8bb5-f63beef71700 |  | note | ○ String records
label | da283e61-f3db-5bc6-a14c-1eaa609930b0 |  | note | ○ Straight edge
label | b067719b-bbcc-5ad5-97fd-08565a5515c2 |  | note | FREQUENCY - 1 test per 20m
label | 62499e09-c94c-5aa6-857e-26354e0168f9 |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | 776a20e0-ab33-5745-973f-58710e913f81 |  | note | ○ Gradual deviations
label | 5c9be90e-0343-5c4b-8642-b24b6dae92db |  | note | ○ Crossfall > 1%
label | 41605090-5591-5e99-87c8-c85943276e7c |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | c48d5c85-058f-56e8-b056-1ffb9ab7f198 |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | b3e3b1a8-e532-529f-b8c6-4443710602a0 |  | note | TYPE - H
label | 26e952c8-ce7a-5bd6-bf89-be955e5b78e5 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | 58bc3782-18b1-5eaa-b04f-0fae8c9286db |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | a265363b-cf70-5369-9e87-c845a0c849a8 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (1)
label | 2632ef9d-e061-55bd-b30e-7e6c0a304576 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 605afe83-557a-54aa-8b28-988272da32ea |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | 0bec952c-0f9f-5059-aa5e-e8a507ca9734 |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | 70bddf83-2304-5823-ab8d-2fa16af683cd |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | 3e8425b3-0d52-579c-a5d5-7bd10bd93ae1 |  | note | TYPE - V
label | 1c601edf-7810-5753-8bb4-db5663653da2 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 6cb7c1d3-f829-5ee8-8537-9e6610b4310f |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 3ffe68ae-dc02-5a7a-b372-fa5e6eed0d5e |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (2)
label | bfb0ce76-7487-5d48-8ab0-50d7d4de5374 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | c23ed7b8-4887-5d56-951c-89121588096f |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | b60fcef9-2257-5adb-9480-6c111fff0f9b |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | f96e7029-acae-57d1-8a1e-f34263c82725 |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | 6eb3bf72-3e8f-5997-a580-dacd14d671ee |  | note | TYPE - H
label | 8583d7b4-c595-5fb7-8f11-8940bf993de1 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 79c51d39-c93a-50ac-bc9f-3824eeabcb61 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 44bbaef9-9566-581d-8e67-3b7016992b33 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (1)
label | 085e6f18-8e60-595d-bc65-5f527fb52660 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | b083d9f0-c89c-5787-866c-4c27f650c8f1 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | bcbe419c-70b5-5712-8d0a-dbc24abaf9f6 |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | e98a234e-fd25-506c-99c4-42aa29d0c953 |  | note | ACCEPTANCE CRITERIA - Zero
label | a318f5c4-9755-5266-bf4d-60676e859a24 |  | note | TYPE - V
label | 46686ee1-3380-5dd5-9bd3-4f69a0d49106 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 5409b3d7-aab3-508d-a216-d4cc043f2c71 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 5c4fa37c-6098-5f71-a697-33fe3e9fd4d1 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (2)
label | ed5e3f69-b4e9-51ae-8a25-bd623e0b32e9 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 44751e3f-4035-5af8-9915-97521e652264 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | 7e3f6797-bdce-51c9-84e5-32a6f344518b |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | 123e9a96-6baa-5aeb-8c06-2e08d1c3d208 |  | note | ACCEPTANCE CRITERIA - Zero
label | 5a001929-0ac4-5937-ac74-1b5060a7c78d |  | note | TYPE - H
label | 8fe8ab65-dc47-5476-a2de-802b5175f701 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | fda14e4a-6af0-5a60-ac46-96b17263d62c |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | bf58ffba-b0d1-59bc-ae26-1ecc0fe46fca |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (1)
label | bd32139e-0370-5c85-b36f-5cdd7d21350d |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | 40f179f5-3d4b-5c0d-8aa0-778a447d904c |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | 0ebc45a0-fdea-51a2-8df9-b71ed4cc9646 |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | 3ed3a809-1a37-50b1-b6df-21a3e4faa1ad |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | d37aaee1-e14f-5512-85fc-336c1bdf4e84 |  | note | TYPE - W
label | cf54edf2-a50a-5ad1-ad5c-b64bc7cca9dc |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | 7adeff46-835d-5321-9caf-90cc9ed387f4 |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | b95b049c-d470-553b-b587-5fc476e23d7d |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (2)
label | 9982ac1e-20a3-539c-9d12-832bc995b9b6 |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | e10b38c0-3e49-51d4-89ca-a5555a3e81ab |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | 5e488647-d613-5b21-8203-720359ae3501 |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | 280ce518-b586-53c1-98f0-016989d44c58 |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | e8a72b9d-42d9-5773-b865-680c76c7f565 |  | note | TYPE - H
label | 66dcbd4a-db8b-5a66-9adb-6d3f95ac6ebe |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | 178bf4a3-7b65-53da-b688-c4fcf90dd721 |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | d3fb8b4b-5dc3-5646-81c4-e813b417af52 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (1)
label | 4ea629d5-4d37-5bf2-928d-f9661ea8252b |  | note | VERIFICATION ACTIVITY - Visual inspection
label | 5b9386a9-3e55-55db-8240-d52464dca702 |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | d66bd668-3435-50fa-b067-fe30437d339a |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 7393e019-5ab1-59bc-b110-bb513dc7bf0d |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | 4fad04d1-8a52-5090-a51c-1f5b528e88be |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | 8c6eaa3c-dc45-58ca-bf48-0b40ebaf8314 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | 3d584caf-eac8-5dc9-90f8-9163f01dcb06 |  | note | TYPE - W
label | 34402131-8052-5e81-8131-58346df98e74 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | ecef18fe-c49a-58eb-95d7-9a0977e69450 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 99aaaa3a-2c30-5e3c-a2d8-13ba4ae53b1a |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (2)
label | 8044f077-3a3e-5f1c-976a-627f493eb6f2 |  | note | VERIFICATION ACTIVITY - Visual inspection
label | 10a63fa1-67d0-5e40-a525-768baaff0132 |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | 6e57a437-73f8-5207-b3e3-7e45dadf213c |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 682d9d5f-370f-5cbf-968f-60822581fea8 |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | 46accc3c-887f-52bd-8b63-32f19ff5dcd8 |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | aaaa2825-5e46-5f19-bd19-dfd1451f9f09 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | e9bb60e5-6020-5537-80e4-0a2f9e19c0e0 |  | note | TYPE - H
label | b8726def-c28b-5f42-ac07-92f38ca8bfb8 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | ecc43946-5a9b-52dd-b2fb-de76e0721a3b |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | dd1f4fff-292a-5f26-803e-7c54d114524c |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (1)
label | 59dac1bd-2ac5-5b39-a521-bb63185b1ae4 |  | note | VERIFICATION ACTIVITY - Visual check
label | cf687347-3068-54a4-954c-383a638d338f |  | note | METHODS OR REFERENCE - NZTA B/5
label | 7c590dd1-3e99-5ecb-8946-d9def4b13732 |  | note | FREQUENCY - Before sealing
label | a839e9a7-882c-5509-930c-53ec28ff1436 |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | c405f4e8-3f0e-517f-9d1c-1862a3ba0988 |  | note | TYPE - V
label | 74bb859d-6ba2-58e0-9a51-51910488611a |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 3857f658-f16e-5d65-aa81-437bdd6bc6b5 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 8250f840-fd4c-59ba-bc46-1c1ddafb52ae |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (2)
label | bc01855c-ad86-5dcd-a9ed-5b6c8b0ad984 |  | note | VERIFICATION ACTIVITY - Visual check
label | a480c21a-472c-5608-831c-acd66ba1dd78 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 25bededf-6bb8-51b6-b00a-b92fb66df918 |  | note | FREQUENCY - Before sealing
label | 5cd9fa95-b5cb-577a-8578-3d5c74c84a3b |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | 01f3bca9-0d22-5416-bb3b-0750ba0bd7a3 |  | note | TYPE - V
label | 2748562b-71a7-5706-9660-ec7c0e52b322 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 72c043b3-c43e-54bd-8d79-18761868ad87 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | b2260cf6-24a5-5c83-af5a-ec391b7f8c0b |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.12 - Pavement Surface As-Built
label | 0352a3f6-5c0e-592a-911a-6a8edca11866 |  | note | VERIFICATION ACTIVITY - Survey
label | eef813dd-65ae-5c1b-9036-36b112812a9b |  | note | METHODS OR REFERENCE - As per approved drawings
label | 1059f7ff-588c-55f1-b588-f2f122113527 |  | note | FREQUENCY - Per installation / Site
label | 5b0df590-0f91-5155-86d3-e479eecf8108 |  | note | ACCEPTANCE CRITERIA - Accurate survey of all topograpgical features required
label | c167cf53-442d-52bb-b195-07a385d3fcbe |  | note | TYPE - V
label | dfeaba35-2dcc-5572-a475-ecbd615887b9 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 9 - Sealing
checkpoint-status |  |  | checkpoint | 9.1 - Sealing
label | fcbea3b7-3455-5124-8fee-a38d4e5b9582 |  | note | VERIFICATION ACTIVITY - See Sealing ITP
label | d8be583b-3a23-53da-a4a3-6ad3d2b61d0a |  | note | TYPE - W
label | b70a6807-a600-51a6-90dc-67ba0c5dad97 |  | note | DESCRIPTION - Hold Point – All hold points and checks in ITP to be completed before physical works continue
label | 70ee2a68-a4e5-5c7c-9bda-c78176d337ab |  | note | RESPONSIBLE PERSON - Sealing Manager
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (1)
label | dcfb9566-23b2-53eb-afb4-b0231872139a |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 68c5bed4-1955-55f8-b968-768afe170cea |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | c141c69a-69a0-5427-8b83-454fbed06519 |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 2c8b6ec9-4224-55aa-9f71-a693bef6c33d |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | ed1f8b8d-1863-51b4-afa4-9056370b46e8 |  | note | TYPE - W
label | 7c252551-e3d8-56c7-87f0-be1332e8c310 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | 23536947-12b9-51bc-9863-2459732ea547 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (2)
label | f0267de6-ea8f-5da9-b858-5f8745508162 |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | b957f1f1-da47-5e41-b3bf-1538fb74150e |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 5d6db280-4b4a-56e9-963f-7a7ef8280b9d |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | bfaa4ef0-3979-5e8d-b90a-78f9ffeb1001 |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | b2195e08-c7bc-52d0-a0fe-6b2ad044978c |  | note | TYPE - H
label | 7878dba1-aba0-52e2-be6f-0188ee743fa7 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | eb292a70-c011-5fff-b3f0-de66f437cf81 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (1)
label | d74eb13f-31aa-56e2-8555-a65dbbbf9f7a |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 4405c1a4-eb92-5653-8b29-ac27b2e6e186 |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | d51b087c-85a5-590a-a400-d3806c6aa70d |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 27544bd3-1195-51ca-ba4f-235c3b2887da |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | b3d426d3-c9bb-5f44-9e1e-81c148ad627d |  | note | TYPE - W
label | 20090940-fe8e-5f49-84d2-0554cff19c94 |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | 1b7fc8d7-7bfa-5a1b-b13f-bf96880c0383 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (2)
label | 1beae96a-c8ae-502e-bc7f-abe6a52a19b8 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | f76c473b-34cc-56b8-b0cb-e1b3eb29c512 |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 3ad7264e-e9de-5b9c-9c8a-bd6ca848cc92 |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 92c9d5f2-ab96-5b6c-91a2-6c849d643b30 |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | cb03b758-7728-574c-9605-0290f670b140 |  | note | TYPE - H
label | 3bfe6153-4d4f-5497-9c2e-8cd2ab41c1b1 |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | cd13ab66-cb25-56d2-9f99-4d8ff6b2b2ec |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Shoulders
checkpoint-status |  |  | checkpoint | 10.1 - Slope (1)
label | 9afe00cc-4a0b-5d02-962a-82244a38a911 |  | note | VERIFICATION ACTIVITY - Visual check
label | 57bf9132-00cd-5148-9198-5a6e54032e49 |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | db8c80ef-d08d-5e4d-b4e8-e7f3538bb062 |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | f8395c2d-d8a0-5c29-8786-935bedfceaf2 |  | note | TYPE - V
label | a5425d10-77c6-5294-82ae-b84341ad81cb |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | a82ecb74-ca95-593c-a039-c7ab2fa64da5 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 9ff29ec4-7210-5326-8cac-13503859d710 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.1 - Slope (2)
label | 491ae794-c465-5300-b632-8a364283ed5c |  | note | VERIFICATION ACTIVITY - Visual check
label | 95f1054e-5aa6-534b-a362-17cc9905841f |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | c0fcc032-f15b-5e50-9986-a59254af6914 |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | a233691f-ecea-53b3-82cc-3f027f90dd4d |  | note | TYPE - H
label | a299dbcf-48bc-53ca-912c-76ee74b9115a |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | fb2b0fca-c364-5a0b-8ca4-d6f3419cc5ac |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 8fc433a9-d0ab-5c8a-8283-1afab55635dc |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (1)
label | 261d6b6c-28de-5633-9934-e9c135d7d649 |  | note | VERIFICATION ACTIVITY - Visual check
label | 7fcbad58-027f-5e62-984e-969c0ee07563 |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | e1e453e4-da81-5e4d-afcb-090f8e8d6522 |  | note | FREQUENCY - All shoulders
label | 8ccfcb69-fb87-5781-a10e-3634f870e3e8 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 26c749ab-a50d-5d2b-900e-3a66ec47934a |  | note | TYPE - V
label | 88e6d9f0-d192-5114-a50b-fc525a3a43bf |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | 6c94d4eb-df92-5e87-933c-86a5101487b4 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | fbd5df32-6489-5d8b-b34c-3cd8bc4271a6 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (2)
label | bfd6a90a-eca8-5841-b3c6-ddb2baca03b9 |  | note | VERIFICATION ACTIVITY - Visual check
label | 625abfa0-5969-59c5-a887-3d6bd366e306 |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | d8d2d03e-8f9a-5b17-baf6-2ae5f5013be6 |  | note | FREQUENCY - All shoulders
label | 756c6781-5243-5ad4-8d82-94ec305c08d5 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 663e91d6-1f17-57b4-b88c-0e49c2be8171 |  | note | TYPE - H
label | 2e7c4e69-1e33-57f7-8a08-5a986dbc0447 |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | 24aabaa3-fbe9-5cf8-b9e4-e4d5e3e986cb |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | bb48c860-5f31-50d0-8ef7-8b832dc71374 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Soiling
label | 35c3208d-a5d3-527e-84f8-14375d826936 |  | note | VERIFICATION ACTIVITY - Visual check
label | 645d8183-e79c-5778-acf5-9d876b569c9d |  | note | METHODS OR REFERENCE - Approved Design Drawings
label | 4c25ff8f-2174-5669-8c08-af56e6d36248 |  | note | FREQUENCY - All areas requiring grassing
label | 02751d17-3d27-5fe5-b7e1-25152413f46d |  | note | ACCEPTANCE CRITERIA - Soiling has been done where required
label | c0d54522-6976-55a0-be2f-317b96fb81f6 |  | note | TYPE - W
label | 12282381-75d4-56ea-b9b9-9d42d9ee827b |  | note | DESCRIPTION - As per the design drawings
label | 634d4972-e980-5bf4-82ea-a3a72e5c5be6 |  | note | RESPONSIBLE PERSON - Renewals PM
checkpoint-group |  |  | section | 11 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (1)
label | e014355f-370e-567e-b597-5a46dc07f542 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 72fedf23-7e5c-51df-9e6e-a639df4e6493 |  | note | METHODS OR REFERENCE - Visual Inspection
label | 6365d55f-1661-5bf3-89e4-86ab9e537cae |  | note | FREQUENCY - All signs/markers
label | 648dc21b-5774-542b-b68c-a6551c8a5ff3 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 66399c06-f5a9-5dca-856e-66a00ecfd399 |  | note | TYPE - V
label | efcba359-34d5-555c-89c7-e030f40002d9 |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | af18a784-3dc0-5068-b722-0e4acbd1e321 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 384597c5-9952-5bad-8568-ff1efd626783 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (2)
label | 0cdb80d2-f20a-5cc0-97f0-538b3ceca21a |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | c594868f-222c-5a26-9a2b-00619932107a |  | note | METHODS OR REFERENCE - Visual Inspection
label | 9aad3823-d49a-5fee-b0da-bec4f3e82e86 |  | note | FREQUENCY - All signs/markers
label | c3353876-a448-55d0-8fb8-ff17e38a53e9 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 58e460ce-80a9-58e5-a98d-1ce0773e7da2 |  | note | TYPE - H
label | f2bb03f0-0432-5d77-8078-7ebb544d6bd9 |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | ef5ae301-cb8b-5500-9770-cc145474ae67 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 3da54011-45dc-54fe-a25d-e28a323f528c |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2 - Grassing
label | b72cc82e-3666-5fc9-b85e-17bfbd948db8 |  | note | VERIFICATION ACTIVITY - Visual check
label | 8c120f77-f5da-5600-8770-fa937f59d2b3 |  | note | FREQUENCY - All areas requiring grassing
label | 4a4e5f4d-88ef-52f7-adec-3b52e95161f4 |  | note | ACCEPTANCE CRITERIA - Grassing has been done where required
label | e9f19a87-0a8b-57be-bb0e-877f57aa0c5d |  | note | TYPE - W
label | 15096be0-e978-5dab-a4e0-f878e64b4adc |  | note | RESPONSIBLE PERSON - Renewals PM
checkpoint-status |  |  | checkpoint | 11.3 - Drains Cleared
label | fb83a689-92df-5462-99f5-f06cc2f0dd71 |  | note | VERIFICATION ACTIVITY - Visual check
label | 31ef54ea-86ee-5439-a9b8-6d28197ef549 |  | note | FREQUENCY - All drains, after all other works
label | dcff77b1-3f1a-5ebc-885d-c5c4c9c48fda |  | note | ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | 80afed09-27d8-517d-8fa5-8a502bbb32ce |  | note | TYPE - W
label | e9f37434-5a25-558a-a7a4-f586c46a7c0a |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 11.4 - Post Construction Design Verification
label | 7be1925b-c846-532b-8bb4-d6116e3947aa |  | note | VERIFICATION ACTIVITY - FWD/Beam
label | 87494346-7979-5906-9eb3-ed45b4037a97 |  | note | METHODS OR REFERENCE - FWD or Beam at 20m Centres
label | 0b1980e8-7a20-5b55-9445-6d28caaa16b9 |  | note | FREQUENCY - On Works Completion
label | 0d88cc2f-7854-531e-a438-c02732e248e8 |  | note | ACCEPTANCE CRITERIA - For information purposes only
label | 9cf5ca49-df27-502f-ac62-b3161c5f00f9 |  | note | TYPE - V
label | 87ae1e15-2dd2-5fa2-a1a3-a47bb76021c0 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 6ecc1bf4-da3b-5e7b-be24-84988f679b8a |  | note | RECORDS / REMARKS - For Unbound Granular pavements <10year design life.
checkpoint-status |  |  | checkpoint | 11.5 - Traffic Management Removed
label | 9cf6a9b6-6b20-53e7-be5a-4bc824383bf3 |  | note | VERIFICATION ACTIVITY - Visual check
label | 2fccdfd9-2d9e-511e-9d69-32a96e728f42 |  | note | FREQUENCY - When safe, after all physical works completed
label | f447a15e-925a-516a-a0a0-8c15fd619825 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 41ae485c-b410-535f-ad1e-f1dfd7bc26d4 |  | note | TYPE - W
label | e6c37e09-2062-5707-b176-1144ed585bf6 |  | note | DESCRIPTION - Hold Point – TMP cannot be removed until site Audited by Renewals PM
label | 17460f5d-f561-5ecb-a5e1-bb54e615a3e3 |  | note | RESPONSIBLE PERSON - Site Foreman / STMS
checkpoint-status |  |  | checkpoint | 11.6 - Site Left Clean and Tidy
label | c5316573-fa6e-5ce6-ada9-c4896b02cdfe |  | note | VERIFICATION ACTIVITY - Visual check
label | 9b4bd71e-7e1e-5bb9-b3be-902723ce75d7 |  | note | FREQUENCY - After vacating site
label | ab1ec920-cd15-5f12-87b4-2d5485db4b42 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 70f316d2-2835-5c49-99b9-efe5dd92b868 |  | note | TYPE - V
label | f0561fb5-8555-5046-a0cf-144275cf9b25 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 70bc2647-dcab-598a-8e2e-ec0dfe3917fb |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-group |  |  | section | 12 - As-built Records
checkpoint-status |  |  | checkpoint | 12.1 - Collect Asset Data
label | cf64b5a8-6a57-5cf0-b1e4-0e1c9e0bf837 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 49f42375-7918-5dd1-8c7e-9007f2fd00d7 |  | note | FREQUENCY - During construction
label | 3e74d6e0-5be3-51a8-a3f5-f52baee5bc5c |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected
label | 6cdf2228-a924-52ca-afb9-abf80f4efdc0 |  | note | TYPE - V
label | 85f50061-c738-58e0-a99c-400ee334db3a |  | note | RESPONSIBLE PERSON - Renewals Project Manager
checkpoint-status |  |  | checkpoint | 12.2 - Enter Asset Data into RAMM and/or Register(s)
label | d59028f3-8a58-54ac-b0c4-552029126962 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | b81c4dfa-9ec1-5f91-877b-9fdae41c936f |  | note | METHODS OR REFERENCE - RAMM
label | a9cb2704-0e89-52c2-8a0f-b6daedd3ae40 |  | note | FREQUENCY - At completion of work
label | 846eef3a-ad43-5cd2-b66e-69aa43792fbd |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file.
label | ef180954-f1ae-56d1-8cf0-1d69a4cacf45 |  | note | TYPE - H
label | 584455e3-21c9-5322-b460-98eedad1bca5 |  | note | DESCRIPTION - Hold Point – project cannot be closed until data entered.
label | 884bcc35-2688-5e77-815b-c059e310a581 |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ WSP Information Manager
label | 5af32f55-717b-506e-8c50-b03c103d9096 |  | note | RECORDS / REMARKS - Submit all RAMM Data to Data Quality Manager for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.3 - Construction Completion Report
label | a92aa340-f9f6-5465-9e15-06b5640b8f2a |  | note | VERIFICATION ACTIVITY - Confirmation
label | bb68cb1b-6c78-5bdf-8bbc-1fffb714a55f |  | note | METHODS OR REFERENCE - Contract Specification
label | 6013fb33-6795-5c72-8317-0bb95b38ff0c |  | note | FREQUENCY - At completion of work
label | 109790b4-2f48-5e20-9304-b96969adea20 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 40dd9b98-bc32-5e31-af9f-aff680de0e63 |  | note | TYPE - V
label | b117694a-a163-53cf-9382-36f6cd710903 |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ Renewals Manager
label | 41198008-1ddf-5ff8-8744-bb3ac0b6e17b |  | note | RECORDS / REMARKS - Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
checklist-sectioned |  |  | checklist | ITP - Palmer Mill Rd - Pavement Renewals - Unbound Granular Overlay | itp |  |  |  | Yes | ITP - Palmer Mill Rd - Pavement Renewals - Unbound Granular Overlay Rev 0.04 | 89734f5d-eff3-4559-af78-c9962633799b
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 69c718d5-fbf0-5a22-b646-3f5c8ddc95e8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | fe7f40bf-00f2-50e9-a38f-12a695ca68d2 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 013507b8-6794-560f-99f8-9a272329d35f |  | note | FREQUENCY - Before work commences
label | c6954585-cd94-5fe6-9b0a-f81340fc92fa |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date
label | 5173da26-7431-55f2-a519-921d48def66f |  | note | TYPE - V
label | b38a2fca-9ce0-5495-9edc-52a34bb7f9dc |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 13ad3cdd-de19-5611-a059-b3de9847d19a |  | note | VERIFICATION ACTIVITY - Confirmation
label | aa3f5e78-8fd7-50a1-bdf3-591d9662934e |  | note | METHODS OR REFERENCE - Contract Specification
label | f8d27493-c059-5e25-a9e3-6115f406f2d0 |  | note | FREQUENCY - At least 24hrs before establishment or work commences
label | 1c76098e-ee40-5ba0-b432-0e1fd2f25b29 |  | note | ACCEPTANCE CRITERIA - Principal's Acceptance according to guidelines in Appendix 6.3
label | 8bb1a8ce-48ee-5595-937e-f9db5a8bf582 |  | note | TYPE - H
label | 3b5cf075-a2f8-58ea-bc3f-34424ed87e7d |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site.
label | dcf6dfe1-6e49-5789-8266-abfa9e525e83 |  | note | RESPONSIBLE PERSON - Renewals Manager
label | 3b25af5f-d87e-5168-9ee9-87bbc72a26c7 |  | note | RECORDS / REMARKS - NZTA to approve.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Notification of Intention to Start Work
label | 171a03c6-8deb-508d-bd57-0e01c50b5970 |  | note | VERIFICATION ACTIVITY - Notification
label | a13d53f1-3ad9-5c1d-93e1-68588378b852 |  | note | FREQUENCY - Before work commences
label | eec0eb41-c858-571d-8235-a89af037c0be |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents
label | 039fdb34-5f5e-5cab-9cd2-e5d690ec381b |  | note | TYPE - H
label | f2469491-d5da-5869-b451-6f4da4a7cd50 |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site.
label | d842c5ad-b1b9-5920-8776-1ad05f3b90f6 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 64896bad-a6d7-5b76-b720-5be14e45eeba |  | note | RECORDS / REMARKS - NZTA to approve letter drop before distribution to residents.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Traffic Management / TMP
label | 74ef5dfa-63cd-5345-863c-2088bb8a555f |  | note | VERIFICATION ACTIVITY - Visual check
label | ef6f5978-0993-54de-8ad8-f6c20e1bc2cc |  | note | METHODS OR REFERENCE - CoPTTM
label | 217f2edc-4bc6-5fe2-9119-0386274e5dc0 |  | note | FREQUENCY - Before work commences
label | df70d859-2abd-5a29-9aaf-bffc6131c0d3 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved
label | e122a9e4-e65e-51dc-9298-f2812a9b4f17 |  | note | ○ Plans approved
label | 5f4fc42d-390c-56f0-b1c1-97e15cd9c505 |  | note | ○ Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely
label | 9fc13983-1beb-5bbc-b9ea-92de703db81b |  | note | TYPE - H
label | 41c3256e-fe81-5f2f-8258-712b1dc0b44f |  | note | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 9798655a-0f24-5065-9510-5913bb6d9f0b |  | note | RESPONSIBLE PERSON - Renewals PM / TMC
label | 76c168f3-d29e-5033-a631-0e7d62b7ec82 |  | note | RECORDS / REMARKS - CAR No., TMP No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Design Report Approval
label | 409c2339-9edd-5585-a292-d29fb76d5537 |  | note | VERIFICATION ACTIVITY - Confirmation
label | d4bbc6cc-6b4a-5a18-8c31-9bc0da511d50 |  | note | METHODS OR REFERENCE - NZTA NOC Rehab Catalogue Design & Treatment Approach
label | 7b3802f7-07b1-5e25-9abd-2a48621d51ae |  | note | FREQUENCY - Before work commences
label | 21fd1004-3527-5aca-aff7-f6493adb3e7e |  | note | ACCEPTANCE CRITERIA - Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document
label | 3c6d613f-b0ba-51c9-b8fa-1350a9e0107b |  | note | TYPE - H
label | 21f38ae2-2eb1-5d9c-a11d-04c1540d9eab |  | note | DESCRIPTION - Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers
label | dfde4499-db7d-558a-a534-8c1c67ad1b7b |  | note | RESPONSIBLE PERSON - NZTA Network Manager & Accreditied Designer
label | 00e0a5ac-c022-52bb-937b-643e64b56a0f |  | note | RECORDS / REMARKS - NZTA Approval to Proceed NTC No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Seal Design Approval
label | edb087bd-375b-5bca-8771-8564fe568b92 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 975d6b2a-ce2f-5d54-b991-86c4173fe7ad |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Regional Sealing Manager
label | 8b8ef9c1-ebd0-57ef-abcd-77298f393dd5 |  | note | FREQUENCY - Before work commences
label | 698e7305-55fd-5643-8d6a-aa10b347ae95 |  | note | ACCEPTANCE CRITERIA - Downer Regional Sealing Manager reviews and signs off on Seal Design proposed.
label | a145ef94-7aa9-56cc-be87-e8c83ee257c2 |  | note | TYPE - H
label | c69a4079-d83a-5614-91cb-2d6c1cec5019 |  | note | DESCRIPTION - Hold point - Review and approval of seal design completed
label | a819e314-2e0b-57c3-aa1f-b16552f8a721 |  | note | RESPONSIBLE PERSON - Regional Sealing Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Project Manager Handover
label | 03b786d4-dc96-500f-99c0-f158721f387a |  | note | VERIFICATION ACTIVITY - Confirmation
label | a72ae243-eed6-55b1-94e2-3726349212b3 |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Designer to PM
label | 9cad1a7c-0cf1-5efb-920d-f0851882c04b |  | note | FREQUENCY - Before work commences
label | 435d684c-e1fb-5194-87c4-1937880c3052 |  | note | ACCEPTANCE CRITERIA - Downer Technical Services Team Designer reviews and signs off on Handover.
label | 44025ed9-4df0-5290-a91e-24d85c362435 |  | note | TYPE - H
label | edf8aa38-1ca0-5c89-8877-751c85223a6b |  | note | DESCRIPTION - Hold point - Handover completed
label | 1fd5e156-90be-50c1-a92f-2a86147fcb50 |  | note | RESPONSIBLE PERSON - Regional Engineering Team Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Crew Pack
label | e265177d-01d9-5d89-9a56-cab106ac5200 |  | note | METHODS OR REFERENCE - Items to be included:
label | 5fa44cc3-b47e-58b9-9ca9-19574f831893 |  | note | FREQUENCY - Before work commences
label | 471e302f-d7b8-536c-91dc-d055961432eb |  | note | ACCEPTANCE CRITERIA - Approved TMP
label | 240dd8fc-6f8e-51db-837e-ec4021e60704 |  | note | ○ Services location plans / Marked out
label | 4c8727ef-61f2-5faa-9f4a-0d0dce0a64a5 |  | note | ○ Approved RQP
label | cea756da-bc4d-5be8-aa81-66c53b7fe6cf |  | note | ○ Approved for Construction drawings & Pavement Design
label | 87408f6d-442c-52bb-9539-7d9518f4fc0f |  | note | ○ Ramm data
label | a6bd42f9-590f-588e-aa51-569f89ff65b5 |  | note | ○ Approved ITP
label | 17110cfe-db58-5071-8888-aac7b9a3df34 |  | note | ○ Crew Briefing Plan
label | 38ea4c80-6321-5890-84e8-a0041277bda9 |  | note | TYPE - H
label | b45f2129-f123-5f91-911d-a52f56f9d962 |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Setout / Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Setout
label | ef5bca6a-61b3-53a0-9565-66934a74e159 |  | note | VERIFICATION ACTIVITY - Survey
label | f6eb6df3-e5a7-5478-82bc-801163fcaf6a |  | note | METHODS OR REFERENCE - As per approved drawings
label | b1389444-9a68-5147-bf23-44c688af7505 |  | note | FREQUENCY - Per installation / Site
label | 6d0fccad-da1f-5308-8af5-db88fe0775a3 |  | note | ACCEPTANCE CRITERIA - Design strings /design surface model loaded for machine control
label | b9b108f2-f407-5c2e-95a7-20cccbb573f6 |  | note | TYPE - V
label | 18796da3-c33e-5f36-b83d-84ff8108baf4 |  | note | DESCRIPTION - Machine control requirement. Downer surveyor required for MC upload and verification of model operation
label | e60f56fc-1e56-5b7c-bbf9-eb934f60a549 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-status |  |  | checkpoint | 2.2 - Services (includes Traffic Count Loops, In-road sensors and Traffic Signal Detector Loops)
label | aa4d1cac-296d-5f48-8507-2d72576c4862 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 9390f217-e93b-5f25-ade6-3fdf6929c385 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | ad7aa500-422a-5cf8-8465-3c8dd8a24c29 |  | note | FREQUENCY - Before work commences
label | 1c4c94f8-0f63-5691-95bf-e8e776671762 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 0ee9378d-80f6-5c0c-9c72-545e77bde9ae |  | note | TYPE - H
label | 4b5e7f4c-1a9e-533b-b8a5-86cba24e92c9 |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
label | f178c87b-ec59-5795-9a40-bc2b7a6906cd |  | note | RESPONSIBLE PERSON - Renewals PM / Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | dc2b0036-d900-5446-830f-f5ace9dea7b7 |  | note | VERIFICATION ACTIVITY - Notification
label | bd5f4ec1-5b48-5c0f-a927-65096d4b42e5 |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | 4277f3d1-bf03-5472-aa63-c2cc916ccb31 |  | note | FREQUENCY - Before work commences
label | 11c424ac-ed4b-560e-a8b6-ea7cb3d95006 |  | note | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | 3a0453d2-cb28-5289-be95-16d0f7a777fe |  | note | TYPE - H
label | 37392619-68fe-5873-9d57-db4ecf1490dc |  | note | DESCRIPTION - Where risk of cultural discovery
label | 64396ec2-0717-5985-a0c5-a6c5c44ebb23 |  | note | RESPONSIBLE PERSON - Renewals PM / Communications Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Archaeological Risk
label | 62a1be40-99b7-5752-89b4-3d62326a127a |  | note | VERIFICATION ACTIVITY - Toolbox meeting
label | e11692f0-b98c-5817-b460-85b55f98503c |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | 3725a1e1-b8ac-5795-b30f-d7c8d809a9b8 |  | note | FREQUENCY - Before work commences
label | 445c7cb3-1e74-5e8a-aace-204c3b292b27 |  | note | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | 2b2f222a-6876-5355-9fb2-217d4b28f3c3 |  | note | TYPE - H
label | 1ce506ba-83e9-5b83-9aa5-749f875092bf |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
label | 1130b6da-f533-5bd8-853e-fd899235534f |  | note | RESPONSIBLE PERSON - Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Traffic Management / Signs Setup
label | 13782b64-1d9d-5097-befb-0b540d871143 |  | note | VERIFICATION ACTIVITY - Visual check
label | 38b729e0-ed33-5677-a2e9-921f521c1d3b |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | c8573486-e46a-5753-b881-e1992e1f9370 |  | note | FREQUENCY - Before work commences each day
label | 10f47b43-3fe1-560d-8822-f3dec58fa406 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | f86194ae-de1a-5e3f-968e-fd86dc418070 |  | note | TYPE - H
label | faaaf12c-415a-5f1c-b8c3-24989003cbbb |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | ac19e8d5-9338-5f50-a319-cf8ac168e89f |  | note | RESPONSIBLE PERSON - STMS
label | 8790b17b-6ff7-5622-9d9b-d2cc24881bce |  | note | RECORDS / REMARKS - Daily site record sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (1)
label | aab88b52-95f0-55f8-a670-bd48e01564bf |  | note | VERIFICATION ACTIVITY - Visual check
label | a8bfdcda-c05c-55e2-acca-2f43695fd239 |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | f7588af8-9988-54e8-9e08-40aeb098f227 |  | note | FREQUENCY - Before work commences
label | 40674da4-df96-5b62-94ef-3e6168237587 |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | fcc55495-fec0-58c0-b7fd-bdc11d5ada62 |  | note | TYPE - H
label | 0674624f-e404-5f02-9ae3-6ae169bbb89e |  | note | DESCRIPTION - Hold point - Walkover required ahead of MS Civil establishment
label | 2ce663fa-1dae-53fb-a832-26b4c7720c05 |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | ada52f04-304a-5ff6-8546-29516fa328e4 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (2)
label | df757145-80fb-59ec-a988-bf3b2f4883b6 |  | note | VERIFICATION ACTIVITY - Visual check
label | 8b82e68e-280a-5663-bd2d-21f7b615c1db |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | f133ec7e-2ac9-5c3a-9cff-8f60d41f72d1 |  | note | FREQUENCY - Before work commences
label | 0f34f0d6-24bc-5a93-8898-0d280b3f7029 |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | 09216ea3-4337-5844-a6ea-9a6c8e2992c2 |  | note | TYPE - H
label | 2f7ff59c-2fbc-55d5-9579-5c2fea5e0652 |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until walkover completed
label | 34f0b761-f633-509a-a960-85c7eead9632 |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | 1e7db83d-4946-5b49-bcd7-81722ceb4263 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminary Works
checkpoint-status |  |  | checkpoint | 3.1 - Shoulder Stripping / Vegetation clearing
label | 79d37452-a80f-59cd-a1d6-e1bf9e1fa28e |  | note | VERIFICATION ACTIVITY - Visual check
label | ef1cab6a-b251-5a85-8c57-1677b4a10879 |  | note | METHODS OR REFERENCE - On site
label | 4104c05b-b8ca-512a-b88c-4c22e30a2d30 |  | note | ACCEPTANCE CRITERIA - Shoulder stripping as per drawings completed
label | 6d941583-a053-578c-97a7-7cf7cacfbbb9 |  | note | TYPE - V
label | 2febadde-1c0b-5e79-9aa5-7942fd174498 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 13e594ee-1401-5491-8040-e282a2962d92 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
checkpoint-status |  |  | checkpoint | 3.2 - Shoulder Buildup AP65
label | 633322ae-12f5-53f9-96d0-7955bf04f565 |  | note | VERIFICATION ACTIVITY - Measure
label | 2aae590b-58b5-5028-ac9b-38e66c29ea15 |  | note | METHODS OR REFERENCE - B/2
label | f46ae9a8-5803-5c60-a712-59a3bb2199a1 |  | note | FREQUENCY - 1 per 20m
label | 6c4d1b98-fbd8-5e5c-ac67-7ca6258bcb91 |  | note | ACCEPTANCE CRITERIA - Shoulder buildup as per drawings completed
label | 09ff0d86-44c8-59bc-929d-5fd08e625196 |  | note | TYPE - V
label | 05b8932b-dee2-53a4-9c7e-2ff514b61d56 |  | note | DESCRIPTION - Greater than 30 CIV
label | 05a61ca8-39fe-526c-a4bb-9ee1774baba0 |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 3.3 - Site pavement A/C digouts
label | 7d610ff1-021d-5ba5-a0e6-f4c1c245e5dd |  | note | VERIFICATION ACTIVITY - Visual check
label | dc98b0d8-f1a1-5048-b122-cb84a917e3ad |  | note | METHODS OR REFERENCE - Check RAMM records for depths
label | d714b4de-fc39-5043-bacd-c8c36fff3a6c |  | note | FREQUENCY - Before Overlay work commences
label | 42ba375b-d4ca-58d0-af82-a0c7367247cd |  | note | ACCEPTANCE CRITERIA - Work completed prior to overlay contractor onsite
label | d7627f39-c258-5bb4-9119-28819cef869b |  | note | TYPE - V
label | b0a2216e-8ef2-576f-a101-87c376680dae |  | note | DESCRIPTION - A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed
label | 6a835f2f-365f-56ad-9faa-3e13276f4c09 |  | note | RESPONSIBLE PERSON - Construction Supervisor / Site Foreman
checkpoint-group |  |  | section | 4 - Culvert extensions / Headwalls / Flumes
checkpoint-status |  |  | checkpoint | 4.1 - Excavation Inlet / Outlet Gradients
label | 69a82460-3d4a-5807-940f-ff9ddf285652 |  | note | VERIFICATION ACTIVITY - Survey
label | 61f5c5b9-0900-50b9-a6d4-8685a8b88c92 |  | note | METHODS OR REFERENCE - NZTA F/3
label | 9882f49b-f33a-5afb-8f1e-971f6137f714 |  | note | FREQUENCY - Once
label | 6205a83f-ba89-5909-bc84-92edfb767f66 |  | note | ACCEPTANCE CRITERIA - Consistent gradient in and out
label | e5e90fcc-4f45-5838-93eb-d95961f2d551 |  | note | TYPE - H
label | 6baf1216-23c5-5c85-be46-7c4b77191350 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | f4b8fe5a-8817-5b5f-9021-f53dba833d9e |  | note | RESPONSIBLE PERSON - Site Foreman
label | 032dfd27-49c6-53b8-ac69-1b791a01bf22 |  | note | RECORDS / REMARKS - Required No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Pipe materials / class
label | 72193052-1f1c-598d-ad67-00d0cc350af5 |  | note | VERIFICATION ACTIVITY - Visual Check
label | ecdf68ef-bdfa-5f95-88f0-cdaebaca5021 |  | note | METHODS OR REFERENCE - NZTA F/3 2.1
label | bc5bdfb3-079c-5361-ae00-ac620ad1c9d6 |  | note | FREQUENCY - Once
label | dd53eb4b-cfaa-58f0-ba41-b34e2c6390e3 |  | note | ACCEPTANCE CRITERIA - Meets appropriate AS/NZ standard reletive to specified type
label | b2b7a61b-a361-573b-a265-073755d51870 |  | note | TYPE - V
label | 749baff8-56ee-5262-9fe5-358ce2690dfc |  | note | RESPONSIBLE PERSON - Site Foreman
label | 400f8b5d-9e32-5083-aead-bdb6b9e17c16 |  | note | RECORDS / REMARKS - Required No
checkpoint-status |  |  | checkpoint | 4.3 - Bedding contact
label | 234bcbe6-4654-525a-969d-fbd35f2b3682 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 74fe1107-254e-588e-8344-be087b1aaaed |  | note | METHODS OR REFERENCE - NZTA F/3 5.1
label | 26c08e27-5ab7-594c-938c-eccd057cc89b |  | note | FREQUENCY - continuous
label | 9166b76b-cef4-54e5-ba72-af68fcff4e2c |  | note | ACCEPTANCE CRITERIA - uniform contact over full length of pipe
label | 69e19b46-f069-52d8-8e2a-d46aa110658a |  | note | TYPE - V
label | 8da23d8b-109e-5d73-bfa8-94ba9e3048e9 |  | note | RESPONSIBLE PERSON - Site Foreman
label | cd63e8b6-f70c-54f3-a0a6-7af6f9fda812 |  | note | RECORDS / REMARKS - Required No
checkpoint-group |  |  | section | 6 - Preteatment of Insitu Materials
checkpoint-status |  |  | checkpoint | 6.1 - Cut to Waste Existing Seal
label | 9d8b982e-cd77-5f88-81f9-c1426a749d5a |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | a7985599-6fb8-5834-bd05-514df41c543a |  | note | FREQUENCY - Prior to material import
label | 31a43089-ee40-567a-83ef-38d8c1d6cd5a |  | note | ACCEPTANCE CRITERIA - No unsuitable material remaining
label | 73b5899d-80f3-5899-b133-3cb54ddfdd51 |  | note | TYPE - V
label | c6dedfa3-8fcf-56e8-8551-e46f2f59c9ec |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 6.2 - Undercut unsuitable areas
label | b2c6442e-ef25-5e21-884a-dd80463b28ad |  | note | VERIFICATION ACTIVITY - Visual Inspection/ measurements
label | e2e366a2-1276-5784-af2e-e5ca2e000a11 |  | note | METHODS OR REFERENCE - Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table
label | d25689b5-107a-5d16-9121-de5c40b59244 |  | note | FREQUENCY - Where required
label | dc4e79ba-44dd-55c0-b95e-2de90ff44c64 |  | note | ACCEPTANCE CRITERIA - All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to
label | 136b854f-1cc0-5dce-a05d-3f833fc9e5be |  | note | TYPE - H
label | 45961f03-85ca-5656-acd7-3078903dc71d |  | note | DESCRIPTION - Hold Point - Organise site walkover with NZTA MCM prior to dig outs commencing. Variation agreed.
label | d2c633a2-72c4-5417-a254-6afdef418408 |  | note | RESPONSIBLE PERSON - Renewals Manager / Site Foreman / NZTA MCM
label | 1b477098-05db-53c5-bb4f-99c59a6bc8f6 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Imported Basecourse Materials Testing
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (1)
label | 7da77bab-2e3d-51fd-8c36-1da5e2523dd0 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | 53fb0c31-9b09-5358-bbe4-5fa927034981 |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.10
label | 4448edbd-5c65-5a25-b423-2843599998b8 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | f2d07548-29e4-54e1-9135-532c108e57f6 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 5cc414d6-a804-52b0-9563-486e938f76cb |  | note | TYPE - V
label | ee247847-8fe5-5fa6-ab9c-f66fe446d540 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | af372d07-d15a-5f17-9878-2a531ba698f0 |  | note | RESPONSIBLE PERSON - Renewals PM
label | ab35841e-64c7-57b2-b544-128ed827f4ca |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (2)
label | cbd5068f-618d-514c-b1fb-0487f380fd9e |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | b7b383d2-4446-591c-b950-52080e07fcb8 |  | note | METHODS OR REFERENCE - NZTA M/4
label | eaae42f9-a7e6-5233-b000-16d66c593194 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 5e66b7c2-b54f-5996-8149-307056fbf070 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 3113d00d-21c7-5aaf-9415-d2efd30dc03e |  | note | TYPE - H
label | f374fc47-516c-532b-8ae4-4662922e0b38 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | c3a6ba0d-99e7-5907-9ab5-ca6ee2f81fbf |  | note | RESPONSIBLE PERSON - Renewals PM
label | e95ee569-f469-5d7a-a60d-4522f52c452b |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (1)
label | 35666a5c-fe50-5877-b8c7-43c06e0d17ae |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | 542c1fcd-5888-5f5e-9863-25e919dbdcdb |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.11
label | 3b09bfb2-5908-5997-8117-d204d96c6ed2 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 56069b26-c523-5a2c-8164-02582f0f0d07 |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | f2c7ca58-f7af-5e7a-b049-c533d05d3732 |  | note | TYPE - V
label | a21ac407-b574-591d-a58e-cc5df522c103 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 7a505bb9-4b3d-5dba-b3b1-9e8dbafc9d9b |  | note | RESPONSIBLE PERSON - Renewals PM
label | dcbbc14a-ff83-5940-8737-ca40212591c0 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (2)
label | d47c3b98-142e-5cf4-82d0-da9740e3d306 |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | 28a621d0-39a3-59ad-8d90-8141935f8405 |  | note | METHODS OR REFERENCE - NZTA M/4
label | 09566c12-fa10-5b27-86ba-5b4872f82ee1 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | bb559c24-f57d-55a0-a151-4a11e464cb22 |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | e165d5ac-c632-5957-aca2-09e3cc3edaf9 |  | note | TYPE - H
label | 7d1ab650-c8a0-500b-a733-40a2b81ba2a7 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 786922b4-8e65-56b3-8786-05e705f639c7 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 10529877-9963-5df2-8836-d3542367a239 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (1)
label | 6179cbdb-f5fb-5913-8b8c-0422de6c7e35 |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | cfd4ca2c-0c17-5fff-be53-a49ef8bfc074 |  | note | METHODS OR REFERENCE - NZS 4407 T3.15, NZS 4402 T4.1.3
label | 84a9408e-222b-524f-ba16-12b0448d3355 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 881b0bc7-6afa-5a0b-bc4b-1c2d33c43240 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | e0768548-edef-5579-9a84-a051a094ee37 |  | note | TYPE - V
label | 31c9a084-afed-5ccd-804e-7106f98faa02 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 71c16140-0a63-5850-9220-5309d9157b2e |  | note | RESPONSIBLE PERSON - Renewals PM
label | 645b7522-1799-50b2-a6f5-7a77e431efb9 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (2)
label | bf8ba1d8-7fc1-5ed8-9667-4b0d73f56e1e |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | b967d637-7039-51a4-badd-e1444469ad4b |  | note | METHODS OR REFERENCE - NZTA M/4
label | 57c93aad-409d-5667-b98b-20e51fff27e2 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 6be53cb1-4c51-5e29-a735-00da93ff37e7 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | a8ecb861-76ae-506f-bff3-2b76acaf5b15 |  | note | TYPE - H
label | 7531e023-42c5-5ab8-b7cc-ad331d94c926 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 4aa568aa-0790-51a8-b73e-6cd908cdb7cd |  | note | RESPONSIBLE PERSON - Renewals PM
label | 9d1131ae-2cb9-5f8c-925a-589a9b45a2d8 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (1)
label | d3000a33-9ff2-5397-b680-e5f941f24298 |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | ee1d10c9-d9e2-566b-bbe0-c00d3f6385af |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | 584564b7-757d-5aa0-bf73-fc1d22d7ff06 |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | 4bb6f3fc-c732-59ef-9ab0-82245b3c3f45 |  | note | ○ 400 - 1500m3 - 3 tests
label | 60f4cdef-0ad1-59eb-a0d6-a67ce635b0ce |  | note | ○ 1500 - 4000m3 – 4 tests
label | c95ef780-0ab0-535a-a22b-d40bf1ab40ec |  | note | ○ >4000m3 – 1 test per 1000m3
label | b1cf6f45-004e-5eaf-b94f-b5a61d58936a |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | 4fdbbfa6-48ef-5dc8-8dfe-44849a970f5c |  | note | TYPE - V
label | 32663f4a-f100-5e00-907a-41ee88907015 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | d198eeef-b369-595b-898c-a31c0f04be12 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 28a59caa-56b3-5a09-9b5f-58e0ff870ee4 |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (2)
label | c82619e1-980a-545d-900c-11b664807963 |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | 4b4e74c9-5706-5733-9517-3aacd1e1eb6b |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | d190500c-5c83-5772-ae75-d7ca2300d323 |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | 428602e9-a545-5acf-bd24-d8fe30979fd1 |  | note | ○ 400 - 1500m3 - 3 tests
label | 56da238b-e09a-5554-9248-92c79278b621 |  | note | ○ 1500 - 4000m3 – 4 tests
label | 9b3fd0d1-ba72-53a4-9ff2-0ab9accb0f82 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 0af736f0-cfdd-534e-9e38-cc2c58326e57 |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | 515a57fa-7807-5af6-8e7e-bb59b1b40382 |  | note | TYPE - H
label | 911afb94-5a0a-552e-87ff-e9959ee4544c |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 871b5677-ab11-562e-9f10-78dc1fcc2fab |  | note | RESPONSIBLE PERSON - Renewals PM
label | 8332257e-2a8e-5ec8-9b55-e7f9168fa3cb |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5 - Imported Basecourse Materials Compaction Testing
label | 09ec7ec4-d925-5431-92d6-3eaa2a5b4bab |  | note | VERIFICATION ACTIVITY - Maximum Dry Density (MDD) at Optimum Water Content (OWC)
label | 3abc400f-c7b0-5028-94fd-3d8136851b7b |  | note | METHODS OR REFERENCE - TNZ B/02 - 7.5
label | 89d4cb22-8188-5b11-b858-9e5105dcafd2 |  | note | FREQUENCY - 1 MDD per 5000m² or if aggregate source or processing method changes
label | 2a1571b0-9a77-57ba-adce-eda393585ace |  | note | ACCEPTANCE CRITERIA - Used to support results required in ITP section 8.4 - Compaction.
label | 64686131-b628-5d3c-b78b-47edc71f0507 |  | note | TYPE - H
label | 02b64886-aa8e-5c2e-a0cc-1b6fd78740ce |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 8141eaba-a252-5023-9809-ef9e80c9fed6 |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.6 - Nominal 150mm Make-up Metal
label | 64eb7d05-2efe-59d7-b7c1-ae12573389ec |  | note | VERIFICATION ACTIVITY - Quantity of material used
label | 74ff38b4-67c9-5926-871f-504d7309d91d |  | note | METHODS OR REFERENCE - 150mm depth over high spots
label | 9cc9012c-de1c-5df0-921e-646756906c18 |  | note | FREQUENCY - Each Subsection
label | 57473305-3bc2-5b69-bf75-477f67be5fe6 |  | note | ACCEPTANCE CRITERIA - Correct amount of material used (M³Solid) as per geometric design / MC
label | 816a924f-db3a-5161-b370-809fb5afd8dd |  | note | TYPE - V
label | 7c4fccc3-1061-5185-8e1a-7f78564f4ae0 |  | note | DESCRIPTION - Spot checks to be taken
label | 707b1ba3-6df8-5d76-9f48-e3b1e1d958d5 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 8 - Construction Quality Assurance (QA)
checkpoint-status |  |  | checkpoint | 8.1 - Tie in taper
label | 0fdedea6-0785-53c4-8e2d-790ea0185ff4 |  | note | VERIFICATION ACTIVITY - Visual Check and Stringlines/Lift Peg
label | 7f347698-1bb7-5b44-81a3-4559f2711511 |  | note | METHODS OR REFERENCE - NZTA B/2
label | 21d2a002-46ce-582d-8532-1d6ab98a1ad5 |  | note | FREQUENCY - Per lane per tie in
label | 73892fdd-e4c4-5834-a3c5-caf312a04a75 |  | note | ACCEPTANCE CRITERIA - Minimum layer thickness as per B/2 section 7.3a at tie ins.
label | faa00f9d-2ac6-5f26-81f9-71839830bc69 |  | note | TYPE - V
label | 8f980a76-e227-512c-a7d2-d10a31630dbe |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 012f6aef-7523-5907-b2f4-66eca494bb16 |  | note | RECORDS / REMARKS - Stringlines recorded and supplied, Photographs
checkpoint-status |  |  | checkpoint | 8.2 - Uncompacted Layer Thickness
label | fc682efd-1851-565f-b6d7-fec5e903f61a |  | note | VERIFICATION ACTIVITY - Stringline/Lift Pegs
label | 2823a2f6-ecc1-5c94-91dd-ead06258a65c |  | note | METHODS OR REFERENCE - NZTA B/2
label | a6448d1f-f57e-5ae9-b538-092bf87c4e3f |  | note | FREQUENCY - Per layer imported
label | a8795b3d-ff09-52e5-aa37-5eaf1f117a9b |  | note | ACCEPTANCE CRITERIA - No imported layer > 200mm no less than 2.5x particle size ie 100mm AP40
label | 447e94c7-7c66-5523-9cac-962902991fa4 |  | note | TYPE - V
label | ef3b4023-ed0a-5e8c-9cdc-10bed882cac6 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 40c13c33-af0b-5bed-81df-67cd2a5b9419 |  | note | RECORDS / REMARKS - Stringlines recorded and supplied
checkpoint-status |  |  | checkpoint | 8.3 - Field Compaction Target
label | 88289b67-150f-5abc-b814-8a4dbcd60d02 |  | note | VERIFICATION ACTIVITY - NDM - Plateau
label | 92d2ea6c-009c-576b-89e8-4179af5c4697 |  | note | METHODS OR REFERENCE - NZTA B/2
label | c20d6c0f-f915-561e-9a04-053a45352f3e |  | note | FREQUENCY - 1 Every 3000m2
label | d95c307f-b59a-50df-bfe0-2929a28bde48 |  | note | ACCEPTANCE CRITERIA - Plateau testing done as required depending on the material variability throughout the site to determine compaction pattern.
label | 4ee82bec-15bc-5b71-a281-9f4934422714 |  | note | TYPE - H
label | a3c7c884-5f64-5f69-97a9-90be37059ca3 |  | note | DESCRIPTION - Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target
label | 064b6408-0a65-5082-be76-dfb2529bd0eb |  | note | RESPONSIBLE PERSON - Site Foreman
label | 4393bb04-2c38-5a97-b287-2fd81e4245d0 |  | note | RECORDS / REMARKS - Verified test results of plateau to be supplied
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (1)
label | d86a1ee4-35ff-51b8-ad25-a5627f8189c5 |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | 05d6e972-f07b-518e-9bc5-cae1922b8dcd |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | b2164bdf-47f6-513b-a0b3-a3ec36eda730 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | d9abe2e6-78d9-55ef-b1b9-49e0e95d1697 |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | 0b730b2a-408a-51aa-948e-77a3c9a5c7dc |  | note | TYPE - V
label | 9d96ace9-a2b5-5d3a-a0da-1e112d37dd24 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | 0bff942c-f208-516b-82f5-e28ced3ce521 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 2caaa7b9-142f-5934-b01a-40a8515dce78 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (2)
label | b56c648a-3061-5d11-b11d-58328e5f1f84 |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | 99938373-257e-5276-81b2-d404507cadd5 |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | 3119ba8e-8146-5809-a878-dd70d50917d1 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | e13e496c-a56a-557c-9e9a-c3e8d13bf694 |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | ee093926-ae8d-563e-935b-7dcb202d7422 |  | note | TYPE - H
label | ca3e3c58-1f04-5f07-99ce-576d475eaa0b |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | b43fdd64-bd81-57c1-8e31-4b015740ed73 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 633f52b6-7b1d-535a-8476-d9e10f82bfc0 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 - Degree of Saturation
label | 00a3b1a2-2300-5a12-88e1-73243434c13f |  | note | VERIFICATION ACTIVITY - NDM
label | 298e4ec9-e36e-55b0-854a-3e19d78ac78b |  | note | METHODS OR REFERENCE - NZTA B/2
label | cf5b0aae-dbe2-5a6d-a0df-88d985ba1009 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 9c5b4590-7e11-5ddf-a940-089d92d9e838 |  | note | ACCEPTANCE CRITERIA - No tests higher than 80%
label | ace7e633-649d-5386-a3fc-dfd7fa923062 |  | note | TYPE - H
label | fe01d359-3193-54b5-bb01-3a01cc6da33f |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD
label | 42b4ee91-f437-521a-9562-67dc1578a4c1 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 530331cd-6b5c-5c72-aee4-4a369ed51dda |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (1)
label | c196737d-a106-5c9a-b675-89af21de95b0 |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | 6f937dd0-372c-5c9c-8f60-36dcae46abe9 |  | note | METHODS OR REFERENCE - Visual inspection
label | c5685068-e556-52ec-afda-e5f9f34f1457 |  | note | ○ Cut/fill tolerance check
label | 4a9741d1-58d1-5c58-a0f3-4b6faaedb24d |  | note | ○ String records
label | 5e07ef2f-0976-545f-8c4e-efaa980fa0d1 |  | note | ○ Straight edge
label | a92288f6-63e9-510a-acc1-89a0dd821d89 |  | note | FREQUENCY - 1 test per 20m
label | 0d7c0f8c-3f46-5dd9-a1a5-6ec3ea07ff02 |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | 4d6e5611-c244-53b2-956f-10aea0a1f6e0 |  | note | ○ Gradual deviations
label | f4b81d3d-8633-58bc-bf8d-11e8565dd695 |  | note | ○ Crossfall > 1%
label | 9251ef13-3ac7-5c24-93ec-e913610c8be9 |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | 75e27413-fbf0-5dd3-a5b4-704c41d36464 |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | eeeeac3e-07a2-53a0-8a6b-9d423e3d14a1 |  | note | TYPE - V
label | d18b0431-fb83-5598-8ce4-88e46beefa59 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | 4fb87b1a-1b66-5f34-8b26-5f499bfd6c61 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | e48ae1be-02fe-5f59-ab7d-3592e382f0f9 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (2)
label | 68104267-33ac-5968-8975-9c491d15ac7f |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | 332bf98c-7ba3-59e5-9498-f09011b4c2ff |  | note | METHODS OR REFERENCE - Visual inspection
label | 40933bbd-3ace-57e6-8ce7-fa38c3105774 |  | note | ○ Cut/fill tolerance check
label | 4b20c1dc-9578-5f51-ae96-ce283463d894 |  | note | ○ String records
label | 86ff5d8c-5176-58a1-8506-db3dd76b3415 |  | note | ○ Straight edge
label | ada393df-4bc2-5497-8f4c-10e5d70b45e6 |  | note | FREQUENCY - 1 test per 20m
label | e444657c-20ff-54b1-8bd7-cfab490f1a90 |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | e9dbed30-20cf-5c0a-b5c5-e83716b22799 |  | note | ○ Gradual deviations
label | cc728eaa-9b0f-5a49-bf05-9dc724c41381 |  | note | ○ Crossfall > 1%
label | 893b7d53-f3a8-526f-ba5b-90854c05377c |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | 1f616d96-ee72-5f81-bbcd-e8f27d774ff7 |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | 7b6517e9-9e3f-5c96-9f50-ec2d0ceb4b44 |  | note | TYPE - H
label | 642c25cb-fcee-5382-af54-cd66e6eeee07 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | 42995c13-0106-5e0a-ac4a-3efefde1aae6 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | 0928dcd8-d6b7-58fa-8b31-1dc13b351174 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (1)
label | b5706030-5918-5fa7-8719-374675eef495 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | f7e9de00-223c-5a50-a69d-f4092d84ec46 |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | d5ba33d6-2d9e-5238-89a5-ed5dbd770bde |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | 71e26797-b1f6-5cf9-8b68-ed2a939c8688 |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | d85c91c5-9293-5b51-83fc-2b7be9920b72 |  | note | TYPE - V
label | 84aa1628-cdad-5489-b4ba-e590390f1a51 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 08cf8f1a-e715-59d7-8dbe-f54362050270 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | c3bde08d-d1b2-526c-9a5d-a762aa9a7c52 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (2)
label | 2b532da3-33cc-5e40-a752-0363072b9499 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 4645b196-f25a-5e98-8137-64e5a8a25e93 |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | b3fef7b0-d7b0-53bf-8b15-c2d9d396a1b3 |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | 98f021f7-5f69-5ce2-9dfb-acf714952cdf |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | cbe1bdc8-e6a0-579d-a6d7-c4a1802927c3 |  | note | TYPE - H
label | 8c94d594-2992-508a-84ae-f7639ac08f49 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 8e7a3deb-db6d-5983-bc10-22c8e41e4577 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | f3cceaa5-9993-547d-a529-739ee437fd81 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (1)
label | 961831a4-a983-5d75-be1a-6c19543c06c0 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 529f7b90-f124-53f3-9dc8-12630e59a431 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | 5a3f1f51-fe69-5fc2-860a-ce1cbf4759ad |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | 82867474-94a2-5cd6-9e49-dec0d4323d21 |  | note | ACCEPTANCE CRITERIA - Zero
label | 75bd4170-6fb8-55b8-a785-d7211d63ac5c |  | note | TYPE - V
label | 436be156-03d2-5a98-8287-55a49bd25a97 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 2fb2ffa2-9e7e-51cd-b58c-e03f9cffcf04 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 0e099386-0448-5446-b3db-d7a31495e26f |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (2)
label | 968f14e3-e42e-55df-8207-78e16ebe778c |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 67562f33-b1d1-54df-a5ac-32f0a4dedd89 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | 22e34524-61b7-5f03-8b9e-26e08b2d856e |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | fe24f5a3-4b3c-570c-a53c-d8996b7ea7dc |  | note | ACCEPTANCE CRITERIA - Zero
label | 5f7b6280-9021-518c-b092-5db43eaadd7f |  | note | TYPE - H
label | e4778c03-c334-581c-9a3c-f22d2924d380 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 2cab1271-b342-5533-9842-5a1fb0f4da34 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | e9472951-b64e-5a9a-8d46-ca2a538c5a5d |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (1)
label | db7119ea-1a8a-58fd-a575-21cdfe6413a2 |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | c50e27e9-2784-5fda-82ac-02d74b984cce |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | 0288e739-ce64-5ed5-9ad7-5baf846a59a0 |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | b971b0dd-d767-5ced-a140-a52d86793937 |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | 3d61259d-95f1-559f-9c80-804d77370d1f |  | note | TYPE - W
label | 7cd3a83d-408f-5909-9354-eca24229558e |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | ac2b10fd-61ad-555b-a55f-ad8522f356af |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | 87e4c5dc-f238-5520-83aa-c61a5495658b |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (2)
label | bb0a8148-edce-58f0-9fc1-54e5e1359592 |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | 906a84e6-123c-590f-ac0a-7c342e426083 |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | dabd85ec-3a7c-5d0c-99b9-65420055254b |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | 44610161-7245-5a0a-a6a7-cbbf87411de1 |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | 6ea4c2d4-a336-5ee0-a27a-920f0442e6e0 |  | note | TYPE - H
label | 4f205d71-158c-5bd7-8584-4e8ca99f415d |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | 27af0c93-d4de-5f88-b2d8-d9a33b21be12 |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | 77dd1339-8002-50ca-a379-07c12b944abf |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (1)
label | 5d0e5b0a-f0ee-5bd3-9e71-0339b103e437 |  | note | VERIFICATION ACTIVITY - Visual inspection
label | b2d744e5-1b8c-5000-9117-d83afe25a4bf |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | 8e5fc11b-2f76-5181-b229-1673b4d54661 |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 4770e211-8b33-5892-9adf-fd619575fda1 |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | 5f5f4bac-3deb-5bef-bbd8-ef5f56b69449 |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | 715b71bb-2f22-547d-b44e-d91588bddf29 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | caca3a87-0881-5814-856c-70046d689278 |  | note | TYPE - W
label | 00eabad9-dc29-5d5c-9d6f-125f890daa4b |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | ea8ee03c-5838-5926-a7e2-cb363d4b7de5 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 3a116a48-ce1a-5fc8-a02e-aa284b6c19ea |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (2)
label | c4ee06aa-d1d6-5764-9e5c-5760534b69b2 |  | note | VERIFICATION ACTIVITY - Visual inspection
label | 663ad6da-08a4-5983-b352-56e0428b1745 |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | 6435ca3d-5593-54db-b21a-5d2b52c41af0 |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | eee80342-229e-5ad0-91c3-817d6ac45c40 |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | ce3e1622-cf42-5de5-a2d2-e57f8587136d |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | 9e1d29f2-498f-54dd-8b81-cefd29eb1a32 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | 63fdb745-c1f9-5d71-9393-b933a9ba147a |  | note | TYPE - H
label | 5af4f950-e986-57b5-ad2b-e99528a2def6 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 683776cf-92b2-5e1a-9008-852092abf9d0 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 5ffc98dd-f92c-5f7a-8ade-ceaf5c110508 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (1)
label | f691db41-92ac-5dc8-971a-4216a846b044 |  | note | VERIFICATION ACTIVITY - Visual check
label | f977b4e6-174a-5a77-9308-6444c0dcda69 |  | note | METHODS OR REFERENCE - NZTA B/5
label | c1985e97-6ed6-5837-bdcf-7b0c0c20f67b |  | note | FREQUENCY - Before sealing
label | 8adb87ed-b12d-55cb-ac2b-b3ff1e9a42c9 |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | d5bec4ce-7756-55ca-88bc-59e953dbc030 |  | note | TYPE - V
label | 49776c86-ce72-56e4-b71b-86e55ac20856 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | df24303e-eab0-5224-8b6b-a1adaa7b2eda |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 2e2c64ee-0cd4-5751-a03b-c3e9cde3f4cf |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (2)
label | f5987cad-e309-5c53-b464-a721cff4d638 |  | note | VERIFICATION ACTIVITY - Visual check
label | 29ecdfd0-993f-5adc-81d9-4a499df6a62f |  | note | METHODS OR REFERENCE - NZTA B/5
label | eeb3b145-2cae-50a8-823b-dfa36bd52063 |  | note | FREQUENCY - Before sealing
label | df6801dd-04ec-542e-8fb5-25246ced2662 |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | e253687c-46e2-59cb-b607-194e3864e26e |  | note | TYPE - V
label | 74eb7951-1602-5cc5-82e5-ec1cb4eb7469 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 89da530b-0448-56eb-8738-45eaf22c09bf |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 7158843a-20f4-5c19-84b3-279eec9ca1dd |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.12 - Pavement Surface As-Built
label | 8a1581d7-600f-545e-b051-a2803d715db8 |  | note | VERIFICATION ACTIVITY - Survey
label | 30f29017-211b-59c1-9d91-c7ce451882aa |  | note | METHODS OR REFERENCE - As per approved drawings
label | 1856fa64-9618-5aa0-bea2-960391e71767 |  | note | FREQUENCY - Per installation / Site
label | d9ba34e9-7c56-547f-83a5-8683584d0a37 |  | note | ACCEPTANCE CRITERIA - Accurate survey of all topograpgical features required
label | 8737f2f8-b5ed-516f-90eb-7dd326a52db4 |  | note | TYPE - V
label | c9de7d63-8629-5adf-a996-ea874dbe6d5e |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 9 - Sealing
checkpoint-status |  |  | checkpoint | 9.1 - Sealing
label | 5b430349-4c95-5ccc-a156-d7db19ecb2c0 |  | note | VERIFICATION ACTIVITY - See Sealing ITP
label | 9bde4af0-11c5-543d-940a-7bc23d37c09b |  | note | TYPE - W
label | 78f76881-8f7a-57ec-9d60-b081a5b3b178 |  | note | DESCRIPTION - Hold Point – All hold points and checks in ITP to be completed before physical works continue
label | b5ebb4dd-1b71-5acf-8cf6-9d93476be7a3 |  | note | RESPONSIBLE PERSON - Sealing Manager
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (1)
label | 0e88f3a1-2ab1-5ab2-ad59-709e705432b0 |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 692084bc-c121-510c-a598-54b86d522f26 |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | fb005431-6945-595d-9114-02b215854344 |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | f0ebfccf-8b3a-58c1-a161-25006a406af7 |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 6604439a-9bd7-50b3-8d94-0d227c8fba7f |  | note | TYPE - W
label | 47d3c720-3e41-5b78-9eeb-7a56ce0cae35 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | d9ada5ed-135d-5469-a54e-fa4a1029e860 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (2)
label | c8a0ad98-1dba-5405-a87c-40f1c8bf7d14 |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | cff3ccec-0331-5065-a0f9-ebc8782ee8ff |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 82ec7b45-e237-5d36-b2cc-3320d03b25a4 |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 0ae66614-ae4e-5c7a-85b1-8be5fb7e22f7 |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 3a492a0e-6dc1-5b98-9660-68caa4e93770 |  | note | TYPE - H
label | e559fb90-2994-5326-80a8-0f544efca432 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | 5767feaa-1867-57f8-981f-7985636b0922 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (1)
label | 2f92c32b-d34f-5aef-aea9-7b81e5ff7960 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | e353be0b-1804-520c-8fb8-3f34496d4f0f |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 61f789f3-1ee2-5db5-b3ef-4b199d62f154 |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 26047a63-f603-5981-b43b-781034a7f0c3 |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | c2bc451e-34a6-58bd-ab5f-31eba06f143d |  | note | TYPE - W
label | 7fc3acaf-ea41-5b46-a3a8-27a0839a6ed9 |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | 98e99822-5adc-5d7d-a464-c5223094493e |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (2)
label | f76a36ec-3330-556c-9780-47f523e5fee6 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | d302e567-957d-510f-8740-64698c14e4bb |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | c52fbb48-9af0-5999-9c52-84773f2f4119 |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | deeedac3-790f-5f20-a985-2d6ea5fe53ee |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 42bb8056-d7d3-5582-90df-8cc2e38a074f |  | note | TYPE - H
label | 2c5a9baf-651f-5503-abca-49a9245695d1 |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | bc1d8d41-3106-5d81-8f59-5c009e8e46c7 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Shoulders
checkpoint-status |  |  | checkpoint | 10.1 - Slope (1)
label | d55a2ea9-8e3c-5f19-b2c6-0e5699dec65c |  | note | VERIFICATION ACTIVITY - Visual check
label | ca033b4c-db74-538f-8f37-b514be4472d7 |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | fdcb73ec-c5e0-56dd-a603-06bb1714da92 |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | 88fe922b-3b0f-552b-a0f6-84b189074d9f |  | note | TYPE - V
label | 66253c0b-e80e-5784-889d-7c59191dcf27 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | e0aa29a3-6674-5b5c-a1a4-3a827cfdc02f |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | ce2baef1-a494-5c17-9292-bca3bf52d935 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.1 - Slope (2)
label | dba4bb32-5b02-5445-8e05-20106e1a644b |  | note | VERIFICATION ACTIVITY - Visual check
label | 287e9417-8eee-564d-b060-1cda93cb59b5 |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | 338c9080-4681-537c-83aa-b3c373b868ca |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | dab33a0e-f293-5122-ade7-a6ee70604319 |  | note | TYPE - H
label | 815516fd-2a13-5272-921e-4f7668a52f1c |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | fafa2b9f-492e-5a5e-8ff1-9a4a3ab04130 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 78aacdb6-442f-5b23-918b-0d9dbbd923c3 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (1)
label | 95bdd0e5-d03d-55f2-9145-39fd07cdb5dd |  | note | VERIFICATION ACTIVITY - Visual check
label | 33d96957-396e-5ac1-a924-492cc45cb92f |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | 6a3a7e76-9ea1-58dd-9418-c30c935673e9 |  | note | FREQUENCY - All shoulders
label | ef279894-fc88-52eb-925b-451d9b90caf4 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 7ebee46d-bce5-5bd9-aaae-7f3966576b33 |  | note | TYPE - V
label | c87ed761-ff17-5aa3-adee-1cc971fa0073 |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | a95c9d28-d455-5a84-b4d7-23c54aa482d2 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | ee437c9c-3075-596c-8ad8-b3bc44d21e4e |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (2)
label | eb3ad0ba-f945-5f61-996f-46192b61dbee |  | note | VERIFICATION ACTIVITY - Visual check
label | d1d1c355-36cf-59b6-ab10-8142a27b6e4c |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | 795d6358-898e-51fe-ad9f-bd63a4d11ce6 |  | note | FREQUENCY - All shoulders
label | 2019cc1b-38cf-5794-9a66-f9c97298a742 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 35691ab8-0481-5a71-92eb-ee11bcd30332 |  | note | TYPE - H
label | 9cf296e5-2b41-51ec-bdd7-15f848139a94 |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | f5305504-1c56-598d-9ba5-bdda7b93bfce |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 02e75ea4-12f0-57bb-909b-f800fa8c8f3c |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Soiling
label | 6e0cf039-716e-5911-8c29-c63ca52aa1c7 |  | note | VERIFICATION ACTIVITY - Visual check
label | 661a8c78-dbb5-504d-9e8f-fdb611096ee8 |  | note | METHODS OR REFERENCE - Approved Design Drawings
label | 201b0524-7289-5cd7-9155-932266db965a |  | note | FREQUENCY - All areas requiring grassing
label | 89807266-5ecc-5a3c-8349-c32412da0ef4 |  | note | ACCEPTANCE CRITERIA - Soiling has been done where required
label | 189c1d5e-b600-584e-a52d-d7f09fcab913 |  | note | TYPE - W
label | 676d9a94-c882-5cdd-9b62-d8de634fc6f6 |  | note | DESCRIPTION - As per the design drawings
label | 9bd790cf-5847-5f01-9f38-178acf54c336 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 0388c203-6495-5f77-98b0-bf8b8033c1fb |  | note | RECORDS / REMARKS - Required NO
checkpoint-group |  |  | section | 11 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (1)
label | 2b33657c-0659-5979-9cdc-488ab55b4f0f |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 7fac88a7-e16a-5355-a35c-5398e0b5ddb8 |  | note | METHODS OR REFERENCE - Visual Inspection
label | d5713a2f-a043-5c7e-adb3-ad238949a9df |  | note | FREQUENCY - All signs/markers
label | b5bbd5c9-32b9-524b-b875-0590d44fe37f |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | eaa76b34-404f-59b4-ae2c-9284e4238cfe |  | note | TYPE - V
label | d84de29a-50b2-510a-a677-a696a0845577 |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | 30074f42-85c1-5475-a819-086b4386a805 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | b94db81a-5c6e-582b-b243-05244eac06ee |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (2)
label | 53d36a67-33a6-5600-adb1-05ce88bd875f |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 717eb80c-853c-573f-aa87-0fe4e6e48d88 |  | note | METHODS OR REFERENCE - Visual Inspection
label | 7cd28c0a-ae10-52af-b4f6-bb315bd6e6fe |  | note | FREQUENCY - All signs/markers
label | 257f31f1-8275-52bd-bda1-130c58a1677c |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 8b39a7c3-ab94-55de-abd8-12f493ad3f41 |  | note | TYPE - H
label | 87e7be36-65ba-5890-8315-6af1853f06c3 |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | c6c024be-fda7-56c3-889e-3921c8c21bb3 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 3768df71-0d78-5f06-82ce-06121f5300ff |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2 - Grassing
label | dd6872c5-cb61-5a64-ae1c-c306b97ae60c |  | note | VERIFICATION ACTIVITY - Visual check
label | 5f8ec10d-5405-560f-baa9-18c275ba5ede |  | note | FREQUENCY - All areas requiring grassing
label | 731ade5b-274c-5ee1-9d9e-e4394402c013 |  | note | ACCEPTANCE CRITERIA - Grassing has been done where required
label | b85cfeef-722d-5ede-8218-e4e0954cbe29 |  | note | TYPE - W
label | 248cdbe6-933b-5c1c-8230-0e710f844d63 |  | note | RESPONSIBLE PERSON - Renewals PM
label | f5b8ca1b-5223-5a2b-bb77-04e82cdbfd6e |  | note | RECORDS / REMARKS - Required NO
checkpoint-status |  |  | checkpoint | 11.3 - Drains Cleared
label | 1c5911a0-73c2-55c9-aa90-d0443ff05652 |  | note | VERIFICATION ACTIVITY - Visual check
label | f68943bc-2e26-5795-8cd5-73411ca3e4aa |  | note | FREQUENCY - All drains, after all other works
label | 895de663-142e-5920-82e3-af40a4aac3a7 |  | note | ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | 82b66521-570a-51b8-88b5-2a732c2c1506 |  | note | TYPE - W
label | d10ea99d-c521-5840-8030-025640e63b9e |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 11.4 - Post Construction Design Verification
label | 95f624ff-f747-51ca-94e3-cb003f894013 |  | note | VERIFICATION ACTIVITY - FWD/Beam
label | 87ac5278-fb26-5796-b4dc-44243e9bb468 |  | note | METHODS OR REFERENCE - FWD or Beam at 20m Centres
label | a87abe56-26ab-5c59-9380-0a2033e51cd8 |  | note | FREQUENCY - On Works Completion
label | 373e1e3b-a726-5610-9a7b-53783dca0a2f |  | note | ACCEPTANCE CRITERIA - For information purposes only
label | 2e6b1de5-c647-5949-9b31-bd21d46a621e |  | note | TYPE - V
label | 3b414adb-1803-5498-a4d1-129ea82b2290 |  | note | RESPONSIBLE PERSON - Renewals PM
label | fa063681-146e-5a09-9adc-0a64379adb5c |  | note | RECORDS / REMARKS - For Unbound Granular pavements <10year design life.
checkpoint-status |  |  | checkpoint | 11.5 - Traffic Management Removed
label | f339098c-4589-5dbc-b90a-e46d9c481ce0 |  | note | VERIFICATION ACTIVITY - Visual check
label | ea6bc6cd-2fa0-5895-af71-ed56958864fb |  | note | FREQUENCY - When safe, after all physical works completed
label | b9b5d63e-f7ce-5eef-9f97-11aec569241c |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 35729127-6f83-5a62-9825-4d569862e8a9 |  | note | TYPE - W
label | 0b742ecc-e65c-5382-9e2b-3431f2dedb64 |  | note | DESCRIPTION - Hold Point – TMP cannot be removed until site Audited by Renewals PM
label | ee296a54-6749-5287-a4e0-7bbdcf196781 |  | note | RESPONSIBLE PERSON - Site Foreman / STMS
checkpoint-status |  |  | checkpoint | 11.6 - Site Left Clean and Tidy
label | 1ebb4bbf-76fb-5331-925f-0df24ba7aae0 |  | note | VERIFICATION ACTIVITY - Visual check
label | 78090225-8429-5e6e-8e27-985b1079e0a6 |  | note | FREQUENCY - After vacating site
label | b0bfe51f-ed3e-5309-9053-5a0ecc62434b |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 5858e396-40f0-5c5d-9f00-505652b368b4 |  | note | TYPE - V
label | b4e4386f-8a77-55a8-99d1-f70b1a14a909 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 6a11215b-96b7-5f2b-bee5-8ae9d2507645 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-group |  |  | section | 12 - As-built Records
checkpoint-status |  |  | checkpoint | 12.1 - Collect Asset Data
label | c97f416c-e3d1-582e-91ea-f42dbde929cc |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | c9f590d0-686b-5a4c-9b91-912939e86de4 |  | note | FREQUENCY - During construction
label | 435f00fc-455f-5a23-b243-722d64e9a6ac |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected
label | f9633e08-814d-5bfd-99be-570c425222fd |  | note | TYPE - V
label | cb7980a6-b782-5424-a545-a682913804b4 |  | note | RESPONSIBLE PERSON - Renewals Project Manager
checkpoint-status |  |  | checkpoint | 12.2 - Enter Asset Data into RAMM and/or Register(s)
label | db6e5d56-7841-50f9-955a-70f7ba4e5e28 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | a2ff2882-200d-5012-bdaf-2c91db119f76 |  | note | METHODS OR REFERENCE - RAMM
label | 1b8aaff6-40ab-58b7-ab50-2fe6fa2c50de |  | note | FREQUENCY - At completion of work
label | 835c71c4-c828-5951-aa0d-5bf6c4a816fd |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file.
label | 45d3b88f-27c3-544e-aed1-783c54aa88a1 |  | note | TYPE - H
label | 2ed60faa-2209-5d28-b688-d27f8ac1492a |  | note | DESCRIPTION - Hold Point – project cannot be closed until data entered.
label | cdfd59ad-630a-5d44-a780-d231f8198060 |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ WSP Information Manager
label | 64ce43f5-32d0-5afe-99ad-1b148b67545b |  | note | RECORDS / REMARKS - Submit all RAMM Data to Data Quality Manager for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.3 - Construction Completion Report
label | ea683f0c-3928-568f-ad80-bdd361dc48b4 |  | note | VERIFICATION ACTIVITY - Confirmation
label | e59bdb15-212f-533a-85ca-b4396026041f |  | note | METHODS OR REFERENCE - Contract Specification
label | 449d92f4-e287-55ff-abc1-09a2108d1b09 |  | note | FREQUENCY - At completion of work
label | ca730404-8393-5e4b-bd99-81ffb46e2c28 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 2e799c82-1688-5ef8-809d-02538f1d9783 |  | note | TYPE - V
label | 290bc142-2449-557f-b9b7-3a8bf60b6e6a |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ Renewals Manager
label | 4f6a2ac7-52c9-5b1d-821c-3e0667d5a0c8 |  | note | RECORDS / REMARKS - Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
checklist-sectioned |  |  | checklist | ITP - Iwitahi - Pavement Renewals - Unbound Granular Overlay | itp |  |  |  | Yes | ITP - Iwitahi - Pavement Renewals - Unbound Granular Overlay Rev 0.04 | 8ad8b3d5-69f1-49e4-ba66-4fee900acfd2
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 4174d4ce-68c0-5a2d-8c08-a652405e5410 |  | note | VERIFICATION ACTIVITY - Confirmation
label | b54e17b3-c560-52b5-9435-f527542d3fd4 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 8072b1c8-e7cd-5337-b673-b903e8d06488 |  | note | FREQUENCY - Before work commences
label | a6595f6b-63e6-52ac-8aa7-e2aeeaad3041 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date
label | e8d3e827-6afe-5a41-9fb2-3944076624bb |  | note | TYPE - V
label | a8788723-14fa-59cf-abb8-439ceabd3218 |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | f6c96b9c-22e8-5f18-ad63-76e580663a61 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 963abe80-f351-5dd0-905c-5b8176981a22 |  | note | METHODS OR REFERENCE - Contract Specification
label | 26ba1b67-91ba-52e3-83f4-9ef3ee34fca0 |  | note | FREQUENCY - At least 24hrs before establishment or work commences
label | 6c045521-4819-5c72-bd6b-7bdcd7ca13ac |  | note | ACCEPTANCE CRITERIA - Principal's Acceptance according to guidelines in Appendix 6.3
label | d2c64ab1-fc41-5673-a3d6-7fae9031305e |  | note | TYPE - H
label | 039e0739-085e-5947-bad1-e2128269e7a0 |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site.
label | 5644e635-69ad-50e6-8ad5-638721565b4f |  | note | RESPONSIBLE PERSON - Renewals Manager
label | 94b4d0d7-8b50-5fc8-9ec1-0f70ff0bfaca |  | note | RECORDS / REMARKS - NZTA to approve.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Notification of Intention to Start Work
label | 2e73fec6-b90c-58ee-a8c3-fb284ad37f1f |  | note | VERIFICATION ACTIVITY - Notification
label | 00357885-bafc-53d9-aad9-ad2b8ce974b7 |  | note | FREQUENCY - Before work commences
label | 13603f8e-ebe7-53f2-9232-b20bd0d9f404 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents
label | d12d80b4-886e-58aa-8dfd-fbac7bd45a2f |  | note | TYPE - H
label | 11a46082-8e41-5ba4-8eef-f26f06ccee1e |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site.
label | e498d376-b3d0-591c-a17b-43962e93e55f |  | note | RESPONSIBLE PERSON - Renewals PM
label | 4db00372-2e60-5c7a-bf7e-ba168de5478b |  | note | RECORDS / REMARKS - NZTA to approve letter drop before distribution to residents.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Traffic Management / TMP
label | c1e059b2-39bb-5b78-ba94-604aee7cc969 |  | note | VERIFICATION ACTIVITY - Visual check
label | 695cb8a1-9fa0-54bd-9176-3a89a696e890 |  | note | METHODS OR REFERENCE - CoPTTM
label | 11d9ad4e-a8f9-5b66-9a88-f26be5fb9301 |  | note | FREQUENCY - Before work commences
label | 06067fa7-9355-5363-8633-7033b2cd7b04 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved
label | 65423902-c366-505c-bf97-2ca12eabd3a8 |  | note | ○ Plans approved
label | 5a9f2453-2cc2-573e-96d3-a766b0f9fc3a |  | note | ○ Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely
label | d5628bb2-087d-56db-b363-83d7b893a872 |  | note | TYPE - H
label | 3ce95e5e-183f-59bc-802d-a7f492cb1329 |  | note | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 88fa0771-7002-5e60-88f8-ef5ff0023ff3 |  | note | RESPONSIBLE PERSON - Renewals PM / TMC
label | 1402478c-cba8-5395-86d9-70796bbd1720 |  | note | RECORDS / REMARKS - CAR No., TMP No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Design Report Approval
label | 871f79aa-37e7-5ab5-a113-e9845350d0e8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | dd1cd4f6-2d72-59ec-83d8-1bfcbe802573 |  | note | METHODS OR REFERENCE - NZTA NOC Rehab Catalogue Design & Treatment Approach
label | 8ecb4ab2-a6b8-5932-a7af-dacb90120a7e |  | note | FREQUENCY - Before work commences
label | c9e77489-7780-5efd-8981-4f539a3d161c |  | note | ACCEPTANCE CRITERIA - Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document
label | 0f69bd80-5421-5f4c-a102-ef37dc744f6a |  | note | TYPE - H
label | e72cf4b6-59e7-50d2-8c93-db0bc31e4021 |  | note | DESCRIPTION - Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers
label | bf0f7168-d408-50a0-8711-cbe32a8699b8 |  | note | RESPONSIBLE PERSON - NZTA Network Manager & Accreditied Designer
label | 1d699fa4-5e72-5e6d-b22a-05ca38762d1d |  | note | RECORDS / REMARKS - NZTA Approval to Proceed NTC No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Seal Design Approval
label | 869b8a7d-2e51-5dff-b4f3-e60e6ff04be8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 5d21ce06-fe2b-5b64-a1b4-86cc8c55121e |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Regional Sealing Manager
label | 9a77e3ba-9b2d-5e22-8c1a-3d52997f9ae6 |  | note | FREQUENCY - Before work commences
label | a7af861e-3c17-5707-88a9-3510dcfe39ca |  | note | ACCEPTANCE CRITERIA - Downer Regional Sealing Manager reviews and signs off on Seal Design proposed.
label | 602603a5-0810-53a5-81a1-b968d7b5b12a |  | note | TYPE - H
label | 7c41c8d2-3170-5c96-b246-380089410876 |  | note | DESCRIPTION - Hold point - Review and approval of seal design completed
label | e5f187ea-fc61-57d5-b261-3b220c6382cb |  | note | RESPONSIBLE PERSON - Regional Sealing Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Project Manager Handover
label | 5206ffe8-011c-552b-b7f5-470eac701eb6 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 18f4b48a-2a14-545c-85c2-62d3a44280d1 |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Designer to PM
label | 2d3476a2-101c-5811-9510-79e0f8b7394e |  | note | FREQUENCY - Before work commences
label | 74a27e6d-c389-5e6e-bdfd-ba45c76c6ec5 |  | note | ACCEPTANCE CRITERIA - Downer Technical Services Team Designer reviews and signs off on Handover.
label | 9361718d-29c2-50ad-bce7-937e52984dc7 |  | note | TYPE - H
label | e0a14cee-7fe8-5040-a5d7-51678c518fab |  | note | DESCRIPTION - Hold point - Handover completed
label | b29b8ed9-d165-5631-a2f3-3010f3edc764 |  | note | RESPONSIBLE PERSON - Regional Engineering Team Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Crew Pack
label | 247e01c2-8733-55ec-9d0e-45a9ba89a57b |  | note | METHODS OR REFERENCE - Items to be included:
label | 607e4b70-79f8-50ee-b949-eff6cce15b40 |  | note | FREQUENCY - Before work commences
label | 7876468f-9d5f-5374-8dcc-a84221eb1834 |  | note | ACCEPTANCE CRITERIA - Approved TMP
label | 19e0ab71-ef6b-53f9-8b26-a4dba6b1b647 |  | note | ○ Services location plans / Marked out
label | 4f0dd21d-3143-5b7a-b25e-95f7cf1597ee |  | note | ○ Approved RQP
label | 3079f8c1-4f39-5e7d-92d6-7cbaf94bf019 |  | note | ○ Approved for Construction drawings & Pavement Design
label | de8c860f-eed6-5d3b-abc3-d78d286ef5c1 |  | note | ○ Ramm data
label | a2cd6441-478d-5850-9203-e88f8c11c5aa |  | note | ○ Approved ITP
label | e4b5ba24-3ff5-59f3-bb80-16dde478a13a |  | note | ○ Crew Briefing Plan
label | b6043334-149c-5338-a1a9-5984da43aa5a |  | note | TYPE - H
label | 774b017d-dff3-5ccd-8446-ee06789f0050 |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Setout / Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Setout
label | 40a29005-7ffd-599a-9fec-3e2090d15aa8 |  | note | VERIFICATION ACTIVITY - Survey
label | 10830f96-e29a-5f75-a019-50e1532f6865 |  | note | METHODS OR REFERENCE - As per approved drawings
label | 7f44fee1-d4fd-575a-9a38-005e62873fe5 |  | note | FREQUENCY - Per installation / Site
label | 5775a855-27bc-5150-b69c-44b2eeb19262 |  | note | ACCEPTANCE CRITERIA - Design strings /design surface model loaded for machine control
label | bafb1550-2f5a-56a7-86a2-253aae7c594f |  | note | TYPE - V
label | 542d5bd0-be91-5bfd-8cfa-7d1ced3b38cc |  | note | DESCRIPTION - Machine control requirement. Downer surveyor required for MC upload and verification of model operation
label | 45c18f7d-15aa-5676-a6d6-4fbf61a550e7 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-status |  |  | checkpoint | 2.2 - Services (includes Traffic Count Loops, In-road sensors and Traffic Signal Detector Loops)
label | 356487f0-c4d9-5b12-b409-fe2839f055ec |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 3438b6a3-ffed-5b10-9bf1-0957f051fe56 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 50d22b6c-24fc-566d-9d22-4c95f2b84c2b |  | note | FREQUENCY - Before work commences
label | 61fcf6a2-5b3f-5bf0-a919-2dadb56edaaf |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 9d9dce90-4146-5125-b4f1-9ef0454496f5 |  | note | TYPE - H
label | cab39e48-a4da-59ac-85f8-899053e14ad8 |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
label | 53cbc340-f906-5aef-9f60-d86fcc42a430 |  | note | RESPONSIBLE PERSON - Renewals PM / Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | 488ce35e-6826-51f0-8fe7-2326338e75ab |  | note | VERIFICATION ACTIVITY - Notification
label | 51e5c60e-3ea1-584e-b169-e32e84a5f2fb |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | 65372dbf-0c1f-57ed-a6e9-87d42a7c2530 |  | note | FREQUENCY - Before work commences
label | 31589fe3-04f5-5d52-9598-c497dba1cdf9 |  | note | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | 3bab52b3-1316-5b9e-ab5c-7bce01d04284 |  | note | TYPE - H
label | cb20f2cb-ab3e-554d-bbc0-1266ff0752da |  | note | DESCRIPTION - Where risk of cultural discovery
label | 932992c3-5e0e-5d6e-9e24-a9ee982d63bf |  | note | RESPONSIBLE PERSON - Renewals PM / Communications Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Archaeological Risk
label | f2be61fc-8cce-5976-8c5a-04d819c82c4c |  | note | VERIFICATION ACTIVITY - Toolbox meeting
label | 0e757e7f-a87c-5249-b59c-41a810ccfdb7 |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | 79db126b-e79e-5b59-af48-d0663cc8ced1 |  | note | FREQUENCY - Before work commences
label | 29926a16-419c-5d08-8694-0c08d32b57a3 |  | note | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | e248172e-7fb2-5726-97d6-95fff1eccd15 |  | note | TYPE - H
label | 78934691-427d-5d4a-b96a-34f766955cbe |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
label | 55eac36b-93e1-5c9a-a526-2f5fea4883fc |  | note | RESPONSIBLE PERSON - Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Traffic Management / Signs Setup
label | 6e0f9a44-8d96-5e54-914c-eb0a7b25e9c1 |  | note | VERIFICATION ACTIVITY - Visual check
label | 34e0891b-8fe4-5160-8b66-4fca5e2b7852 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | c37d7a85-025e-5a38-949e-b0ded29abc92 |  | note | FREQUENCY - Before work commences each day
label | 0a89284c-1758-581f-b2b7-d6c9a52bce3e |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 39439cc4-c376-5ace-878e-595cfefca927 |  | note | TYPE - H
label | 7e88d047-35ef-5fbb-8c45-e83486025de3 |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | f5f447fc-bc84-5753-9039-b8bb71ee0d13 |  | note | RESPONSIBLE PERSON - STMS
label | dc21d79d-5d2d-5e74-9f8c-0a94d5352c57 |  | note | RECORDS / REMARKS - Daily site record sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (1)
label | 1938e3f3-a897-5807-803b-adf8fdda71a0 |  | note | VERIFICATION ACTIVITY - Visual check
label | e554f227-41d8-5a3c-91c1-758122f5853a |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | e239b8f7-6d3a-5f67-9a8c-360c45bef817 |  | note | FREQUENCY - Before work commences
label | 748020af-1691-55fa-a2dc-9ec7d26b1bc1 |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | 3efa15a3-ce2d-554c-997a-3f55f516b794 |  | note | TYPE - H
label | 2c5f839c-03be-5577-bbaf-768d05a23efc |  | note | DESCRIPTION - Hold point - Walkover required ahead of MS Civil establishment
label | f40666da-9812-5075-bdbb-1291c03b2151 |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | c3dab642-0e95-5b33-a420-6b6f52a55ee0 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (2)
label | 8b422dc0-8a43-5811-b46e-a92face94d19 |  | note | VERIFICATION ACTIVITY - Visual check
label | 4b1e613f-cdae-5087-9263-7886dbf72920 |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | 49bc23f5-167e-5bab-ac31-eb62c06eaa20 |  | note | FREQUENCY - Before work commences
label | 0d685b05-8f36-5e18-bfed-cb96f606377b |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | 926f6cb8-1bd8-5bbe-bdb2-d792731c67a0 |  | note | TYPE - H
label | 0bfd01ee-42a9-59d7-a6bc-05e44f7d4d94 |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until walkover completed
label | 26850dfe-55be-5766-a947-605477d628d5 |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | adbb3129-f55a-5a77-9612-150849b6a2e6 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminary Works
checkpoint-status |  |  | checkpoint | 3.1 - Shoulder Stripping / Vegetation clearing
label | 5f8552e7-ad98-58cb-96fb-2756fc8058a2 |  | note | VERIFICATION ACTIVITY - Visual check
label | 225f3861-9873-5d47-b8f4-67fc3b06c261 |  | note | METHODS OR REFERENCE - On site
label | ee3506a4-2c6a-5fc1-8f1c-1a5662e0ccf3 |  | note | ACCEPTANCE CRITERIA - Shoulder stripping as per drawings completed
label | 8d8bf9e5-e5ef-5663-bdbd-e667aa34c088 |  | note | TYPE - V
label | 7ca014fe-0126-5cea-bdc7-025754d7605b |  | note | RESPONSIBLE PERSON - Site Foreman
label | 9c538d4d-6ea3-5b48-93b9-d40bfd65a06c |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
checkpoint-status |  |  | checkpoint | 3.2 - Shoulder Buildup AP65
label | fe691580-bf67-5d32-bf2c-9f4594ab4cd5 |  | note | VERIFICATION ACTIVITY - Measure
label | 9126f82f-791a-5493-a834-f99605a98bc7 |  | note | METHODS OR REFERENCE - B/2
label | 2c6e30cf-334c-554e-8b1d-44ab45e17ce8 |  | note | FREQUENCY - 1 per 20m
label | cbfb869b-1a72-535b-a6f9-a238a201223c |  | note | ACCEPTANCE CRITERIA - Shoulder buildup as per drawings completed
label | 7431126f-5682-5b95-b729-a129fd2a2f00 |  | note | TYPE - V
label | 5de04cc7-48a9-5b52-b4a3-fd57c224f208 |  | note | DESCRIPTION - Greater than 30 CIV
label | feae84d0-bb3f-5480-b633-4333f095a5da |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 3.3 - Site pavement A/C digouts
label | 095209ed-8861-5250-ac45-042033729a9b |  | note | VERIFICATION ACTIVITY - Visual check
label | 5e2d9938-da90-5f93-a776-f57594db8758 |  | note | METHODS OR REFERENCE - Check RAMM records for depths
label | d962feec-4565-5c02-82e4-e60c5bd67add |  | note | FREQUENCY - Before Overlay work commences
label | 1a89557a-a598-5134-b039-c615bdba786a |  | note | ACCEPTANCE CRITERIA - Work completed prior to overlay contractor onsite
label | e9212990-5af0-586b-a7c8-18109058ef17 |  | note | TYPE - V
label | bfafeb32-dd75-5542-bf0f-37f1ecf62aef |  | note | DESCRIPTION - A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed
label | 85414b80-d123-545a-b44a-e3d54b16dc1d |  | note | RESPONSIBLE PERSON - Construction Supervisor / Site Foreman
checkpoint-group |  |  | section | 6 - Preteatment of Insitu Materials
checkpoint-status |  |  | checkpoint | 6.1 - Cut to Waste Existing Seal
label | 00aa479d-0981-5596-b2b7-04ac3620f086 |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | 4a81a9dd-c785-5ea5-a4fd-f70045943e90 |  | note | FREQUENCY - Prior to material import
label | 3d66c84f-9d07-55eb-a6d1-ff243242bf22 |  | note | ACCEPTANCE CRITERIA - No unsuitable material remaining
label | 53c6c742-bf75-54bd-8196-58eac5179134 |  | note | TYPE - V
label | ae45ddc8-510e-515f-adce-7047fcfb4cd1 |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 6.2 - Undercut unsuitable areas
label | cd98ff46-9ad4-51f9-920d-f366b2afa182 |  | note | VERIFICATION ACTIVITY - Visual Inspection/ measurements
label | 5be4c427-1bf7-5389-937b-0b425ee08fd8 |  | note | METHODS OR REFERENCE - Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table
label | f76f1124-a6ab-56bf-8bd0-b4d608b02a89 |  | note | FREQUENCY - Where required
label | 1b63ab1e-6fa9-5d0b-93f3-d569344fab02 |  | note | ACCEPTANCE CRITERIA - All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to MDD
label | 5dfecfdc-7e68-551c-ad10-6fabeaafd905 |  | note | TYPE - H
label | 10f78e9f-eb79-56c3-88d7-e741abb2fc67 |  | note | DESCRIPTION - Hold Point - Organise site walkover with NZTA MCM prior to dig outs commencing. Variation agreed.
label | e861ac5d-7410-5f49-b80d-490572e7e28e |  | note | RESPONSIBLE PERSON - Renewals Manager / Site Foreman / NZTA MCM
label | 8da79086-e232-5fca-8c32-d5ef821e122a |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Imported Basecourse Materials Testing
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (1)
label | 12a514f7-b406-5e2f-abff-66ac2115cdb8 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | 7d24083b-6bd2-5603-805b-34376eea8ea7 |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.10
label | 8a53b035-b889-5204-bcfd-f6c29ad59aae |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 5cf14533-0268-5bc1-bff8-990f6aa9b240 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 79c4cd97-c80a-51cf-932a-dd7a8b1bc071 |  | note | TYPE - V
label | df392f2a-101e-5d40-ad31-adfd91eb737b |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 32a59d9b-0b28-5ba5-b12c-39f028c0d94d |  | note | RESPONSIBLE PERSON - Renewals PM
label | 7f8e248a-c027-5105-8c79-96213789262a |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (2)
label | 2a5e8daa-0aa0-5658-948b-ef8c2b0290d2 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | 2e8171ef-0913-5e73-a168-c8ad735b7490 |  | note | METHODS OR REFERENCE - NZTA M/4
label | e526cb5b-f56c-543e-8d79-dad27ce3f0c6 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 1ed7c049-499e-5c00-bd23-97e1a2ff8112 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 93e83829-6237-5075-a5e3-bdf6c8aa61e7 |  | note | TYPE - H
label | 0edde843-3457-50eb-999b-5800a624e82f |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 13c9c982-7a54-5f8b-8b90-a1ab218069ea |  | note | RESPONSIBLE PERSON - Renewals PM
label | 94b29787-36b8-5650-bc43-5f72f461de34 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (1)
label | fdfd9c3c-3592-52da-b104-dc01ed4c3bc1 |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | e769e590-b55e-533e-8ef4-bf8d1674889c |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.11
label | 0dd5e2c4-6264-53a1-ab70-d213a8bb0ede |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 39d28852-70c3-51ea-a2ef-48a0124d7d06 |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | 6b841133-54a7-59b7-a733-f0ce35741509 |  | note | TYPE - V
label | 1a004706-74e4-55a0-998c-c6715435fc49 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 009539c3-da9e-5d38-bba1-2e9d5233e27f |  | note | RESPONSIBLE PERSON - Renewals PM
label | 571a9134-a6a1-56b6-b5e1-93818ec05c57 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (2)
label | b2290bbe-d458-5a84-863f-d5eb2f63ff07 |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | ee0a8063-996a-5d4e-8bc7-679e5019b035 |  | note | METHODS OR REFERENCE - NZTA M/4
label | 052724ba-c592-5479-9515-dbf9145286f4 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 8926b0ab-ee59-5df0-86dd-4433aa52a5b7 |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | aed4bb68-a5de-5cc9-abac-b39d97bdd600 |  | note | TYPE - H
label | 03372c40-f72b-59e1-a4cf-8a40bbacb4c7 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 69256ed2-5b18-5f87-a69c-b0b2ef6c9aa5 |  | note | RESPONSIBLE PERSON - Renewals PM
label | f88bf855-1ad2-5168-bc4f-e263644bcc6e |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (1)
label | 3a648f14-a2ac-55bf-affc-30ba70071583 |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | 8ffd9b41-b753-5913-81e8-40c9be921039 |  | note | METHODS OR REFERENCE - NZS 4407 T3.15, NZS 4402 T4.1.3
label | b1af47a4-2c2c-51a9-a6fd-89c2549556b0 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | c22fadee-605d-50d9-8eef-b50585cf2fa2 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | 6400fc55-4eea-538e-9dae-ab93b602f554 |  | note | TYPE - V
label | 2e6bc3fd-8898-596c-aedf-328c8b326532 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 384f61e6-ff10-5fcc-8f57-9a2b7ffb3e33 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 60c245bc-657a-5051-ae67-5ddefbc99592 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (2)
label | 95b959c2-4166-5316-9500-31b33b381e29 |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | 827f53dd-d92e-59f3-a8d0-22fbd0996dd4 |  | note | METHODS OR REFERENCE - NZTA M/4
label | fc66b998-cb96-5cc9-bf09-031bdde74782 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | f83df81d-f60f-5072-8e26-525ad6fd8792 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | 44de2906-4950-5595-987e-856b1547222d |  | note | TYPE - H
label | 3fb36a52-eb59-5b08-a971-a06a48c89181 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | de6ba235-2312-5038-a762-e684c00709c6 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 3dd30a01-44d2-551f-acd8-ed1da1e66629 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (1)
label | 0cdfa523-639e-5d5e-945b-1572be5f9e0c |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | 1357228d-c2da-542e-9798-5cb0faa16f5c |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | d16144f7-3ec6-590b-957a-26d994da63ed |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | d4671062-4ecd-5318-be2e-8a0aa3f27c2e |  | note | ○ 400 - 1500m3 - 3 tests
label | 8f44868e-c853-5594-9b66-27f11066b37e |  | note | ○ 1500 - 4000m3 – 4 tests
label | c5420735-ea4b-5ea5-b902-94c3e40d03e2 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 66170267-05a7-5165-85ba-fb11abcb41c7 |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | 66ce3c16-88bf-5543-911f-39760f733f27 |  | note | TYPE - V
label | b4531cbf-eaed-5b1e-bf7e-db085541c409 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 02bea9cb-085f-5bab-b816-ab4470bdaf87 |  | note | RESPONSIBLE PERSON - Renewals PM
label | a4d55e48-e3e6-5f39-8c78-7c7f891b9693 |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (2)
label | 255521a6-243e-596e-a073-9ecdfcc4a91c |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | ac7accd2-1a7a-516f-9007-1cca4e56c22a |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | d6c3af08-ae81-5de2-899b-55048eb7ddac |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | 4fd5ea65-4991-50dc-9cb8-2e85fed3105b |  | note | ○ 400 - 1500m3 - 3 tests
label | b37966b9-139b-54dd-8758-e6d09f17d406 |  | note | ○ 1500 - 4000m3 – 4 tests
label | e89e21ba-c37c-51db-86c5-9ef3d4abfa72 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 6c25e3d1-209e-5db2-8c3e-33cd91194d5a |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | b5e8a72d-2c93-5969-b804-698bde262c88 |  | note | TYPE - H
label | df1b5de6-17cc-5b87-8199-8accd9c81458 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 5f2a3791-0207-59a2-a24e-3fa4d8d1630c |  | note | RESPONSIBLE PERSON - Renewals PM
label | 504206e8-a6f3-563c-b1e1-f19ee3afb53e |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5 - Imported Basecourse Materials Compaction Testing
label | f2b9e8cd-1039-5105-a6d9-601764671da3 |  | note | VERIFICATION ACTIVITY - Maximum Dry Density (MDD) at Optimum Water Content (OWC)
label | 83a1541f-bcdd-5315-928e-cb0c1675961c |  | note | METHODS OR REFERENCE - TNZ B/02 - 7.5
label | e4bd87df-90c1-5573-bfb5-aff53625f7b7 |  | note | FREQUENCY - 1 MDD per 5000m² or if aggregate source or processing method changes
label | 369158e1-9cd4-5aa6-a7c1-1f8446c63a1b |  | note | ACCEPTANCE CRITERIA - Used to support results required in ITP section 8.4 - Compaction.
label | ddd6b1b0-bcde-5eb6-ba1e-1525146fa090 |  | note | TYPE - H
label | d35c593f-5409-514d-b040-a86f77d00ef6 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 2a10c039-fd05-5be8-9278-71879dc576cc |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.6 - Nominal 150mm Make-up Metal
label | c0350608-6ac8-5bfb-900c-6ba196c9d192 |  | note | VERIFICATION ACTIVITY - Quantity of material used
label | 649c82a3-7307-5421-a48e-e60c3e1e672f |  | note | METHODS OR REFERENCE - 150mm depth over high spots
label | 1f48bdbe-d83c-530e-995f-37078f03eb17 |  | note | FREQUENCY - Each Subsection
label | 7e79577b-fe0b-5859-b071-5fd6a9934961 |  | note | ACCEPTANCE CRITERIA - Correct amount of material used (M³Solid) as per geometric design / MC
label | cc0aedfb-bad7-55ce-96f3-199f74afe146 |  | note | TYPE - V
label | 86d73361-ef4d-57f9-aac0-24b97dc6b1bc |  | note | DESCRIPTION - Spot checks to be taken
label | f558e3cd-a4c0-5ce1-a8ba-c277b2a4bf2c |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 8 - Construction Quality Assurance (QA)
checkpoint-status |  |  | checkpoint | 8.1 - Tie in taper
label | 85ca84f4-43ac-5412-9007-3868cdc355ca |  | note | VERIFICATION ACTIVITY - Visual Check and Stringlines/Lift Peg
label | 6b9bda98-c3de-59af-b8b5-7d50b55e8fc7 |  | note | METHODS OR REFERENCE - NZTA B/2
label | b2773533-0326-5192-a041-be972494a771 |  | note | FREQUENCY - Per lane per tie in
label | c79e5326-6c0c-5096-afef-f0b9946738e5 |  | note | ACCEPTANCE CRITERIA - Minimum layer thickness as per B/2 section 7.3a at tie ins.
label | 3be9cc66-9edf-5592-8f77-beabfec0b683 |  | note | TYPE - V
label | 046c5078-4809-5aca-b89e-cd19dc1f056f |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 204cfe2f-34af-5aa7-b7dc-7e6e21cd532a |  | note | RECORDS / REMARKS - Stringlines recorded and supplied, Photographs
checkpoint-status |  |  | checkpoint | 8.2 - Uncompacted Layer Thickness
label | 2e2fbc4b-5937-5ccc-887d-4868162c98e6 |  | note | VERIFICATION ACTIVITY - Stringline/Lift Pegs
label | b32598c3-1266-5ecc-935a-136e27c9d4c4 |  | note | METHODS OR REFERENCE - NZTA B/2
label | c82bf8ed-17d5-5619-8167-2ece3e98fcfc |  | note | FREQUENCY - Per layer imported
label | 09e9231a-72e4-5196-b302-800a311c7e13 |  | note | ACCEPTANCE CRITERIA - No imported layer > 200mm no less than 2.5x particle size ie 100mm AP40
label | 05de832e-4e1f-539a-a4a1-172d55e3e81f |  | note | TYPE - V
label | 21e76a75-1ca9-538f-9c3a-9660036854da |  | note | RESPONSIBLE PERSON - Site Foreman
label | 369dd850-2361-5dac-8d90-216f9960910c |  | note | RECORDS / REMARKS - Stringlines recorded and supplied
checkpoint-status |  |  | checkpoint | 8.3 - Field Compaction Target
label | 27031d5f-e683-571f-bb6e-50a60070e849 |  | note | VERIFICATION ACTIVITY - NDM - Plateau
label | 251a4976-1d93-5821-b004-ab41646ba198 |  | note | METHODS OR REFERENCE - NZTA B/2
label | 0c38ddc1-e664-5e13-a3c5-72013a79be2b |  | note | FREQUENCY - 1 Every 3000m2
label | 47c8dc3d-505a-53fe-a261-dac6d0a420a4 |  | note | ACCEPTANCE CRITERIA - Plateau testing done as required depending on the material variability throughout the site to determine compaction pattern.
label | 0f325da1-8fe4-5717-a3ab-86ef325adb74 |  | note | TYPE - H
label | 388727f8-d54d-59ee-b993-feabde6d9b21 |  | note | DESCRIPTION - Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target
label | a0acad78-4e15-544d-a982-099c20c42e66 |  | note | RESPONSIBLE PERSON - Site Foreman
label | b33867e2-055d-5ad8-8515-559a09e4222b |  | note | RECORDS / REMARKS - Verified test results of plateau to be supplied
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (1)
label | 61898ec1-a8a0-5b8b-8a79-62a3df63b2e3 |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | 9f972995-6ba8-5d09-8b0d-44114180d136 |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | 48e59a12-dc64-5d8e-a2e7-481eb1ec92bc |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 730ecd35-8fc1-5d7a-bfcf-d37aa4fac8f3 |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | 8aa72d64-70ea-5681-bf15-964136e34ef4 |  | note | TYPE - V
label | a576acd3-b8c8-5467-800a-7ad6410a7ccd |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | 15efd0c5-54d8-5f82-9e8d-434842b109f1 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 0d765d51-5190-5255-83c6-4eb575f8ffa8 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (2)
label | ba6c2f02-91fe-5fb7-b4ae-5ff21444b626 |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | c6927d3c-8a60-597e-a360-a39aa10efc31 |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | 6e634ddf-76d8-5f46-b78a-0f7e98538492 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 8dbfaa2a-e87e-579e-92d2-f98190e6d5a2 |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | 562c7717-986c-58fa-b263-367148caa572 |  | note | TYPE - H
label | e4bcecbc-a29d-5594-9f65-5aea397aa841 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | 32c93d02-ecdf-503a-830b-cb1012614745 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 6c85ef0e-773c-56d7-ac3a-f3b25c3d341b |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 - Degree of Saturation
label | d4b26b13-c59a-5968-a9a9-0aae7dde6cb5 |  | note | VERIFICATION ACTIVITY - NDM
label | 5f31525d-d0dc-5c47-8572-6fc99309c3d9 |  | note | METHODS OR REFERENCE - NZTA B/2
label | 5514106a-fb06-56ce-a17b-012b29d5da0b |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | d5ac245c-3408-5a97-9674-6bdb7e4f12b9 |  | note | ACCEPTANCE CRITERIA - No tests higher than 80%
label | 71477c87-4827-568b-b127-becbd37de865 |  | note | TYPE - H
label | 30101b4b-c922-503a-94a3-759ee814d005 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD
label | d461ac26-cb08-54c1-b73a-b845493d5c56 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | d9492faf-1f52-5448-956b-2f87ce6ef0a1 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (1)
label | 61c59679-2b42-5088-bf85-d4101d7d5cdf |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | fd4f45b6-b753-52c4-99bd-4b814dc398df |  | note | METHODS OR REFERENCE - Visual inspection
label | 714dd7cc-4e3e-52d0-8175-fb1df41d99c3 |  | note | ○ Cut/fill tolerance check
label | 177b35f2-71f8-5f6f-a603-464addd338f7 |  | note | ○ String records
label | 962edfb5-0616-52a3-b66a-93f7e1545436 |  | note | ○ Straight edge
label | 5c8ac09e-29be-529e-90b0-a39d486fb404 |  | note | FREQUENCY - 1 test per 20m
label | 95c09bf1-2160-5d5e-9593-0d0f462a955d |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | 4b879488-79fa-5c41-b53d-5e71c96d22db |  | note | ○ Gradual deviations
label | 0175185b-4d81-5d3d-b779-90a85f857e67 |  | note | ○ Crossfall > 1%
label | 366dcd3f-0bdc-57ae-97ee-31325dd744d1 |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | c8bcd17e-c069-5f8d-98d6-71d541bea003 |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | 32c7c050-cc55-5c11-817f-54298697088f |  | note | TYPE - V
label | a40a3f45-2980-527f-8a18-a6a4d54da91a |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | acd4adfa-4486-5174-a09b-f83265e06b79 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | 0b14a5f3-cecc-5c01-a156-5f36fd4107ce |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (2)
label | a11fca4f-9949-5f78-b4c7-6bd36569a8de |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | c6bdd420-1c3e-5695-826a-6e4770fab45d |  | note | METHODS OR REFERENCE - Visual inspection
label | c44414cc-1a4f-53b7-bda7-8f6ba1d22cbe |  | note | ○ Cut/fill tolerance check
label | e8832226-6242-5c61-a968-bb2c55e481a5 |  | note | ○ String records
label | e7c36fec-2acb-5320-9d81-867ccc722a6d |  | note | ○ Straight edge
label | e885b1f3-98da-5f26-802d-32ab1b3ff8a5 |  | note | FREQUENCY - 1 test per 20m
label | 93de8536-a2c6-5232-84a7-5ef9d8f883db |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | 20b4ec76-9f33-5c65-a79c-2e2ee9f2d6be |  | note | ○ Gradual deviations
label | a0efd23f-da09-5135-800f-47b0fb54fc8f |  | note | ○ Crossfall > 1%
label | 7c5981c4-0506-5a4b-b087-27664c4cfe8c |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | d648fd95-2bd3-565b-9bef-48099af34276 |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | 2e1e8666-915e-5550-9392-401c45fb26d7 |  | note | TYPE - H
label | b566f00e-1303-551d-a37c-dd8152210c9e |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | 7c4125e9-bc43-55cf-905b-95993006de80 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | b29bc749-eb23-5053-b6f5-148e867f9a84 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (1)
label | f27851c1-d610-5eee-a3db-a3b95be97db5 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 0bc675d2-ec6b-5d48-885a-10bbba478dc6 |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | b23aa7c1-74af-543d-b623-808de20dcd33 |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | db944eca-b2ad-57a5-9dcd-17d9f2b2a07b |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | f8aa7373-8917-5421-80a2-5da3d2154007 |  | note | TYPE - V
label | caf081c5-7e08-5d2c-83c0-8b52e3583b28 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 3ca52b57-2b6f-5185-95f0-d4cb05d7b6d2 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | cc2849d5-4f88-5244-b76c-4971fe95b31a |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (2)
label | 7be1112b-f133-5e84-a58f-0221f44daff2 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 670e88eb-7031-5bc7-b123-b66839d8a5c6 |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | a79c18a0-d326-56ef-b360-ad3831b45f0e |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | 4a287642-c1b2-5798-abc1-92c172d5e8e0 |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | 6e8b11be-34d6-5c77-90ab-ab6fb027f839 |  | note | TYPE - H
label | 15f9d893-cb6d-50a5-b28f-fc952894b71e |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | c4aa98ad-466d-5ef4-9aeb-6a4cbe205fad |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | c5f1ec9a-2663-55cc-b9e9-395a2df07f5c |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (1)
label | b1ee256a-2f1b-5808-9cc1-1f9a3743c05c |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | e6dd4a9c-a3a4-5e91-aab3-0b592eb95cd0 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | ff2a8a85-8674-5be8-98fe-f429c55d7cca |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | 9d2eb660-0ac5-5851-a08c-4d1fdbbe8070 |  | note | ACCEPTANCE CRITERIA - Zero
label | d187b3b1-625f-5ba7-9981-c91725600b2b |  | note | TYPE - V
label | 5a19fef1-9fb9-5928-99d9-0e0fa828ae5c |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 830fa2db-70c0-5d33-bb40-2471e0ac3e98 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | f72aa05b-2540-5f0d-80d0-4a58bc5f2bba |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (2)
label | 075fb1e1-32a9-5bcc-981f-f17b4d81b33c |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 591b8c1b-f5b2-5b03-b9c3-05a604551d49 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | a82886d4-0fc0-5a07-abb4-d53b94272a91 |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | c0ecd3c1-98d2-5383-b5d6-7c16b3a3ea26 |  | note | ACCEPTANCE CRITERIA - Zero
label | 0e3a3d52-377d-5704-add3-057a4a14a2d0 |  | note | TYPE - H
label | bd622de7-ac28-5481-8b99-53a171db1f9f |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 51e9f99e-5dba-5e63-8337-84e2f30573f6 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 971fcf14-522d-5aa7-a230-af32eca4e0ae |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (1)
label | 48e2c2cf-2deb-5840-a9dc-e3b49fe0a640 |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | 6202e655-76fa-51fd-8ed5-1eeee3f3a9bd |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | b6a09c32-c1aa-5532-8aa7-29570282ac40 |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | 7487e034-ad90-5a9d-b5a4-dff4cf91699f |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | 9652151c-78d3-5566-ba6b-4c7db2bd941a |  | note | TYPE - W
label | 03adb84d-9d37-5d76-8649-12bf486865b0 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | f62955e1-0ad0-54d8-919e-4ac324b8ab66 |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | 943b99ac-3347-58c0-b9a6-d39eeeecc5ed |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (2)
label | 96f295f8-7826-5f60-9c2c-589ab4755376 |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | 57c2bfc4-4a68-50c9-980d-bbc6ef7d8209 |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | a3c751db-448b-5ce3-9a06-fa24affb0526 |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | 50e8113c-fa17-512b-a0bb-ba62f0b428eb |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | a3a719c2-1139-55ed-9520-b0959499bbab |  | note | TYPE - H
label | 1793135c-bba6-5212-89f8-3f92d99e03f1 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | adc337c2-db00-59a5-aafb-d58449d86d27 |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | b270a724-0697-5cbd-99b9-faaf9c036967 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (1)
label | 26b07094-8c0a-5f95-a8d0-0af78d32b3a1 |  | note | VERIFICATION ACTIVITY - Visual inspection
label | be639fef-563c-5ae5-873d-7b2943e4bd5a |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | 07436a81-e130-5bc1-8bc8-53fa9bf807e3 |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 1476a551-9396-5093-9dcd-84b24ea85a0c |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | de898be6-1d39-5de3-bdac-00a279e07ca7 |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | 9582c6de-1ea9-5d93-9e5b-191b45dd5bc7 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | f41d37e1-3d00-5a37-b9af-86f00f62bed3 |  | note | TYPE - W
label | f4531fcd-56b6-51aa-8adf-24f85d91c6a4 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 7072ec66-c1b4-5d03-9e9f-bc3aa25d53bb |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | f0dfed0b-491b-5cb4-9c0b-67b67013034f |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (2)
label | ae1c0a1b-3f79-5de6-88dc-92f078014554 |  | note | VERIFICATION ACTIVITY - Visual inspection
label | cf1f6a18-f55c-54ae-9fbe-a81d9f1fdf47 |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | d8641c67-96ac-5c41-85d0-4a612130d5f8 |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 7954c483-32b2-5766-bac2-7c1fc8dafb8b |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | 1763015d-5d60-5592-9f33-692517af0a68 |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | 348ab231-e30c-5a87-8bb2-ce5c45f39829 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | 24a1ec32-edaa-5f4f-a081-46bbb3283c56 |  | note | TYPE - H
label | 8fcaec9d-fce4-590b-8397-62dfcd7c4dc4 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 50a428e7-2542-5594-a8eb-750ca166f3fe |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | b9f11c11-39bb-5474-bcb0-8fb17d3eff46 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (1)
label | c7b7ad45-791f-56c4-a35a-6619bf18e2d1 |  | note | VERIFICATION ACTIVITY - Visual check
label | aaab7c99-9518-5de6-a5ac-53869653bbf7 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 9c567a29-76ed-56bb-8698-3c0821156e9c |  | note | FREQUENCY - Before sealing
label | 35582649-5d14-5260-8159-bd2316e86ec2 |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | 8f951e51-ef6b-5fc7-a321-bb49366bc072 |  | note | TYPE - V
label | 5635d18c-8ef4-54af-9925-56a50db552d9 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 8da82fd0-5820-511c-bc4d-4ca6f125ad5f |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 765fece2-85d4-589e-be8e-8e0d0443b645 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (2)
label | f80ed86f-a245-5c56-a64d-bbe2b9d135e8 |  | note | VERIFICATION ACTIVITY - Visual check
label | 96a8aa60-2e82-5340-8b35-b296395b1205 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 9cf392f1-0d2d-5c26-8750-071e664f1909 |  | note | FREQUENCY - Before sealing
label | 3c8bd6c2-c85d-5924-be71-1e4f2aadaf25 |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | b8128da4-560c-5f13-823d-5839a7c9851f |  | note | TYPE - V
label | 878ea548-dd4c-5c15-900a-289cc720ce42 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 7a505248-22dc-5d11-adde-468533031b82 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 9c7cca66-5224-5a71-b1a3-9a29f83b0733 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.12 - Pavement Surface As-Built
label | 181a22d5-4e8a-5714-888a-0fb76a619538 |  | note | VERIFICATION ACTIVITY - Survey
label | 0c69b92a-4b53-578c-a946-545215b2aa53 |  | note | METHODS OR REFERENCE - As per approved drawings
label | c1e82ca8-b293-5c21-a5f2-435685c4ea19 |  | note | FREQUENCY - Per installation / Site
label | 621c947e-0930-505a-b012-4df6039a4f6a |  | note | ACCEPTANCE CRITERIA - Accurate survey of all topograpgical features required
label | 35c495ae-fc57-5404-b18e-430d43c9a873 |  | note | TYPE - V
label | c450d201-282b-5d22-a468-5caf963baaba |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 9 - Sealing
checkpoint-status |  |  | checkpoint | 9.1 - Sealing
label | f6f55159-5957-59cb-9090-1c74f043c7c6 |  | note | VERIFICATION ACTIVITY - See Sealing ITP
label | 3ae56a97-4a55-5d8d-a6cf-b04fca0f804b |  | note | TYPE - W
label | 0fa4e98f-2b05-508a-a3a9-e8619b9b178e |  | note | DESCRIPTION - Hold Point – All hold points and checks in ITP to be completed before physical works continue
label | 8156aa22-d2e2-5617-9631-1cbdf8d85ba5 |  | note | RESPONSIBLE PERSON - Sealing Manager
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (1)
label | a3516a7c-e14e-5bd4-bd39-28d7efc42c2b |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 3760689d-641b-5f9e-8015-5f0c3573006d |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | a126dfe3-081c-530b-934e-28d2809e0c2e |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 8551bb80-bdc9-5ff5-bcfb-1d8c9116c879 |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | ade0b743-57a2-522c-ab2b-2fb507325e51 |  | note | TYPE - W
label | 0ef5842f-19d6-50d3-b2dc-f2839b0c13f0 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | 11d64d63-cab2-5553-8743-6189e406550b |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (2)
label | 58ea5c07-2481-5990-8848-157343ed92fa |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 37561c02-b3b0-5db7-8862-0f01307db03c |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 909ba1ff-02ba-5a5d-ab04-51f1c7f686f9 |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 5e7c4258-a5de-5954-87b4-d25b532d7c7b |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 3fc43b5d-09e9-50f0-bf9b-bed667573589 |  | note | TYPE - H
label | 29ab1e4e-976c-5a3b-a244-3c2d110d2f16 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | 9da5b22b-4c36-5201-bb3f-cb84a14f992f |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (1)
label | 3cfa5f3f-87b5-5cbb-90a8-ec891d4c1217 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 0fd059ae-e3d4-530a-a3f6-e8696fc3817f |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | ce3bcff1-86f0-5268-9e21-48ed3a155e54 |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | ac207708-639f-59fc-8af6-e437c22974c8 |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 85a7f205-7509-5174-85f9-08e1dcb15824 |  | note | TYPE - W
label | d782bf17-4d4d-56dc-b09e-f06ae34525c8 |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | f029b072-9b86-58c6-aa46-be366941fb99 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (2)
label | ce1350f1-050b-5584-8702-19cf4c637dd0 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 0bebd4c3-111c-5b4c-9484-a5cdc9834969 |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | a3b05b57-aefc-587e-abf6-252747e8ec2c |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | d39570a9-dbe5-5f58-ac0b-114af41d3452 |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | f92e3375-ece5-5807-8f7b-07714d55bba2 |  | note | TYPE - H
label | 71b58a40-a22b-5326-b77a-58ed2ee1b4cc |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | 3bdaf16a-2dc9-53a0-953d-50eece51aa54 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Shoulders
checkpoint-status |  |  | checkpoint | 10.1 - Slope (1)
label | ae6adee2-f02d-5df7-9dc1-fe055e97aaa5 |  | note | VERIFICATION ACTIVITY - Visual check
label | eae61bc3-6b86-5835-8286-07bbd9b23480 |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | f4a0eeb9-b0bb-5e20-bde7-27fe14c22316 |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | 2e099382-2698-5b72-b1ad-71cbaf0b0d66 |  | note | TYPE - V
label | ae09d6fc-162e-5753-a26a-20a6a8e2f9f8 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | ca6ebcb6-bdd2-5552-9117-ab5c9fce42e1 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 2290f5a7-21ce-5f63-8c16-a0890558c4db |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.1 - Slope (2)
label | 0e6f90f6-f41b-526e-8760-679b6d3a48e3 |  | note | VERIFICATION ACTIVITY - Visual check
label | cfd12a45-fc33-54ed-938a-3af530c093bf |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | 003966f9-773d-5e8a-bbfd-3504b7563551 |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | d89b6410-9522-517a-ac54-6331e1752326 |  | note | TYPE - H
label | 82523abe-61b7-5691-9c6a-2901e6acc851 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | 8cc85784-dd43-50e4-b60a-d139a689f795 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 6f1a4353-8f1b-5e24-9180-b9e484274dbc |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (1)
label | 5af0c234-4016-5b00-8c10-f208cdf8496b |  | note | VERIFICATION ACTIVITY - Visual check
label | 753d8bcc-5049-5635-8f62-2e4ee659ac41 |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | 0307040f-fbec-5582-9118-fa8fa829147e |  | note | FREQUENCY - All shoulders
label | b6b5de73-dbd4-5aaa-8228-923340e4fc51 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 40d89b7c-1d20-536f-8daf-ed592862288c |  | note | TYPE - V
label | 01e05c46-c5d5-599e-b5d6-ea93d628d5d3 |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | 32b54fab-9d2f-54e4-9417-f88fe1fbddbb |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | faf90808-178b-5f4b-9c03-f8de977d4c34 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (2)
label | ad1bd09d-05c6-5388-97bc-d4b8a819f1e6 |  | note | VERIFICATION ACTIVITY - Visual check
label | b4902124-78a8-58a5-8bfa-52f961d1b4fa |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | 40abf2b8-ba05-519d-b08c-0f8be7cb7c8b |  | note | FREQUENCY - All shoulders
label | a6355474-5306-550d-b7be-4435fcf46408 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 4bdd6041-dd81-5321-ab32-c61b3b6a3774 |  | note | TYPE - H
label | ca892842-ce5a-52b1-9a93-b5100ec51c2f |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | 87200761-aa28-5f54-80bf-f82014604c09 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 333cfd86-5eac-5cb9-b19c-a3b962a90050 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Soiling
label | d21e13f6-e567-5a24-af07-7b7eac644899 |  | note | VERIFICATION ACTIVITY - Visual check
label | 7c57e045-62c3-51de-adc9-93c8b69f0129 |  | note | METHODS OR REFERENCE - Approved Design Drawings
label | 6d9cddac-5849-5811-8942-f143c05dc868 |  | note | FREQUENCY - All areas requiring grassing
label | f10894b5-d7d0-57c4-9a24-ce814a60afc8 |  | note | ACCEPTANCE CRITERIA - Soiling has been done where required
label | dfd174a2-80bd-527c-b727-dfec046ee9ca |  | note | TYPE - W
label | 2c26a672-c8b9-599f-951c-3eef93af6432 |  | note | DESCRIPTION - As per the design drawings
label | 6071c7a2-b588-504d-8ac1-75194098d6f3 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 74b239be-f16a-5ab0-a482-6ac1c866b5a4 |  | note | RECORDS / REMARKS - Required NO
checkpoint-group |  |  | section | 11 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (1)
label | d6312605-7699-509b-9f86-70f6504d9496 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 779fea10-c8c3-5f8c-8e57-23225fe5736b |  | note | METHODS OR REFERENCE - Visual Inspection
label | ae5ac836-c11b-5c2b-91d0-1ca55cdb59cf |  | note | FREQUENCY - All signs/markers
label | 459191f8-eb03-53f2-b38d-06a4bfb142d1 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 606df3f5-b685-5699-b664-21708c4e640e |  | note | TYPE - V
label | d743be98-b22b-5527-826d-82e0e0b0face |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | 446b40e7-b174-56c9-a672-056d527b1a90 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 14f35c34-3b14-5c7e-83ff-6245429fdae7 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (2)
label | 30e269c3-7cc1-5768-a237-c10dc954f11b |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 611cfb65-87c2-5c9d-aade-35d19dd0de7a |  | note | METHODS OR REFERENCE - Visual Inspection
label | 9c68a54a-d918-50ee-af74-43acbd81151d |  | note | FREQUENCY - All signs/markers
label | 01b2906f-3607-5687-a4df-3ca28d52ea91 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 599f1581-fe39-539a-8db1-68784aad36e3 |  | note | TYPE - H
label | 5d5d82e5-6409-5a59-92d2-2eed92bb35dc |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | a8700ef3-0a98-5d6e-8e78-005a319937a3 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 4a4c6252-784f-5095-ac4c-bce514d530ad |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2 - Grassing
label | b0ac5743-38bc-5546-a917-1f2d7593a443 |  | note | VERIFICATION ACTIVITY - Visual check
label | 975d8fee-c3c4-51b6-bd09-455224076483 |  | note | FREQUENCY - All areas requiring grassing
label | 77a543fc-981d-5355-9ea0-528977672101 |  | note | ACCEPTANCE CRITERIA - Grassing has been done where required
label | 781c9a4e-2439-5d58-8bdc-604e1d6e9b6a |  | note | TYPE - W
label | 52040fdd-833a-55ab-9072-210f6a6d32bc |  | note | RESPONSIBLE PERSON - Renewals PM
label | fd176520-8e58-5fff-821f-58594e1854d2 |  | note | RECORDS / REMARKS - Required NO
checkpoint-status |  |  | checkpoint | 11.3 - Drains Cleared
label | 61dcc4b1-eb65-5c24-b11e-5de0bf23a47d |  | note | VERIFICATION ACTIVITY - Visual check
label | eef4028e-5b39-5ae9-92af-539a0874bfbd |  | note | FREQUENCY - All drains, after all other works
label | eef66e30-9eb8-5e27-bb48-e9ccff5e7aed |  | note | ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | b25bc46a-aca1-5380-9288-6a710c3d4031 |  | note | TYPE - W
label | a1852e13-49f9-59af-a393-cf5b171605c6 |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 11.4 - Post Construction Design Verification
label | 8f14c0ae-1c4a-52c3-9a5a-72d9b8d10807 |  | note | VERIFICATION ACTIVITY - FWD/Beam
label | 5e1236d1-d5f3-51d2-a1be-ec319c431a0e |  | note | METHODS OR REFERENCE - FWD or Beam at 20m Centres
label | e7d83a16-3186-5eb5-8ec5-868babf217a6 |  | note | FREQUENCY - On Works Completion
label | feb06662-92e3-5150-bc29-f958bd0b96b7 |  | note | ACCEPTANCE CRITERIA - For information purposes only
label | e7a0fd7a-2fa9-5a02-9b7d-470190bb3070 |  | note | TYPE - V
label | 26e4609a-89b4-5739-9f9c-78888ce14092 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 5e672693-b269-5a6c-8f94-6c37b7d46ba6 |  | note | RECORDS / REMARKS - For Unbound Granular pavements <10year design life.
checkpoint-status |  |  | checkpoint | 11.5 - Traffic Management Removed
label | cc4f2699-ff79-5d31-bf09-6f7995612733 |  | note | VERIFICATION ACTIVITY - Visual check
label | c7fe37f9-df90-52fa-b4aa-0deb3c6d1569 |  | note | FREQUENCY - When safe, after all physical works completed
label | b6a93134-868e-514e-b124-09ce03ba50fc |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 8a40ac9a-bba0-5ae9-a1c4-961bf05e4daa |  | note | TYPE - W
label | 82a8b0c1-a1e7-59c9-8e21-5e04d9970599 |  | note | DESCRIPTION - Hold Point – TMP cannot be removed until site Audited by Renewals PM
label | 10fb8e47-f87e-532d-b750-cd3706c908b9 |  | note | RESPONSIBLE PERSON - Site Foreman / STMS
checkpoint-status |  |  | checkpoint | 11.6 - Site Left Clean and Tidy
label | dc700c70-23be-5b34-ba6d-40faa8ff3e4c |  | note | VERIFICATION ACTIVITY - Visual check
label | e8ed4b27-a565-56b5-ab11-3ee70029b09b |  | note | FREQUENCY - After vacating site
label | 13547f71-bb4d-5fdd-b1f8-dbc0cacf74f3 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 8bbe4dc3-8c3a-5a67-add8-ba44f8f8e8c4 |  | note | TYPE - V
label | 0c01aafe-f01d-5a08-af1c-31fd2b90c1b9 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 69bd0f89-bc6d-5979-b47a-aca97f8eff0b |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-group |  |  | section | 12 - As-built Records
checkpoint-status |  |  | checkpoint | 12.1 - Collect Asset Data
label | a56c9473-43f5-5a41-92bb-2a606ac85df3 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | b6cae779-7c9f-52b7-9bd0-6438ba232e72 |  | note | FREQUENCY - During construction
label | 3a75cbe3-b7e6-5b79-a092-ef9de5241dee |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected
label | 59e9685a-5b3a-55a3-9198-d319001878bd |  | note | TYPE - V
label | ee8eb160-c6e9-5657-915d-b77db19caa91 |  | note | RESPONSIBLE PERSON - Renewals Project Manager
checkpoint-status |  |  | checkpoint | 12.2 - Enter Asset Data into RAMM and/or Register(s)
label | e329fccf-6670-5106-a507-68bcc941b28d |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 5027bdb5-992e-5e84-a833-e03fc4a0adda |  | note | METHODS OR REFERENCE - RAMM
label | 1541e7ab-d4e8-57f2-8006-48607612ad1e |  | note | FREQUENCY - At completion of work
label | 7889e25a-b8c9-50a9-9962-a1fdd46a8221 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file.
label | 8b64f0b8-36f6-579a-b8ed-02ad68460ae7 |  | note | TYPE - H
label | b5b42763-3118-543b-a19d-c18a6fa52393 |  | note | DESCRIPTION - Hold Point – project cannot be closed until data entered.
label | debf7f9f-c234-5e76-9bc0-d6cbc7f4ed46 |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ WSP Information Manager
label | 7978929d-99a9-53e9-b46e-47f12b41401a |  | note | RECORDS / REMARKS - Submit all RAMM Data to Data Quality Manager for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.3 - Construction Completion Report
label | bd2c50e6-633c-5903-b6e7-0ac22bad3bed |  | note | VERIFICATION ACTIVITY - Confirmation
label | af78067b-505e-5624-9c0a-ea3485943dbe |  | note | METHODS OR REFERENCE - Contract Specification
label | e1f24a66-05a4-57aa-993b-19d67cb19ed7 |  | note | FREQUENCY - At completion of work
label | 3ef00c76-5534-5ab7-a91d-170e3214d9d8 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 2ba7bde7-07c5-543a-aa67-a2396ef15468 |  | note | TYPE - V
label | 3d525d82-fd4e-5247-9e66-4667c4b30920 |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ Renewals Manager
label | 77606164-3bb9-5650-8561-b097c792d4f4 |  | note | RECORDS / REMARKS - Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
checklist-sectioned |  |  | checklist | ITP - Dicks Hill - Pavement Renewals - Unbound Granular Overlay | itp |  |  |  | Yes | ITP - Dicks Hill - Pavement Renewals - Unbound Granular Overlay Rev 0.04 | 9fbbda81-a9b9-4946-ad0e-30014af22ddb
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 62967c0b-4cd6-5dd3-a243-57bef2c74530 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 52f031d8-58db-588d-9726-746a715d374f |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 50d7eb20-6b28-533c-a3f2-8e03da434a8e |  | note | FREQUENCY - Before work commences
label | 2533f57d-9b4f-5ec8-b441-a9cd664a689b |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date
label | ebbc8b53-d2d0-5dde-84bf-b7765c1e00b6 |  | note | TYPE - V
label | e290eade-1419-5cd0-99d0-001ee96f83b2 |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | ebbd56bb-bcdc-56ba-8a91-8b77ab8d0efb |  | note | VERIFICATION ACTIVITY - Confirmation
label | 4da1870f-1338-5909-9c55-fc4fea056459 |  | note | METHODS OR REFERENCE - Contract Specification
label | ce88502b-b84d-5b5e-9c15-1133748229ce |  | note | FREQUENCY - At least 24hrs before establishment or work commences
label | 957ee9f6-87de-504f-8ce0-726fda4c0eab |  | note | ACCEPTANCE CRITERIA - Principal's Acceptance according to guidelines in Appendix 6.3
label | 30ce55ac-6126-5f7a-8a0f-184de08341ce |  | note | TYPE - H
label | 36cb8a6c-0227-536f-8821-1fdac5e3bf6c |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site.
label | 3750f703-319e-5c3a-91c4-b048851f7c8e |  | note | RESPONSIBLE PERSON - Renewals Manager
label | 1d4e56d1-6a74-5f1c-8221-3f06bb3f1bde |  | note | RECORDS / REMARKS - NZTA to approve.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Notification of Intention to Start Work
label | 70be37eb-86c8-5275-8b54-9418d1f5ddf9 |  | note | VERIFICATION ACTIVITY - Notification
label | 08f07bd4-c87d-5bff-881e-6d7cf7c49550 |  | note | FREQUENCY - Before work commences
label | cd12f995-d8ba-54aa-a5d2-894495845f9f |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents
label | 2bd9bbc0-f1e1-5dfe-bf5e-dacef19176c2 |  | note | TYPE - H
label | f7f0f4a9-e250-55da-bb63-09a5afd716f9 |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site.
label | 4f41a852-89d6-521f-a347-840807980081 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 15eafec3-e766-597a-a635-4a71fd0487f6 |  | note | RECORDS / REMARKS - NZTA to approve letter drop before distribution to residents.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Traffic Management / TMP
label | 1f57fb3b-78e4-5930-8c56-79cd1b60f219 |  | note | VERIFICATION ACTIVITY - Visual check
label | 0eff6c20-d2b8-57bd-bb0d-c7631ce1d534 |  | note | METHODS OR REFERENCE - CoPTTM
label | 4dc8c272-2419-5240-a824-05688cb70407 |  | note | FREQUENCY - Before work commences
label | b49f94a6-cfbd-5880-bed4-05c8ff66c50a |  | note | ACCEPTANCE CRITERIA - TMP checked and approved
label | 7049d262-5fe6-5796-a522-b412f1e3ead5 |  | note | ○ Plans approved
label | 1f570c35-1f6e-58e1-8382-722b02855f36 |  | note | ○ Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely
label | 22c331fd-24d2-5b5c-82fc-419ee47520b8 |  | note | TYPE - H
label | 37631dc7-e514-505e-a661-c6380235dbaf |  | note | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 52254d0a-75fd-5274-b73f-05fc376bd959 |  | note | RESPONSIBLE PERSON - Renewals PM / TMC
label | a8e9adb3-2223-5474-9080-c64b77c5b3dd |  | note | RECORDS / REMARKS - CAR No., TMP No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Design Report Approval
label | c2e74890-c83b-5613-829c-e7a39b479d5f |  | note | VERIFICATION ACTIVITY - Confirmation
label | afd3c171-7b38-53a5-bcde-eb0d39a34da3 |  | note | METHODS OR REFERENCE - NZTA NOC Rehab Catalogue Design & Treatment Approach
label | d66b2ca4-c5b0-5516-b41c-f97eb9b50b30 |  | note | FREQUENCY - Before work commences
label | 4d76b8b3-2a08-597e-843d-f4355ec5754b |  | note | ACCEPTANCE CRITERIA - Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document
label | bef7cf80-8019-5044-91bf-0ef64d48b4a8 |  | note | TYPE - H
label | b3278926-5c82-52ac-b725-b7d0178776c1 |  | note | DESCRIPTION - Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers
label | 9daf295d-193f-5129-83d8-22dda7ce5f15 |  | note | RESPONSIBLE PERSON - NZTA Network Manager & Accreditied Designer
label | f41a038a-6cdf-5dab-a899-5ef96917c53b |  | note | RECORDS / REMARKS - NZTA Approval to Proceed NTC No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Seal Design Approval
label | 9c165e6d-7dc3-5d2c-8460-cc426918a5c8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 74590cf1-c53b-520a-a501-bb0f0c1afc66 |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Regional Sealing Manager
label | 2a327da6-e990-5158-bcb0-1a7d5c7245d0 |  | note | FREQUENCY - Before work commences
label | e7061eed-e724-5fe7-b234-f440614cc119 |  | note | ACCEPTANCE CRITERIA - Downer Regional Sealing Manager reviews and signs off on Seal Design proposed.
label | 2b9f162d-d2e5-595c-9972-90bd103685d5 |  | note | TYPE - H
label | cd9aa2f7-e1ad-5798-91e9-14bfe1015096 |  | note | DESCRIPTION - Hold point - Review and approval of seal design completed
label | ce3fd99d-1666-53a5-80e6-cdc756b6b98f |  | note | RESPONSIBLE PERSON - Regional Sealing Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Project Manager Handover
label | 0f240a2f-acda-5c99-b069-43e0ccfa6135 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 97625650-d5fa-53a4-868e-2e84c3340ae8 |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Designer to PM
label | f5e3ca02-4e92-53fb-85f6-85fb5f54c3d0 |  | note | FREQUENCY - Before work commences
label | 347e4c04-ef46-527d-b8b7-e8d5288db13d |  | note | ACCEPTANCE CRITERIA - Downer Technical Services Team Designer reviews and signs off on Handover.
label | 1d186fa8-33db-5c32-85f5-5faca34eb342 |  | note | TYPE - H
label | 3f5ecd26-05bd-5d57-9d3c-01b4f37c9c80 |  | note | DESCRIPTION - Hold point - Handover completed
label | d04db8a8-2a96-5214-b15c-e99486997e11 |  | note | RESPONSIBLE PERSON - Regional Engineering Team Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Crew Pack
label | a5aad8c6-9392-5b42-8602-229828c59aa5 |  | note | METHODS OR REFERENCE - Items to be included:
label | 84ebf4fe-741a-55bc-af38-73c74dcbd7b7 |  | note | FREQUENCY - Before work commences
label | 9d871df0-38db-52a6-98b2-f641375a5cd1 |  | note | ACCEPTANCE CRITERIA - Approved TMP
label | 4b3309de-fab6-5c15-9cf1-4e9c25fe2272 |  | note | ○ Services location plans / Marked out
label | e01c0769-a6e6-56aa-89df-dbdb44c7a9c7 |  | note | ○ Approved RQP
label | 0f40767d-2a47-5c02-aa63-ace5880c1f04 |  | note | ○ Approved for Construction drawings & Pavement Design
label | f1779a05-2d15-59f9-96f3-e794151f1a0a |  | note | ○ Ramm data
label | 55fa1308-05e5-5ed0-873b-80881c46fcab |  | note | ○ Approved ITP
label | 43193988-a85c-5ec9-8a71-7f868a930c8b |  | note | ○ Crew Briefing Plan
label | 732db3e3-daa0-57a7-8861-d34b01db7f20 |  | note | TYPE - H
label | 1b6a4e42-7a1c-5d68-be93-a8d7b5a73624 |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Setout / Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Setout
label | f6e7d9fa-3101-59f7-9de3-a7ae5bf7e475 |  | note | VERIFICATION ACTIVITY - Survey
label | e782f1f1-af03-53c8-a490-a496fe2a1152 |  | note | METHODS OR REFERENCE - As per approved drawings
label | b294f941-0270-5b3d-8dde-4c22a38311fe |  | note | FREQUENCY - Per installation / Site
label | abe30858-9f24-5a1e-9b0b-c6ffe8fefc9e |  | note | ACCEPTANCE CRITERIA - Design strings /design surface model loaded for machine control
label | 4cfa47f8-1c30-5371-8152-ad1433b8729a |  | note | TYPE - V
label | 81bd12b8-c8b7-55fe-b0b3-e88539cb868f |  | note | DESCRIPTION - Machine control requirement. Downer surveyor required for MC upload and verification of model operation
label | f269116f-3d73-5751-9e4e-bb2e7dd6fbf3 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-status |  |  | checkpoint | 2.2 - Services (includes Traffic Count Loops, In-road sensors and Traffic Signal Detector Loops)
label | b50f50aa-3417-5921-8cba-67302a468064 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 1c978f70-ead1-5c9c-a851-21fef68c0931 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | b0773806-31bd-5d78-8e29-d809f6cb1149 |  | note | FREQUENCY - Before work commences
label | 736d2fc7-18ae-5ec8-8f6e-8bc2fd2a9bb8 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 5865d1b7-5cbc-52cb-a2e2-138db1934201 |  | note | TYPE - H
label | 19f62254-7c8d-5d2e-9dd7-4f8db28f4386 |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
label | 3513d327-d1ab-5c46-8646-caa5bd54e7fc |  | note | RESPONSIBLE PERSON - Renewals PM / Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | 83b17aa1-2b55-567e-9856-f0e4bf50766a |  | note | VERIFICATION ACTIVITY - Notification
label | 96a90613-43e1-5d26-85e1-eda6ac1f4568 |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | 623e8d36-730a-5311-950c-7d187112d6bb |  | note | FREQUENCY - Before work commences
label | f27734df-4ce9-5509-b0fe-ac74e5c63050 |  | note | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | f31aeccc-d2fd-5123-b540-233f6f741e87 |  | note | TYPE - H
label | cfba24e3-b326-5776-9dad-2bb87ccc3b30 |  | note | DESCRIPTION - Where risk of cultural discovery
label | 54622aad-0e49-5deb-b655-2fafd2e34f38 |  | note | RESPONSIBLE PERSON - Renewals PM / Communications Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Archaeological Risk
label | eb672b3a-37ab-5422-a2a2-0afbe1f3b44b |  | note | VERIFICATION ACTIVITY - Toolbox meeting
label | ddc8c935-5e87-5845-87ba-969571b57027 |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | d6f840c8-5a4b-5191-ba18-c44b22141036 |  | note | FREQUENCY - Before work commences
label | e4edc9ff-a8a6-5239-bc09-df807455c9cb |  | note | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | 47aa9e8d-1597-5994-9d4e-3a7b7c1f4858 |  | note | TYPE - H
label | 7e4bf4f6-18c6-5887-a656-2c56dc4438a1 |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
label | e8ab4bd2-704b-5aad-8ea2-fee4e8e9eb2f |  | note | RESPONSIBLE PERSON - Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Traffic Management / Signs Setup
label | fdb587c4-bf49-5747-bf6c-e994f9e20d49 |  | note | VERIFICATION ACTIVITY - Visual check
label | 930060cf-188e-54dc-bd62-96980e5ebfc0 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 1326060f-0825-5bec-8a97-dc5bed907d59 |  | note | FREQUENCY - Before work commences each day
label | 23abf242-34a3-5b82-85da-024c9c545ded |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 4794c2fc-ec16-5793-97c3-5c6cf0dac05e |  | note | TYPE - H
label | 35bd2983-6c6f-5d18-906d-400509976c0b |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | f7c82fe1-f715-5d8e-96d6-fc739bd56527 |  | note | RESPONSIBLE PERSON - STMS
label | bb729598-37c1-522c-a4af-2bd638310ca1 |  | note | RECORDS / REMARKS - Daily site record sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (1)
label | b455f53c-e915-50cf-bd6e-487913d12fc1 |  | note | VERIFICATION ACTIVITY - Visual check
label | 78966986-97be-5d82-bf44-c713bf27f728 |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | dc02bb5e-732e-51db-bebc-e347e5ab98aa |  | note | FREQUENCY - Before work commences
label | 2205b5e9-d3b7-504b-9cbb-8f8ed3716bbd |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | 88261eff-f041-5801-9853-c59f8aee13ea |  | note | TYPE - H
label | 69e5918d-c330-57eb-ad44-02f8ad8145b7 |  | note | DESCRIPTION - Hold point - Walkover required ahead of MS Civil establishment
label | 29114664-7ca1-5d7f-b968-9bb6839b9323 |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | 7cbd4d7e-392a-55ab-88a6-e54a123326fd |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover (2)
label | 05568e4e-1f7c-5457-b990-04410e6615d5 |  | note | VERIFICATION ACTIVITY - Visual check
label | d5e8ed0e-2fa3-53d1-945e-28857d91476b |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | ac6edb84-0fef-5fc7-960a-c4755d786d84 |  | note | FREQUENCY - Before work commences
label | c006464b-39ec-53d9-956f-c08c1420e506 |  | note | ACCEPTANCE CRITERIA - Principal / MS Civil / Downer Acceptance
label | 07998de9-d710-573b-898f-1937d992dab1 |  | note | TYPE - H
label | d2b0755a-044c-56cc-b53c-a6e4e681f244 |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until walkover completed
label | 2d56dde3-f5d8-5062-b6d6-5466d1e5d0f5 |  | note | RESPONSIBLE PERSON - Renewals Manager / Construction PM / NZTA MCM
label | 7a2496a8-bef2-587a-9b3e-95409f3a7dff |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminary Works
checkpoint-status |  |  | checkpoint | 3.1 - Shoulder Stripping / Vegetation clearing
label | a4e47437-7786-5392-a1a4-3a938f9de174 |  | note | VERIFICATION ACTIVITY - Visual check
label | 611c1d5b-ee22-55f2-aea5-873ebf9b2720 |  | note | METHODS OR REFERENCE - On site
label | 161f9cd8-c4df-597d-93e3-e42c594af3bc |  | note | ACCEPTANCE CRITERIA - Shoulder stripping as per drawings completed
label | 27102ad5-53bf-501e-9849-885662135386 |  | note | TYPE - V
label | 7b23d41b-62b4-59c7-92e4-66c3830d8d8b |  | note | RESPONSIBLE PERSON - Site Foreman
label | c81bff18-6f7c-5c8e-8f57-df2b1878fc8b |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
checkpoint-status |  |  | checkpoint | 3.2 - Shoulder Buildup AP65
label | 693ba66c-355b-5b9e-9667-b74b19277393 |  | note | VERIFICATION ACTIVITY - Measure
label | da787566-0f4f-5896-9fed-cc0a0f2c222e |  | note | METHODS OR REFERENCE - B/2
label | c9d89f39-fe2d-5836-9a21-b69c9d0796f7 |  | note | FREQUENCY - 1 per 20m
label | 038dc7a4-5e52-5bfe-9c8d-d91c1f1462fe |  | note | ACCEPTANCE CRITERIA - Shoulder buildup as per drawings completed
label | fd3a676c-8687-5cc3-a856-8a9aaee389b9 |  | note | TYPE - V
label | 0ceed5d4-8eba-5344-a05e-725d5409d80a |  | note | DESCRIPTION - Greater than 30 CIV
label | 14e8d42f-a83e-56c8-8e91-9abbc1e4d828 |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 3.3 - Site pavement A/C digouts
label | 11bb71d1-5126-55c0-bb2a-0827cd8597e7 |  | note | VERIFICATION ACTIVITY - Visual check
label | 73562db6-6ebe-50d3-80ef-8a503cc40f8e |  | note | METHODS OR REFERENCE - Check RAMM records for depths
label | dfc3e066-82f6-5527-98bb-a37beaa4ebc0 |  | note | FREQUENCY - Before Overlay work commences
label | 219325e4-f0b5-5713-94a8-7d57ab12c301 |  | note | ACCEPTANCE CRITERIA - Work completed prior to overlay contractor onsite
label | 2559b86e-d8d1-5b11-aa20-6d2b2a0530c2 |  | note | TYPE - V
label | 48ab0aef-bf52-5d1a-a827-4e9a691097b7 |  | note | DESCRIPTION - A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed
label | b6d920ae-4854-54cb-afa2-a485932b9d8e |  | note | RESPONSIBLE PERSON - Construction Supervisor / Site Foreman
checkpoint-group |  |  | section | 4 - Culvert extensions / Headwalls / Flumes
checkpoint-status |  |  | checkpoint | 4.1 - Excavation Inlet / Outlet Gradients
label | 1d769675-11ea-5dc2-a594-4cfceb4f4127 |  | note | VERIFICATION ACTIVITY - Survey
label | d2c0b3bc-8627-5cfb-9eda-be3df36ab3f5 |  | note | METHODS OR REFERENCE - NZTA F/3
label | 1040d9bb-992c-5a3c-8de6-72d587d7b909 |  | note | FREQUENCY - Once
label | 0652241f-c951-52aa-ba79-e8a17b27dbd1 |  | note | ACCEPTANCE CRITERIA - Consistent gradient in and out
label | 75858b11-69ee-5d77-949d-6e3a9c4c9210 |  | note | TYPE - H
label | 3cb8ffe4-a108-531b-9c29-f5fa9ce334b8 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | fb922825-f3c5-5595-8537-b46bdd452966 |  | note | RESPONSIBLE PERSON - Site Foreman
label | ac5daec3-acb9-583d-914e-9c1fb04325da |  | note | RECORDS / REMARKS - Required No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Pipe materials / class
label | cad6ba67-a958-50a5-8268-b65dc076de71 |  | note | VERIFICATION ACTIVITY - Visual Check
label | b41c8131-72b2-5b1c-a702-031aed11ceb1 |  | note | METHODS OR REFERENCE - NZTA F/3 2.1
label | fdcc0e9f-2cc3-5e72-8a45-d2510f07c669 |  | note | FREQUENCY - Once
label | 6b38c8c4-ca58-5529-9e60-8734877a48d0 |  | note | ACCEPTANCE CRITERIA - Meets appropriate AS/NZ standard reletive to specified type
label | 0d099c99-c064-5350-a1b0-753fb32f0b9d |  | note | TYPE - V
label | 650d19ad-0bd6-5462-a3af-94f09763c11d |  | note | RESPONSIBLE PERSON - Site Foreman
label | f6301181-ebd1-5c3a-967d-8346d9e04443 |  | note | RECORDS / REMARKS - Required No
checkpoint-status |  |  | checkpoint | 4.3 - Bedding contact
label | c155af03-6911-5a11-830f-64e361972719 |  | note | VERIFICATION ACTIVITY - Visual Check
label | a6f55de2-746e-5885-9bf0-02fae35b90b2 |  | note | METHODS OR REFERENCE - NZTA F/3 5.1
label | c5ead6a2-9612-5b7d-bb96-fc7183ce924c |  | note | FREQUENCY - continuous
label | 4fdf7169-bcd8-525d-a2fc-dc79d7adf538 |  | note | ACCEPTANCE CRITERIA - uniform contact over full length of pipe
label | dc194fa1-dcc1-55a8-a504-3090e35e5e4a |  | note | TYPE - V
label | 885ae294-66b0-5c51-8f9a-73a19a926645 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 813f9043-6f5b-5faf-8f96-e9d6255d4817 |  | note | RECORDS / REMARKS - Required No
checkpoint-group |  |  | section | 5 - Subsoil drainage
checkpoint-status |  |  | checkpoint | 5.1 - Trench
label | 96f95890-90d3-5d7d-a711-b5f8bc3905cf |  | note | VERIFICATION ACTIVITY - Visual
label | bcb7c714-bc6f-5c24-8557-7654432f2777 |  | note | FREQUENCY - each site
label | 086fcc67-a628-599a-8623-60c258d97697 |  | note | ACCEPTANCE CRITERIA - Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm
label | c17bc68c-913c-50ce-aade-d3a51513cdb3 |  | note | TYPE - H
label | fba63dbd-44ec-5146-9968-0df6fa36ff9d |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | 0cdf9149-7952-5d07-b18e-f7718007723e |  | note | RESPONSIBLE PERSON - Site Foreman
label | b18fa327-02a8-55f3-be35-18ebe18ad816 |  | note | RECORDS / REMARKS - Required No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Drainage material
label | f4540e25-27b0-5390-98d5-c33697d6d906 |  | note | VERIFICATION ACTIVITY - Visual
label | fb224626-6b84-5a5a-b1fa-fa7571434c2e |  | note | FREQUENCY - each site
label | bbfc6ccf-4b57-5468-83a8-f9239abc38c1 |  | note | ACCEPTANCE CRITERIA - 7-12mm clean filter material ( grade 2 - 4 Sealing chip
label | f3470682-ef47-5d24-8e52-42c5b0c5e09a |  | note | TYPE - H
label | fdf0249a-0ef4-55a4-ba1e-beff47317d89 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | eaf77404-7a63-5e89-bd96-3f9e4cd2749a |  | note | RESPONSIBLE PERSON - Site Foreman
label | aa84b238-f3e6-5306-99a7-b7a8ff4f263d |  | note | RECORDS / REMARKS - Required No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Pipe type
label | 8eee143e-c96a-5ad8-bb78-217a39789e5a |  | note | VERIFICATION ACTIVITY - Visual
label | 54807990-68a4-597f-8110-03b76a6498f4 |  | note | METHODS OR REFERENCE - Diameter as per the design drawings
label | 5f07a935-3a9d-5e4d-b8a9-ea0eb597edfe |  | note | FREQUENCY - Use outside traffic Lane
label | 716be849-1bd4-5a44-a411-d05be6cedc8b |  | note | ACCEPTANCE CRITERIA - Docket to confirm
label | 9a879f2f-51d8-57a7-ab33-bcd113a28e37 |  | note | TYPE - V
label | 946c0a87-48cc-508c-ad39-1fd44795c5f5 |  | note | DESCRIPTION - "Nova flow"
label | a46daf9f-712e-5e61-9a60-437a2e0f886f |  | note | RESPONSIBLE PERSON - Site Foreman
label | e5f5b7f3-8da9-59e3-bb33-a7d9e79b1b63 |  | note | RECORDS / REMARKS - Required No
checkpoint-status |  |  | checkpoint | 5.4 - Filter Fabric
label | 49f16e90-feb0-5709-b154-588639ab3777 |  | note | VERIFICATION ACTIVITY - Visual
label | ca6d309b-bde4-5ad5-8b39-748fba216aae |  | note | ACCEPTANCE CRITERIA - 150mm lap, top of fabric minimum 150mm below FSL
label | a9bb4463-d737-5891-aa2d-b99753a8c904 |  | note | TYPE - H
label | 06b5ab89-0115-5736-a9f6-255e73572ebb |  | note | DESCRIPTION - Hold Point – Visual check prior to reinstatement
label | 96f56329-762c-5a6c-9b67-e8cdec9d4bdd |  | note | RESPONSIBLE PERSON - Site Foreman
label | 5569898a-2583-5d7c-ad77-72bfa759e103 |  | note | RECORDS / REMARKS - Required No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Outlet
label | 0078d672-8ba7-5f7d-a158-c2cf06b35d45 |  | note | VERIFICATION ACTIVITY - Visual
label | eb41cfbd-913c-5892-821c-d09b9c71ae8e |  | note | ACCEPTANCE CRITERIA - Connect to sump barrel, culvert of construct Concrete Apron
label | 606da22a-9801-5355-b27b-d948a6a4311f |  | note | TYPE - H
label | 3a0cb6bf-de47-5420-bb8d-401f6f68092d |  | note | DESCRIPTION - Hold Point – Visual check prior to reinstatement
label | d9754401-b83e-5489-81da-88804ffeb53c |  | note | RESPONSIBLE PERSON - Site Foreman
label | 454f83a4-d22c-5a6d-9f85-c2bc2ccfd10b |  | note | RECORDS / REMARKS - Required No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Flushing / Cleaning eyes
label | c307f800-950e-5a0b-bcfa-1614bd8f291b |  | note | VERIFICATION ACTIVITY - Visual
label | ebf7d1a1-a1c7-5cca-b4bd-e858a4f58d53 |  | note | METHODS OR REFERENCE - To be placed & constructed as per Approved Drawings
label | 8eb9b558-c9ce-5889-b31e-101a53736fa5 |  | note | FREQUENCY - Each free end
label | 1fbb9ca8-1caf-5fe6-b302-33205585aa91 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 9d332f42-579d-514f-8809-da3351e96ed7 |  | note | RECORDS / REMARKS - Required No
checkpoint-status |  |  | checkpoint | 5.7 - Reinstatement (1)
label | 6a2b6b90-b625-5f9a-9a67-ea56215d0c27 |  | note | VERIFICATION ACTIVITY - Sealed Pavement
label | 06363443-3b75-591f-8791-17f3b04a1573 |  | note | ACCEPTANCE CRITERIA - Pavement matches surrounding, surface with AC or 3/5 chip
label | 684d7caa-cce1-5205-9524-9c09c8381ccc |  | note | TYPE - V
label | eee48ba9-31dd-58ba-970e-4d6dcecb3985 |  | note | RESPONSIBLE PERSON - Site Foreman
label | e8036265-428a-547d-9e10-2082ac9c6c02 |  | note | RECORDS / REMARKS - Required No
checkpoint-status |  |  | checkpoint | 5.7 - Reinstatement (2)
label | ec563514-839b-5472-ae95-a6ff5ff0d9a1 |  | note | VERIFICATION ACTIVITY - Berms and shoulder
label | 76155f55-e9fb-5d64-a1f1-f65cf6f51204 |  | note | ACCEPTANCE CRITERIA - Top min 150mm impermiable backfill
label | 2c7485e5-b121-57a6-a9b2-ceb1ed4173f8 |  | note | TYPE - V
label | cb4becc6-4d4a-562b-9c30-9c67341d001a |  | note | RESPONSIBLE PERSON - Site Foreman
label | 0f57a39d-da56-5c7f-965d-3adf5ce45627 |  | note | RECORDS / REMARKS - Required No
checkpoint-group |  |  | section | 6 - Preteatment of Insitu Materials
checkpoint-status |  |  | checkpoint | 6.1 - Cut to Waste Existing Seal
label | fe5cf9ff-79b3-55da-88d3-08ea24485ffd |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | dc858513-5242-5e83-83f5-7ab27e512065 |  | note | FREQUENCY - Prior to material import
label | 96d43e0c-6229-5ca3-b9f7-2cd11c689280 |  | note | ACCEPTANCE CRITERIA - No unsuitable material remaining
label | c05b2eb9-d476-5034-b018-999c4c2a6cda |  | note | TYPE - V
label | 645766df-f274-5e6d-a54d-9ea92da72646 |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 6.2 - Undercut unsuitable areas
label | ae1c58c5-79cd-5618-ad2b-8c71653f2917 |  | note | VERIFICATION ACTIVITY - Visual Inspection/ measurements
label | 3b75c757-273a-596c-b63f-ef9793d72eba |  | note | METHODS OR REFERENCE - Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table
label | eee25a99-e81d-5a00-9d03-292bd019588a |  | note | FREQUENCY - Where required
label | 1bd29579-60fb-5b44-9057-ae57669be68b |  | note | ACCEPTANCE CRITERIA - All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to
label | 27dc5b11-a4d0-5d25-bb32-e358f266ba4e |  | note | TYPE - H
label | 028a3bdb-035d-56a5-9606-4fe546d82317 |  | note | DESCRIPTION - Hold Point - Organise site walkover with NZTA MCM prior to dig outs commencing. Variation agreed.
label | ec7f1621-104f-591b-993a-d99d1a3ba8ce |  | note | RESPONSIBLE PERSON - Renewals Manager / Site Foreman / NZTA MCM
label | c08cb649-ba83-542b-b35b-7c10aebd758c |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Imported Basecourse Materials Testing
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (1)
label | d1830ef2-6cd3-506e-a6bf-87b3140405a4 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | ef65ee5d-3c8e-587c-87e2-96db0c697371 |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.10
label | 0e13f435-89e5-5c5f-b07e-58a9e5d6ef8a |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 201edb5f-1fdc-5ae6-a6eb-bfeeae593748 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 7d8cc9b2-3ec9-5ad8-a2ad-6f1653423c90 |  | note | TYPE - V
label | 0a44581e-e015-5fef-85be-b26042814fd4 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 5f22201f-a65b-5b33-aabe-96dc0314cab7 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 3fb74b90-7e0c-56e8-ad8a-7a6a70a05fd0 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance (2)
label | 399b203d-8e5b-506b-b2d5-78f10aa82891 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | 4c1a31c9-6aca-51ad-8d98-bdd09a4ab402 |  | note | METHODS OR REFERENCE - NZTA M/4
label | 8e7674c4-43a1-5960-b4bc-948f092a9b7f |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ae8c4b66-56a8-5e8c-ad6b-df763c547380 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 38a71dd2-318c-55b8-bd68-46e377b387f1 |  | note | TYPE - H
label | 3b744d17-15b3-5573-9cae-21b3027f0eef |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 9965ad72-247e-5977-8ea5-732a0497bf02 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 79437a4c-985b-5a1b-8229-85a240307b59 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (1)
label | 4ed8ce2d-aacf-5ff8-b44e-bc039cc79801 |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | f70228b1-29f3-5d6f-8df8-2a5b24751f92 |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.11
label | 2eb64202-eb12-559c-9b94-53a074396a8d |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | da585789-a6a7-5b62-b6ae-1bca1d17b2c4 |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | 9984e09c-9dac-5ce6-b958-8614b9cec6d8 |  | note | TYPE - V
label | 0c2da2fa-f578-5ba6-871c-49b5749697e0 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 9f083364-0c04-5a66-9bff-771bd7fab7ad |  | note | RESPONSIBLE PERSON - Renewals PM
label | 76892b08-4f19-55b3-a01c-33eb46a79791 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality (2)
label | 0a78d10e-f3fa-5b48-817a-d00446f87d6d |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | 78961259-2153-5a44-906f-7e74554bc40f |  | note | METHODS OR REFERENCE - NZTA M/4
label | cac4693d-80ba-5aa0-a000-cd60ffd4bf06 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 727615f2-f96a-5ae3-a254-4b37b272b375 |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | af9e460d-0f1f-5020-94c3-368c37b3c51c |  | note | TYPE - H
label | 9b24048d-5287-524c-93fa-6ea5066a2ffa |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 028c5a3e-1caf-5a46-9e92-17016a5d663d |  | note | RESPONSIBLE PERSON - Renewals PM
label | 2880ae6a-ce77-59dd-a670-ea034463084a |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (1)
label | e1b318ca-c58d-5dec-b1b4-fab83d61833a |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | f21df49b-038e-599a-8ecd-fab0916ffaa7 |  | note | METHODS OR REFERENCE - NZS 4407 T3.15, NZS 4402 T4.1.3
label | 3dc5a8a3-2f99-5887-9903-35a88e045dae |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 6c113ae6-3cca-59ac-b6c4-9333bdcaaf24 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | f62a31b0-11a6-5986-a564-1154abee86da |  | note | TYPE - V
label | 93f6bc2f-3b16-5013-bba8-02e7a8858b3d |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | a4c4bccd-2c20-52c6-8091-6528739a8aca |  | note | RESPONSIBLE PERSON - Renewals PM
label | 73dacd51-fbb6-5bc3-b67b-36d135f20c0e |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength (2)
label | 4d87eace-392a-5247-926c-6c827248730e |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | ec19eaae-ea6f-526c-9a8f-b0923d6ab220 |  | note | METHODS OR REFERENCE - NZTA M/4
label | c26d8fbf-8ce4-554a-9f49-815a329a89b1 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 9b89c367-0deb-5832-989d-d34277e1d874 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | 434aefb5-2c96-50ed-a450-26e49ca2ab16 |  | note | TYPE - H
label | 6bc4d68c-a55c-5c76-95f6-4fd57eee8900 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 0d8c34d2-8471-5f69-8d8e-c8b9de1a379a |  | note | RESPONSIBLE PERSON - Renewals PM
label | b1a96757-d099-585a-8797-aa64ca8a2301 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (1)
label | 9303b3cb-46c3-5e3b-a616-e2ea4f32b29b |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | 7446d006-82f7-5c49-9966-4593bb55e0f7 |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | f17daf3a-671a-5711-9a3c-2a90c3209ee0 |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | a1ef6812-26d4-5c4c-b837-4459ff6ca644 |  | note | ○ 400 - 1500m3 - 3 tests
label | e000801a-da40-51fb-a7b0-cab537a2254a |  | note | ○ 1500 - 4000m3 – 4 tests
label | c58bae87-417e-5775-8455-bc4e73a82291 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 19e39d40-37c5-5098-ad9b-d1d833158b6f |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | 850d1a1b-9fe0-5484-b049-873011d034c7 |  | note | TYPE - V
label | 3adf5706-dc48-5351-9cd0-818e67d9a3d4 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | dd4d9bcb-f078-541f-9b73-9390301ba457 |  | note | RESPONSIBLE PERSON - Renewals PM
label | b8645d45-38da-5a1c-9826-48fe0861306b |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
checkpoint-status |  |  | checkpoint | 7.4 - Imported Basecourse Materials Production Property Testing (2)
label | 759e2afe-4977-5918-8f48-97e462732559 |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | 2993112e-b90f-5b30-86ad-026176a3fb3c |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | 86576306-2533-5372-8abe-21a9567a1586 |  | note | FREQUENCY - 1 - 400m3 – 2 tests
label | 44788c8e-9863-5831-aad6-d1bcc9659a7d |  | note | ○ 400 - 1500m3 - 3 tests
label | 63ad17ad-156e-5300-b41e-b33b115303da |  | note | ○ 1500 - 4000m3 – 4 tests
label | 5e418292-33f1-5c67-8a46-c41fe0dcdcb3 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 776d8d89-24fe-54da-9c55-2ecd54487c68 |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | 7b39d44f-2fc6-5e3e-ac64-93df3b10708f |  | note | TYPE - H
label | 1cca052e-d23f-5fac-a5df-9f84e489e875 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 82da0ab4-ba9f-50cd-9e28-419e9173a0ef |  | note | RESPONSIBLE PERSON - Renewals PM
label | 310df432-daff-5ee9-b8c8-7cbfaca1344e |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5 - Imported Basecourse Materials Compaction Testing
label | ea33d604-a081-5f71-9779-bfa053171c3a |  | note | VERIFICATION ACTIVITY - Maximum Dry Density (MDD) at Optimum Water Content (OWC)
label | ae0f33c3-29dd-5fce-b039-50862f1a09aa |  | note | METHODS OR REFERENCE - TNZ B/02 - 7.5
label | 894cb311-a402-591c-893b-ba297951f1f1 |  | note | FREQUENCY - 1 MDD per 5000m² or if aggregate source or processing method changes
label | fc3ae01c-d377-56d3-9b82-b0cd910daa80 |  | note | ACCEPTANCE CRITERIA - Used to support results required in ITP section 8.4 - Compaction.
label | f7909070-aa61-50d5-b454-b490df9fe8b9 |  | note | TYPE - H
label | 15ace85a-e239-5298-8269-bb767253f9f2 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 784ead15-3bc9-55d2-9aeb-f067e31b055d |  | note | RESPONSIBLE PERSON - Renewals PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.6 - Nominal 150mm Make-up Metal
label | e4445148-15d6-5059-9385-d55d2737d9e9 |  | note | VERIFICATION ACTIVITY - Quantity of material used
label | 079bbf8c-d72a-522e-839f-cfe28805eb47 |  | note | METHODS OR REFERENCE - 150mm depth over high spots
label | dcf1b495-00a3-5e70-92d5-d5b49e631533 |  | note | FREQUENCY - Each Subsection
label | 84dea8d1-a44c-5a81-a3ec-e08b44cd35cf |  | note | ACCEPTANCE CRITERIA - Correct amount of material used (M³Solid) as per geometric design / MC
label | b8e881e2-9508-56b3-a1be-4cee81802b48 |  | note | TYPE - V
label | e7af3e1b-8087-5df2-8a0f-5011cd1c24bb |  | note | DESCRIPTION - Spot checks to be taken
label | edd65553-acd9-5fa4-b163-d6a0440080c3 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 8 - Construction Quality Assurance (QA)
checkpoint-status |  |  | checkpoint | 8.1 - Tie in taper
label | db8c31d5-408c-5cb0-bb30-a004a4316627 |  | note | VERIFICATION ACTIVITY - Visual Check and Stringlines/Lift Peg
label | 2b4f30b0-dd64-5cec-b79f-029452897323 |  | note | METHODS OR REFERENCE - NZTA B/2
label | 18a3903e-7b98-5d37-9a3c-a6184d591bb3 |  | note | FREQUENCY - Per lane per tie in
label | a038c477-5573-5464-bb3d-24ccbef4d65e |  | note | ACCEPTANCE CRITERIA - Minimum layer thickness as per B/2 section 7.3a at tie ins.
label | c0570384-738b-565e-8137-dcf1b25cc478 |  | note | TYPE - V
label | 5a139dd3-1885-55ac-b080-b8c1177a8ed4 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 77ed9846-028a-5931-9760-bae6bc6c2203 |  | note | RECORDS / REMARKS - Stringlines recorded and supplied, Photographs
checkpoint-status |  |  | checkpoint | 8.2 - Uncompacted Layer Thickness
label | 6be4037e-a229-5a9c-9ca3-726cb584fd12 |  | note | VERIFICATION ACTIVITY - Stringline/Lift Pegs
label | 3230ad8f-60cc-51ca-a994-f56119222ea4 |  | note | METHODS OR REFERENCE - NZTA B/2
label | b323cafb-7608-5b11-ba3f-d0a4e81d9e9a |  | note | FREQUENCY - Per layer imported
label | 51e02bde-853d-55d4-83ff-00f828593169 |  | note | ACCEPTANCE CRITERIA - No imported layer > 200mm no less than 2.5x particle size ie 100mm AP40
label | 26f889dd-0a8d-5090-b0a7-5567e6273400 |  | note | TYPE - V
label | d6ef5500-7651-5749-8d66-bc36d6e129c1 |  | note | RESPONSIBLE PERSON - Site Foreman
label | 16405b25-b90b-5661-990d-0217e324979d |  | note | RECORDS / REMARKS - Stringlines recorded and supplied
checkpoint-status |  |  | checkpoint | 8.3 - Field Compaction Target
label | 99eee62f-ecc3-56cc-8a4d-71c8d2b26ca7 |  | note | VERIFICATION ACTIVITY - NDM - Plateau
label | a2425d8b-179c-56c1-9495-45c8e9f864e4 |  | note | METHODS OR REFERENCE - NZTA B/2
label | c206353c-e00c-58be-8e42-1f842a2711fe |  | note | FREQUENCY - 1 Every 3000m2
label | 6440d9f7-e274-5b26-a20f-4fa84f080f1e |  | note | ACCEPTANCE CRITERIA - Plateau testing done as required depending on the material variability throughout the site to determine compaction pattern.
label | b1809a3a-950d-5964-8ddc-270e5cc76b8e |  | note | TYPE - H
label | efdacde1-f857-5136-938b-31cea0bd849e |  | note | DESCRIPTION - Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target
label | dc22d858-1a73-50a8-9c93-d5021cb93c32 |  | note | RESPONSIBLE PERSON - Site Foreman
label | c7497b36-58b4-53ce-b814-f9fe4a55006f |  | note | RECORDS / REMARKS - Verified test results of plateau to be supplied
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (1)
label | 53c7074d-076d-5f93-a4e0-df39dac804eb |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | ce93784d-80a0-5212-85dd-b4cb47279e1f |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | 7c2dde54-1dc8-5e46-8ffc-baf1ea111321 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 48e54a66-57bc-5991-86c7-6548ed09e6d0 |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | 2c7446a4-646e-5e26-bf63-c6d5120bee86 |  | note | TYPE - V
label | 49e4c08d-0677-5d2b-841d-3ba6dfcbc78c |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | 9b221557-4888-53e0-86d7-347ffcf4bc5b |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 2595900a-874b-5d31-ad3e-03bc7b5089c4 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
checkpoint-status |  |  | checkpoint | 8.4 - Compaction (2)
label | 6c3fd1b8-3595-580b-985b-5ebe2881f2fa |  | note | VERIFICATION ACTIVITY - NDM T23 & Backscatter
label | 44a4a763-5c2f-5042-84b5-6f40074233a4 |  | note | METHODS OR REFERENCE - NZTA B/2 - 7.5 (b)
label | 83f703e5-81f7-5a76-9ece-ae4e929c0627 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | a2b826f4-532a-58bc-9a13-e82975caef2a |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Laboratory MDD, Minimum ≥ 95% Laboratory MDD
label | e93db509-b6c0-5201-894d-c61e7c6a1285 |  | note | TYPE - H
label | 47efea13-430a-5bcb-b64e-c82a7cb02319 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Laboratory MDD) Compaction equipment shall be sufficent to achieve 98% MDD
label | 90b8b37c-f8c7-5d8f-ba85-ebf73421337a |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | bf19e185-ce3d-532d-888a-405ee54d0e27 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 - Degree of Saturation
label | ff74b9b8-4392-5e95-a6f5-4e13d1cc9291 |  | note | VERIFICATION ACTIVITY - NDM
label | 74e26ed9-e5d7-5006-8fb0-e142e27f50bb |  | note | METHODS OR REFERENCE - NZTA B/2
label | b4f6640f-a3bd-527c-af98-5d56ce6c1ea7 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 0e0acc45-a839-5f73-aaca-c39894c68957 |  | note | ACCEPTANCE CRITERIA - No tests higher than 80%
label | 9623e459-ecdb-5860-8619-a41a9b7b294e |  | note | TYPE - H
label | d385a50c-9bfd-5091-a415-bde4f22dab83 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD
label | 5cceb3af-f1c8-5a1c-a8f9-6cf29fda46cf |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 6ea0e925-224f-58b3-835d-6d511f7f8d48 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (1)
label | 91773527-cab8-5fa6-b01b-293fd7f890a5 |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | 21453c6a-248e-52ce-90b3-cdad702f8a34 |  | note | METHODS OR REFERENCE - Visual inspection
label | a684db9b-cee3-598d-9530-fca97b9e4d02 |  | note | ○ Cut/fill tolerance check
label | 47c64595-ae69-537c-9a4c-ffdb7a90f998 |  | note | ○ String records
label | f6fc485f-046c-5a0b-9538-cd88ab3a7034 |  | note | ○ Straight edge
label | b3db7455-4ca2-5fe0-896e-5e6b6ae8547b |  | note | FREQUENCY - 1 test per 20m
label | b015e95e-cf0f-5bb5-bdaa-3e05699f1992 |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | 177873ea-9b11-56c7-9e99-1b384bde9252 |  | note | ○ Gradual deviations
label | 5d23cf82-f5d0-5789-9864-2a454da3749d |  | note | ○ Crossfall > 1%
label | 6f93e9f9-0a87-51e8-8989-d71d392d5856 |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | e82f2f99-174b-595f-81f2-a0942760ebfd |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | 4e1877c2-f91e-572a-8b29-d2b73abdb2a5 |  | note | TYPE - V
label | 9d80d4fc-0167-5c55-b352-08111da63af4 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | c52b23ce-37d5-5d83-b778-48cd3bbcd9dc |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | 1234a570-e760-53b2-8254-6015a9dc1bf2 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.6 - Surface Shape / Profile Layer Thickness (2)
label | 3b0ffc4b-8f05-54fd-ab3d-1300bb2bdd9d |  | note | VERIFICATION ACTIVITY - NZTA B/2
label | 0f02e57d-62cf-5d07-af40-59b5cf7f3f3e |  | note | METHODS OR REFERENCE - Visual inspection
label | 43183fa5-46be-5184-9daa-ea443d68467a |  | note | ○ Cut/fill tolerance check
label | 7f97a547-cced-595f-8682-4815c9fa011a |  | note | ○ String records
label | 4b6faaa9-1af1-5078-97a4-a413a386930c |  | note | ○ Straight edge
label | 015c182f-ef5f-5398-bcab-4eb54acbae73 |  | note | FREQUENCY - 1 test per 20m
label | 922b4ed9-b0f1-5305-bcaa-47fb6bd9054c |  | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge
label | 5de81592-9edc-53c2-adc6-172c2a409875 |  | note | ○ Gradual deviations
label | 2e8ba2dd-d3cd-5d7f-ae70-94d52e3a8958 |  | note | ○ Crossfall > 1%
label | 945453ad-601b-5f6c-b090-9f2d97eadc39 |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | cdfe1a21-23e8-5093-a286-867a4eec6c0a |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | 99ece523-7427-5af3-922d-cc6c36193747 |  | note | TYPE - H
label | f43bb8a5-ab50-5cd9-8724-9929b158ff6b |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. MSCivil Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | 63ba7e91-e9d4-59d7-8815-273bd47d82b1 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM / Surveyor
label | e8ca9a79-46d9-5a4e-bda9-ed7394030dfa |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (1)
label | 2302e36a-93cf-5b27-a1a9-ebff5bff43b1 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 77c919e5-0607-5924-877c-2f0c42f9acb0 |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | 639ed34c-d163-5eb3-8907-c7e829bc8161 |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | 6d7fb548-a932-5bf7-8b13-5f8aed42cbd8 |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | 9b32f6fd-0d20-5b49-a134-a5fb1aea89e7 |  | note | TYPE - V
label | 9b8b39dd-4f2c-5075-b22f-ca4551ba843c |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | e16ff6f2-fcc2-5a30-9000-10065ce2db53 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 160a1854-caa9-5427-81fc-0002e58e4a85 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.7 - Tolerances / Width Unconstrained (2)
label | 9e083621-e724-507e-8bfe-a9a8cca0f7c4 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 037bedd5-3762-5037-8b44-becb535f0878 |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | fbc191c7-8cc4-5c6a-a8f1-464f721dadcd |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | 9819a936-d365-57f9-bed6-70801990c093 |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | a6040588-043f-5616-9795-6120caa81b94 |  | note | TYPE - H
label | b34b68c1-e978-52bd-9588-a30899ffdd20 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 068b9de7-c591-5946-b94c-d712fd2b6024 |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | caf4791a-bd3b-5559-8d0d-433e902a578e |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (1)
label | e4e305e0-14ad-57d9-9d66-9401733c0aff |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 3d3f2c7f-a158-52b2-bc2a-50a8dea9e044 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | f7ab5682-f2ec-5ae3-90db-8db1981746ea |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | b15d4ec3-d7bb-527c-932d-4fd83287a61a |  | note | ACCEPTANCE CRITERIA - Zero
label | 8f2d8a45-56c6-5c05-9196-751c56cc841e |  | note | TYPE - V
label | c6d2fb23-1ca6-50b5-8530-5991a95945cb |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 2402457c-8721-5a83-b4a3-3fa58ae9a97d |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | deac929d-a098-5da9-a16a-8183485a1249 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
checkpoint-status |  |  | checkpoint | 8.8 - Tolerances / Width Constrained (2)
label | 2b6fffd4-e31a-5ba7-a923-527749d217c1 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | c171cecc-897a-57e2-8eee-d057840ab125 |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | 4b481457-f669-58eb-8de4-81eb81e9eddd |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | d2587cd6-3dc0-506f-adaa-96b62c84f6da |  | note | ACCEPTANCE CRITERIA - Zero
label | 1ebeaaec-a142-542d-81f2-a3f3536bc422 |  | note | TYPE - H
label | 8b070d83-511d-531f-ad8e-3d54b795adbd |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | bbaad58d-7209-5ea8-972d-2b24213726eb |  | note | RESPONSIBLE PERSON - Site Foreman / Renewals PM
label | 0a891800-6139-583e-83e8-1f45495a82a9 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (1)
label | cef63896-9125-5d14-8c94-9206c753f15a |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | d22218b6-4586-58e6-ab70-3ac6a4dea03e |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | 24c888a8-61be-5bc0-b524-13a54105578d |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | babce2e8-a392-5b59-8452-663e90a4efdb |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | 554d3c5d-02b2-5fb8-818d-24477f434b59 |  | note | TYPE - W
label | 36397f88-02c4-5bd0-b32e-6f7fbffede13 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | d7ae931f-d0fd-5dd7-88ee-ccb6116be1b1 |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | 16b53308-2640-5621-8f8d-22c55c5c471b |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.9 - Ride Quality (2)
label | 2f73badb-112d-5212-895d-d0217cbd1284 |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | 88c0ed52-9043-56a6-b1e8-d4f8856f53d3 |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | 1d78fa8d-ad1f-5c24-987f-17fa4d9b26ea |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | 37b87fd8-0af0-55e3-8a2c-c23855afc424 |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | 4c9d94f4-4408-5722-ae4e-0b8b32d36258 |  | note | TYPE - H
label | 697f7305-0b0c-5b00-8147-352fc465f5b5 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | b08d9c55-5f0d-5159-86f5-7e8e778f4821 |  | note | RESPONSIBLE PERSON - Road Science/ Renewals PM
label | 0753f0a3-0a5e-5531-a24d-b49fc6e81be4 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (1)
label | 7ee1e15a-89fd-5d5b-97e7-1ab1c921300a |  | note | VERIFICATION ACTIVITY - Visual inspection
label | 61d04f0f-5021-53cf-acda-39770a46011a |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | 53e5e0dc-ca93-535d-8e4f-fbf59bfe824a |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 01d3a897-b69d-513f-999c-7211c8a9c978 |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | 96997c15-a850-5495-96e5-d4128d15639d |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | 3902da58-ff79-568b-a040-c64ce25f385a |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | 0a59a82c-5c06-5abb-afa5-2f5cec788983 |  | note | TYPE - W
label | 58b2170a-9d58-58ae-9565-47a53fd57c7d |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 5375e780-a68a-52a7-805c-2873fe37df1a |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 662570f1-7f05-519a-a6f0-2c7acbc4defb |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.10 - Mosaic Surface (2)
label | e432ff5a-1a04-5175-b0b0-8db688107236 |  | note | VERIFICATION ACTIVITY - Visual inspection
label | ac0dcba3-3248-54de-9461-b8438762ca4a |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | 1088c9bb-ca2b-5405-8b4a-e83cc0a03982 |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 6af03869-e747-5a5d-8c68-5ed3a0a578df |  | note | ACCEPTANCE CRITERIA - The large aggregate is held in place by a matrix of smaller aggregates
label | ead7f3b1-796e-5003-94ef-4451cad61217 |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | a34d81dd-66e4-5d59-8dd2-a37604328490 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | cc77af4c-e800-5657-b250-48849d68632e |  | note | TYPE - H
label | 4064db4f-53a9-5575-a11f-1b58910f117b |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | a9c1d3f1-0ab3-5153-9726-6f584e449d27 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 22735eb5-a977-5864-a19a-a64089a7b86e |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (1)
label | df68d905-5876-58c9-905a-ab78dd0391ff |  | note | VERIFICATION ACTIVITY - Visual check
label | f450c2e4-1a06-5e07-ab2d-ef28542c2a5f |  | note | METHODS OR REFERENCE - NZTA B/5
label | 5b9f42b8-fba9-5b88-86db-73bce8623f9c |  | note | FREQUENCY - Before sealing
label | 1b2d85a6-cac7-5b4a-923d-b7560d0f1e8c |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | f7bea7bf-e825-54c2-b1e1-0a4fb70157b2 |  | note | TYPE - V
label | fc871870-8402-5a5d-b218-37913423509e |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 6dcc4523-40bf-550c-b30c-00d676042d3e |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 4d093c7e-c6d4-5214-80e6-abf17ff9dc77 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
checkpoint-status |  |  | checkpoint | 8.11 - Preseal Check (2)
label | 30f2b33a-9df9-537d-aaf2-4dffba4fc7c9 |  | note | VERIFICATION ACTIVITY - Visual check
label | 9ef0e24f-daa3-5f86-8d4f-6e8ad89153c7 |  | note | METHODS OR REFERENCE - NZTA B/5
label | e0072547-1fe4-5f45-9624-a78c3c848052 |  | note | FREQUENCY - Before sealing
label | 2f9393e7-8a19-554b-8a2d-03eb6a5fd860 |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | 943df0dd-df87-59c0-b19c-8013aee5555c |  | note | TYPE - V
label | 3909b00f-57d0-5693-bb64-a6eefc190895 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 267c39d9-77fd-562b-8778-1da15c814b42 |  | note | RESPONSIBLE PERSON - NZTA MCM / Renewals Manager / Site Foreman / Sealing Manager / Renewals PM
label | 4cac5185-3fcf-5932-a3b9-e2576765d85f |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.12 - Pavement Surface As-Built
label | e3f13509-7915-586a-97c2-efc5af8cb5dc |  | note | VERIFICATION ACTIVITY - Survey
label | 4055da2e-1776-58db-9a7a-294193fc9414 |  | note | METHODS OR REFERENCE - As per approved drawings
label | d3cf13b8-be8c-5451-ba6e-809b5ef614d4 |  | note | FREQUENCY - Per installation / Site
label | f7bdebcf-2196-50b9-8105-2dedf2311244 |  | note | ACCEPTANCE CRITERIA - Accurate survey of all topograpgical features required
label | c348b379-fe54-5637-80eb-faa5e64b8164 |  | note | TYPE - V
label | 6fb39356-6403-5b1f-bb85-52fb7e3443f7 |  | note | RESPONSIBLE PERSON - Renewals PM / Surveyor
checkpoint-group |  |  | section | 9 - Sealing
checkpoint-status |  |  | checkpoint | 9.1 - Sealing
label | 5eccfbf3-acfd-53e5-82c9-b7b1934e6b54 |  | note | VERIFICATION ACTIVITY - See Sealing ITP
label | 673478ec-0860-50d1-a634-2b0e398c77bd |  | note | TYPE - W
label | 7c74d274-0094-5c02-b20a-c1cd7fb72594 |  | note | DESCRIPTION - Hold Point – All hold points and checks in ITP to be completed before physical works continue
label | a0e736c2-6456-50bb-b76c-c5112af20be7 |  | note | RESPONSIBLE PERSON - Sealing Manager
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (1)
label | 0e873553-ba13-55c2-882c-ce20edb39cbd |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | e6fd8fc3-d241-5e78-8b2d-233e50fe991c |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 1955dfbb-bc3b-506e-93de-551d17fe79e9 |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 7a5ea49c-9d0b-5278-8ea7-b76cc0f8f382 |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 647b289e-4f87-55cc-b790-7e29b75bb931 |  | note | TYPE - W
label | d5ee163f-64a5-51dc-83e8-e8af8cf1afa5 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | 4d24122d-356d-50f3-bc5d-ec18ebac767d |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.2 - Sealing TMP and Aftercare Process (2)
label | 7e20be79-6a28-5686-a2d5-c038c7be23e9 |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 254bbca2-ea73-52e3-b6f2-58167607452a |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 48111a3d-fa65-5295-bd34-b81e58815a02 |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | ca2f7445-b7de-5349-b1b1-47475420cffa |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 4c148ac6-2c65-5577-9241-865daf5e4512 |  | note | TYPE - H
label | e76a0970-6125-5dd1-b350-9f636d798e4d |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | c71ed007-46e5-564d-b167-001c24129249 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (1)
label | e81b0d64-73a3-5a1c-8cb9-9c2a33d95068 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 40392e2d-f3c3-5a85-9c67-7e4d35cf1a3c |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 2d02447d-f072-5afb-8636-4be349860446 |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | cfd33e06-9f1b-5eaf-87d7-8879ab9fa751 |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | fbe72b07-437b-5ce3-a0ec-adcaef0ef154 |  | note | TYPE - W
label | faa6d97a-67fc-5806-923e-5df3eb9f683f |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | 9efd77b4-41cb-5a22-9bcd-1767db306923 |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
checkpoint-status |  |  | checkpoint | 9.3 - Sweeping of Sealing Works and Handover to Roadmarkers (2)
label | 35da5502-e577-518e-96a5-df69d0731fa8 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 1c09c1b1-a6b5-5b6a-bc8c-0d231b62a20d |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | fd867026-17d3-5a35-9e4f-839e5e4c6a13 |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 87b812d4-61ff-5c0b-8022-f3d2b5724677 |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 5cd1dcea-8742-56fd-8e63-60d03f48377a |  | note | TYPE - H
label | 4ccbee59-d379-50f6-bf11-b99713fff75c |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | 9b6fd7b9-97e7-5d39-8515-4e3cc22ffb1d |  | note | RESPONSIBLE PERSON - Renewals PM / Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Shoulders
checkpoint-status |  |  | checkpoint | 10.1 - Slope (1)
label | d0c7f885-8637-57dd-a267-7f1c6eddeb10 |  | note | VERIFICATION ACTIVITY - Visual check
label | 6d82ca89-8882-596e-accc-142540cca3b0 |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | 85b58c83-3899-574c-a572-52ec928c0d0b |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | fc4a8522-e35f-54d1-9bda-d03c602cefd9 |  | note | TYPE - V
label | c1df5ede-3f8f-5f21-bffd-01e7bed1ae15 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | af9cf611-b5f0-56d5-809e-74ca1ac22846 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | ee6ddea6-638c-5721-8e98-1ca102348cd4 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.1 - Slope (2)
label | 45783a6f-2f2f-5bcc-b4db-2c498f249fa7 |  | note | VERIFICATION ACTIVITY - Visual check
label | 7916c3fd-b16f-5584-9cb4-0743bd5937e1 |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | 2c44363e-0596-5ff2-9a0f-a062f29c4c73 |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | a984252d-9e8d-5935-8617-77ba67641f72 |  | note | TYPE - H
label | 3a948933-f2c3-57d6-99fb-3150bf37d0dc |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | a388c27a-384b-595e-92cc-6fbeb25bb5a2 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | bd705f2c-1d22-5348-ba85-c2a1fcda82a1 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (1)
label | 99de3e3d-9f54-5560-a9af-0fa6ef0c465e |  | note | VERIFICATION ACTIVITY - Visual check
label | b99a7e7e-2944-5234-8999-5e3f81d4cdd1 |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | c3fcb75a-2142-58ac-b7bd-10f10f3bd1d9 |  | note | FREQUENCY - All shoulders
label | bb88b175-2bfa-5954-9c40-32a0868d0b32 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | b5c23f43-ac86-52b1-946c-d995d9faa8df |  | note | TYPE - V
label | 8409abfa-8484-5e55-8479-8978c40f1b6b |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | 140877bb-3863-529f-82f4-d02c27b0be17 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 361ba673-c025-5327-b16d-5f64c460c3b8 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 10.2 - Compaction (2)
label | 991f9312-c4e4-53c1-8bb0-1693e78ceb21 |  | note | VERIFICATION ACTIVITY - Visual check
label | 7791cdc2-0edb-584b-baf1-fb64e4e7b689 |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | f47d4b4d-a4e3-5c44-8ae2-c1ed8003834e |  | note | FREQUENCY - All shoulders
label | 82511183-703a-5f5c-9e6d-c2aced1b03f0 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 090facb1-e7b1-5189-a462-568978b2b4a7 |  | note | TYPE - H
label | 5eef20e5-fb91-5ca2-ac79-f7e6a03a32a4 |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | 919e1733-5cdf-5833-95b2-4e4a12068344 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 17347f2f-1e7f-55ac-8d4b-6fe0ba8df911 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Soiling
label | ed621871-dacb-5544-93b3-ae9a5378364f |  | note | VERIFICATION ACTIVITY - Visual check
label | ba9c08bf-763d-5214-b8d3-4a7ff14df6f9 |  | note | METHODS OR REFERENCE - Approved Design Drawings
label | 664a0d9c-15c2-5e96-ab3b-977db4f43dc6 |  | note | FREQUENCY - All areas requiring grassing
label | f4cacc01-a7fa-5040-bb42-6abd454aa3b5 |  | note | ACCEPTANCE CRITERIA - Soiling has been done where required
label | 5b68da22-1413-53ff-a4e2-2f0cee787df1 |  | note | TYPE - W
label | 09ad51ea-7f73-5ef0-a3a3-849804d6ad5f |  | note | DESCRIPTION - As per the design drawings
label | 66cdc007-ddbc-5d0d-83e7-3c2794c866e3 |  | note | RESPONSIBLE PERSON - Renewals PM
label | cb4561ce-d172-568b-b250-268466b9497b |  | note | RECORDS / REMARKS - Required NO
checkpoint-group |  |  | section | 11 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (1)
label | 9e3782d1-ca56-5b80-bafc-a215b5cd0572 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | f1beeeb6-e297-5500-a5c2-99b32aceab92 |  | note | METHODS OR REFERENCE - Visual Inspection
label | 1e1cb76b-1c18-592c-aea3-6d9bb3b61c60 |  | note | FREQUENCY - All signs/markers
label | 50808b28-397e-52f2-9716-c2526d5187f7 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 5ec882fc-9825-59ec-8d18-4fa6b625c7da |  | note | TYPE - V
label | 323cd178-b2cd-5644-8c6a-cabb567928af |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | 1c3f6370-a7f0-5476-83ed-b4c37e9c3a82 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 0f7310ed-e958-52d2-8606-713b518e0d6f |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-status |  |  | checkpoint | 11.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced (2)
label | e09c5ff0-d34d-5874-b3f9-9c22ce8de493 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 8fca4607-7d3e-5e5c-af44-e14823e438ca |  | note | METHODS OR REFERENCE - Visual Inspection
label | 621ddad0-2d97-5b42-9a73-620a06b8f577 |  | note | FREQUENCY - All signs/markers
label | cf75cf47-1943-5e31-87f1-85f96e803258 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 9f082279-20ed-5fa3-a1d1-de3659d48a1c |  | note | TYPE - H
label | 195c275f-bea0-5376-aab6-dea5a6f39c0d |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | c928202e-cfec-52d0-bc0a-d75daaf030fe |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | 5f5a3dde-0032-53c5-b6ae-7acb7fd9b424 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2 - Grassing
label | a1d34e2a-55a0-586b-a200-946383f41235 |  | note | VERIFICATION ACTIVITY - Visual check
label | 3c9f8cbb-e0f4-5339-b05c-6e182f5e4788 |  | note | FREQUENCY - All areas requiring grassing
label | a9d5e4d8-10f6-51a7-a0f1-0eb4cf6a43c7 |  | note | ACCEPTANCE CRITERIA - Grassing has been done where required
label | a5a816a6-e275-5d8e-928d-b23f0dea0549 |  | note | TYPE - W
label | 608ff340-ba1a-5c54-88e5-46bb06b7c0d0 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 20a56e04-63f9-532d-b58f-8f00d58b4491 |  | note | RECORDS / REMARKS - Required NO
checkpoint-status |  |  | checkpoint | 11.3 - Drains Cleared
label | f27c9589-83d2-5e96-a6cb-95f5c8fcfa63 |  | note | VERIFICATION ACTIVITY - Visual check
label | 6c73ca5f-1aa5-5577-9248-11d1fc175072 |  | note | FREQUENCY - All drains, after all other works
label | 604afc55-89aa-52ce-805f-083afdb36ba4 |  | note | ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | f62965db-d1ec-51ba-9375-d188c5bfaf88 |  | note | TYPE - W
label | 5150fd9a-4fc7-5346-865c-1dcafabc7514 |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-status |  |  | checkpoint | 11.4 - Post Construction Design Verification
label | 82713ab8-1adf-5caa-ab90-11e4c7ed4108 |  | note | VERIFICATION ACTIVITY - FWD/Beam
label | 544292e2-ddf8-5cfa-aa36-832104ac9600 |  | note | METHODS OR REFERENCE - FWD or Beam at 20m Centres
label | 32afaf89-6e74-5aef-bac9-bdc08d73c03b |  | note | FREQUENCY - On Works Completion
label | 4b6acf8f-6533-5ad7-80c7-0a585cbe89c0 |  | note | ACCEPTANCE CRITERIA - For information purposes only
label | b80fae87-88e5-5b61-8e51-ffcf873c3dc3 |  | note | TYPE - V
label | d3f51e17-22c6-5500-89be-f870df90868c |  | note | RESPONSIBLE PERSON - Renewals PM
label | a326025f-2ea1-5003-922e-c47e70e03399 |  | note | RECORDS / REMARKS - For Unbound Granular pavements <10year design life.
checkpoint-status |  |  | checkpoint | 11.5 - Traffic Management Removed
label | 9130a634-6ec3-5d94-adf7-2c74f04382a4 |  | note | VERIFICATION ACTIVITY - Visual check
label | ef91b97a-8475-5265-bf36-b4551d7cf060 |  | note | FREQUENCY - When safe, after all physical works completed
label | 1d6970d6-5b2f-5992-bcce-58c7ec8b8a54 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | f700a066-41b1-5435-a0c4-45e0e164ffd1 |  | note | TYPE - W
label | 62954365-9bad-5d72-a130-9c67ed6613a9 |  | note | DESCRIPTION - Hold Point – TMP cannot be removed until site Audited by Renewals PM
label | 7244113b-a412-5259-b814-43fb825b5f09 |  | note | RESPONSIBLE PERSON - Site Foreman / STMS
checkpoint-status |  |  | checkpoint | 11.6 - Site Left Clean and Tidy
label | de9c4953-2488-55b7-ad74-bb09d70568a0 |  | note | VERIFICATION ACTIVITY - Visual check
label | 9ea14f70-fb11-5af3-973f-d578f847ba93 |  | note | FREQUENCY - After vacating site
label | 99cbbbf7-1841-56cd-ab68-3c97755d8e51 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 5378337e-a856-5e9e-8e73-01612962b311 |  | note | TYPE - V
label | 54ae03f3-0252-52ac-b1cd-d064b5a30883 |  | note | RESPONSIBLE PERSON - Renewals PM / NZTA MCM
label | fba8b730-7198-5780-b15e-f40a6e65c60a |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-group |  |  | section | 12 - As-built Records
checkpoint-status |  |  | checkpoint | 12.1 - Collect Asset Data
label | eb914b2c-8d64-5c88-9b50-dd711ee0ff84 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 2e0ca53d-879f-5e00-8ed8-911d6ddab2cc |  | note | FREQUENCY - During construction
label | f7efb07c-33d3-511b-9fda-b21752b1b2e6 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected
label | e41bae56-dd4d-5088-9efa-e8fb11d5e3a2 |  | note | TYPE - V
label | 567d2fa7-e46e-525c-86b7-00d5219ab01b |  | note | RESPONSIBLE PERSON - Renewals Project Manager
checkpoint-status |  |  | checkpoint | 12.2 - Enter Asset Data into RAMM and/or Register(s)
label | 86b5af35-8d48-5533-982b-d08e19f78a8f |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 5802b541-0ae3-51d0-ac06-9e559a1e2de7 |  | note | METHODS OR REFERENCE - RAMM
label | 24533839-bfda-52ab-875d-48e8ce9aac9d |  | note | FREQUENCY - At completion of work
label | fc360655-7bf0-5b01-9f0a-ac8f499d713d |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file.
label | 4e2bc78b-cdcc-5879-bfab-d6f594ab5110 |  | note | TYPE - H
label | e43dfb2d-b78a-58df-a3ff-df725119ee4c |  | note | DESCRIPTION - Hold Point – project cannot be closed until data entered.
label | a1509267-4b34-54e6-b5f3-8d329cfb1b0a |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ WSP Information Manager
label | 523592c1-3424-557e-b90e-d1c8f23afa62 |  | note | RECORDS / REMARKS - Submit all RAMM Data to Data Quality Manager for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.3 - Construction Completion Report
label | d5a41a45-f570-5631-b613-c9e2b4ccbc80 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 23c1c48a-e0c2-5b93-971b-8d878a86496a |  | note | METHODS OR REFERENCE - Contract Specification
label | c025b05c-8d42-5d82-8117-fe432b4f38bb |  | note | FREQUENCY - At completion of work
label | 0fe8ebe7-1252-5da0-9479-3fbe36ab368c |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 3978cfeb-9f29-5d27-a407-3a3dd9229acf |  | note | TYPE - V
label | f422799a-02e2-5b1e-9a1c-86d9c0322d55 |  | note | RESPONSIBLE PERSON - Renewals Project Manager/ Renewals Manager
label | c352c229-eecf-5ab0-9fa3-391118eac497 |  | note | RECORDS / REMARKS - Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
checklist-sectioned |  |  | checklist | ITP - 0.5 FBS - Baldwin Rd - Pavement Renewals - Foam Stabilisation | itp |  |  |  | Yes | ITP - 0.5 FBS - Baldwin Rd - Pavement Renewals - Foam Stabilisation Rev 0.9A | ae1aa895-59d4-4aa3-bdb7-87ce14edb249
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 81b691f4-27f4-58f0-86da-143c592079cc |  | note | VERIFICATION ACTIVITY - Confirmation
label | 246a969e-f526-5dff-b176-6296e6384e2c |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | ac2ebfc4-d1f4-57c5-830b-9aaa2da0d21f |  | note | FREQUENCY - Before work commences
label | f5777de5-edad-55ad-a1c1-9f91c84370b3 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date
label | f2e72ccb-f127-518c-bd8d-24dd3e2aff1d |  | note | TYPE - V
label | eda8d829-2dca-5179-988a-d9be5f72fca1 |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | e5645491-e433-5d99-ab2f-707d1bf37aba |  | note | VERIFICATION ACTIVITY - Confirmation
label | 686d5a96-c750-523c-8bec-d8222483a194 |  | note | METHODS OR REFERENCE - Contract Specification
label | 072bd985-502c-5449-8129-baaf5f8eaeb4 |  | note | FREQUENCY - At least 24hrs before establishment or work commences
label | 59d150bd-d279-5bd8-97a3-22f7f843717a |  | note | ACCEPTANCE CRITERIA - Principal's Acceptance according to guidelines in Appendix 6.3
label | c62f6b3e-7d6b-51da-8c8b-edc9805e76c5 |  | note | TYPE - H
label | b0247280-4aa6-5cdf-8f3c-2ce3616d713c |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site.
label | 17abf39e-82bd-5fd5-b1f7-54903bbce9f1 |  | note | RESPONSIBLE PERSON - Renewals Manager
label | b13d3cd4-c430-5830-bfe2-0f06a31d8f5b |  | note | RECORDS / REMARKS - NZTA to approve.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Notification of Intention to Start Work
label | b7db24e5-4365-5fb9-b439-2d40ce9c964f |  | note | VERIFICATION ACTIVITY - Notification
label | f18a1a9d-1890-57cd-a9d2-02ed5f222843 |  | note | FREQUENCY - Before work commences
label | 5471ab54-3eca-5493-b912-7e5a2da2dac9 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents
label | f9dd4921-21d7-5949-8e6e-00a79a9a00fc |  | note | TYPE - H
label | fd63eab9-d7d1-5ac1-8f17-0148b60a3345 |  | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site.
label | c59a8ff8-ddd7-5958-853a-6fa53f98ad8f |  | note | RESPONSIBLE PERSON - Construction Supervisor / Renewals Engineer
label | bd5c92de-ada1-5c7b-bb11-1b574b271697 |  | note | RECORDS / REMARKS - NZTA to approve letter drop before distribution to residents.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Traffic Management - TMP
label | d57b5b16-83dc-587e-a0fc-315c99f275e9 |  | note | VERIFICATION ACTIVITY - Visual check
label | 401587be-72a3-53fe-a462-72e4565d6735 |  | note | METHODS OR REFERENCE - CoPTTM
label | f0874052-2a9c-5aa9-bd3f-0412c06bd1bb |  | note | FREQUENCY - Before work commences
label | 7dd69cf5-4f6a-5f5c-af90-81b6de40a51c |  | note | ACCEPTANCE CRITERIA - TMP checked and approved, Plans approved, Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely
label | 33555d50-04ec-5635-a361-24e3fd99ce9e |  | note | TYPE - H
label | f64bf4e1-2184-5a65-9693-deb8547dbf0d |  | note | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | be227b83-0e67-5d20-a7bd-d79f20d8db19 |  | note | RESPONSIBLE PERSON - STMS
label | ef250e19-bd03-50a4-929f-85ec423d4d35 |  | note | RECORDS / REMARKS -
text | ee08150f-cee8-503a-adcc-8f1c87a7e1bc |  | textbox | ○ CAR No.
text | 69cabfb1-269d-5d2f-98cc-9f418802fb40 |  | textbox | ○ TMP No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Design Report Approval
label | 5cfe6f9d-561d-5620-a210-6913433970dc |  | note | VERIFICATION ACTIVITY - Confirmation
label | 88864f5e-e452-5d00-8044-81dc89fb7547 |  | note | METHODS OR REFERENCE - NZTA NOC Rehab Catalogue Design & Treatment Approach
label | 4a31757c-b060-54bc-aa5d-a3a2eae404fa |  | note | FREQUENCY - Before work commences
label | e3fb54b1-7d96-53a8-95df-c37de47db46b |  | note | ACCEPTANCE CRITERIA - Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document
label | 85514ec8-4bcb-50b1-866c-07589847ea0b |  | note | TYPE - H
label | 63915706-66b5-53ed-ae7e-87ee0bae4349 |  | note | DESCRIPTION - Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers
label | 03d93068-cb66-5c3c-b1f7-b10e27ba78ce |  | note | RESPONSIBLE PERSON - NZTA Network Manager & Accreditied Designer
label | 974b5d7c-16f3-57ff-8035-2aa0a16d379a |  | note | RECORDS / REMARKS - NZTA Approval to Proceed NTC No.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Seal Design Approval
label | 549db5af-4710-576f-816e-f0c204b54c3d |  | note | VERIFICATION ACTIVITY - Confirmation
label | c0ac1f61-6f0a-5960-aae0-3479d7cf85bc |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Regional Sealing Manager
label | 11bda4b7-5f18-5b80-867e-72b69c6e9844 |  | note | FREQUENCY - Before work commences
label | badea3d0-57c8-577d-91bd-84f9fb794409 |  | note | ACCEPTANCE CRITERIA - Downer Regional Sealing Manager reviews and signs off on Seal Design proposed.
label | c34eac82-8093-5fbd-a9fe-7c19cfca944c |  | note | TYPE - H
label | 06f18cb3-a831-57c6-bcf7-26f98d02f78d |  | note | DESCRIPTION - Hold point - Review and approval of seal design completed
label | 18f2f6fb-609d-53da-a39d-a60d558189ce |  | note | RESPONSIBLE PERSON - Regional Sealing Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Project Manager Handover
label | 16290f8c-08e2-525a-b8cc-73bae6ef47d7 |  | note | VERIFICATION ACTIVITY - Confirmation
label | f08129dc-d7bc-54c3-a9a4-eb8bf88062e3 |  | note | METHODS OR REFERENCE - Review and Sign off by Downer Designer to PM
label | ad164f6b-48d1-5acc-a32f-1f11fce3e13e |  | note | FREQUENCY - Before work commences
label | d431ce04-9104-56cb-b53e-520966d22ff0 |  | note | ACCEPTANCE CRITERIA - Downer Technical Services Team Designer reviews and signs off on Handover.
label | 1a21f6d5-f091-5065-b93e-deaefff6f38e |  | note | TYPE - H
label | 516880e5-fe04-5b76-b7ec-4bfee95d523d |  | note | DESCRIPTION - Hold point - Handover completed
label | 60cd7bd2-26a6-5084-90b1-bf133b5c144e |  | note | RESPONSIBLE PERSON - Regional Engineering Team Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Crew Pack
label | 74897b4c-cb4c-5d9d-bdc5-cb04c47b4829 |  | note | METHODS OR REFERENCE - Items to be included:
label | 85f759db-bf88-5a83-9496-4900702c0f00 |  | note | FREQUENCY - Before work commences
label | 86b57159-aad1-5899-ae74-78138c08529f |  | note | ACCEPTANCE CRITERIA -
label | 0dd1a212-f202-56fa-a486-a4b3201f2cde |  | note | ○ Approved TMP
label | 21832361-3373-5e5d-9718-31eb6f5c40ad |  | note | ○ Services location plans / Marked out
label | b159267e-1270-5d20-9e92-23b659b21dce |  | note | ○ Approved RQP
label | f086157f-2e28-5dd9-af07-9cfae3f19c5d |  | note | ○ Approved for Construction drawings & Pavement Design
label | ab1168ca-fbd9-57e3-a12b-2612962d2aba |  | note | ○ Ramm data
label | 6544a587-28fb-5658-80b1-943455e0619d |  | note | ○ Approved ITP
label | ef554ebb-e364-5a71-88cb-2734a627a2e6 |  | note | ○ Crew Briefing Plan
label | b0497b78-2b77-5a58-9ca6-fc00a3953a1b |  | note | TYPE - H
label | 61556059-ca37-57d4-ae7c-72edec46db4d |  | note | RESPONSIBLE PERSON - Downer PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Setout / Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Setout
label | 612f4464-3bb3-55ed-9729-1c667f76a9d9 |  | note | VERIFICATION ACTIVITY - Survey
label | 2fd49992-32a0-5965-8847-7b59d8e5100a |  | note | METHODS OR REFERENCE - As per approved drawings
label | bb37380e-e8a1-5782-8aff-34da0f11e75f |  | note | FREQUENCY - Per installation / Site
label | 401bacb5-bc9c-5fe9-be7c-09b2e28e3998 |  | note | ACCEPTANCE CRITERIA - Design strings /design surface model loaded for machine control
label | 87a65d68-a6cd-57ce-a5fb-266d31160435 |  | note | TYPE - V
label | 3f3ee831-7346-5985-9722-4ba7a564d68f |  | note | DESCRIPTION - Machine control requirement. Downer surveyor required for MC upload and verification of model operation
label | 4fdb7d20-def3-5ee6-9346-31c6d92e21db |  | note | RESPONSIBLE PERSON - Downer Approved Surveyor
checkpoint-status |  |  | checkpoint | 2.2 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 7faf074c-b87d-5a73-86e8-f6e2fe951fb0 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | ec034d11-2100-5f16-a446-3c5e48778f2a |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 31f5cc35-3f8b-50ea-b47e-d9d88c0701e3 |  | note | FREQUENCY - Before work commences
label | 1d70a0e5-cc92-52bf-a732-52821db1e803 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 5f35d627-74e9-5ba6-97b0-20ab2596420f |  | note | TYPE - H
label | 740ac460-1e2e-5735-b752-6044c942b83b |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
label | d5fe749f-4b22-5ebf-827d-2ee920eec8fa |  | note | RESPONSIBLE PERSON - Construction Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | 1f353693-8242-5a96-9bbe-7b97318ab271 |  | note | VERIFICATION ACTIVITY - Notification
label | 42387ea5-5e49-5b79-bffe-8670698dee55 |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | d09645b2-d902-54c9-bf1c-c3adb2d16798 |  | note | FREQUENCY - Before work commences
label | 2ae8817c-ad73-5e87-bbdf-c29c327e9044 |  | note | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | b72aa311-7289-5592-9a68-ed8b289075bd |  | note | TYPE - H
label | 90b51223-2c09-5cd3-a52e-64c46f6bdbf9 |  | note | DESCRIPTION - Where risk of cultural discovery
label | 4583e850-03fc-540e-b694-b438a3c85067 |  | note | RESPONSIBLE PERSON - Renewals Engineer / Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Archaeological Risk
label | e6731f87-e3aa-50d9-acea-006e4e74dc0e |  | note | VERIFICATION ACTIVITY - Toolbox meeting
label | 8fc8a20d-d3a0-5a26-b4e7-f7e46993bdbe |  | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | 394c0d2f-7d45-5e8c-90d7-ac6d7d7f91c7 |  | note | FREQUENCY - Before work commences
label | 81968565-a8d8-5900-8a94-3e85d0f4e142 |  | note | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | 89e5c036-ff61-5de0-a5d1-63f01ccfc0f9 |  | note | TYPE - H
label | 520a01b2-1fc7-55a3-bd7d-c71a719a6441 |  | note | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
label | 5f2c4e6b-b531-5a94-8b57-72562bbbf9aa |  | note | RESPONSIBLE PERSON - Construction Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Traffic Management - Signs Setup
label | faf672c2-8c32-58f5-8f94-6446ef35616b |  | note | VERIFICATION ACTIVITY - Visual check
label | 3c11517d-051a-53f6-94d4-2cbe24c1b8cd |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 9707a8c4-cc13-5627-8322-4e6816380f71 |  | note | FREQUENCY - Before work commences each day
label | 8bd42984-9769-58ff-b6f4-ff9893703289 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 3bfc9fdf-5fe2-5cd0-a646-c734c5c82967 |  | note | TYPE - H
label | 49d1363e-8ae0-5bc9-964f-80273d00b14c |  | note | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | 444606cd-8aef-5dd3-8fd7-61f846f64c92 |  | note | RESPONSIBLE PERSON - STMS
label | 06b803c8-a960-599d-a318-a004fb4a99ff |  | note | RECORDS / REMARKS - Daily site record sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pre-Construction walkover
label | dd886108-d9fd-5989-a1c7-9877dab1d724 |  | note | VERIFICATION ACTIVITY - Visual check
label | 7fa01943-50fc-5fd8-8f22-7b603d30609e |  | note | METHODS OR REFERENCE - Approved Crew pack on site 2 weeks prior to work comencing
label | c7f23b61-d05e-5c8f-963b-c08af6c7b149 |  | note | FREQUENCY - Before work commences
label | f60daafe-47eb-5d01-a4b6-52cd7f34bf00 |  | note | ACCEPTANCE CRITERIA - Principal / Highways / Downer Acceptance
label | f1755a72-7197-5f7a-9ff5-26e6af60d39b |  | note | TYPE - H
label | 0fadc5d2-e093-5e7e-b826-e83f9735eca5 |  | note | DESCRIPTION - Hold point - Walkover required ahead of Highways establishment, Hold point - No physical works are to be commenced until walkover completed
label | 9a5e62bf-4044-54f5-85d7-4b35956e3251 |  | note | RESPONSIBLE PERSON - Renewals Manager / Highways PM / MCM
label | 43dfeef1-48bb-5b83-a7ff-95e0ebfa9cda |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminary Works
checkpoint-status |  |  | checkpoint | 3.1 - Shoulder Stripping / Vegetation clearing
label | 00154d25-8da5-522e-b0a9-1aa360b88b52 |  | note | VERIFICATION ACTIVITY - Visual check
label | 4da1afe9-9ed2-57db-89c6-a0aed8ac9cbc |  | note | METHODS OR REFERENCE - On site
label | 45ca9169-fdaa-5b4d-a168-6b94b522fcb0 |  | note | ACCEPTANCE CRITERIA - Shoulder stripping as per drawings completed
label | 0e8f840c-fc2d-57f5-b511-eba1e6b729ce |  | note | TYPE - V
label | bd570030-4949-50d2-b6b3-a23efe5f9a55 |  | note | RESPONSIBLE PERSON - Construction Supervisor / NZTA
label | 8b7993ff-c7a8-5048-a953-7edbbe2deec5 |  | note | RECORDS / REMARKS - Invite for NZTA to carry out joint site visit to complete visual inspection
checkpoint-status |  |  | checkpoint | 3.2 - Site pavement A/C digouts
label | a1602394-909c-5112-958c-3d396391559d |  | note | VERIFICATION ACTIVITY - Visual check
label | e58146d6-d8c8-5196-989e-9394815362f3 |  | note | METHODS OR REFERENCE - Check RAMM records for depths
label | 56e4e518-1fef-5a02-bdb3-ffbbebf90aa8 |  | note | FREQUENCY - Before Stabilisation work commences
label | a7e7663f-03f8-5521-ad9a-e6ab194f7615 |  | note | ACCEPTANCE CRITERIA - Work completed prior to stablisation contractor onsite
label | 7b4a7545-0043-5c74-b433-6780fdda5ecc |  | note | TYPE - V
label | c0c44bac-2703-5aa5-b3a5-0c0092fcf260 |  | note | DESCRIPTION - A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed
label | 5f8337e9-b758-5989-aa4a-6822843f414e |  | note | RESPONSIBLE PERSON - Site Foreman
checkpoint-group |  |  | section | 4 - Culvert extensions / Headwalls / Flumes
checkpoint-status |  |  | checkpoint | 4.1 - Excavation Inlet / Outlet Gradients
label | 6f0b4912-9dfd-538a-bb88-8cda3ff0ae3f |  | note | VERIFICATION ACTIVITY - Survey
label | 6a8b8a35-8f2c-539f-9901-6409c5e335a2 |  | note | METHODS OR REFERENCE - NZTA F/3
label | aeaeb3e1-bda1-5d16-81fc-f9214e6b5ae7 |  | note | FREQUENCY - Once
label | e093d409-abd8-5329-8c75-639b53ac09c9 |  | note | ACCEPTANCE CRITERIA - Consistent gradient in and out
label | dca8502a-9b49-5bae-834b-5f57feee89f1 |  | note | TYPE - H
label | 8e417503-3b1e-5e6b-aaa1-4c4bf2f6d089 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | 7f650129-ca1a-54fa-91e0-05cd543b1ba5 |  | note | RESPONSIBLE PERSON - Site foreman
label | 8297d4d2-3845-5c60-921e-958c999079e8 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Pipe materials / class
label | 732f7e06-ca8a-5f50-8a60-9fff527fa50b |  | note | VERIFICATION ACTIVITY - Visual Check
label | bdc53969-e0ef-531b-9d88-eb7d780408bc |  | note | METHODS OR REFERENCE - NZTA F/3 2.1
label | 96c67e41-2b5e-52a0-9a98-8ec64508cde8 |  | note | FREQUENCY - Once
label | 13653d48-d84c-5031-8fca-cb2436077373 |  | note | ACCEPTANCE CRITERIA - Meets appropriate AS/NZ standard reletive to specified type
label | 8a21a9c5-11f8-55d1-8676-2c5260386284 |  | note | TYPE - V
label | 1cd64d73-06bc-549b-ba7c-c0d54b17203a |  | note | RESPONSIBLE PERSON - Site foreman
label | 6b364498-ad01-52c1-9569-2a32842ee186 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Bedding contact
label | c8c72e58-a3b8-5f0b-89e2-b395f1342296 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 7c24d688-9a0e-5bf5-a3f3-36546684fbac |  | note | METHODS OR REFERENCE - NZTA F/3 5.1
label | dedc6ee4-f9a0-5323-9e9b-31838164ca0c |  | note | FREQUENCY - continuous
label | 2dfe3d16-8c16-51fb-aa1d-4dbfa3d2456a |  | note | ACCEPTANCE CRITERIA - uniform contact over full length of pipe
label | 05473fb9-0815-544f-a559-165baf2d0df2 |  | note | TYPE - V
label | 7f06cc10-d99f-550d-9eb5-4a13255ab103 |  | note | RESPONSIBLE PERSON - Site foreman
label | 2428c503-4349-5d9b-a927-1aeaeb29a510 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Subsoil drainage
checkpoint-status |  |  | checkpoint | 5.1 - Trench
label | 81e4bce9-d59e-58e0-bee9-60cac4c56289 |  | note | VERIFICATION ACTIVITY - Visual
label | 89a4eb3a-a763-58ac-b4c6-d5c2556c477b |  | note | FREQUENCY - each site
label | a3ff6dfb-0858-577a-a732-962117704a03 |  | note | ACCEPTANCE CRITERIA - Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm
label | 708c6371-0a65-5160-9f46-1d40205ed1da |  | note | TYPE - H
label | c5996b61-0bd4-52c4-afe5-d72c976346f5 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | 8d0a0bd2-f18e-53ec-9ee5-af3ba7e64db1 |  | note | RESPONSIBLE PERSON - Site foreman
label | 69c7d28a-f310-559a-919f-8cac1fe36683 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Drainage material
label | d9c54a23-3391-5a75-84f7-5d6e37539f78 |  | note | VERIFICATION ACTIVITY - Visual
label | 0d910f05-d40c-569c-ab0c-d300786dfc63 |  | note | FREQUENCY - each site
label | e0e5cafc-e4ec-5b27-919b-876c0b3c1569 |  | note | ACCEPTANCE CRITERIA - 7-12mm clean filter material ( grade 2 - 4 Sealing chip
label | 217b9b0c-97c2-5734-bb2f-1baf3e82cc0f |  | note | TYPE - H
label | 6f5a809e-b61c-5985-a718-6bf26eabefc6 |  | note | DESCRIPTION - Hold Point – Visual check prior to pipe placement
label | 2e9f6efc-9dfd-577b-8c9f-61fa8d101ac5 |  | note | RESPONSIBLE PERSON - Site foreman
label | d3d24cf2-21a6-53fd-8cb1-7b0eedd0dd71 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Pipe type
label | d47e7a56-c356-5b23-a411-46bf24c7d035 |  | note | VERIFICATION ACTIVITY - Visual
label | a6ff8d03-c18d-5914-93fd-b5e4f79b5051 |  | note | METHODS OR REFERENCE - Diameter as per the design drawings
label | 2c070149-edec-5207-a6e1-6f235e4a54fd |  | note | FREQUENCY - Use outside traffic Lane, Under traffic lane
label | 8de5d566-bd98-5f1f-a024-6e0194b384e0 |  | note | ACCEPTANCE CRITERIA - Docket to confirm
label | 7ab7f2d4-ddb9-50cf-b138-34687398a0b9 |  | note | TYPE - V
label | b8a109cb-a1b6-5c8b-8d91-9819d5905400 |  | note | DESCRIPTION - "Nova flow", Nexus
label | 0945418f-5f94-55a3-ac41-ca6082f03550 |  | note | RESPONSIBLE PERSON - Site foreman
label | f6033456-fc3b-551d-8bcb-e02a92175eca |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-status |  |  | checkpoint | 5.4 - Filter Fabric
label | 85a1cf30-7295-5c78-9f09-fd88f8ea1c30 |  | note | VERIFICATION ACTIVITY - Visual
label | 6f9ac685-315c-5802-a20c-e42bbdc8ffbf |  | note | ACCEPTANCE CRITERIA - 150mm lap, top of fabric minimum 150mm below FSL
label | 0587c518-8d7e-5d19-bd5c-6ee3ffc63d25 |  | note | TYPE - H
label | be53ff8d-9a61-5a9a-8ac7-a7c7f49091b7 |  | note | DESCRIPTION - Hold Point – Visual check prior to reinstatement
label | 2d24ed7c-1062-58a4-b6f9-207d58065670 |  | note | RESPONSIBLE PERSON - Site foreman
label | df58fcda-ec26-5c41-81c4-5c4d1db9e986 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Outlet
label | 6a4e5747-ecf6-5c26-8e6c-8c727473eff8 |  | note | VERIFICATION ACTIVITY - Visual
label | 96e6032a-4c14-528e-b352-e69e41ee3277 |  | note | ACCEPTANCE CRITERIA - Connect to sump barrel, culvert of construct Concrete Apron
label | 0eaba051-e892-5ae8-9842-43d856c8892b |  | note | TYPE - H
label | 7ae49bbe-3613-504d-befe-70dd5b7d2b6f |  | note | DESCRIPTION - Hold Point – Visual check prior to reinstatement
label | d3dd0a7e-f085-5f04-a093-e0babf50c44d |  | note | RESPONSIBLE PERSON - Site foreman
label | a2c6380c-f2e0-5360-9db0-4b17d8b25723 |  | note | RECORDS / REMARKS - Required Yes / No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Flushing / Cleaning eyes
label | 15c928ac-e964-504e-930c-7223ef507916 |  | note | VERIFICATION ACTIVITY - Visual
label | e5acde71-7ca0-5923-88ef-dfe4b01076c0 |  | note | METHODS OR REFERENCE - To be placed & constructed as per Approved Drawings
label | 1c12e7c5-d97b-5555-b68f-0024c434df4b |  | note | FREQUENCY - Each free end
label | 41a44a0d-2ae0-5d87-84ee-fba87c6ebe99 |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-status |  |  | checkpoint | 5.7 - Reinstatement
label | 1dc36b24-a196-52db-86f4-6448e5f64486 |  | note | VERIFICATION ACTIVITY - Sealed Pavement, Berms and shoulder
label | 1cbf34f8-20b5-5ada-8f7f-32727da0c876 |  | note | ACCEPTANCE CRITERIA - Top min 150mm impermiable backfill
label | e50f8f48-c750-58ee-b6b7-2c3b0517ee3a |  | note | TYPE - V
label | 30a3039a-d6d9-5bd6-8ab1-d1552677b5c2 |  | note | RESPONSIBLE PERSON - Site foreman
label | 6c8bc5c4-df0a-5863-87ba-c9010be40d6e |  | note | RECORDS / REMARKS - Required Yes / No
checkpoint-group |  |  | section | 6 - Preteatment of Insitu Materials
checkpoint-status |  |  | checkpoint | 6.1.1 - Pretreatment Stabilising Agent (where applicable) - Quick / Hydrated Lime or KOBM
label | 258a751f-bbc5-55b3-98a4-0186a58e1981 |  | note | VERIFICATION ACTIVITY - Mat Test 1m² canvas
label | 78f929b6-baf5-58c4-98cb-34d0f2b35d64 |  | note | METHODS OR REFERENCE - Pavement design report
label | 30ed42ac-7713-5dc9-9da6-acb2f4ff8bc3 |  | note | FREQUENCY - Every 400m²
label | e59ab17e-09fd-5caa-8daa-7f11f8767b4a |  | note | ACCEPTANCE CRITERIA - Within ±0.5kg/m² of the specified rate
label | 22d9776d-8852-549a-ac43-19e436da4dfe |  | note | TYPE - V
label | 92870d06-7678-5c17-84be-0f60c84bab2f |  | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | a2b96fba-0d79-5feb-a30e-1207dc50936b |  | note | RESPONSIBLE PERSON - Highways Site Foreman
label | d3985a83-05c9-5cb1-9446-af0eae4b07cd |  | note | RECORDS / REMARKS - Daily Job Record
checkpoint-status |  |  | checkpoint | 6.1.2 - Pretreatment Stabilising Agent (where applicable) - Quick / Hydrated Lime or KOBM
label | e6e35942-8607-5687-a07b-20541b15cf42 |  | note | VERIFICATION ACTIVITY - Average usage test
label | c9fd16ff-8e0c-539a-be9a-622d989da9ec |  | note | METHODS OR REFERENCE - Pavement design report
label | 86cbdcf1-30e1-52b9-b481-daffc6f5a192 |  | note | FREQUENCY - Upon emptying the spreader and bulk tanker
label | 7f37d4b4-7086-5492-baf3-15758dde0f23 |  | note | ACCEPTANCE CRITERIA - Withn ±2.5% of the specified rate
label | 7ebeccc8-4ac0-5c9a-939c-7df7f3007fe8 |  | note | TYPE - V
label | f756a3a0-b836-520b-90fc-d90cc94cf931 |  | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | 8f7984b3-af1c-5382-918e-56d7370cd905 |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 6.2 - Stabilising Depth
label | cd0efb45-9163-5d23-9fe3-e23dd9635a8d |  | note | VERIFICATION ACTIVITY - Depth measurement
label | 97cd7bac-1cf6-5afd-82bb-61c68aceebcd |  | note | METHODS OR REFERENCE - Design drawings
label | db32798f-64d3-5390-86f0-a4b8742e3cb8 |  | note | FREQUENCY - At both ends & sides of cut and every 200m
label | 86d77219-b555-5aaa-a66d-c515a2a8829f |  | note | ACCEPTANCE CRITERIA - -5mm +15mm of design depth
label | 3e56d187-8c48-54da-a21e-8a189a2e87d1 |  | note | TYPE - W
label | 42d358b0-a82d-5674-bc8b-d0ecef403a9e |  | note | RESPONSIBLE PERSON - Highways Site Foreman
label | 0cffc610-1f19-577f-aaab-255189b0e3e4 |  | note | RECORDS / REMARKS - Daily Job Record
checkpoint-status |  |  | checkpoint | 6.3.1 - Pre-Hoe
label | 77e5e687-66fc-5404-9895-bfe676db614a |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | 00abae32-3239-56c9-bf98-a14684041836 |  | note | FREQUENCY - Each Subsection
label | e323c41d-6322-50c5-8526-4bb1926071e1 |  | note | ACCEPTANCE CRITERIA - No unsuitable material found to be sampled
label | 7d993cac-a8e4-59e8-9d78-b1ef46d7d94c |  | note | TYPE - H
label | 465861ae-3fdc-56eb-a165-7cb0d1d1b1b1 |  | note | DESCRIPTION - Hold point - Hoed material to be checked to ensure consistencey and no unsuitable material found, Sample to be taken for future testing if required
label | ed661fec-433d-5e85-a125-b9b26660ae69 |  | note | RESPONSIBLE PERSON - Renewals Manager / Highways Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3.2 - Visual Inspection post Hoe - Proof Roll and Joint Inspection
label | f53169f7-8f6e-5528-93a0-e26268136676 |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | 95ec8096-7a52-5250-94f5-eed2d9fa037b |  | note | METHODS OR REFERENCE - 6x4 truck fully loaded or similar equivalent
label | 5b2b5996-c39a-5d57-b015-cd094c9f5d8c |  | note | FREQUENCY - Each Subsection
label | f76570dc-6411-54fd-9f24-5d4c998c882f |  | note | ACCEPTANCE CRITERIA - No significant movement of the pavement under proof rolling and/or trafficing, for subgrade contamination
label | 05186712-a48f-5289-96d8-3a5336201f1b |  | note | TYPE - V
label | 1e186fdb-faf7-56f9-b633-0352b14e7e8b |  | note | DESCRIPTION - Testing to be carried out imediately after compaction
label | 0ab4784b-0d46-5a36-bcfc-085067276c40 |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Downer PM
checkpoint-status |  |  | checkpoint | 6.3.3 - Visual Inspection post Hoe - Material FBS Suitability
label | ffcc9608-dc78-5050-b613-1fa2b89fedd5 |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | 1717b74a-df02-54a6-9cb9-bcc9cb577170 |  | note | METHODS OR REFERENCE - Particle size to be 50mm or less
label | 6f234002-8d66-5620-868e-39035bb2f4ed |  | note | FREQUENCY - Each Subsection, as required
label | 706d92a4-c474-5327-83e0-784a11ac2fb4 |  | note | ACCEPTANCE CRITERIA - No large slabs of existing wearing course or strongly bound base
label | 8e5feb92-5ebf-50e9-914e-c48515f9e48d |  | note | TYPE - V
label | fcf281f9-006b-556b-aaa0-65db557b3c32 |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Downer PM
checkpoint-status |  |  | checkpoint | 6.3.4 - Undercut unsuitable areas
label | 4437bebe-f340-570e-a4dc-e0e6d2be6103 |  | note | VERIFICATION ACTIVITY - Visual Inspection/ measurements
label | 39d1bfc7-fb2d-589d-961d-9d1e84399c8d |  | note | METHODS OR REFERENCE - Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table
label | d69cfd9b-a04c-515a-8b9f-6da14efd0d12 |  | note | FREQUENCY - Where required
label | a230fd4f-7959-55f2-8f32-f31cf5f8a2a5 |  | note | ACCEPTANCE CRITERIA - All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to
label | 7a07385d-8ce5-520b-ab50-924192a81970 |  | note | TYPE - H
label | 98fdf424-4c5e-58c9-858c-b7a8a7c94e9e |  | note | RESPONSIBLE PERSON - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3.5 - Shape & Compact Hoed layer
label | ee683edf-02c5-5819-9623-1b746bf4aa4c |  | note | VERIFICATION ACTIVITY - Check for 75mm overlay
label | 050a4883-d32f-5393-b67d-90c57530556a |  | note | METHODS OR REFERENCE - Shape to correct as per the existing surface
label | 6baaa371-1098-57d5-83e9-4aef7553bcdb |  | note | FREQUENCY - Every 20m
label | 4b796d9c-c018-55af-af2f-e84c0ad3587d |  | note | ACCEPTANCE CRITERIA - Max 200mm layer depth to achieve compaction & trimmed to match existing shape and trafficable
label | 881a47ac-0b1f-5d2c-90bf-4694146a778c |  | note | DESCRIPTION - Verified min 75mm overlay depth with no removal of pre hoed material in the traffic lane
label | c9492434-096a-574a-a3f9-3f59b57cbb2d |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Downer PM /Downer Surveyor
label | 02a79f67-f20f-5e31-a924-318351bda6b6 |  | note | RECORDS / REMARKS - Joint inspection
checkpoint-group |  |  | section | 7 - Imported Basecourse Materials Testing
checkpoint-status |  |  | checkpoint | 7.1.1 - Imported Basecourse Materials Source Property Testing - Crushing Resistance
label | f9fabd02-d9aa-5799-98d1-e46db9f73368 |  | note | VERIFICATION ACTIVITY - NZTA M/4 Crushing Resistance (CR130) Test
label | cfcdbfd4-d2e6-5d62-b8b5-1eba4ecf4b8b |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.10, NZTA M/4
label | 29a189cd-3b1d-55e8-8b89-b7a4c87d69af |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 467bcc35-903c-5f17-9680-56b2979fde64 |  | note | ACCEPTANCE CRITERIA - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 69616003-a1b8-5aaf-a5df-f5c838617ece |  | note | TYPE - V, H
label | 93d7645f-082e-5afa-97e3-ba1b92f0258e |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | dc53c65d-6276-56dd-921f-7149de30dc91 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 21bef540-d64f-51ab-b481-1a365114ad42 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1.2 - Imported Basecourse Materials Source Property Testing - Weathering Quality
label | b92f5b0a-dc0c-55b1-91b8-5611efd9dbd5 |  | note | VERIFICATION ACTIVITY - Weathering Quality Index (WQI) Test
label | 9e66e067-2b48-5f60-8916-60742b787ff8 |  | note | METHODS OR REFERENCE - NZS 4407 Test 3.11, NZTA M/4
label | c94e4638-03cd-531f-8629-43f888526f21 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 37246a66-61fa-5d04-92c0-f0f4f10c7992 |  | note | ACCEPTANCE CRITERIA - Must have quality index of AA, AB, AC, BA, BB or CA
label | c043dd55-4e13-5c0f-a9ff-1b29af601e2b |  | note | TYPE - V, H
label | 0e02ac13-169b-5ba7-9193-c218267ee101 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 18a3ff45-1682-5101-b621-a29adc769bc3 |  | note | RESPONSIBLE PERSON - Renewals PM
label | f333efb6-84e1-5d84-8c9d-0cf2aaf66065 |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1.3 - Imported Basecourse Materials Source Property Testing - Bearing Strength
label | 6057db6e-3ebb-5cb9-ac4a-a0f902c21605 |  | note | VERIFICATION ACTIVITY - Californian Bearing Ratio (CBR)
label | 8431b558-e0fe-5a94-a027-38d4c127a667 |  | note | METHODS OR REFERENCE - NZS 4407 T3.15, NZS 4402 T4.1.3, NZTA M/4
label | 219785ba-4527-5fa1-9b4b-081c974f7f19 |  | note | FREQUENCY - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 37fcbbe6-5245-5145-abfc-556a3404a598 |  | note | ACCEPTANCE CRITERIA - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | 5ef77bdf-0f5f-54ce-9698-811e2b5a13e7 |  | note | TYPE - V, H
label | 2059f9d0-ae69-5aff-aa2c-081bd1f5ce97 |  | note | DESCRIPTION - Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old
label | 83650b12-9c4c-5946-b6f3-fc77732090a4 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 8add0971-1752-533f-b49e-c701e5fa98ff |  | note | RECORDS / REMARKS - All source aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Imported Basecourse Materials Production Property Testing
label | 4a0188a6-2065-5d61-841c-736db830ca41 |  | note | VERIFICATION ACTIVITY - Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF)
label | f97dab77-d5d0-57e7-8035-83a905cdc586 |  | note | METHODS OR REFERENCE - Refer project specification and NZTA M/4
label | e525144d-e143-513f-b0cb-5741c7da08c3 |  | note | FREQUENCY -
label | 5fdc8cd9-c867-5b67-b156-34fd732c5261 |  | note | ○ 1 - 400m3 – 2 tests
label | 6d1ce3b2-da5a-5d39-b69b-173f656add78 |  | note | ○ 400 - 1500m3 - 3 tests
label | 320fa1ae-3cc5-592c-a318-ad375a4326b5 |  | note | ○ 1500 - 4000m3 – 4 tests
label | b297555f-649f-5afa-a284-e1cef8c5dca2 |  | note | ○ >4000m3 – 1 test per 1000m3
label | da17ed8b-6fe8-58be-9f4b-ba14878177a4 |  | note | ACCEPTANCE CRITERIA - Refer project specification
label | acba2473-c48a-5af1-a88d-767772eb11c0 |  | note | TYPE - V, H
label | 484c8885-568f-5d61-b1a1-27e46adf5fb6 |  | note | DESCRIPTION - Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old
label | 49fce37b-cd36-5111-ae51-05021076c212 |  | note | RESPONSIBLE PERSON - Renewals PM
label | 1ad013a6-68fa-5f42-8a0f-4ccc8543f51d |  | note | RECORDS / REMARKS - All production aggregate test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Nominal 75mm Make-up Metal
label | 9691755f-97e3-5c9f-88ed-333f43eb8fef |  | note | VERIFICATION ACTIVITY - Quantity of material used
label | aee898bb-9b14-53d7-a11f-04c61513947d |  | note | METHODS OR REFERENCE - 75mm depth over high spots
label | 84bf3065-8708-541c-81a7-57615fc79af1 |  | note | FREQUENCY - Each Subsection
label | 8d55b64a-b842-5134-bee4-fb3237189a6a |  | note | ACCEPTANCE CRITERIA - Correct amount of material used (M³Solid) as per geometric design / MC
label | 436b5c10-f125-5c7d-b042-26029422049a |  | note | TYPE - V
label | 10f43770-9801-5bda-8982-ba8c47e8ccf5 |  | note | DESCRIPTION - Spot checks to be taken
label | 7f6c8edf-eec4-5200-8c18-90bf2b56dc73 |  | note | RESPONSIBLE PERSON - Downer surveyor
checkpoint-group |  |  | section | 8 - Foamed Bitumen Stabilisation
checkpoint-status |  |  | checkpoint | 8.1.1 - Stabilisation Agents - Foam Bitumen
label | ab6a7fa4-5870-5619-beb7-843ad23ba569 |  | note | VERIFICATION ACTIVITY - Laboratory testing
label | c1d8e646-53fa-5a5e-8887-984a7077f412 |  | note | METHODS OR REFERENCE - NZTA B/5, NZTA M/1 (B/7)
label | a5bfdc5c-18bf-5d06-968d-b67aa2cc2da4 |  | note | FREQUENCY - Per batch
label | 5b1308a4-810f-586d-82d7-099012f169ff |  | note | ACCEPTANCE CRITERIA - 80/100 or 180/200 Pen Grade, Minimum expansion of 10 times original volume, & half-life of at least 6 seconds
label | 03085ba3-d009-5040-bf7c-3824468d26e3 |  | note | TYPE - V, H
label | 65f4a180-7019-58fb-80ae-dff4fd969f15 |  | note | DESCRIPTION - Renewals Engineer
label | 8b89246c-45f8-5329-9847-39619100c16a |  | note | RESPONSIBLE PERSON - Renewals Engineer
label | e66fd2e5-e9df-5a9f-878d-dfada9d6afda |  | note | RECORDS / REMARKS - All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.1.2 - Stabilisation Agents - Cement
label | 87708e8b-7e02-524c-89cf-6cd998854d64 |  | note | VERIFICATION ACTIVITY - See NZS 3122
label | a396805f-d48f-5210-afef-a3da0cecb8dd |  | note | METHODS OR REFERENCE - NZS 3122, NZTA B/5 Cl. 4.1.2
label | 3d6a713d-a455-574b-b5b8-30589ff6b9cd |  | note | FREQUENCY - Per batch
label | 052a514e-3842-5ab8-a3b4-65541995dc30 |  | note | ACCEPTANCE CRITERIA - Cement must comply with NZS 3122
label | 8ff87679-212a-59db-bcec-9588ad8e9ea3 |  | note | TYPE - V, H
label | eff8175f-a85c-51d2-b7ef-f3bf8b3120ed |  | note | DESCRIPTION - Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier (this is to be done once for contract)
label | 3cd74c30-674b-5a20-95a5-e3b8689bdf3d |  | note | RESPONSIBLE PERSON - Renewals Engineer
label | 4a6aeb3f-7150-59ff-aa1b-430e26b9abad |  | note | RECORDS / REMARKS - All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.1.3 - Stabilisation Agents - Delivery
label | d7df4649-f19c-589e-9659-77ac585bb3ac |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | d0e13494-486e-58db-958c-1a1cec54703b |  | note | METHODS OR REFERENCE - NZTA B/2
label | 59d0777f-4379-550b-b5e4-a94f7281924a |  | note | FREQUENCY - Upon delivery
label | 4e8364b9-9429-53ec-a3f2-cac2ee5ebe2a |  | note | ACCEPTANCE CRITERIA - Stabilising agents to be delivered in tanks or trucks with Certificate of Loading
label | ddb0fe45-cc43-5fc9-a2cf-ef72bd143b02 |  | note | TYPE - W
label | 533c4862-4a86-5ab7-a139-b2d7b20cf2a8 |  | note | DESCRIPTION - Certificate of loading to be checked on site
label | 4e6dcb09-b1fa-51fa-b008-616eded3a46c |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.1.4 - Stabilisation Agents - Bitumen Storage (1)
label | 822c6355-51a4-52e8-b13a-2a94c3dbe430 |  | note | VERIFICATION ACTIVITY - 80/100 Pen Grade
label | 9f20f23a-cee4-51ea-8840-fd70799a9f8f |  | note | METHODS OR REFERENCE - NZTA B/5
label | 7fa608d4-4672-52cf-8719-d42cad0de8ca |  | note | FREQUENCY - 2 hours before use
label | 20a09734-3736-586b-b6dd-21d418b62d1a |  | note | ACCEPTANCE CRITERIA -
label | ddd28d3d-6268-52d8-8e53-605ce5fa87e0 |  | note | Max storage temp: not exceed
label | b528c461-3dbf-5643-a464-1557b2101bf5 |  | note | 125°C for > 24 hours & 175°C for < 24 hours
label | 79bf004a-60b8-5bb6-b849-e6d8f5d50fd5 |  | note | Application temp: min 175°C - max 190°C
label | 05ffe9e9-e192-5874-81f3-f8775898b3c3 |  | note | TYPE - H
label | 5d8d4756-da07-51b0-841c-13dc013dc44a |  | note | DESCRIPTION - Any bitumen that has been heated above the maximum shall be removed from site
label | ff5ff3f4-ad11-5fe4-94d0-e1b6870456fa |  | note | RESPONSIBLE PERSON - Highways Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.1.4 - Stabilisation Agents - Bitumen Storage (2)
label | 808faccb-8133-5df3-839d-204d4e66108b |  | note | VERIFICATION ACTIVITY - 180/200 Pen Grade
label | cb4bd81c-2727-57bd-83c6-01adc46567d7 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 289dbc3f-2f70-588e-bed4-1ee28dc05011 |  | note | FREQUENCY - 2 hours before use
label | f20875f3-8daf-51c5-8f74-6ab6a6d6e09e |  | note | ACCEPTANCE CRITERIA -
label | 6820ed3a-c974-5d56-8d70-2699026d1dbf |  | note | Max storage temp: not exceed
label | c84acb03-6b6d-5dc0-a5b4-1cf1057c886e |  | note | 120°C for > 24 hours & 170°C for < 24 hours
label | 6a1fe4bb-905d-5889-853c-66f1d64bcdd2 |  | note | Application temp: min 170°C - max 185°C
label | b8a651ee-4694-5f33-b4a2-c13b16e001b0 |  | note | TYPE - H
label | 26af0808-3bac-5f3a-b7a3-f07fd4afce38 |  | note | DESCRIPTION - Any bitumen that has been heated above the maximum shall be removed from site
label | a9bc3dcc-b20e-5e4d-8bbf-3a0975fcc956 |  | note | RESPONSIBLE PERSON - Highways Site Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 - Water
label | ed4d7e81-aff8-54ce-a39d-049d03a2b859 |  | note | VERIFICATION ACTIVITY - Obtained from a suitable source
label | 0af07473-61bd-52e9-ae9e-4ad39b510100 |  | note | METHODS OR REFERENCE - NZTA B/5(B7) Portable PH testing
label | 6d02898f-95c8-5f57-8896-3916d645dd0e |  | note | FREQUENCY - Ongoing
label | 89d1a9c9-b18a-535e-846d-d0e1def65f3f |  | note | ACCEPTANCE CRITERIA - Water for stabilisation, construction and curing is tested for correct PH for each site
label | 67536d77-bea4-50fd-92f6-de06d9410e3c |  | note | TYPE - W
label | 5296330c-f00e-58eb-b02e-62bfdcc5a60d |  | note | DESCRIPTION - Certification required for each site (PH 5.5 -7.0)
label | 143a7ca1-ecf2-5a50-9e70-efdfdad26d4e |  | note | RESPONSIBLE PERSON - Downer PM
checkpoint-status |  |  | checkpoint | 8.3.1 - Weather Limitations - Temperature
label | 6a9688df-61cf-5de4-b513-8f5340cc08b9 |  | note | VERIFICATION ACTIVITY - Measure Temperature
label | 3e116c2e-2406-537b-a952-bc3bf186ea29 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 2fe319a4-6985-5a50-bab9-fc72e0c43472 |  | note | FREQUENCY - Daily
label | 66c97472-9791-5819-a71f-87e9c2e786e3 |  | note | ACCEPTANCE CRITERIA - Stabilised material before compaction 20°C
label | 7ad41317-20a1-5e1d-a585-f22a6ad3920a |  | note | TYPE - W
label | 66f96d66-96f8-5287-a938-af4c25d1336e |  | note | DESCRIPTION - Work shall not be started if temperature is below the respective minimums.
label | 519f46e3-9f25-5325-8c8b-0f37d79e4be7 |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Downer PM
label | c626e842-6eb8-5965-929f-7b7008124d17 |  | note | RECORDS / REMARKS - Joint Inspection
checkpoint-status |  |  | checkpoint | 8.3.2 - Weather Limitations - Wind
label | 03e878f1-71d6-5cec-b2f3-4428e5d56b83 |  | note | VERIFICATION ACTIVITY - Assessment
label | 216e31c6-6497-5617-942d-fb8769f77e25 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 7bb8e36b-1e86-51c3-affd-40d77f25cd71 |  | note | FREQUENCY - Daily (SEE remarks)
label | 502a6736-2b1d-5529-afda-636873724e67 |  | note | ACCEPTANCE CRITERIA - Maximum windspeed of 25km/hr checked from metservice website
label | ea5cda3e-1ad6-5e32-bbf6-6c03d0851fe6 |  | note | TYPE - W
label | d9841d1c-951e-5a1b-91ff-0e450304060d |  | note | DESCRIPTION - Work shall not be started if windspeed exceeds the maximum
label | ba93563f-9f8f-5864-9ed3-bcb6c2e8952e |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Downer PM
label | bfc97b25-330c-5739-bb08-38a4a9b4ddd1 |  | note | RECORDS / REMARKS - Not applicable if direct injection used
checkpoint-status |  |  | checkpoint | 8.3.3 - Weather Limitations - Rain
label | 8bc727b7-dd30-5460-b82f-14089ebc8610 |  | note | VERIFICATION ACTIVITY - Check forecast
label | edf371bb-4d12-5a17-af19-2615eceb2dd2 |  | note | METHODS OR REFERENCE - NZTA B/5
label | fc89efb8-e9e0-51e3-8693-177a2ac5bb4a |  | note | FREQUENCY - Daily
label | c1f6ca5e-eadf-588a-9390-75e30564e67f |  | note | ACCEPTANCE CRITERIA - Low likelihood of rain
label | bdf30c6b-7975-577b-a843-be23171326dd |  | note | TYPE - W
label | 600a3fb5-ded9-59b9-8d94-5acf88ec8e21 |  | note | DESCRIPTION - Work shall not be started if rain is forecast for the immediate work day and the following day for the aftercare.
label | 31735fb0-dbf8-5e6c-a0f4-2b2fa8350c2f |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Downer PM
checkpoint-status |  |  | checkpoint | 8.4.1 - Spreading - Cement (1)
label | 9a097a9b-95ae-5670-96fb-c57e1c404523 |  | note | VERIFICATION ACTIVITY - Mat Test 1m² canvas
label | 7fb42536-1c23-5216-83e8-8a07f65356e9 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 0c6b61d8-65b4-5dd9-b0dd-cce8a0560402 |  | note | FREQUENCY - Every 400m²
label | 98bf6033-ede0-5c98-a5eb-a991e74c2115 |  | note | ACCEPTANCE CRITERIA - Within ±0.5km/m² of the specified rate
label | f2b4664b-e6d7-5662-a683-b9592c18d909 |  | note | TYPE - V
label | d01d99de-cfe9-5dfd-bc14-dbd1341b66e4 |  | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | 6e4047f7-f34a-50a2-b102-d52a8eacd0e7 |  | note | RESPONSIBLE PERSON - Highways Site Foreman
label | 6a27c494-a96c-5da0-9316-5226d1b4da18 |  | note | RECORDS / REMARKS - Not applicable if direct injection used
checkpoint-status |  |  | checkpoint | 8.4.1 - Spreading - Cement (2)
label | 55833fa9-540f-5a7e-a2c7-2f7a5771663f |  | note | VERIFICATION ACTIVITY - Average usage test
label | 96d8a3f8-d78f-5665-8332-8237e1bf6cc0 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 698929ad-eaef-5a14-898e-cf99539e30a0 |  | note | FREQUENCY - Upon emptying the spreader and bulk tanker
label | a422d147-f63f-597f-aa8a-bfe426e523e1 |  | note | ACCEPTANCE CRITERIA - Withn ±2.5% of the specified rate
label | cde64dc0-15af-5993-90df-ea295a826f7b |  | note | TYPE - V
label | 66141d2d-634f-5d3e-93d1-5abc3d462458 |  | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | 60b0b11e-2271-5c9e-95dc-469fd59ef18f |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.4.2 - Spreading - Bituminous Agents (1)
label | 1fa055e6-2123-5097-8975-94db85620a18 |  | note | VERIFICATION ACTIVITY - Flow meter display
label | 6cc12099-1126-5cd5-b44b-4ab0f4a88345 |  | note | METHODS OR REFERENCE - NZTA B/5
label | c583e475-446f-5c01-b2cd-200daa3fcb48 |  | note | FREQUENCY - Continuous
label | 0de30bdc-4ecf-500c-9853-0aa9cddc4700 |  | note | ACCEPTANCE CRITERIA - Withn ±5% of the specified rate
label | 76036f4e-1504-5e44-84bb-34aaae8adaa9 |  | note | TYPE - W
label | 814068c2-af6c-588a-a4c0-4eaa4da69e48 |  | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | a5985ae2-7c70-5fd4-a354-11b9beadcae4 |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.4.2 - Spreading - Bituminous Agents (2)
label | 3e569451-5870-5b58-adfd-48d1925ca2d7 |  | note | VERIFICATION ACTIVITY - Microprocessors reading
label | 8c92482a-8fc2-5e1d-aaa7-923fc1a3d4cd |  | note | METHODS OR REFERENCE - NZTA B/5
label | 2bb153e3-37c6-5e5d-ac57-bb49a613f041 |  | note | FREQUENCY - End of each run
label | 7d63a45e-b4bb-5ac3-a7c5-cbbc509843f8 |  | note | ACCEPTANCE CRITERIA - Withn ±3.0% of the specified rate
label | 76297428-8a36-5b69-9d58-9864df1e2a59 |  | note | TYPE - W
label | 1e55235b-db06-50f4-a12d-89a7f28c4a82 |  | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | bf2e420e-008b-5fb1-b8f9-6ec269c409c3 |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.4.2 - Spreading - Bituminous Agents (3)
label | 1b7a771f-c374-5d04-b825-02e7e3b82dfc |  | note | VERIFICATION ACTIVITY - Average usage test
label | 579d952f-ad2a-59d0-8a6b-8a25813e0951 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 67660bd7-ced8-5b98-9ca5-d30eb8866662 |  | note | FREQUENCY - Upon emptying the bulk tanker
label | bb3c1847-b5fc-54ff-97d4-d64eca77cff3 |  | note | ACCEPTANCE CRITERIA - Withn ±2.5% of the specified rate
label | 58ee2e34-307d-57df-8144-ae7692a679df |  | note | TYPE - W
label | 152d4172-e345-524e-b106-5e5aa29aecd2 |  | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | 7f04d3ed-bbe0-5bea-996c-4314095c0216 |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.5.1 - Time Limitations - Cement
label | 8959f1ee-eb4c-50d1-98a5-fbc219240591 |  | note | VERIFICATION ACTIVITY - The maximum time period from mixing to primary compaction
label | b50b00f2-d014-5932-8376-43b39c384bf4 |  | note | METHODS OR REFERENCE - NZTA B/5
label | ffd3509e-fde9-5d19-accd-7651edb31a5e |  | note | FREQUENCY - Post stabilisation
label | b746b1d2-46c9-5c8b-9067-c1ccdb87523c |  | note | ACCEPTANCE CRITERIA - 2 hours - Time start to time end to be recorded
label | 44622b89-2c5a-54c9-b69b-4446cecacea7 |  | note | TYPE - H
label | 64a18702-39b6-5f1a-82b6-1b5502bf62ad |  | note | DESCRIPTION - Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances
label | 66bcc360-02c2-5af2-9d0c-efd42d2d9b4b |  | note | RESPONSIBLE PERSON - Downer PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5.2 - Time Limitations - Foam Bitumen
label | a63e86ca-7728-54ca-8826-dcc4b11cf55a |  | note | VERIFICATION ACTIVITY - The maximum time period from mixing to primary compaction
label | fd1d9181-33a1-5caa-b745-c7d9b3c2c83e |  | note | METHODS OR REFERENCE - NZTA B/5
label | 5d871f21-90be-516f-a1a2-f81eda7126b7 |  | note | FREQUENCY - Post stabilisation
label | f39458bb-b037-5210-9c8a-7b40c6fcd741 |  | note | ACCEPTANCE CRITERIA - 4 hours - Time start to time end to be recorded
label | 874db5e5-755b-5556-9cfc-85465dc4cfbb |  | note | TYPE - H
label | ee7eca6e-0d18-5286-b529-fef215e14db2 |  | note | DESCRIPTION - Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances
label | f095124c-4a55-52d4-a52f-13e6b9f3621e |  | note | RESPONSIBLE PERSON - Downer PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5.3 - Time Limitations - Combination
label | ece20e43-a63b-55e0-973a-4e48d3fdbce1 |  | note | VERIFICATION ACTIVITY - The maximum time period from mixing to primary compaction
label | f1fe5d40-aff8-5b4c-8f73-7c08275bf51b |  | note | METHODS OR REFERENCE - NZTA B/5
label | 84e6b822-c8e2-5aa3-8586-b826ecea33b7 |  | note | FREQUENCY - Post stabilisation
label | c63b1134-9e9c-5886-9f25-9bc663da074d |  | note | ACCEPTANCE CRITERIA - The shorter of the individual agents
label | 86836d6e-04e6-593d-86bb-2984e426a18c |  | note | TYPE - H
label | c879bc9c-b245-509f-aa58-1fe6c6c3d894 |  | note | DESCRIPTION - Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances
label | be89d6d1-90c6-5ae3-81a8-d6490d391e2e |  | note | RESPONSIBLE PERSON - Downer PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.6.1 - Insitu Mixing - Cut Depth
label | 7b566834-7871-5e94-9f99-09dbc4b9ddb1 |  | note | VERIFICATION ACTIVITY - Depth measurement
label | b50a79da-13ff-5bbe-b919-c060cf504a3c |  | note | METHODS OR REFERENCE - NZTA B/5
label | 45e97fbd-d293-53c5-b1dd-5241756bf0ad |  | note | FREQUENCY - At start & end of cut and every 200m
label | 64333dc5-ae70-528d-bb98-1e06b5163bb7 |  | note | ACCEPTANCE CRITERIA - -5mm +15mm of design depth
label | 28aca747-6aac-5244-b160-cd1cab7675ed |  | note | TYPE - W
label | e208a646-a6a7-5554-ad60-3d5c370ec852 |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.6.2 - Insitu Mixing - Join Overlap
label | 9eff2d29-acc7-56a0-baba-f411d7aa83f9 |  | note | VERIFICATION ACTIVITY - Inspection
label | 2b67981f-1712-5606-bfff-6dd651bf934a |  | note | METHODS OR REFERENCE - NZTA B/5
label | b531632d-42e7-56c2-b2e7-6ecb5d852fc5 |  | note | FREQUENCY - Continuous
label | 221c271f-0778-5bfc-a6a4-67f7f81b0a42 |  | note | ACCEPTANCE CRITERIA - 100mm overlap
label | c6f764ef-a8cc-5652-996b-de59d8b8fef5 |  | note | TYPE - W
label | 1c4c324d-2894-5993-a7fb-be5e26e6557e |  | note | DESCRIPTION - All cuts shall overlap by the minimum acceptance criteria
label | 9087ddb6-f715-57e1-8367-cb057e64870a |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.6.3 - Insitu Mixing - Particle Breakdown
label | d8cba060-5ae2-5b3c-b95f-636429649e59 |  | note | VERIFICATION ACTIVITY - Inspection
label | b2d6bfdc-6633-5bf9-bed8-998b4e60b9b9 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 309a3afd-a695-5d30-a314-d1592eeda622 |  | note | FREQUENCY - Within the first 20m of each run, and where ever material changes
label | 04818f05-37bf-596d-a196-424deefaee56 |  | note | ACCEPTANCE CRITERIA - Well mixed material with acceptable particle size distribution
label | 1972ed43-3001-5a73-9b74-03551834f6c1 |  | note | TYPE - W
label | 0e5af050-89b8-5775-9a19-363d859588ac |  | note | DESCRIPTION - Where breakdown is excessive, method of milling should be altered to avoid such breakdown
label | ba92cccb-9a08-5f0a-ba1f-6f7b59aa0f2a |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-status |  |  | checkpoint | 8.6.4 - Insitu Mixing - FBS Quality
label | f7c9db62-caab-5c23-9d75-0b58a85b5234 |  | note | VERIFICATION ACTIVITY - Inspection
label | 19800cbd-8424-5f27-b372-b6b6c3d494ca |  | note | METHODS OR REFERENCE - Visual Inspection
label | 5c40bd2d-179f-53f3-938d-8c70bb9d9d58 |  | note | FREQUENCY - Continuous while stabilisation is progressing
label | 89dc3a6a-0ae1-51f6-b056-b798588abc27 |  | note | ACCEPTANCE CRITERIA - No bitumen stringers or blobs observed (See Assessment of hoe'd materials)
label | 3f2f5122-be9a-54c8-8a50-eac72a9356e7 |  | note | TYPE - W
label | b4927380-adbd-58d4-857b-29564dea0caf |  | note | DESCRIPTION - If bitumen blobs or stringers are found the the construction of FBS stops and the equipement is fixed so that there are no bitumen blobs or stringers found
label | 8fe088af-755c-561d-9e2c-825e3991890d |  | note | RESPONSIBLE PERSON - Highways Site Foreman
checkpoint-group |  |  | section | 9 - Construction Quality Assurance (QA)
checkpoint-status |  |  | checkpoint | 9.1 - Field Compaction Target
label | e1a95147-77d3-5de4-803b-a8a7536a06dd |  | note | VERIFICATION ACTIVITY - NDM - Plateau
label | 914d46e6-c0d7-55d6-9345-85367e368983 |  | note | METHODS OR REFERENCE - NZTA B/5
label | 9d1de383-dbf1-59a4-a274-c241ff229f48 |  | note | FREQUENCY - 1 Every 3000m2 or once daily
label | c5e94df8-dbde-5515-979e-c25c7a99d57a |  | note | ACCEPTANCE CRITERIA - Plateau testing done each shift / as required depending on the material variability throughout the site to determine compaction pattern.
label | 406cea76-c55f-5c08-8bbc-1aaf6f7816b9 |  | note | TYPE - V
label | 8c02d07f-c5a5-5532-8e73-c327090ea50e |  | note | DESCRIPTION - Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target
label | 805133a4-480f-5c7f-80a3-a7a5985058ad |  | note | RESPONSIBLE PERSON - Highways Site Foreman
label | 41487d90-f624-536f-a93c-7d7fdf56c32b |  | note | RECORDS / REMARKS - Verified test results of plateau to be supplied
checkpoint-status |  |  | checkpoint | 9.2 - Lab testing
label | 81359028-5861-5fb0-86c1-f3dfac064a8c |  | note | VERIFICATION ACTIVITY - ITS/ UCS test
label | c0b27ee0-62d2-5eed-8766-d2735180ad5b |  | note | METHODS OR REFERENCE - NZTA B/5
label | 3886ea7a-49c0-5b4a-93db-ff393ea7f33f |  | note | FREQUENCY - 1 Every 3000m2 or once daily
label | 025d0155-d41e-51ba-ba93-a86e1f633944 |  | note | ACCEPTANCE CRITERIA - Testing to be completed each shift / as required depending on the material variability throughout the site to verify compaction.
label | 78a8c73e-1b49-5811-8c01-58ac1b5410b0 |  | note | TYPE - V
label | 427077a6-1a5e-558c-9f81-613bf6be85fa |  | note | DESCRIPTION - Tests to be cured & achieve as per specification.
label | e1668a12-a22d-5f35-b400-f04349741248 |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Renewals PM
checkpoint-status |  |  | checkpoint | 9.3 - Compaction Testing
label | 6d9fbaa3-5f5a-5ff1-9b73-ab337ce602db |  | note | VERIFICATION ACTIVITY - NDM
label | e4a1eb58-20fe-5311-ad5d-c9c8fcfe46df |  | note | METHODS OR REFERENCE - NZTA T23: 2021 Direct Transmission
label | 2aa7db37-600b-579b-a9c1-c9de68d6f0a5 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 128f56cb-59ea-580d-957c-1ed7906d8c6c |  | note | ACCEPTANCE CRITERIA - Average ≥ 98% Plateau, Minimum ≥ 95% Plateau
label | 757a99d6-e747-57e0-9a41-73b689423755 |  | note | TYPE - V, H
label | 3268b823-8043-5aaf-ab41-510d87396d3b |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD
label | f81c268b-e1a2-5305-8198-9b8c6c5c3308 |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Renewals Engineer
label | 8544e486-8080-5ecb-8218-57c5fa76754b |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.4 - Surface Set Up / Clegg Hammer
label | 093504e2-d965-569a-a10b-4edb327d3674 |  | note | VERIFICATION ACTIVITY - Clegg Hammer
label | 0085916c-bca1-574c-bd59-07a5d61b70c1 |  | note | METHODS OR REFERENCE - Certified Clegg hammer (Current Certification sticker) & calibrated prior to use
label | d2268177-ed8a-54a4-a8bd-ed05d3ceeb66 |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 3557cfb0-3dfc-5f63-8b92-e622a10b496e |  | note | ACCEPTANCE CRITERIA - CIV ≥ 40
label | 28d945cb-6a2d-5211-ae29-a64c23ded153 |  | note | TYPE - V, H
label | 412074c8-e8d6-5047-938b-981174e2fbfa |  | note | DESCRIPTION - Hold point - membrane / chipseal placed once CIV ≥ 40
label | 14fa4ab3-353e-5a48-8911-8aec496e17fb |  | note | RESPONSIBLE PERSON - Construction Supervisor/ Renewals Engineer
label | deeb11d0-0c5f-508f-b1f5-c9309157589c |  | note | RECORDS / REMARKS - All test results to be submitted to NZTA for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.5 - Degree of Saturation (DOS)
label | 451384ce-063d-5278-a298-4955bfdec6cf |  | note | VERIFICATION ACTIVITY - DOS
label | f93bbdf0-a35d-5bc3-8142-0bae34200f5c |  | note | METHODS OR REFERENCE - NZS 4407 Test 4.2.2, NZTA B/5 Cl. 7.12
label | 86b0b091-306d-5578-a0c9-9088e0f05b3f |  | note | FREQUENCY - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 60d49ffe-79ca-5b5a-bdbb-e84e867430a4 |  | note | ACCEPTANCE CRITERIA - For information only
label | c0e557d7-1353-5aa0-a9f2-9f7e3bd42c4f |  | note | TYPE - V
label | fe1bf4fc-d6e0-54c4-aff0-d120a5e60bd9 |  | note | DESCRIPTION - Soild density to be measured.
label | 80126c59-a5ad-5d44-88a0-c2d466add56c |  | note | RESPONSIBLE PERSON - Downer Lab technician
checkpoint-status |  |  | checkpoint | 9.6 - NDM moisture correction
label | ac988ecc-63ad-5d4f-9f85-9202db7532ba |  | note | VERIFICATION ACTIVITY - NDM & Lab MC
label | 50ba8afa-73bf-5728-a1f1-c8c3ff7a6b0a |  | note | FREQUENCY - 3x Moisture contents per single plateau test carried out
label | 2cff7e7a-6b29-5e5f-8512-3bfebe2a944d |  | note | ACCEPTANCE CRITERIA - Information only
label | 6cb1435c-8494-59b5-8656-e63935edd644 |  | note | TYPE - V
label | 780d88f6-963d-5a42-ab05-49634a80c5f0 |  | note | DESCRIPTION - Correction offset to be applied per site
label | cdd4983f-ca1c-5bab-a2e5-274fc2d1f07f |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Renewals Engineer - Relates to field plateau testing by the laboratory
checkpoint-status |  |  | checkpoint | 9.7 - Surface Shape / Profile Layer Thickness
label | 0cb0b3ad-9960-544d-b914-7fa1a0101385 |  | note | VERIFICATION ACTIVITY - NZTA B/5
label | acd8f04e-cabd-5da7-be49-eba4eb7b7c24 |  | note | METHODS OR REFERENCE -
label | a346ecd8-9168-51f8-83a1-aa90fe0eaa50 |  | note | ○ Visual inspection
label | 07f7f915-114a-5b00-b31c-3e39ab584f7f |  | note | ○ Cut/fill tolerance check
label | 68fc98c5-b81d-57b4-99d4-7908c107fc7e |  | note | ○ String records
label | 7706a03a-6020-5dfa-932b-9895767cc861 |  | note | ○ Straight edge
label | 436e3b8f-45b7-5efd-827b-75bc1b165b8b |  | note | FREQUENCY - 1 test per 20m
label | 665ab25e-1325-5608-a9ae-3c971c893549 |  | note | ACCEPTANCE CRITERIA -
label | b1c67783-ad60-5104-a759-c055edc5eaf2 |  | note | ○ ≤10mm variance from 3m straight edge
label | 71903455-df87-5e66-b41e-cc6059280ba0 |  | note | ○ Gradual deviations
label | 37e7243b-6115-5456-a88a-dbfbc14a4040 |  | note | ○ Crossfall > 1%
label | 6bc62540-44e2-5748-81a5-ea3b318ab61d |  | note | ○ Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | 833fa24d-6efd-5c20-b080-a2b4f0ffeec0 |  | note | ○ -5mm +15mm or ±5mm at lip of concrete channel where applicable
label | 1372e332-b319-57ce-b824-7c30200248d9 |  | note | TYPE - V, H
label | 2e292471-8813-5b79-9f8e-b5f99983266f |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved. Hiways Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area
label | f823548a-2865-5b0b-b302-ac2d92003541 |  | note | RESPONSIBLE PERSON - Highways Site Foreman/ Renewals PM/ Downer surveyor
label | 8e9caa55-0d0d-5e34-a291-967f943076ba |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.8.1 - Tolerances - Width Unconstrained
label | 938070bf-2e8b-58cc-95a9-81186b805925 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | dc6fbfff-9701-5cd5-b684-f147d51dae39 |  | note | METHODS OR REFERENCE - Confirm offset from lift pegs
label | 4dcc3e64-08c0-5306-925c-f1cced33c0ba |  | note | FREQUENCY - 2 at every lift peg or per 180 m2
label | 3f99db0a-961c-52a3-9b1c-08968f44dda3 |  | note | ACCEPTANCE CRITERIA - - 20mm, + 100mm
label | fb6d4398-06c2-5594-8391-71dc3e1e6325 |  | note | TYPE - V, H
label | 09ddf547-9d96-5398-93ca-1fc3b4a8963d |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | b786ecdc-397d-5510-877a-864d5865c39f |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Renewals PM
label | eb540334-39e7-5e4e-9f39-26dd7bffccba |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.8.2 - Tolerances - Width Constrained
label | b6b1c87d-c197-51fc-ba21-a53f6da670b1 |  | note | VERIFICATION ACTIVITY - TNZ B/2
label | 6b355806-4d05-548d-a6d8-aca1ea526f6c |  | note | METHODS OR REFERENCE - Stringline/lift pegs
label | 47ec3afa-7741-5860-95d9-721347608c7c |  | note | FREQUENCY - 3 at every lift peg or per 180 m2
label | ec9b28ff-e73b-5edd-ba9a-785f2ba5e612 |  | note | ACCEPTANCE CRITERIA - Zero
label | 49619bb9-852b-50f4-921d-c091b0c84ad8 |  | note | TYPE - V, H
label | d69fa55d-49c3-5406-a4fc-d3d3dabf8016 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | 8add6e22-e708-52ab-a8ef-38a866964674 |  | note | RESPONSIBLE PERSON - Highways Site Foreman / Renewals PM
label | ac5915ae-18e6-59dd-acdb-8c879db91fe9 |  | note | RECORDS / REMARKS - 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.9 - Ride Quality
label | 195d472a-edfd-5ca3-860c-f534bd9df91a |  | note | VERIFICATION ACTIVITY - Owner acceptance test
label | 5790f4da-0f1a-5a3c-843e-9da18be12e5e |  | note | METHODS OR REFERENCE - As per Contract Documents OPM42
label | f3e3b626-af08-5985-be6b-efbad7135ede |  | note | FREQUENCY - 1 ride test for each lane following Basecourse completion prior to surfacing
label | de0b0285-701c-5e9a-937f-bd7756d77711 |  | note | ACCEPTANCE CRITERIA - Rolling 100m average NAASRA <75 counts/km
label | 9cc98284-cf46-524b-8836-a950c8530e66 |  | note | TYPE - W, H
label | 611e0baa-ea6a-5d38-98ee-54fb605b26ab |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions
label | 757f5a59-0f4d-5f24-bff5-81fef2954d2f |  | note | RESPONSIBLE PERSON - Road Science/ Downer PM
label | 2c59811c-1a4e-5ade-9089-9d3b45a86b1f |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.10 - Mosaic Surface
label | 43441fd7-b307-5bad-8d53-5f3906449c89 |  | note | VERIFICATION ACTIVITY - Visual inspection
label | 321ad0a7-52ec-56ed-8b1d-9035c45a7392 |  | note | METHODS OR REFERENCE - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | 1007128c-2c46-54fd-a8b9-6ea3d8de62f5 |  | note | FREQUENCY - Overview of site for tight mosaic surface
label | 0a29ceaf-cbf7-5065-b47f-5493ede73769 |  | note | ACCEPTANCE CRITERIA -
label | 6cc80832-604b-56a4-bcff-eec98aa2d953 |  | note | ○ The large aggregate is held in place by a matrix of smaller aggregates
label | 889178d4-37eb-5add-8af5-b385e1b83393 |  | note | ○ The smaller aggregate is held firmly in place by fine material
label | 15a35656-ca8a-594a-adea-8c988ce14de8 |  | note | ○ The matrix does not displace under normal trafficking or sweeping
label | 3a6ab31b-b406-5e1f-93b2-3af0e4c775ff |  | note | TYPE - W, H
label | f1bfe250-9025-516f-b8ae-e7861dc71cdb |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | f7e83d35-8e70-5d61-812d-d843079ed119 |  | note | RESPONSIBLE PERSON - NZTA Network Manager / Renewals Manager/ Highways Site Foreman / Downer PM / Downer Sealing Foreman
label | 9b944650-0c62-5295-8310-71dceb1f2a21 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.11 - Preseal Check
label | 77e4245b-297e-5243-b1e9-4fe13097bdf3 |  | note | VERIFICATION ACTIVITY - Visual check
label | e5bcc359-9ce7-53a0-8fbc-6f1f8d82489c |  | note | METHODS OR REFERENCE - NZTA B/5
label | 9b33e78e-0eb9-5046-9ef5-ca652c1d378d |  | note | FREQUENCY - Before sealing
label | c26d0de4-45d0-54df-ab44-28b616124c20 |  | note | ACCEPTANCE CRITERIA - All prior ITP checks have been completed and signed off, No caking layers present
label | e9740aaa-9e2b-53fc-8aef-a3a286f7feb6 |  | note | TYPE - V, H
label | 39218790-716a-5151-8615-34c580019e80 |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
label | 3269ec84-cf41-5c0d-89ae-49a9d35a17ba |  | note | RESPONSIBLE PERSON - NZTA Network Manager / Renewals Manager/ Highways Site Foreman / Downer PM / Downer Sealing Foreman
label | 247f2584-898c-55e5-a14c-2977d3ed2703 |  | note | RECORDS / REMARKS - NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.12 - Pavement Surface As-Built
label | b47dcc4f-bcd4-53bb-9ba5-cb0f99289309 |  | note | VERIFICATION ACTIVITY - Survey
label | 6496c81b-ad67-57e6-8f8e-f6b8b2ac1e08 |  | note | METHODS OR REFERENCE - As per approved drawings
label | 04e305f6-4c1c-5e5e-956e-35a9473a5ed4 |  | note | FREQUENCY - Per installation / Site
label | 511c5e08-43f6-53b0-bb7a-6ee6856febc7 |  | note | ACCEPTANCE CRITERIA - Accurate survey of all topograpgical features required
label | a4e76c75-a400-5e91-af29-cfd0ab8b4eb4 |  | note | TYPE - V
label | 79f1540b-77c5-53cc-a93a-3331e3df3653 |  | note | RESPONSIBLE PERSON - Downer Approved Surveyor
checkpoint-group |  |  | section | 10 - Sealing
checkpoint-status |  |  | checkpoint | 10.1 - Sealing
label | a5bb057b-8af5-53ff-90bc-5f43b560d69c |  | note | VERIFICATION ACTIVITY - See Sealing ITP
label | ec008903-70b1-5f9a-878a-09dc21660717 |  | note | TYPE - W
label | 6e5590a1-bfeb-52c5-be2c-39b9d70fa1d3 |  | note | DESCRIPTION - Hold Point – All hold points and checks in ITP to be completed before physical works continue
label | 93d2bfad-e19d-5ef0-84d0-5fe89435e297 |  | note | RESPONSIBLE PERSON - Downer Sealing Contract Manager
checkpoint-status |  |  | checkpoint | 10.2 - Sealing TMP and Aftercare Process
label | db7ed9d4-f400-5cd3-951e-f4efc90f7504 |  | note | VERIFICATION ACTIVITY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | c1cf2396-8bee-5223-982a-d307597b1f25 |  | note | METHODS OR REFERENCE - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | a0283ad8-4201-5e4d-b902-b0685e46cd4e |  | note | FREQUENCY - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 6d00a1a8-f005-5ef6-8750-441b76f4a2f7 |  | note | ACCEPTANCE CRITERIA - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 7a1685c3-cd54-5c0d-ba4b-e29fa17ab5ff |  | note | TYPE - W, H
label | f21422c2-63a3-51d5-b6b4-7177520afb10 |  | note | DESCRIPTION - Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
label | f1cf7187-f888-59db-a8a4-706673e3c058 |  | note | RESPONSIBLE PERSON - Downer Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Sweeping of Sealing Works and Handover to Roadmarkers
label | fe6bf99d-00cf-53be-97f8-24b6eccbe8d0 |  | note | VERIFICATION ACTIVITY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | a8133d7a-c4f2-5e9f-8933-2df55959eff3 |  | note | METHODS OR REFERENCE - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 67a34043-7905-54fa-ae6c-b36ff4ab207d |  | note | FREQUENCY - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | f48f3946-b71d-5909-b68a-c3c6933e7dd2 |  | note | ACCEPTANCE CRITERIA - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | e0ea2148-b29d-54c3-97fc-e32e2c1625d5 |  | note | TYPE - W, H
label | 28513dc4-d06e-5644-bff3-b96fa58ad52d |  | note | DESCRIPTION - Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.
label | 2e25eac6-c3e8-5b29-bf39-e25a3f4db21d |  | note | RESPONSIBLE PERSON - Downer Sealing Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 11 - Shoulders
checkpoint-status |  |  | checkpoint | 11.1 - Slope
label | 43edf718-3128-5f64-877f-8ac32c4170b8 |  | note | VERIFICATION ACTIVITY - Visual check
label | 95856f2e-8415-50a9-bdac-118835781bb7 |  | note | METHODS OR REFERENCE - Visual inspection with smart level
label | 1c7bdffb-7def-5eaf-ba5a-1b11c13dd68a |  | note | ACCEPTANCE CRITERIA - Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation
label | 6fa75ba4-298f-58ea-b2b6-87036dc2aec2 |  | note | TYPE - V, H
label | 32ae3a3b-826d-52d3-babb-bedd722b94fe |  | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | 4874b3a3-7d11-516e-9d85-1bbb9a0baae0 |  | note | RESPONSIBLE PERSON - Construction Supervisor/NZTA
label | e8787fef-4128-5e95-b4a5-42c5e8c0485f |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2 - Compaction
label | 74508982-b00b-54e9-b8e5-f0ac3583d901 |  | note | VERIFICATION ACTIVITY - Visual check
label | 4fa20a4a-5e91-564b-b7ed-13d756757581 |  | note | METHODS OR REFERENCE - Drive over 4 tonne, check wheeltracks
label | b758198d-3ff0-59d2-a786-02f8208aba7c |  | note | FREQUENCY - All shoulders
label | 3bc9f6ac-d89d-5e2d-8433-e53401f55551 |  | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | 116c2c31-a0f4-5708-a080-b4ffc3c1151c |  | note | TYPE - V, H
label | 85899901-1928-548b-9255-f27fdf8bfbaa |  | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | a5df81c6-3b0a-5a0d-8504-83cbb9d69056 |  | note | RESPONSIBLE PERSON - Construction Supervisor/NZTA
label | ae2d076f-2b58-5fd3-a2dc-c6508e651739 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.3 - Soiling
label | 9617c5a9-3d4c-5e4c-abc9-086e0c1b67ab |  | note | VERIFICATION ACTIVITY - Visual check
label | 5bdb93ac-9fd5-5435-b5e0-615dc55bedc8 |  | note | METHODS OR REFERENCE - Approved Design Drawings
label | 5a2bf8ec-32b3-5e4c-a1ca-3f89460c59cd |  | note | FREQUENCY - All areas requiring grassing
label | 590ef3e8-cda6-541a-bc73-8ba25359c3e8 |  | note | ACCEPTANCE CRITERIA - Soiling has been done where required
label | 25b9df36-934a-5988-ae89-14ac95734d72 |  | note | TYPE - W
label | 35002cc8-79b7-58cb-ad31-cea3fec5d35a |  | note | DESCRIPTION - As per the design drawings
label | ea72c04e-ef21-5519-b794-2fc3dff0d9cb |  | note | RESPONSIBLE PERSON - Construction Supervisor
checkpoint-group |  |  | section | 12 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 12.1 - Traffic Services - Marker Pegs/ Signs/Markings/RRPMs Replaced
label | a90b8532-f5fc-577b-9196-4f12455a9de5 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 3dea580f-eb45-5fc4-a708-c9979e508f85 |  | note | METHODS OR REFERENCE - Visual Inspection
label | fcc9dc06-d55c-5e91-a6ab-f92284b61aab |  | note | FREQUENCY - All signs/markers
label | 15dc241b-43e0-541a-b4d7-5e42315dcf9c |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 109b8aab-230b-53de-8160-b01cea826389 |  | note | TYPE - V, H
label | 97ae8a01-2b7a-553e-979b-7346acfd78b8 |  | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | 0564498b-ed97-5d84-a6a2-2b8f8ae4216c |  | note | RESPONSIBLE PERSON - Construction Supervisor/ NZTA
label | 6442101e-77a9-5880-90e0-bde3e2fd014f |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.2 - Grassing
label | f5743dc4-7c7f-5adc-badc-6fe61cad70a6 |  | note | VERIFICATION ACTIVITY - Visual check
label | bd054c14-424b-52d1-88b3-2aef94efc1ed |  | note | FREQUENCY - All areas requiring grassing
label | 542da39c-c5c1-53a8-b5d6-00f2385355fa |  | note | ACCEPTANCE CRITERIA - Grassing has been done where required
label | ccb67730-21f1-5cb8-9134-2e16e04b90dc |  | note | TYPE - W
label | c71fea0d-85a2-5d71-8b99-3021ee1532af |  | note | RESPONSIBLE PERSON - Construction Supervisor
checkpoint-status |  |  | checkpoint | 12.3 - Drains Cleared
label | f50f4c85-5774-52f6-bdb6-117b5a62bf23 |  | note | VERIFICATION ACTIVITY - Visual check
label | aa57775b-09c2-55dc-a6e8-c6e835849300 |  | note | FREQUENCY - All drains, after all other works
label | 4aa60522-a9c0-59a6-880e-65d42d2cf96c |  | note | ACCEPTANCE CRITERIA - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | 0ab162df-e89b-57a4-9ee0-0b10b7043f77 |  | note | TYPE - W
label | 37bd4af6-d67f-5afe-a7d0-358f8d096e3e |  | note | RESPONSIBLE PERSON - Construction Supervisor
checkpoint-status |  |  | checkpoint | 12.4 - Traffic Management Removed
label | 1493e158-a4a4-5c1f-a5cb-a951f9df03f6 |  | note | VERIFICATION ACTIVITY - Visual check
label | b54d82f5-8cd0-57c3-a36d-58b05c919f7a |  | note | FREQUENCY - When safe, after all physical works completed
label | 0b2204aa-ff80-524a-8d0a-d6063e26844d |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 22753623-d0b0-522c-8742-e193e1e69d1e |  | note | TYPE - W
label | f6be1050-abc7-5d25-ad1f-9b50630b03fd |  | note | DESCRIPTION - Hold Point – TMP cannot be removed until site Audited by Downer Construction Supervisor
label | 87e9a021-a055-510d-ad6f-aa4b4416c372 |  | note | RESPONSIBLE PERSON - Construction Supervisor
checkpoint-status |  |  | checkpoint | 12.5 - Site Left Clean and Tidy
label | 0dac55f6-aa5d-5268-8a9b-8f182dfbf714 |  | note | VERIFICATION ACTIVITY - Visual check
label | 01b8220e-185e-5af4-bafe-5872b836c586 |  | note | FREQUENCY - After vacating site
label | f64b83b8-b41b-51e1-b76c-a5e1745e07e8 |  | note | ACCEPTANCE CRITERIA -
label | 0e39d0c2-afeb-5510-90f8-b8c272094ee7 |  | note | ○ Stockpiles removed
label | 45b1ad73-7c14-5f99-bee0-532a12d89ec5 |  | note | ○ Plant removed
label | c2c35350-924e-56a5-874e-029c75b94d50 |  | note | ○ Litter cleared from site
label | 7f7f0dff-adb6-54f7-ba01-fb29703e4e16 |  | note | TYPE - V
label | 6cd58c8d-8d3c-5a0a-8db3-6de1f5b63917 |  | note | RESPONSIBLE PERSON - Construction Supervisor/ NZTA
label | 15c88d17-652c-597f-acd9-026e85a79747 |  | note | RECORDS / REMARKS - Invite NZTA to carry out joint site inspection to inspect site.
checkpoint-group |  |  | section | 13 - As-built Records
checkpoint-status |  |  | checkpoint | 13.1 - Collect Asset Data
label | 1e39cd81-9ad9-5136-899d-0b8124155e27 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | b58a7c04-7028-50f7-b8a5-34f7ec28b576 |  | note | FREQUENCY - During construction
label | 0ef8d185-07b1-5741-bbfe-62c28050052a |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected
label | b02ba4bd-a6b1-58fd-b539-29ac9c2ee3b9 |  | note | TYPE - V
label | 1e1911da-33b4-53a5-aa9e-f6b5dc181e71 |  | note | RESPONSIBLE PERSON - Renewals Engineer
checkpoint-status |  |  | checkpoint | 13.2 - Enter Asset Data into RAMM and/or Register(s)
label | 29434d9c-7a5c-5591-a052-01a6b2a0cfac |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 68d3dbcc-b14c-5615-8229-43deb6385ce9 |  | note | METHODS OR REFERENCE - RAMM
label | 95a9ec5b-81d9-59ea-9ae2-bc50f90fda71 |  | note | FREQUENCY - At completion of work
label | 54590bb2-067a-50c6-9a4d-0330386f833a |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file.
label | e4fe798d-5812-5123-99ed-cffe0474544a |  | note | TYPE - H
label | 844fb061-292b-5b46-bf82-4a3e9f94629d |  | note | DESCRIPTION - Hold Point – project cannot be closed until data entered.
label | 8adb87cb-49c8-5f45-ade2-3d4903331965 |  | note | RESPONSIBLE PERSON - Renewals Engineer/ WSP Information Manager
label | e97d5f2e-d4cc-5f80-bb20-9209305c148c |  | note | RECORDS / REMARKS - Submit all RAMM Data to Data Quality Manager for review and verification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.3 - Construction Completion Report
label | f7ae1d1a-4d18-5cfd-9bc1-8ce70c49a89a |  | note | VERIFICATION ACTIVITY - Confirmation
label | aab4b7ab-4d1c-5c0d-94be-a0be0cd12351 |  | note | METHODS OR REFERENCE - Contract Specification
label | 3581fd14-93fd-5605-b72e-1a9deb199a15 |  | note | FREQUENCY - At completion of work
label | f805f6d5-85c2-5b50-800a-e53d63307542 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 25a19735-6c8e-508e-901f-968b5b20ec96 |  | note | TYPE - V
label | 7de3bfcd-7926-5657-8725-c47b1d403b24 |  | note | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
label | 0432267e-8a36-5ca4-a14a-c548836f722b |  | note | RECORDS / REMARKS - Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans