## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | DI-PM-TP022 Rev 3 | itp |  |  |  | Yes | DI-PM-TP022 Rev 3 | da28de13-0101-4658-be8c-a3a7e83bb60e
checkpoint-status |  |  | checkpoint | Rip & Remake and Stabilising Repairs Downer Activity #39
label | ab9a7335-3cf9-5f2a-b180-aa9b5290cc4e |  | note | VERIFICATION ACTIVITY - Visual - Levelling pavements
label | eb654c99-665b-5d89-a5ee-7dc816626647 |  | note | METHODS OR REFERENCE - As per work procedure: HDC WMS STABILISED REPAIR
label | 6425cf10-caf0-57c4-8121-6a5e41e0bd30 |  | note | FREQ. - As Programmed
label | df073837-2ea7-544b-ae3f-a1515ffd7fb5 |  | note | ACCEPTANCE CRITERIA - C2 MINOR SURFACE LEVELLING
label | 7d8dd860-e1d6-5d9c-b093-a21741bc0fcb |  | note | INSPECTORATE* V/W/H: DNZ - V
label | eb5d9ba7-e49f-5cb3-aba4-ccd3a72b67b9 |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | d55fe772-f284-5fd2-bfe9-ec70efecfcf6 |  | note | RECORDS / REMARKS incl NCR ref - Record on: HDC Pavement Repairs QA Spreadsheet and hand in to supervisor
checkpoint-status |  |  | checkpoint | AC Levelling Downer Activity #52
label | 53c44a9a-de21-5706-825d-aebab9e487c8 |  | note | VERIFICATION ACTIVITY - Surface Levelling
label | f4722e64-a2df-5046-ae6a-7ed0cc3c4abe |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP039 Repair Surface Depression – Hand Premix
label | 43fb55e0-9340-5495-9850-68991ce92a3b |  | note | FREQ. - As Programmed
label | 6e8cde2b-722b-538d-90f8-dc00a4d449bf |  | note | ACCEPTANCE CRITERIA - C2 MINOR SURFACE LEVELLING
label | cebb9840-ea64-520f-a313-d3a831ee0b53 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 8621a48a-fd35-5d90-8ace-5629ac2d3c1c |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | de709c11-67b0-53a4-865b-e8744203078f |  | note | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP236 Surface Depression and hand in to supervisor
checkpoint-status |  |  | checkpoint | Edge breaks Downer Activity #108
label | e327dd03-662f-573e-a0c9-ff70bbfd60f9 |  | note | VERIFICATION ACTIVITY - Size of repair
label | 071663f4-1d60-59a3-aed5-4c51d43865d4 |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP036 Edgebreak Repair - Formed Shoulder (Manual Premix Method)
label | e6be27d7-fdf2-56cd-a552-54d3824073e9 |  | note | FREQ. - As Programmed
label | 7b421d11-ae04-5869-9cdf-b1519253ee83 |  | note | ACCEPTANCE CRITERIA - C4 EDGE BREAK REPAIRS
label | e1bbc386-2b9e-56f4-8608-665c4f60ca31 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | dbee1f7b-72e3-51bd-b545-f404acaa19aa |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 9bd971c0-da62-5c85-a785-3dd3e54f23b5 |  | note | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP207 Edgebreak Repair and hand in to supervisor
checkpoint-status |  |  | checkpoint | Dig outs Downer Activity #036
label | a7a769f0-a988-5eb2-bac5-de5be0b67670 |  | note | VERIFICATION ACTIVITY - Identify and method
label | 7cc9ea4d-304c-5276-888c-13bd3e9a49e6 |  | note | METHODS OR REFERENCE - As per work procedure: HDC WMS DIGOUT REPAIR
label | a69d7822-aafb-5614-ab0b-6aea28cfd941 |  | note | FREQ. - As Programmed
label | b669c22a-5e0b-50cc-a5fd-c0e9b5d47ba6 |  | note | ACCEPTANCE CRITERIA - C5 DIG-OUT REPAIRS IN SEALED PAVEMENTS
label | 7b305616-c731-5edd-a253-e1bf5563d8d0 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 2d047dd3-4409-5a68-b880-c2009de7d762 |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 1538cc46-0bed-5453-a6ce-ef52d0f97510 |  | note | RECORDS / REMARKS incl NCR ref - Record on: HDC Pavement Repairs QA Spreadsheet and hand in to supervisor
checkpoint-status |  |  | checkpoint | Shoulder Repairs: Low Shoulder / Shoulder Strengthening Downer Activity #110
label | dc24fc9f-8143-58eb-bef6-4f1eff35c124 |  | note | VERIFICATION ACTIVITY - Size of repair
label | d802872c-2949-5d77-b2df-bc7e3888e70c |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP038 Repair Low Shoulder-Material Replacement
label | 1f1656fb-4243-598c-b1f7-1eed25a96a1b |  | note | FREQ. - As Programmed
label | 4d33a7e4-560e-59e9-8b27-e4bbd80207b0 |  | note | ACCEPTANCE CRITERIA - C6 RECONSTRUCTION & MAINTENANCE OF UNSEALED SHOULDERS
label | 2e27b414-c182-5817-a6d0-5778e5248178 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 1b9b0b70-95d5-5e48-abac-88f8f3d49c18 |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 42a98ca1-e420-5211-bb62-c4dca1cb5aee |  | note | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP235 Shoulder Repair and hand in to supervisor
checkpoint-status |  |  | checkpoint | Culverts / Drop chambers / Flumes Downer Activity #134
label | d6220d01-44ce-5877-8e6b-90b7739c5dd6 |  | note | VERIFICATION ACTIVITY - Repair and replacement
label | 5b06a544-5323-541c-80f2-335cdf4c1d1c |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP082 Install a Concrete Culvert Less Than 900mm in Diameter
label | 7b86c153-6556-5e26-8109-3260353a32f7 |  | note | FREQ. - As programmed or reactive
label | 5047a86a-b1ef-55ea-92bc-75ba62301b22 |  | note | ACCEPTANCE CRITERIA - E3 CULVERT INSTALLATION
label | aaba99b9-82d3-5d4f-a38f-71e1ee2eacf7 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | b447a577-00b9-5f4a-b623-ccff90be3e52 |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 475046fa-1529-5cdd-988a-28f4489b0419 |  | note | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP205 Culvert Cleaning.docx and hand in to supervisor
checkpoint-status |  |  | checkpoint | Headwall Repairs Downer Activity #134
label | 258afa67-e735-5b7b-911c-48049bdf6bf1 |  | note | VERIFICATION ACTIVITY - Repair and replacement
label | 6536cfe0-6b45-5cb8-8e2a-3aa86d934fae |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP083 Install a Culvert Headwall Constructed of Dry Concrete Sand Bags
label | 6b5fd26f-9f8b-5edc-9d1f-e8885677182e |  | note | FREQ. - As programmed or reactive
label | 91182dfe-53e3-5a32-80c7-b3a971630911 |  | note | ACCEPTANCE CRITERIA - E3 CULVERT INSTALLATION
label | 01654791-78d3-512b-a659-54b4f654db33 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 86a2383d-2bbe-5e30-aa78-5703a97e8255 |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | ad3c972d-0523-5e59-9d4a-f5ff28357a9e |  | note | RECORDS / REMARKS incl NCR ref - Record on: DN-GP-GP202 Construct a Sandbag Headwall and hand in to supervisor
checkpoint-status |  |  | checkpoint | Drain Cleaning / Drain Re-Profiling Downer Activity #140
label | b63e8419-3a78-5446-a7da-262792163dc1 |  | note | VERIFICATION ACTIVITY - Visual check for effectiveness of drainage
label | 358d9d8f-b89a-53e2-a6f5-f7b1897037d8 |  | note | METHODS OR REFERENCE - As per work procedure: HDC WMS WATER CHANNEL RECONSTRUCTION
label | 41525b6b-4a0f-5664-9a58-a5b50b1db5e8 |  | note | FREQ. - As programmed or reactive
label | b1d0fd7b-6c71-55f7-b6a8-0002552e01e9 |  | note | ACCEPTANCE CRITERIA - E2 MAINTAIN ROADSDE SHOULDER PROFILES / RECONSTRUCTION & DRAIN INVERT CLEANING
label | 447b3e0e-9880-5bac-ab81-c1a4c21958e4 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 62b1f4ce-91ac-55cf-897e-e3e06a67072f |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 543d46ca-347d-5e8f-ba34-2d64779ae0af |  | note | RECORDS / REMARKS incl NCR ref - Record on: HDC WMS WATER CHANNEL RECONSTRUCTION work procedure and hand in to supervisor
checkpoint-status |  |  | checkpoint | High Shoulder Downer Activity #109
label | 71df3593-bf46-5e97-b1b9-118ea75657db |  | note | VERIFICATION ACTIVITY - Removal of built up material
label | 043d09af-60ee-57e0-80f4-ab707e9689a2 |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP091 Removal of High Shoulders
label | f3d6f5cc-e052-5a06-9112-8c746087a6f6 |  | note | FREQ. - As programmed
label | 14dc3e74-a10b-527c-ad5a-bc89be2f1856 |  | note | ACCEPTANCE CRITERIA - E2 MAINTAIN ROADSDE SHOULDER PROFILES / RECONSTRUCTION & DRAIN INVERT CLEANING
label | 92e170ef-1897-5f5f-a590-38bab75337ea |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 57d47d15-d175-5fd6-9ec7-8f9d3ccebc50 |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 398a62b1-992d-54b8-901f-9105b9cf15af |  | note | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP235 Shoulder Repair and hand in to supervisor
checkpoint-status |  |  | checkpoint | Concrete footpaths Vehicle crossings VC1, VC2, VC3 and VC4 Downer Activity #249
label | 609f9c49-e66a-5b1d-907c-d99aee31c7bf |  | note | VERIFICATION ACTIVITY - Replacement
label | 85d974ce-41a0-58eb-ad51-9ba5d556f955 |  | note | METHODS OR REFERENCE - As per work procedure: HDC WMS CONCRETE FOOTPATH REPAIR
label | e3d314e2-8aa0-59c2-aeca-7a8332b0a368 |  | note | FREQ. - As programmed or reactive
label | af074a99-1208-5fb2-bce2-19b2a5926532 |  | note | ACCEPTANCE CRITERIA - F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | e7856034-8822-5ab9-a426-0952fd7ce4ea |  | note | INSPECTORATE* V/W/H: S/C - V
label | fc033760-f6fb-579d-91aa-939f153b607c |  | note | INSPECTORATE* V/W/H: DNZ - V
label | df7e9c5e-36cc-58b7-aee4-0c014e09b64a |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 753799a9-cc2a-5998-8b26-bd766eb6dae6 |  | note | RECORDS / REMARKS incl NCR ref - Record on: HDC WMS CONCRETE FOOTPATH REPAIR and hand in to supervisor
checkpoint-status |  |  | checkpoint | Asphalt footpaths – Levelling / Rip and remakes Downer Activity #251
label | d694b347-59aa-515c-aeb6-6a66e46669c9 |  | note | VERIFICATION ACTIVITY - Levelling pedestrian pavements Repair surfaces
label | b1b9d18d-c1e1-5721-aadf-edccf9b8592c |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP146 Construct or Repair an Asphaltic Concrete Footpath
label | 83d841b6-6509-5085-b080-50408898e9dc |  | note | FREQ. - As programmed or reactive
label | fa963ca9-1fad-5d41-a518-43234b63db4d |  | note | ACCEPTANCE CRITERIA - F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | 5c71eb70-8134-59a4-af2c-58b691307bdd |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 29a5d2d6-96ea-57ba-8be4-8c2a2cbedf8a |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 4e9f1cd1-b47f-5b86-b67a-745a3cccdc88 |  | note | RECORDS / REMARKS incl NCR ref - Record on: DN-GD-GP229 Repair a Asphalt Concrete Footpath and hand in to supervisor
checkpoint-status |  |  | checkpoint | Kerb and Channel / Stormwater outlets Downer Activity #143
label | bba8b095-7b09-5c56-b2f4-3b5791c16d58 |  | note | VERIFICATION ACTIVITY - Replacement
label | 988e33b6-1e7b-5c96-97bd-7365d8c8b2c0 |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP092 Repair Broken Kerb and Channel In Situ
label | 27d68f51-9f29-5210-ade5-00f1cd6b78de |  | note | FREQ. - As programmed
label | ee2547be-b418-593c-a3a2-abe529309972 |  | note | ACCEPTANCE CRITERIA - F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | 1fc1f83a-f89a-54d1-b838-13dfb405f5f1 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 6fa3824b-bcb7-5782-b2f6-f27164df9718 |  | note | INSPECTORATE* V/W/H: CLIENT - W
label | 776b0211-1ab7-5df2-baf2-329b77db20e9 |  | note | RECORDS / REMARKS incl NCR ref - Record on: HDC WMS CONCRETE FOOTPATH REPAIR and hand in to supervisor
checkpoint-status |  |  | checkpoint | Sight rails Downer Activity #219
label | f432ee74-945e-5885-9e83-949469a20b3c |  | note | VERIFICATION ACTIVITY - Damaged/ Painting
label | f65a1312-99c9-5026-a4dd-d67a04e0c6a7 |  | note | METHODS OR REFERENCE - As per work procedure: DN-GD-GP0130 Install a Timber Sight Rail
label | cd16393f-82c1-54c2-ad18-764f46e26d7d |  | note | FREQ. - As programmed or reactive
label | 1d8f3b64-c3ce-563d-a849-f64c472b6492 |  | note | ACCEPTANCE CRITERIA - G1 ERECTION & MAINTENANCE OF TRAFFIC SIGNS & SIGHT RAILS
label | 870b0fa8-27eb-5c73-8be3-0ef5de063a58 |  | note | INSPECTORATE* V/W/H: DNZ - V
label | 202bb4c3-3f23-5059-b154-d17b6c1d6c8f |  | note | RECORDS / REMARKS incl NCR ref - RAMM entry Recording dimensions and location