## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 500 Granular pavement |  |  |  |  | Yes | ITP 500 Granular pavement | 072bf24c-78dc-46c5-9c36-8c6e76fbacb7
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 500.1 - Determine Embankment / Subgrade Strength (Shoulder Top-up)
label | b26792ea-7e73-58c3-940c-e6430608d9ca |  | note | Detail of Activity: Proof Roll the excavated area
label | 31657240-3ec0-5263-a403-780e2226c654 |  | note | Action: W
label | 123c5260-8e37-58a7-8453-e36d3a361b95 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): All areas of shoulder top-up. 1 Lot < 300m long.
label | fd256845-20f3-5934-951b-037908869642 |  | note | Inspection / Test Method: NZS 4402.6.5.2
label | c1b15d88-542b-5e3d-8422-bd71a678a8f8 |  | note | Acceptance Criteria: No significant visual deformation under the wheel load CBR>10
label | d476b16c-67bf-53eb-9bde-5b580f8f488f |  | note | Record Documents: Contractor's site diary
label | 64b6fd5f-1c2d-520a-8348-adeee327a335 |  | note | Responsibility: Contractor
label | 3b379ee7-c22f-5655-ba47-e574780b20da |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 500.2 - Determine Embankment / Subgrade Strength (Pavement Widening)
label | 48ac77d9-74fc-5107-b6b2-a3f414e28870 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | bcf32447-08fc-5411-9131-551c0446222d |  | note | Action: W
label | cb278398-243f-5aee-a3dc-01e99545e116 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): 1 Scala per 20m of shoulder or
label | 94477450-aab9-59f9-8478-2fb2c4838ded |  | note | Inspection / Test Method: NZS 4402.6.5.2
label | 1b028843-08f3-5b93-b77d-12cfdddeb1b3 |  | note | Acceptance Criteria: CBR >10 For design input
label | 63694c5b-fd26-506c-9067-e76cb4183855 |  | note | Record Documents: Contractor's site diary
label | 99201443-b2a9-52a5-919b-67a7895ce0fc |  | note | Responsibility: Contractor
label | 54e28f4a-9d72-50a8-95e4-441d88ae47a9 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 500.4 - Confirm SIL Material
label | bc96c7e3-09ea-58bc-b553-4eaffb2a8674 |  | note | Detail of Activity: SIL Aggregate
label | 03eef2f5-8b55-50ec-9e43-b68c6f5d5d29 |  | note | Action: M
label | 5ac5b872-866b-566d-8a48-11d29ae0f53f |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
label | 6bd2fde4-19eb-588d-8197-6190b04f036d |  | note | Inspection / Test Method: Crushing Resistance MDD OMC CBR
label | 4bdfcc06-3082-52e3-922e-46134eb1c431 |  | note | Acceptance Criteria: Project Spec 2.2.10
label | 80cc285d-8b3a-59bb-90c7-cec4fb6627db |  | note | Record Documents: IANZ Report
label | df94f8ca-98f4-5935-b474-f2dc705031ff |  | note | Responsibility: Contractor
label | acfa77f3-0b9d-5f33-9779-6832bce4b963 |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.4 - Confirm Subbase Material
label | 71b77441-e471-5c0f-aeee-8349fac2fb5b |  | note | Detail of Activity: Subbase Aggregate
label | b70b9484-c8ff-5b2d-a5b4-968a37c0a11b |  | note | Action: M
label | 406b1f68-6252-5fee-8f99-9f9db351c745 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
label | b5d72ace-1c64-5536-b893-2ae0986b6144 |  | note | Inspection / Test Method: PSD, SE, CI, PI, Broken Faces Crushing Resistance Weathering Resistance MDD OMC CBR
label | a0a695ef-8da0-520c-bd3a-fa3fc3d66e4f |  | note | Acceptance Criteria: NZTA WHAP 65/ Project Spec 8.1.2
label | 03cb70c2-13d1-5840-9eab-fb75e43a751e |  | note | Record Documents: IANZ Report
label | cb16c307-9286-5115-a4b9-93fa6444419b |  | note | Responsibility: Contractor
label | 7bf80e1e-2e98-516d-9763-e283bcbb77ff |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.5 - Confirm Basecourse Material
label | 5ad628ae-ac7f-522e-baa6-95abedeea45d |  | note | Detail of Activity: Basecourse Aggregates
label | bcf22c77-f6f6-5bbf-9cb4-8730d262dc94 |  | note | Action: M
label | 97966ab1-a37b-5691-bd1f-cd46d8ec0ffe |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): Source properties: 2 tests per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
label | e255552d-7cac-56d5-9021-f5ae63830c9b |  | note | Inspection / Test Method: PSD, SE, CI, PI, Broken Faces Crushing Resistance Weathering Resistance MDD OMC CBR
label | 4cceb2d6-5c43-57da-b77e-f6b70cc6b709 |  | note | Acceptance Criteria: NZTA M4 / Project Spec
label | 6b327957-a421-54bd-8625-87c3ea4741ea |  | note | Record Documents: IANZ Report
label | 61ace645-44c0-5195-b1d9-fe002ef6135e |  | note | Responsibility: Contractor
label | 4fb652d4-234c-5be1-9d0c-2ac96a4f38d8 |  | note | Comments: By IANZ accredited lab
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 500.10. - SIL Layer Depth/Thickness
label | c9bb04a9-446d-5f30-a14c-7a6289c631d2 |  | note | Detail of Activity: Scala/Infered CBR of Subgrade
label | 56a755a4-d78b-5dd4-a22c-4c2251855b02 |  | note | Action: H
label | c1137665-749c-5862-8ee1-98b290a3a531 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): All Subgrade Areas
label | 7028cdcf-f397-5a96-8408-8ff61e4e5768 |  | note | Inspection / Test Method: Scala @3 points across carriageway @ 20m spacings
label | 69fd2e3c-6c85-51ea-a380-28b40cdec732 |  | note | Acceptance Criteria: CBR<10 then SIL Layer = 600mm CBR <2 seek advice from engineer
label | 8c76799e-135d-52da-9f0c-055c7ff83ea3 |  | note | Record Documents: Scala Recording Sheet
label | 087e8e0a-6c46-5bba-a307-8f6d1d31771d |  | note | Responsibility: Contractor
holdpoint |  |  | signoff | Hold Point Authority
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (SIL Construction)
label | 24d4004e-9e41-5f27-b85c-9264c5425fea |  | note | Detail of Activity: Maximum Dry Density
label | ec98dbf2-8be9-5ee6-a82d-784a7a698aae |  | note | Action: M
label | 6d0653a2-9f8d-5619-bda0-72070eb28115 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): 5 per Lot (1,000 m2)
label | 8290e1c0-76f6-5aed-8130-c15058d5b419 |  | note | Inspection / Test Method: NZS 4402.4.1.3
label | 0aa2ce25-e5aa-5350-9f17-2863f0b93406 |  | note | Acceptance Criteria: For analysis of DoC
label | 7d667e81-1880-5862-a3c0-b62a22533ef8 |  | note | Record Documents: IANZ Report
label | 73bcb9ee-b52b-5548-ab14-7f421b92ea49 |  | note | Responsibility: Contractor
label | b6464f14-f1c8-51f4-9d09-cff952c6e21f |  | note | Comments: By Contractor with random Verification by IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (SIL Construction)
label | 88eea24a-da91-550f-bae1-0731b555f655 |  | note | Detail of Activity: Degree of Compaction
label | 88bdd147-872e-59bb-b70d-1997699616f3 |  | note | Action: H
label | aa67733e-b21f-581a-8af8-5ddb14d1e1da |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): 5 per Lot (1,000 m2)
label | faf75ef5-6fa3-5068-b4c5-4739f2d6ea26 |  | note | Inspection / Test Method: NZS 4407.4.2.1
label | 68922322-2d12-5246-9497-8b1066d7f074 |  | note | Acceptance Criteria: NZTA B02: DoC e 95% with all >92%
label | 28adc177-ab41-5576-8f83-d2fada755e69 |  | note | Record Documents: IANZ Report
label | c871fecf-74a7-5d6f-97a1-ee0405954442 |  | note | Responsibility: Contractor
label | 13b52520-ee13-5225-841c-5d8d4a3315a0 |  | note | Comments: By Contractor with random Verification by IANZ accredited lab
holdpoint |  |  | signoff | Hold Point Authority
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Subbase Construction)
label | 911dacc7-71d5-5c14-97b7-0eddc6c50e94 |  | note | Detail of Activity: Maximum Dry Density
label | 8e3cc114-a9de-5143-a8a1-70afbf9ae273 |  | note | Action: M
label | 3f4ad5a1-ea67-5e26-b9f0-a60964da53b4 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): 5 per Lot (1,000 m2)
label | 62c97cef-f74b-5635-87cc-e55d7ecacb6d |  | note | Inspection / Test Method: NZS 4402.4.1.3
label | 9b50bbf0-2aa5-5072-af01-8ccb9e937caf |  | note | Acceptance Criteria: For analysis of DoC
label | 0965a9d3-dddb-5d1e-b18b-6ec4fb812353 |  | note | Record Documents: IANZ Report
label | 465db4a4-93f6-502d-9db1-29f811890c2a |  | note | Responsibility: Contractor
label | 0f5cb778-4de3-5c96-aee3-c8fa36be6496 |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Subbase Construction)
label | aeeebcbe-13d7-5420-8514-8d4adb76b90a |  | note | Detail of Activity: Degree of Compaction
label | 017cc82f-651b-5a0a-aa78-b6ebe08c511f |  | note | Action: H
label | b5ace682-04fc-5d26-b96c-97ac82a8e3fb |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): 5 per Lot (1,000 m2)
label | 67003d13-b63b-59dc-9e46-cf97f2f10b18 |  | note | Inspection / Test Method: NZS 4407.4.2.1
label | a79b237b-099a-5ad8-a322-e119b4a77dcd |  | note | Acceptance Criteria: NZTA B02: DoC e 95%
label | e739c810-6014-5b94-a32f-06aab1499d88 |  | note | Record Documents: IANZ Report
label | f285b90a-a525-5fa2-a3aa-8fc823b167c3 |  | note | Responsibility: Contractor
label | 8de6c2c9-4b9d-5487-b28f-1de3f2e398ee |  | note | Comments: By IANZ accredited lab
holdpoint |  |  | signoff | Hold Point Authority
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Basecourse Construction)
label | 0c5e4c17-3c08-554e-ab51-3cc3f456913e |  | note | Detail of Activity: Maximum Dry Density
label | a15394be-5fb8-51aa-8fd7-13734f10056d |  | note | Action: M
label | 939fe3d2-7f1c-5f00-8c7a-17ab81565ce1 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): 5 per Lot (1,000 m2)
label | 53eb1320-68d5-5fe6-9a82-55f8b1851f90 |  | note | Inspection / Test Method: NZS 4402.4.1.3
label | 123ef5cf-e2e5-58c6-882e-ea6e6e2d3cfb |  | note | Acceptance Criteria: For analysis of DoC
label | 5144926c-5e79-5899-83dc-fe4e2bce1b09 |  | note | Record Documents: IANZ Report
label | a05e6a6b-53c6-5eb0-9173-40748019ba8d |  | note | Responsibility: Contractor
label | 644399be-2318-544d-ac3e-79225e68bc02 |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Basecourse Construction)
label | 082e44c7-77b3-5efc-9656-78fff0f130aa |  | note | Detail of Activity: Degree of Compaction
label | 8aff97fb-4251-534d-85f8-56650117a755 |  | note | Action: H
label | fd6b970e-6b4d-56ce-8c05-48e033fd6293 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): 5 per Lot (1,000 m2)
label | 3b0b5759-fb94-5ae1-8c79-8b7068da369f |  | note | Inspection / Test Method: NZS 4407.4.2.1
label | 783707c0-e18b-542c-aa66-7b6c6434211a |  | note | Acceptance Criteria: NZTA B02: DoC e 98%
label | 811e5156-85f5-5964-a954-8e166d783663 |  | note | Record Documents: IANZ Report
label | cb6114e1-855d-576e-9fb0-ebe5b58e26bd |  | note | Responsibility: Contractor
label | a6858cbb-5dfd-5b1a-85c6-4ecf265e5b89 |  | note | Comments: By IANZ accredited lab
holdpoint |  |  | signoff | Hold Point Authority
checkpoint-status |  |  | checkpoint | 500.10. - Surface Finishing Subbase
label | 2a874005-e38c-5652-8ca0-1f402ac1fb51 |  | note | Detail of Activity: Check geometry of the placed fill is in accordance with the design.
label | 74a86481-f791-5010-ac1c-eedc88f01c74 |  | note | Action: H
label | 4459b2a8-6a65-5694-8667-2e3a29ad39e9 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): All Subbase Areas
label | c68e8e26-dab9-5506-85f5-61307e6b54e0 |  | note | Inspection / Test Method: Survey, Stringline dips @5 points across carriageway @ 20m spacings
label | d9c2c50d-913e-5067-84fc-4b1e34103235 |  | note | Acceptance Criteria: Geometry is in accordance with design drawings .
label | c73135a5-23f3-53bd-9a92-055d65793b13 |  | note | Record Documents: Stringline Report
label | d78d7c93-d6c3-5114-9a55-8ec3b3cc7f63 |  | note | Responsibility: Contractor
label | e31df5c5-11e8-5f54-9980-7071486e32d1 |  | note | Comments: Joint walkover between Contractor and Engineers Representative. All points to be within -25mm +5mm
holdpoint |  |  | signoff | Hold Point Authority
checkpoint-status |  |  | checkpoint | 500.10. - Surface Finishing Basecoarse
label | 99e7b64c-2143-5231-a8de-ec367b2d9880 |  | note | Detail of Activity: Check geometry of the placed fill is in accordance with the design.
label | 54ac5944-dd47-5ada-a24e-bf0eb63ccc94 |  | note | Action: H
label | 7683538a-4307-50fc-b2ce-bd0e2560bc84 |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): All Basecoarse Areas
label | b5c1be60-24ed-5386-9967-1df387d14f01 |  | note | Inspection / Test Method: Survey, Stringline dips @5 points across carriageway @ 20m spacings
label | 56d5651e-d280-5817-ab31-75592ffedd25 |  | note | Acceptance Criteria: Geometry is in accordance with design drawings .
label | 4a32c26b-e65e-5d2b-a3ee-9dda54068760 |  | note | Record Documents: Stringline Report
label | 6a100605-90dc-574d-8037-d9a156521f36 |  | note | Responsibility: Contractor
label | 61136edf-fffd-57ee-a5d8-0c35ad9278ed |  | note | Comments: Joint walkover between Contractor and Engineers Representative. All points to be within -5mm +15mm
holdpoint |  |  | signoff | Hold Point Authority
checkpoint-status |  |  | checkpoint | 500.10. - Surface Finishing
label | bc49a370-3787-58f3-83a4-656bd9c5a0a9 |  | note | Detail of Activity: Roughness Requirements
label | a0917096-82fe-5273-81dd-eb9174cd8f7f |  | note | Action: M
label | f39e3bb5-fd2a-50b7-9de6-ff38414fe45f |  | note | Minimum Test Frequency (Lot = 1 days production or 2,500m2): Finished Sealed Surface
label | 2636cd75-be27-549a-a4b8-cb96a7bfeb6e |  | note | Inspection / Test Method: NAASRA Counts
label | 9b838a3e-16e5-5878-ba2e-a6fafe8ce031 |  | note | Acceptance Criteria: Surface shape complies with Section 2 of NZTA TM7003.
label | ed1769cc-6d6d-5d21-9ff9-f27073cc774a |  | note | Record Documents: IANZ Report
label | c24278e7-839b-59f9-9772-7eaf6d3928ff |  | note | Responsibility: Contractor
label | 4fbabb01-cda0-5691-916e-78ad4ed8969f |  | note | Comments: Maximum NAASRA count of 70/100m with a target of 60/100m.
checkpoint-status |  |  | checkpoint | Final Sign Off
label | 290131f6-8823-59f5-a6fe-053fbd282564 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | d0c50d29-aaf7-5330-83a5-28c72a510d55 |  | textbox | Contractor's Rep Name:
text | def2a8ef-2f9b-5d57-87b6-c1924c393d7e |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-sectioned |  |  | checklist | Piling ITP |  |  |  |  | Yes | Piling ITP | 64b1ceac-3a17-48b2-ab5d-8a244d321c2f
checkpoint-group |  |  | section | Pre-construction
checkpoint-status |  |  | checkpoint | 1.1 - JSA signed off
label | 90a6dab7-0b6e-585d-bdc9-65125f7eae31 |  | note | Acceptance Criteria - Written Notification from Downer
label | 09d350e6-83c1-5568-8239-341d27abf117 |  | note | Applicable Standard -
label | 78cfbc6f-e84d-5493-b572-10d1f6659362 |  | note | Frequency - Once
label | eda43e0c-4e46-5fc8-936a-2f2296efdee7 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 1.2 - PIP, Piling Installation Plan Signed off
label | 7e9d7f28-e836-5482-87f3-cbb9d8b66e86 |  | note | Acceptance Criteria - Written Notification from Downer
label | 52434016-6f7a-598f-a9b1-98690bff116f |  | note | Applicable Standard -
label | 082cb9f6-9ab3-57df-bd10-94d03e0b3a66 |  | note | Frequency - Once
label | 60253a93-acdc-5ffc-952e-e63daa82f146 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 1.3 - Shop Drawings: Steel Detail Sheets
label | 912ec419-0df9-5a39-a552-02d0c4efe46d |  | note | Acceptance Criteria - Written Notification from Downer
label | b1d0d643-6b88-561f-8afb-cbb9e00905cc |  | note | Applicable Standard - AS/NZS 1554.3,
label | f45ffe6a-533a-5cc3-8303-6e20019827bf |  | note | Frequency - Once, before fixing cages
label | 692e57c2-bfbe-540b-8c30-e4ba33e69b94 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 1.4 - Mix Designed signed off
label | 36c9d3fa-3a72-5542-ba7b-d2164337317a |  | note | Acceptance Criteria - Written Notification from Downer
label | ab1d0a1f-61dc-5fa4-9c84-be46bec36273 |  | note | Applicable Standard - Waka Kotahi Technical Specifications, BBO Specifications, Construction Drawing Set
label | 5e05a9a0-4434-527d-bbce-13411a0e79e9 |  | note | Frequency - Once
label | 37c409ba-63ac-5bd9-b9a6-9f0d27902def |  | note | Verifying Records - This ITP
checkpoint-group |  |  | section | Construction of Piles
checkpoint-status |  |  | checkpoint | 2.1 - Traffic Management
label | 543b6d54-de68-5704-b8fb-b6a3d528e33d |  | note | Acceptance Criteria - As shown in the Traffic Management Plan
label | b2dff3e1-5751-56d8-9ff7-f112ddb8faa8 |  | note | Applicable Standard - Contract Documents
label | 28fbe13b-c9ba-5f96-81a8-20f1b3af0d8f |  | note | Method - As per the TMP
label | 4da9b357-f5c4-561c-9d97-78628a1f2a67 |  | note | Frequency - Before mobilising piling equipment
label | d00febc9-304a-5dc2-b49e-f6176bc11fe5 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.2 - Water and Power supply
label | a4525a2f-d127-55f3-9cc5-96012a77e73f |  | note | Acceptance Criteria - 2 phase power, tab suitable for hose connections
label | 3b4fa2d0-8e99-5aa1-a46a-fa3f39864d25 |  | note | Applicable Standard - Contract Documents
label | 05fe3572-7142-55c7-b965-6d7330eb67eb |  | note | Method - Visual
label | d442f056-a679-5216-98c0-abb4a4a58197 |  | note | Frequency - Before mobilising piling equipment
label | 4505ec9e-ed85-5e41-8b52-3f104df19986 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.3 - Working platform
label | 41a40f14-6fc5-5b15-87ea-d7ae92279844 |  | note | Acceptance Criteria - Working Platform Certificate
label | 9aeba5f6-1db7-5fd1-8c2e-7cfcf7331208 |  | note | Applicable Standard - Construction Drawings and PIP
label | 302e21f9-fef3-5ec5-95fc-6f83b23224d3 |  | note | Frequency - Before moving piling equipment into position over pile location
label | 8f3a7317-4f6b-569f-a8ae-de916ff61b54 |  | note | Verifying Records - This ITP or Working Platform Certificate
checkpoint-status |  |  | checkpoint | 2.4 - Proof Bores
label | 62c30b0b-8f7c-57be-996c-650c9c69602f |  | note | Acceptance Criteria - Engineer`s review and comment
label | e49af653-2a73-5bb5-8d25-d683089895c0 |  | note | Applicable Standard - Drawing 4001 rev.2
label | e4a1a51e-e98f-5b67-befa-9490795bf0db |  | note | Method - Machine Drilling
label | 80b4e2e6-be50-5f7c-a25a-4b936f568820 |  | note | Frequency - Before drilling commences
label | ed82477b-a84c-5606-bca3-a8bbdca4392d |  | note | Verifying Records - Borehole Records
checkpoint-status |  |  | checkpoint | 2.5 - Surveying Pile Centres
label | 11dc36bf-06c4-591b-bf5c-b02b5276b98f |  | note | Acceptance Criteria - Placing the survey peg on the pile centre
label | abfde72a-b5c0-526d-a1dd-ee512b42045d |  | note | Applicable Standard - Surveying industry standards
label | ffa6696f-fe71-5e46-8dcc-f52cba98b6f4 |  | note | Method - Survey
label | 3755e16f-d50f-5825-b43a-8f1fd1876770 |  | note | Frequency - Before drilling commences
label | efd052ec-9cfa-5f5c-8c85-e27f566c43d2 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.6 - Sediment Ponds
label | 1d4304c1-99e6-5d3a-aea6-34686cfd717d |  | note | Acceptance Criteria - Close to the piling locations, big enough to accommodate water coming from pile holes
label | 216b62c3-3806-5430-9fc2-48169cb74364 |  | note | Applicable Standard - Resource Content, PIP,
label | c908d0c0-2b30-5dc5-ad46-b5bd480cedba |  | note | Frequency - Before drilling commences
label | f580640a-eae0-528c-87a7-6a7fd6d4376d |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.7 - Reinforcing Cage
label | 33bccac6-992a-5606-b84b-d3150650a6ea |  | note | Acceptance Criteria - As per approved details sheet (item 1.3 of this ITP) For example lap length is minimum 1.8m for RB32, Grade 500 steel
label | 41b83122-d0a7-58d5-b999-7188943f59da |  | note | Applicable Standard - Waka Kotahi Specifications, BBO, Specifications, Construction Drawings
label | 17df4c0e-986e-5511-abbd-397ca9f9a80c |  | note | Method - Visual
label | 5a945a17-e457-5547-8e74-0ff11eee79ab |  | note | Frequency - Every Pile Cage
label | 5bb40c13-0641-5e73-9517-ffbbe1b0e555 |  | note | Verifying Records - This ITP and Site Inspection Record Documents
checkpoint-status |  |  | checkpoint | 2.8 - Drilling borehole and Pile socket length
label | 2c984c4b-b416-522d-a78b-534db09ce717 |  | note | Acceptance Criteria - Engineer`s Acceptance, sockets lengths as per approved drawing
label | 9b63f8ce-0885-5da9-b5ae-bff16ff46abb |  | note | Applicable Standard - Waka Kotahi Specifications, BBO Specifications, Construction Drawings, PIP, Drawing 4010 rev.2
label | 9c4d7d78-1103-5a1e-8949-e3a6167e7f05 |  | note | Method - Visual
label | 2d215fe4-0c69-5fa5-a479-1408027565dd |  | note | Frequency - Every Pile
label | 269f886d-64e6-5967-9936-7be4abcdf456 |  | note | Verifying Records - This ITP and Site Inspection Record Documents, Pile Card
checkpoint-status |  |  | checkpoint | 2.9 - Placing pile cage and concreting
label | c2dd1cb2-ff0a-52d1-b2ae-2594a8d5d1e0 |  | note | Acceptance Criteria - Pile cage identification tag matches with pile number. Downer confirms that cage orientation and position are under tolerances.
label | ef6d3820-06c5-54f0-a99d-3d101a899ceb |  | note | Applicable Standard - Waka Kotahi Specifications, BBO Specifications, Construction Drawings, PIP
label | d38fbcd5-fac5-5f01-a517-21c34937a6c9 |  | note | Method - Survey
label | 0241683c-02c0-5a46-9919-b9491b673ff4 |  | note | Frequency - Every pile
label | e142c4e7-51bf-5593-ab2c-ac76cbddff5b |  | note | Verifying Records - This ITP and Pile Card
checkpoint-status |  |  | checkpoint | 2.10 - On site concrete testing
label | 7f3efc84-4ad1-5e77-b59d-3e776c959862 |  | note | Acceptance Criteria - As per approved mix design (item 1.4 of this ITP)
label | 339548fe-cf24-502b-b2c8-75b21d08d291 |  | note | Applicable Standard - PIP, Waka Kotahi Specifications, BBO
label | 9142b370-4771-5ea2-9464-e50964162aea |  | note | Method - In-situ test
label | 41d04a1d-197f-5596-9c43-8985e3a40e9a |  | note | Frequency - Each delivery
label | c447892c-25a6-57c1-963b-5bdd21b832df |  | note | Verifying Records - Concrete docket
checkpoint-status |  |  | checkpoint | 2.11 - Removal of permanent casing
label | 46896bc0-d9c8-5e09-9cf0-ef714a24a266 |  | note | Acceptance Criteria - As per tolerances
label | f791f8a0-bc73-5a7d-9a8d-7b4ea16359ae |  | note | Applicable Standard - Construction drawing 4010 Rev.2, Waka Kotahi Specifications, BBO
label | aa352b5c-1102-5080-aea7-b9c6c21fb730 |  | note | Method - Survey
label | df428316-662b-5dca-8073-363404875a6f |  | note | Frequency - Every pile
label | e227f944-42da-5c48-a544-4da41b085e49 |  | note | Verifying Records - Pile Card
checkpoint-status |  |  | checkpoint | 2.12 - Concrete crush test
label | 485117cc-aa26-5bf1-b747-2e3a159b057f |  | note | Acceptance Criteria - Minimum 40 MPa for 28 days samples (3 samples for 28 days and 1 sample for 7 days)
label | cc600708-96e0-5e55-9c8a-d0db6d8e7c6a |  | note | Applicable Standard - Waka Kotahi Specifications, BBO
label | 3cd5267c-849d-56ef-aee0-256a2d72a642 |  | note | Method - Laboratory Crush Test
label | 71c35469-65cf-5fdd-9cfe-40cc1ab835f7 |  | note | Frequency - Each pouring day
label | f8749333-659b-5c8c-8dee-46cf427e7f55 |  | note | Verifying Records - Concrete test results
checkpoint-status |  |  | checkpoint | 2.13 - Integrity testing
label | eecdc486-3157-5ca4-be0d-04b627ad0d01 |  | note | Acceptance Criteria - No major defects or flows
label | 85eeea85-0ad4-53e6-9627-87b575789a94 |  | note | Applicable Standard - Drawing 4001 rev.2, PIT Specifications
label | f73a0898-2a09-5152-b536-4e1eb16a0b4a |  | note | Method - Pile Integrity Testing
label | 3fcb72c0-5d12-5b03-88d3-dcacd866a5f5 |  | note | Frequency - 50% of piles
label | f3e0b905-dc31-5531-87cc-d14a580f8bb5 |  | note | Verifying Records - Test results
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 27d6248d-9e58-535f-bed8-6d349dea1fa0 |  | textbox | Contractor's Rep Name:
text | 93b9a3a8-b03e-5a27-90f1-54f0133565f8 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | Concrete Pre-pour Inspection |  |  |  |  | Yes | Concrete Pre-pour Inspection | 94ba6086-ea82-4612-8e0c-df83573a1de1
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Engineer notified of pour
text | 98ffea72-4951-5484-a1cb-4a448e1233c5 |  | textbox | Date
text | 7006f770-0251-5e19-ad15-3a83db9ada77 |  | textbox | Drawing Number and Revision
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Installed as per formwork design
checkpoint-status |  |  | checkpoint | Permit to load issued
checkpoint-status |  |  | checkpoint | Dimensions correct
checkpoint-status |  |  | checkpoint | Position and orientation correct
checkpoint-status |  |  | checkpoint | Forms vertical, plumb and true
checkpoint-status |  |  | checkpoint | Forms coated with release agent
checkpoint-status |  |  | checkpoint | Forms clean and clear of debris
checkpoint-status |  |  | checkpoint | Joints sealed
checkpoint-status |  |  | checkpoint | Pour level marks
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Correct grade reinforcement
checkpoint-status |  |  | checkpoint | Correct bar size
checkpoint-status |  |  | checkpoint | Correct number of bars
checkpoint-status |  |  | checkpoint | Correct spacing
checkpoint-status |  |  | checkpoint | Starters bars included
checkpoint-status |  |  | checkpoint | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
checkpoint-status |  |  | checkpoint | Correct weld lengths (min 10 x bar diameter)
checkpoint-status |  |  | checkpoint | Correct lap length (min 50 x bar diamenter or as per drawing)
checkpoint-status |  |  | checkpoint | Correct lap position (staggered appropriately)
checkpoint-status |  |  | checkpoint | Longitudinal bars terminate with 90 or 180 deg hook)
checkpoint-status |  |  | checkpoint | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
checkpoint-status |  |  | checkpoint | Reinforcing adequately tied
checkpoint-status |  |  | checkpoint | Chairs or spacers fixed in place
checkpoint-group |  |  | section | Embedded items
checkpoint-status |  |  | checkpoint | Block-outs, ducts & cast in items installed
checkpoint-status |  |  | checkpoint | Correct position, level & alignment
checkpoint-status |  |  | checkpoint | Securely fixed in place
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Correct location
checkpoint-status |  |  | checkpoint | Adequately prepped
checkpoint-status |  |  | checkpoint | Joint board installed