## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | F2LSIP - ITP 02 - Earthworks | itp |  |  |  | Yes | F2LSIP - ITP 02 - Earthworks | 1359cf13-a212-41f0-9cf0-19408f27f11e
checkpoint-group |  |  | section | 2 - Earthworks
checkpoint-status |  |  | checkpoint | Earthworks
label | 3e326628-f355-5059-a47a-e69515b1edbb |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | 84b6f92b-a0a6-5986-b837-9f8e87ff8ecd |  | note | Acceptance Criteria - All below requirements are met and approved by CR
label | 6fa8366d-dbb1-5185-b4a9-e5bbb34a92d8 |  | note | Verifying Document - Referenced Item numbers as below
label | 6ceaf1ab-b612-55b7-be00-76bcda0c5514 |  | note | Frequency - Once post construction
label | 026ccb25-518a-535a-b525-2161837546e4 |  | note | Inspection Type - Hold Point
label | c2f3c44f-f074-579f-8063-7a947ae0f501 |  | note | Inspection: Key - H
label | d5e6e8e5-262f-5e64-a1cf-6bbdbc294d1f |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.1 - Source Properties Imported Fill
checkpoint-status |  |  | checkpoint | 2.1.1 - Bearing Strength
label | 034bce19-f1be-526c-bf00-c7ac9ae94e56 |  | note | Inspection Point: Quality Control Activity - Sampled from truck or stockpile onsite as per NZS4402 clasue 1.6.3 & 1.6.4
label | dba550d1-d2c4-5c40-8087-80fff9b23537 |  | note | Acceptance Criteria - CBR > 40 as per NZS4402
label | 48ac598a-3ae3-5e55-8e9f-910821de0ab7 |  | note | ○ Note: For Hard Fill CBR, the target CBR is determined by trhe following formula:The tests shall consist of 4-day soaked CBRs carried out to NZS 4402. If the sample mean is C and the standard deviation is s then C must not be less than 40 + 1.3s.
label | f55f6fef-54a3-5257-b322-ad9707c0e8bc |  | note | Verifying Document - IANZ Lab Report
label | a2c8d184-5b1e-5462-9855-715f54711533 |  | note | Frequency - Once per stockpile
label | 9bac91f0-141d-5480-b984-ac12816e40ec |  | note | Inspection Type - Review
label | 5cc71418-cc8a-5014-a2c0-3e796b8f0b19 |  | note | Inspection: Key - R
label | 6ef5a83a-d6db-5beb-b482-31c91fd2c8e3 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 2.1.2 - Weathering Resistance
label | bb13e171-20e7-53d8-a125-040d8760dd0c |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 2aae11a5-8002-51ff-a9b1-fe42ff8bfb36 |  | note | Acceptance Criteria - QI = AA, AB, AC, BA, BB, CA, CB as per NZS4407 1991 Test 3.11
label | 4d0db376-8cb1-5b8b-8e90-4055979fb916 |  | note | Verifying Document - IANZ Lab Report
label | a705e371-ed5a-5575-a5ce-780226c509c7 |  | note | Frequency - Once per stockpile
label | 217c14e1-3990-5dbb-b733-4509f327ad23 |  | note | Inspection Type - Review
label | fd7f6ac9-b667-553b-b87e-aa095c963bed |  | note | Inspection: Key - R
label | 5dd4e181-535f-53ce-988d-dd5cf0899428 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 2.1.3 - Grading Limits
label | fc3a78db-189a-5637-ac08-cdaebdf3d4cb |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 5147c797-51c1-518b-88a2-05bdf50eed48 |  | note | Acceptance Criteria - Grading within envelope as per table 302.2.3 (Technical Specifications) Tested in accordance with NZS4407 1991 Test 3.8.1
text | 94f9e33b-db3b-5131-b9f4-ad4e506ca021 |  | textbox | Maximum Material Particle size:
label | 781aadca-11a4-555b-a379-6e039dddcdad |  | note | Verifying Document - IANZ Lab Report
label | 759c4c76-3d45-5740-b5b7-d5d33c7be3f8 |  | note | Frequency - Once per stockpile
label | 01ef96f8-2561-5a9a-820e-84af55ba4242 |  | note | Inspection Type - Review
label | 4a578c1c-3c23-55e8-aa09-241631089094 |  | note | Inspection: Key - R
label | db064eb4-774b-5447-a099-c0da5853b47a |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 2.2 - Construction
checkpoint-status |  |  | checkpoint | 2.2.1 - Topography Survey
label | 12ac868b-08cb-5a3c-921d-d0fa839cf0f3 |  | note | Inspection Point: Quality Control Activity - Pre-Cut/Fill Survey
label | 182e900e-ae07-5e2e-8ae4-468acfdac2d3 |  | note | Acceptance Criteria - Within Design Expectations
label | 1cc3e027-a46e-5db1-8a80-3c3003ae0457 |  | note | Verifying Document - Survey Data
label | 8d5786cb-8160-50c4-80a8-a9ef5ab17e77 |  | note | Frequency - Once per construction area
label | 6a96901e-18aa-5517-914e-96736f493f7e |  | note | Inspection Type - Action
label | 56aac1b2-ba07-5fcc-941f-6430c3aedd2b |  | note | Inspection: Key - A
label | a4ebe0a6-ade7-5447-83a4-dfd97aa18da1 |  | note | Inspection: By - SV
checkpoint-status |  |  | checkpoint | 2.2.2 - Survey Set out
label | 462b5f80-ce17-5b2c-a2fa-823fa2af1a15 |  | note | Inspection Point: Quality Control Activity - Onsite Setout
label | da2b9918-8174-5bb1-b7e2-6de7a822f2c2 |  | note | Acceptance Criteria - Survey have setout using pegs or similar, the location of the pavement in regards to horizontal and vertical alignment, as per design. Existing surface to be surveyed for quantity measurements prior to topsoil strip, prior to cut or fill and after completion of Cut or Fill.
label | d2217be2-fbf5-5f13-9dfe-6e9e0e5a7d2d |  | note | ○ Note: Prior to Cut and Fill Operation, Site Clearance and Topsoil stripping is required.
label | c33b3e80-3f94-52cf-b32a-ba22329b38fe |  | note | ○ NZTA F/1: Clause 3 - Clearing
label | b9210cd4-3059-5375-a523-eaaef2eb72cf |  | note | ○ Clearing shall include complete removal from the site of trees, logs, scrub, grass, roots, and other vegetation fences (if any) and debris. All material removed shall become the property of the Contractor and disposed in a safe and legal mannner. Burning of rubbish & vegetation is not permitted at any time; irrespective of Local Authority permission.
label | 41fc24b3-8271-59eb-b3d5-6169bf11258b |  | note | ○ NZTA F/1: Clause 4 Topsoiling - Removal depth100mm thick. Only Topsoil under the footprint of works shall be removed.
label | 1f3dd101-fd00-56d2-acb1-ad7b71e4e9e7 |  | note | 4. REMOVAL OF TOPSOIL
label | ecc590f5-99e9-5ae6-b0df-fa47bda09d85 |  | note | 4.1 Topsoil shall be removed within the limits of the earthworks. Care shall be taken during the removal to avoid contamination of the topsoil.
label | 5bfaa295-3f9e-5c11-ac8b-f3921afe0ecf |  | note | 4.2 Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. The Contractor shall control all stockpiling operations oto ensure the maximum utilisation of each area.
label | 3e20d7c7-be9d-514c-82be-cafe5490f575 |  | note | Verifying Document - N/A
label | 1ac5a966-416f-5b68-bec7-0772d19aeee6 |  | note | Frequency - As required
label | 03c5e67f-52ed-53ab-bd99-90152d321727 |  | note | Inspection Type - Action
label | 0ca37d6c-0671-5481-acb2-c54ef54a934d |  | note | Inspection: Key - A
label | 4c45a27c-f75f-5131-968d-ad9eab122f36 |  | note | Inspection: By - SV
checkpoint-status |  |  | checkpoint | 2.2.3 - Visual inspection of final trimmed subgrade surface
label | 4c7b7832-6c28-560a-b009-38ce8d480dee |  | note | Inspection Point: Quality Control Activity - Pre pavement construction visual inspection
label | b4a4b09c-db41-5dee-ab86-3871ca2d0548 |  | note | Verifying Document - Site Inspection Form
label | cde1c861-b4aa-5597-8a32-4a96bf346dc5 |  | note | Frequency - Once per construction area
label | 2ae468ca-2b1a-54e4-acbd-a8f3ef04fc48 |  | note | Inspection Type - Witness Point
label | b7c97525-164c-5445-a792-4ed551511bc0 |  | note | Inspection: Key - W
label | be568821-6517-5233-93ce-f97a037b937f |  | note | Inspection: By - PM & ER
checkpoint-status |  |  | checkpoint | 2.2.4 - Compaction (granular)
label | ca42d5ee-3cea-5725-89fc-1c9cfaae5baa |  | note | Inspection Point: Quality Control Activity - Proof Roll
label | cba0c0ef-e5c5-5099-abc2-d21e5ddc8232 |  | note | Acceptance Criteria - Surface impression not greater than:
label | 2473dcd1-724f-557e-820d-17315704edb8 |  | note | ○ 7mm for bulk fill
label | 7e241fb9-53a1-5aaf-abc6-f722e2395d95 |  | note | ○ 5mm for subgrade fill
label | 61dfa798-3f1f-53a3-b056-c3401d070014 |  | note | ○ Using 11t Smooth Drum Roller or equivalent.
label | 3c2bed23-8915-50d8-a056-c519f47b92b0 |  | note | Verifying Document - Site Inspection Form
label | ce4209c6-3ee1-5667-89a9-3fc2835a9833 |  | note | Frequency - Once per construction area
label | 0ed4b33b-975f-5f3b-90e6-ca83fa167b08 |  | note | Inspection Type - Hold Point
label | d9026e84-ac52-5443-90d1-ac6855b3f90b |  | note | Inspection: Key - H
label | 7b2b39ce-74c0-5ce1-935d-bce7d089b08c |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.5 - Compaction (Non-granular)
label | f44a3e56-459d-5183-aaa8-9db307a71bce |  | note | Inspection Point: Quality Control Activity - Wet density measure
label | db9f64e0-1fb9-5f9d-a5d1-fe2498be410e |  | note | Acceptance Criteria - See TNZ F-1 1997 Clause 10.5.2 Non Granular Material
label | 7b61fe51-089d-5705-89c4-0c0ea02c917c |  | note | Verifying Document - Site Inspection Form
label | ce480512-86d6-57c9-8360-4d93218c759d |  | note | Frequency - Once per construction area
label | 0e2b329d-eb3a-5a17-8741-70e9167cd854 |  | note | Inspection Type - Hold Point
label | df0a1fd3-c704-5e0f-b704-5104add2cacb |  | note | Inspection: Key - H
label | 493d4917-a00c-55b3-bf17-2ddb33fe7130 |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.6 - California Bearing Ratio
label | ac6190da-0d6d-5412-ad89-6e1cb00428fc |  | note | Inspection Point: Quality Control Activity - DCP Testing
label | 497b561a-3cbb-58dd-9685-87b85d45284f |  | note | Acceptance Criteria - Equivalent CBR value of ≥ 2%
label | 16b958ec-6746-5a13-8350-94ea4870e6c0 |  | note | Verifying Document - DCP Test Report
label | ede16ebd-8d28-5c0c-b882-159b2ab488d1 |  | note | Frequency - TBD by Engineer
label | 6b7eaa0c-d0f2-59fb-ac9d-d9c7b9e187a2 |  | note | Inspection Type - Hold Point
label | b549ec38-f2d4-5d75-9b0e-369e399911f2 |  | note | Inspection: Key - H
label | 33b3c0ee-c05d-50b1-b2c3-c540bb44eba0 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.7 - Surface Finish Tolerances
label | 23fa4726-c21e-527e-922b-0cb8c31a35ad |  | note | Inspection Point: Quality Control Activity - Straight edge, as-built and inspection
label | c40da5ca-6b9e-52b4-8a64-5b6b407247a1 |  | note | Acceptance Criteria - No point varying more than 30mm on a 3m straight edge laid parallel to centreline, or x-section camber board at 90° to centreline. No ponding where design slope ≥ 2%
label | e835162c-cc80-5194-85e7-832a862dd6c1 |  | note | ○ RL Tolerence = +0 - 30mm from design
label | 05decf45-c223-519f-87b5-ecf4f3f58ba8 |  | note | ○ Survey data / As-built drawings to be submitted to engineer.
label | a719518e-9659-56bf-b290-7e294d8c03d3 |  | note | ○ The subgrade surface shall not pond water, where the design slope of the subgrade is 2% or steeper.
label | 17c0f6cb-fcde-5f42-a5da-ff5168feb03f |  | note | Verifying Document - Straight Edge form, as-built survey data, visual inspection
label | 90b0a51a-7a7f-56b4-93cd-e0cf5c7273ba |  | note | Frequency - TBD by Engineer
label | d45c84bd-bcc6-5937-84b4-509b160aa920 |  | note | Inspection Type - Hold Point
label | 4f884997-c374-5526-9c9d-962a6d454e6b |  | note | Inspection: Key - H
label | 33ccb6a8-a1be-5c61-a14f-122c1d6a0002 |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.8 -
label | cfd456d1-4b2b-545c-9419-94f701f8ea03 |  | note | Inspection Point: Quality Control Activity - Subgrade Testing and Improvement
label | e0773857-e23a-5c04-91de-4cb6a859278a |  | note | Acceptance Criteria - The in-situ subgrade shall be:
label | 6db922ab-682b-5825-b4cc-628a5081914a |  | note | – Tested with Dynamic Cone Penetrometer (DCP) as out in Section 505.2.3
label | d57119a9-dae4-5201-997d-25e0b16df9dd |  | note | – Proof roll as per the requirements as out in Section 505.2.4
label | cbd124d1-1448-5b0d-b585-71922708ef46 |  | note | Acceptance of the subgrade shall be confirmed by the Engineer and shall be based on achieving a minimum CBR of 6%.
label | 9200c402-7fc6-578f-8b87-0a727637d509 |  | note | Where DCP tests show areas less than the design CBR, these areas shall be treated by undercutting the subgrade and replacing with:
label | 0007871b-703d-51cb-bf73-1d77922bb427 |  | note | ○ AP65 subbase quality material (4% ≤ CBR < 6%), and
label | 82328e27-1a83-5796-ab4d-dc9623fd0cbd |  | note | ○ AP65 subbase quality material and a Class 1 Geotextile with triaxial geogrid on top of the subgrade (2% ≤ CBR < 4%).
label | a2adb85a-09af-5982-b5ba-d7bcb80424df |  | note | The undercut requirements, if a minimum CBR of 6% is no achieved, for the SH01N widening is shown in Table A505.2.1.
label | 4231d271-af17-5ab9-92f2-63b6a2f5e249 |  | note | Verifying Document - IANZ Lab Report
label | 38ebc3ba-196c-5c3f-ac60-e5464fbfdf52 |  | note | Frequency - Each layer constructed.
label | d0a14cf0-14c3-53c7-aa1b-25db2c126f67 |  | note | Inspection Type - Hold Point
label | 04fd50d7-46f0-5307-8e74-d5efdd83f9b9 |  | note | Inspection: Key - H
label | 27419e5b-cf82-53cc-9595-18a196faa71f |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | F2LSIP - ITP 03 - Drainage | itp |  |  |  | Yes | F2LSIP - ITP 03 - Drainage | 19a555c1-e65d-4ceb-92ad-c6d974a0db7e
checkpoint-group |  |  | section | 3 - Drainage
checkpoint-status |  |  | checkpoint | Drainage
label | 3ab9e6a6-31d9-5a9e-beb9-cf76cd389fcc |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | f69efe61-98ff-596d-b901-746e0adeee33 |  | note | Acceptance Criteria - All below requirements are met and approved by CR
label | fc135155-a025-51aa-9277-82682ddf4644 |  | note | Verifying Document - Referenced Item numbers as below
label | c10f6bb4-1466-5927-9693-2a5db4bff46d |  | note | Frequency - Once post construction
label | 11b61b40-e0a9-57f0-aba1-5ec491b03869 |  | note | Inspection Type - Hold Point
label | 54371e5d-8cc2-5b8f-9f6e-1d04ad0e796e |  | note | Inspection: Key - H
label | f8ee28f0-a3be-51b5-88ba-59ec3e86d7bf |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.1 - Materials
checkpoint-status |  |  | checkpoint | 3.1.1 - Concrete Pipes
label | 3622edad-69d0-5725-8abc-9ed0293f6552 |  | note | Inspection Point: Quality Control Activity - Documentation review prior to installation
label | ba85602b-64c9-5254-8e42-aee9234ae288 |  | note | Acceptance Criteria - To comply with NZS 4058:2007. Designed and installed to NZS 3725 2007. Shall be class 4 unless noted otherwise on drawings.
label | 00275dd0-a02d-5124-b0ce-b6e7f46f2833 |  | note | Verifying Document - Manufacturers Certificate
label | 5043538b-73ca-558f-b0e6-48acf716ef59 |  | note | Frequency - Once pre construction
label | 6d24eb9f-fe67-53e0-a934-3c1157441938 |  | note | Inspection Type - Review
label | dbd6b5f4-7f0a-5f73-9148-4d28c18e2ea9 |  | note | Inspection: Key - R
label | 208e8709-06d6-5b57-a03f-1aa657e0dcd4 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 3.1.4 - Manholes, Catchpits and Precast Concrete Structures
label | f52eacb4-3e27-5116-846d-a012f9da07bf |  | note | Inspection Point: Quality Control Activity - Documentation review prior to installation
label | e7a10330-9189-5c13-b0c8-db2fcd7530a3 |  | note | Acceptance Criteria - Precast structures to comply with NZS 3106. Joints to be interlocking, self centering type. Sealed with butyl mastic or similar approved.
label | 21730269-5402-54b5-986f-5489de7ca9fa |  | note | ○ Manhole rings to be minimum 1050mm diameter, ubnless otherwise stated & comply with NZS 4058.
label | efff7eb4-0407-5958-b4fc-ebbbef491ac0 |  | note | ○ In-situ RC to comply with Specification: Concrete (structural) & SPecification; Reinforcement.
label | cc555986-3489-50d6-ba23-01510e852dd7 |  | note | ○ Gratings, manhole lids and frames to be Class D complying with AS 3996, cast iron.
label | e2cd54b6-7f49-54da-9f71-4f7b0a1c69f4 |  | note | ○ HD grates, lids and frames used in roadways, verges, sideways. Light duty elsewhere.
label | 1dbb64d1-7c44-5e43-bcc6-b8cadfe0b1fa |  | note | Verifying Document - Manufacturers Certificate
label | e6d527fd-d697-5eff-a593-97b80971b845 |  | note | Frequency - Once pre construction
label | 92c4b0aa-a3ba-5eb6-852d-9b8e82c56530 |  | note | Inspection Type - Review
label | 6047f207-493e-5c23-a026-ab52064b6248 |  | note | Inspection: Key - R
label | 261a4db5-f34c-5eb7-ae76-95217963b23b |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 3.1.7 - Concrete
label | 465d36f1-62f9-5036-b327-40aacf36b703 |  | note | Inspection Point: Quality Control Activity - Documentation review prior to installation
label | 329e660c-6ac6-504a-b7d8-704470eebd73 |  | note | Acceptance Criteria - Concrete work shall be in accordance with Section 410 of this Specification unless stated otherwise in the Specification and/or the Drawings.
label | fd03a053-d8bd-5860-a68e-8d6807d7534c |  | note | ○ Precast headwalls/wingwalls design drawings to be submitted for approval pre construction. Design to comply with project requirements and relevant NZS standards.
label | b1e641f5-7f8f-5b57-9773-87fe6c4c6ecf |  | note | Verifying Document - Manufacturers Certificate
label | 903af5ac-c839-53cd-bedf-ddcde332c14d |  | note | Frequency - Once pre construction
label | 80e7fff7-db99-56c0-8658-169d37ed495a |  | note | Inspection Type - Review
label | 958b79cd-1ae9-5373-b3bf-17524cf95226 |  | note | Inspection: Key - R
label | 026bf72b-8c88-5067-bbbe-e3dfb87d2740 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 3.1.8 - Granular pipe bedding and surround / Placing Geotextile fabric under rip rap
label | ba4b137b-872a-5693-a518-163a683d89fb |  | note | Inspection Point: Quality Control Activity - Documentation review prior to installation
label | 6aaa0679-661a-5e43-b10e-47f08a5afef4 |  | note | Acceptance Criteria - Granular material to comply with grading as per NZS 3725.
label | 4bd4f6f3-9e5b-55c0-9689-a5b952604f6a |  | note | ○ Flexible pipe bedding to be AP5-20 or pea metal depending on pipe diameter, sand bedding allowed in sand enviroment.
label | cd639acc-f801-5c09-a3cb-358c8b439b41 |  | note | ○ Rigid pipe bedding, surround and haunching material to be as per drawings or AP20.
label | c7d427f9-be57-51f6-93a5-a8d5e6c3fab2 |  | note | ○ Material to be free from organic matter.
label | d1a767bf-5e14-55b5-8f3a-4b45e9fb0918 |  | note | ○ Grading curve formed for each material.
label | 78bafc0f-9cd7-5efb-bfe7-7bcf71b41b12 |  | note | ○ Material Grading as per NZS 3725:2007
label | b0943dd1-45e3-5da8-8812-f1778bb17bab |  | note | ○ The bedding shall be enveloped in geotextile filter fabric (Terram 1000 or Bidim A29) that complies with TNZ F/7 geotextile, minimum strength class C, and minimum infiltration Class 1.
label | 3b690c3c-5fa2-59c5-953e-5ae1a9335f1f |  | note | Verifying Document - Manufacturers Certificate
label | 91a5d035-ddfd-50fe-9e19-a5b3c004f828 |  | note | Frequency - Once pre construction
label | 19f0c849-591e-5937-b4cb-54d91fa28384 |  | note | Inspection Type - Review
label | 34738998-9cbb-5b22-8cf5-1328f3f46379 |  | note | Inspection: Key - R
label | 94107d84-b407-5021-9657-d675a98ca1dc |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 3.1.9 - Scruffy domes
label | 42121338-d9e8-58ae-9efc-3e516ccaa162 |  | note | Inspection Point: Quality Control Activity - Documentation review prior to installation
label | 75549bac-3817-56b0-afcb-899906336177 |  | note | Acceptance Criteria - Manufactured & installed to approved supplier recommendations. To be bolted to riser with SS bolts. Shop drawings to be approved prior to construction. Structure to consist of galvanised steel to NZS 4671 and galvanised to NZS 4680.
label | 12b9bc83-a631-55f4-9b30-8b27d9429ff0 |  | note | Verifying Document - Manufacturers Certificate
label | dd4c8624-3aec-5876-ada3-64631bf90709 |  | note | Frequency - Once pre construction
label | 356adc17-ea69-5c47-a02e-1716ef10c316 |  | note | Inspection Type - Review
label | 33f8e558-1936-5cc3-b778-d4223573edae |  | note | Inspection: Key - R
label | 9ae2dd9b-98d7-583d-ade7-4e1fe74f90f8 |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 3.2 - Design
checkpoint-status |  |  | checkpoint | 3.2.1 - Confirm drainage design
label | ab84a85d-2e13-59a3-aeed-35b8d279d1c6 |  | note | Inspection Point: Quality Control Activity - Design review
label | 1d10fe34-1675-5206-9315-8cfc466eab7c |  | note | Acceptance Criteria - ER to provide sufficient design.
label | 31badf6d-251b-56d5-bfaa-7cb1e191b28e |  | note | Verifying Document - NTC
label | e90d2910-c4ed-56ab-bd5c-7afc7663f3c5 |  | note | Frequency - Once pre construction
label | aec3e279-b2f9-5a2a-af8e-8f87a953f388 |  | note | Inspection Type - Hold Point
label | c537ff03-fb1d-5cb7-a343-302d1c56c5e6 |  | note | Inspection: Key - H
label | 07950a51-09c6-55b2-a0b6-0477e3d8da99 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.3 - Construction - In accordance with NZTA F/3 & NZS 3725
checkpoint-status |  |  | checkpoint | 3.3.1 - Material Delivery
label | b20adfad-ab77-50ce-9980-488a223b1b3a |  | note | Inspection Point: Quality Control Activity - Visual Inspection of pipes / precast structures upon delivery to site.
label | 97e5019e-00ce-5b7d-8db3-b686b96014a0 |  | note | Acceptance Criteria - Visual check to ensure materials are free from cracks, gouges or other deformations that could be detrimental to the life of the product.
label | 19925cb4-d1c3-5770-93cf-d320ef35daa3 |  | note | Verifying Document - Material Inspection Form
label | 234e89b1-7c0d-5f7e-bb1b-615ef01fe1c6 |  | note | Frequency - Upon Delivery
label | 0891a4f0-5050-51f0-a509-94dcb361bbdc |  | note | Inspection Type - Witness Point
label | 3643dd99-d66d-5ba2-bb95-4d6a017ed343 |  | note | Inspection: Key - W
label | d761c993-3171-57d2-b8e0-a9382b1e6bc5 |  | note | Inspection: By - PM/PS
checkpoint-status |  |  | checkpoint | 3.3.2 - Survey Set out
label | 0b139a19-9d43-504d-8226-04f040caf15f |  | note | Inspection Point: Quality Control Activity - Onsite Setout
label | 51a9c4e2-fa69-58bf-bc19-eb7396476433 |  | note | Acceptance Criteria - Survey have setout using pegs or similar, the location of the structure in regards to horizontal and vertical alignment, as per design.
label | 5b2b3a53-adbb-56f6-91da-48ff5b9b2c52 |  | note | Verifying Document - N/A
label | a5351783-f7a0-58cf-8410-5d2789d6eaeb |  | note | Frequency - As required
label | 6bacee24-2a8f-52ba-96cb-97406eb2c60e |  | note | Inspection Type - Action
label | b442504e-2995-5fbf-b2c0-f26d40ed7664 |  | note | Inspection: Key - A
label | 69ac2d54-6f14-5a12-bf10-987e55bab9b3 |  | note | Inspection: By - SV
checkpoint-status |  |  | checkpoint | 3.3.3 - Trench / Swale Inspection
label | 0431da6d-5aa0-5f91-a95e-60d947ebec5e |  | note | Inspection Point: Quality Control Activity - Visual inspection of drainage trench to enusre correct grade as per design
label | d2ab4d88-5ac7-55b1-bc7a-d9af56a8d7fe |  | note | Acceptance Criteria - Grade of trench to be constructed as per design drawings and complys with NZTA F/3.
label | cb08c835-e549-5bb9-bcc0-8b3e7323e89b |  | note | ○ The compacted trench base must have a dry denmsity of 95% standard compaction before placing bedding.
label | e6849746-500b-5e65-9f0e-6b801dd6587f |  | note | ○ Where bottom of trench is existing ground, DCP test at 10m spacings prior to placing bedding. CBR > 2
label | 57c56402-7b24-5b25-8862-0e83fba0f1fc |  | note | ○ NZTA F/3 - 3.6 - Unsuitable Foundation Material.
label | 870e6846-d157-5bc4-bf73-7e3e6e33f191 |  | note | ○ Unsuitable material shall be removed to a depth of 600mm (or any greater) and replaced with approved material in layers of 150mm loose depth whch shall be compacted as specified in either the relevant standard or contract documents.
label | 16170ec2-197b-5c17-ae26-a0f2efbd6a5c |  | note | Verifying Document - Site Inspection Form, DCP Test Results
label | 653b4af6-5e96-5b04-8ba1-d46df5fd7c31 |  | note | Frequency - Prior to laying pipe
label | c49581e7-82eb-5b0e-a52a-cfa51d159e78 |  | note | Inspection Type - Witness Point
label | cd9d68ed-a8bc-5239-9e42-4849391c4bb3 |  | note | Inspection: Key - W
label | 23772f76-cab5-5c04-b54c-e87f5ce15f9c |  | note | Inspection: By - PM/PS/ER
checkpoint-status |  |  | checkpoint | 3.3.4 - Construction Inspection
label | a838e4ed-a2a9-5eb3-9d79-a80a6d2de934 |  | note | Inspection Point: Quality Control Activity - Visual inspection of completed drainage line including all attached structres
label | ea334c21-036e-5706-8422-c77b033eb5e5 |  | note | Acceptance Criteria - Engineer to inspect constructed drainage line for workmanship and defects prior to backfilling
label | a385f55e-821d-53df-b6d9-d4a9e43dffc0 |  | note | Verifying Document - Site Inspection Form
label | 7891c30d-06d4-5612-91bf-9b186e3b2d83 |  | note | Frequency - Once pre backfilling.
label | 48c04c82-a6b0-5f9e-befe-a44105118c82 |  | note | Inspection Type - Hold Point
label | b334f8bc-e01e-511b-be19-d9c96fabe435 |  | note | Inspection: Key - H
label | e543af1c-cd91-5861-a032-466ab48021ea |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3.5 - Bedding, haunching & cover
label | 23418e42-974c-50a0-8d5b-26b8377f3f96 |  | note | Inspection Point: Quality Control Activity - Visual inspection & density testing
label | ac54a756-d07d-5345-9a5f-0f87d87fb65c |  | note | Acceptance Criteria - Bedding material to be compacted to a density index of 70% or relative density of 95% OMC.
label | c01a4bad-2328-560f-a7a2-96f5ad449ecc |  | note | ○ Minimum embedment zone as per table
label | 1cc4ecbf-5d0b-50a6-9eed-4cf8c287e2ee |  | note | – – – – – – – – – – – – – – – – – – – – –
label | e6e7f828-59aa-57d6-9497-904bc75ed18e |  | note | Pipe OD mm ¦¦ Bedding below base of pipe mm ¦¦ Bedding above crown of pipe mm ¦¦ Bedding either side of the pipe mm
label | 953ccdfb-690a-5a10-a66b-1af072a37abe |  | note | – – – – – – – – – – – – – – – – – – – – –
label | e156d37e-57f1-5f90-bef5-a7799b6ad2dc |  | note | ≤600 ¦¦ 100 ¦¦ 150 ¦¦ 150
label | 5741f089-1cfa-5a36-9698-afa04a19e74a |  | note | >600 and ≤1200 ¦¦ 100 ¦¦ 150 ¦¦ 200
label | 87f83bed-4886-55cc-a17a-c62c16b0df88 |  | note | ≤1500 ¦¦ 150 ¦¦ 150 ¦¦ 200
label | 82a9ced6-3311-5b98-83cb-e13314ec0e7c |  | note | >1500 ¦¦ 150 ¦¦ 150 ¦¦ 250
label | 59706903-3a1d-58e1-9cda-d74b2018cabd |  | note | >1800 ¦¦ 200 ¦¦ 150 ¦¦ 300
label | bc6f2523-1eb5-5ba5-bca2-25e5ef49da83 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | f1332299-0b64-5c79-92da-44ff8168c386 |  | note | Verifying Document - Test Record & Site Inspection Form
label | dba0ee5e-dbfd-53b8-8a86-15e952c39a5b |  | note | Frequency - Once per drainage line
label | 175d5743-1b87-54a3-8987-f7dfdb315737 |  | note | Inspection Type - Witness Point
label | 32a82ce9-2ffc-5d78-a9a4-b5caf157d28b |  | note | Inspection: Key - W
label | 2a8b6b76-2b19-5c09-996d-6d673f510895 |  | note | Inspection: By - PM / ER
checkpoint-status |  |  | checkpoint | 3.3.6 - Survey As-Built
label | 2dd28256-f9e7-56f9-a965-dfb40a04c99b |  | note | Inspection Point: Quality Control Activity - Check relevant to design
label | 7e4179ee-62a2-5d63-a89b-60766e335903 |  | note | Acceptance Criteria - Constructed structures to be within design tolerence as per clause 402..4.3.
label | 0fba9ae5-7fa8-5b18-9d31-c19cdc97dc7b |  | note | ○ As-built data recorded and submitted to client.
label | b59aae1d-7e43-5afd-a458-7a99d8a6c2d0 |  | note | Verifying Document - Survey Files/As-built drawings
label | c59fa5c1-9cd4-5baa-9406-e6915225fa89 |  | note | Frequency - As required
label | 34a2bbb4-8bde-541c-8882-5d31bec2aff7 |  | note | Inspection Type - Hold Point, Action
label | cc614829-f388-54e5-8582-46d0c44fdf1d |  | note | Inspection: Key - H, A
label | a9bb1c49-58eb-54b6-9f0f-fd63f97b8e9f |  | note | Inspection: By - PM/ER, SV
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3.7 - CCTV & Hydrostatic Testing
label | d73c48ac-32b7-583c-8fa9-1746ddcbf672 |  | note | Inspection Point: Quality Control Activity - Pipes < 600mm diameter shall be hydrostatically tested and inspected by CCTV to identify any leaks or deficiencies in joints.
label | d97fd37e-29c5-5774-b450-f13e6716baa1 |  | note | Acceptance Criteria - No leaks or joint deficiences within pipe effecting operation.
label | ffdfed85-a160-5069-996c-894739363792 |  | note | ○ Closed-Circuit Television (CCTV) Inspection in accordance with the New Zealand Pipe Inspection Manual (latest edition).
label | ffa7ead0-7474-5280-946b-340783afec78 |  | note | Verifying Document - Testing certificate & CCTV Footage
label | 5eddf322-aefa-554e-8132-9ba7f89dc780 |  | note | Frequency - Once post construction
label | 72622305-603b-5c55-9af9-f1a010a018f8 |  | note | Inspection Type - Witness Point
label | 3cbcad6a-2bd1-5775-b7cb-d70e55d5fff1 |  | note | Inspection: Key - W
label | 7b5d0b48-681c-518b-b55c-8878abf98584 |  | note | Inspection: By - PM/ER
checklist-sectioned |  |  | checklist | F2LSIP - ITP 09 - Road Signs | itp |  |  |  | Yes | F2LSIP - ITP 09 - Road Signs | 2224a125-ff69-492e-a112-d6879ab63ecb
checkpoint-group |  |  | section | 9.0 - Road Signs
checkpoint-status |  |  | checkpoint | Road Signs
label | 191c91b2-440c-591c-9049-5221c7b9bb39 |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | 55e33445-64f9-5f02-9153-4deae7b538c0 |  | note | Acceptance Criteria - All below requirements are met and approved by ER
label | 92ef1f83-28b3-5735-bc84-782eac193051 |  | note | Verifying Document - Referenced Item numbers as below
label | 346862b7-b04c-5c43-89d3-bde195473058 |  | note | Frequency - Once post construction
label | fd3dd9d9-7020-59aa-bf4a-88935bfbff1a |  | note | Inspection Type - Hold Point
label | 35d44cf3-b3c0-560e-91af-3c6eaad633d9 |  | note | Inspection: Key - H
label | 393ee649-62cf-5c50-aa4e-2cea46b660e0 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9.1 - Materials
checkpoint-status |  |  | checkpoint | Materials / Retroreflective Requirements / Contractor's Signposts Design
label | 52bccfa9-61fe-5a9b-a12f-0e01a1919547 |  | note | Inspection Point: Quality Control Activity - Pre Installation - Compliance Check
label | 59773d31-6015-5627-b30c-56afa0da8a94 |  | note | Acceptance Criteria - All materials to comply with relevent clause under TNZ P24 2020
label | b861876e-b972-547b-92f4-851aa595a758 |  | note | ○ The minimum standard of retroreflection for signs shall be as detailed in Table 810.2 in the technical specifications
label | 5c465349-c2c6-5edb-a92b-dbe14f539150 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | eb4904e4-f4bd-5460-a498-5e6776a0a787 |  | note | TABLE 810.2: MINIMUM STANDARD OF SIGN RETROREFLECTION
label | 51f57b01-4672-5f23-af75-14dfa6cfcee0 |  | note | SIGN TYPE ¦¦ STANDARD OF RETROREFLECTION
label | 4ffb5d21-0d0b-5575-bd1f-d83b1a3aa15c |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 90fee082-2f3d-574a-9896-621cc006da1b |  | note | All signs with white or yellow backgrounds, such as regulatory parking and permanent warning signs ¦¦ Class 400
label | bf61601c-16ff-5dac-ac76-76fe6650a881 |  | note | All RG5 "Stop", RG6 "Give Way", RG-6R "Roundabout Give Way", RG-17 "Keep Left", and RG-17.1 "Keep Left Twin Disc" signs ¦¦ Class 900
label | 2f1b5eaf-ec7e-5580-9512-04e8384ed0a2 |  | note | All other regulatory signs ¦¦ Class 400
label | b4975bdd-2e6b-59fe-981c-70d74bbc8d02 |  | note | All ground-mounted information signs with a red, green, brown or blue background (guide, motorist service, and tourist signs) ¦¦ Class 400
label | c79d6dac-ec45-56b6-b514-806fca7ac877 |  | note | All Overhead Signs ¦¦ Class 900
label | 2309caff-230d-5063-a8f1-e61c46506217 |  | note | Chevron sign boards and single chevrons ¦¦ Class 400
label | a5882cad-3dd5-5ef0-826a-de0886e4d842 |  | note | Panels with white background for black-on-white signs with less than 30% black on the sign face ¦¦ Class 100
label | 99f2d4a5-b06e-5ed3-b51a-7060599f5796 |  | note | Belisha discs and red and white banded railway crossing cross-buck poles ¦¦ Class 400
label | 0f36b44e-64f9-5b30-bf60-3d885b4564d5 |  | note | Permanent warning signs and chevrons as instructed by the Engineer ¦¦ Fluorescent signs
label | 92fde45d-911b-507e-bf16-acada676f10c |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 7331ae6a-7c80-5bfc-8e04-3ea256f999cc |  | note | ○ The contractor shall design all signposts, poles and foundations in accordance to NZTA P4: 2020 and submit to the Engineer for Information and Review a month prior to installation.
label | 36683682-809f-5975-b7e1-ad4ea9aa8e6c |  | note | Inspection Type - Inspection / Review
label | cb38afa4-bc74-5387-95ca-438ad6f5266f |  | note | Inspection: Key - I / R
label | 81984c7e-681f-5887-8736-69a2e56c2242 |  | note | Inspection: By - PM/PS/ER
checkpoint-group |  |  | section | 9.2 - Installation
checkpoint-status |  |  | checkpoint | 9.2.1 - Delivery / Confirm Services
label | 015c3610-911c-5e56-90c1-c3126f1387ab |  | note | Inspection Point: Quality Control Activity - Inspection upon delivery
label | 32d4f710-ca3a-5d2e-844b-2d376a66c7d8 |  | note | Acceptance Criteria - Signs to be checked for any damage upon delivery, return to manufacturer if damaged. The Contractor shall confirm the location of all underground services within the vicinity of a ground-mounted sign prior to its erection.
label | 74bb9187-56a4-5441-a993-bc9eefcd0b9e |  | note | Verifying Document - Delivery Checklist
label | 1bb88942-2cdb-581e-98a3-8b1014d6d757 |  | note | Frequency - Once Per Delivery
label | 79e845ee-5bef-5a82-bb90-4396399af5f6 |  | note | Inspection Type - Check
label | 261e846b-d738-5d16-bc13-6519145dc2f8 |  | note | Inspection: Key - C
label | 46474144-f202-50c8-b5ce-37b5b68235c9 |  | note | Inspection: By - PM/PS
checkpoint-status |  |  | checkpoint | 9.2.2 - Positioning & Orientation
label | c2f85251-a58b-5ce1-8050-6315e76bcbf7 |  | note | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | 3ff46bf4-e233-5d2d-b055-a71e947d8ee8 |  | note | Acceptance Criteria - Positioning & Orientation to comply to TNZ P24 2020 Clause 7.3 & 7.4
label | e7f3c8c2-cfc5-556a-a430-d7b7080cbb33 |  | note | Verifying Document - Site Checklist Form
label | 2c4376f9-c6f2-567d-9051-d98ac5222c5d |  | note | Frequency - Once per sign installation
label | d4bc828e-ac7a-5340-997f-6d889e4b498b |  | note | Inspection Type - Inspection / Review
label | 34641350-53fa-52f1-ad30-49624345e575 |  | note | Inspection: Key - I / R
label | 21fe223d-ce3f-5df1-b2d7-e09258af1f7f |  | note | Inspection: By - PM/PS/ER
checkpoint-status |  |  | checkpoint | 9.2.3 - Sign Support Selection
label | aff9c75d-5f90-50e0-9195-12c63dc514cc |  | note | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | 0905c4c0-fc93-5e8d-b09d-01553d30af80 |  | note | Acceptance Criteria - Supports to comply as per TNZ P24 2020 - Table 7.1
label | 631a18fc-2b57-507a-a990-665091b16107 |  | note | Verifying Document - Site Checklist Form
label | 7e7ee7e1-ad75-5c6d-80cf-1400e8e603f6 |  | note | Frequency - Once per sign installation
label | 7e8caaf7-cc07-5c07-83f7-95fe467be464 |  | note | Inspection Type - Inspection / Review
label | 8a10d95e-0bd6-56e7-8559-f0d8eac40317 |  | note | Inspection: Key - I / R
label | 37f5ee3d-b32b-58e4-b930-d925b0edd3e6 |  | note | Inspection: By - PM/PS/ER
checkpoint-status |  |  | checkpoint | 9.2.4 - Foundations / Construction Records
label | 49bcfa6d-1d86-5a22-82b6-0e7939d8b279 |  | note | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | 7b656da3-8da2-5923-a64f-a21431dce306 |  | note | Acceptance Criteria - Foundations to comply as per TNZ P24 2020 Clause 7.7 Foundations. The contractor is to maintain construction records of each sign that clearly show that all posts, poles and foundation details comply with the requirements of the specification.
label | 3731ec94-b2ae-5e8d-8da2-9e34044e51c1 |  | note | Verifying Document - Site Checklist Form
label | ec8b0a03-c7b9-5b54-8e2e-dc71603c0d6c |  | note | Frequency - Once per sign installation
label | 03041349-741c-5786-87de-942fe0602ea7 |  | note | Inspection Type - Inspection / Review
label | 0674b17c-8b9b-5ecb-a838-3ce494aa4468 |  | note | Inspection: Key - I / R
label | 029898a6-b416-56ee-a60f-f5918a477bac |  | note | Inspection: By - PM/PS/ER
checkpoint-status |  |  | checkpoint | 9.2.5 - Daytime Survey
label | 50ade3fd-1b9f-5644-baca-0c6585c582c9 |  | note | Inspection Point: Quality Control Activity - Post construction survey
label | 4d212a77-1fc5-59f4-ab00-41e57a725fe4 |  | note | Acceptance Criteria - (a) The actual sign face is free of environmental soil such as mildew or lichen growth
label | cbec0af6-e9c6-5e7f-9afa-09abd1c795b3 |  | note | (b) No physical damage has affected or risked sign face readability and or sign integrity
label | fdbf108d-0eed-5bcf-af75-02eacf3f411d |  | note | (c) No vegetation or other structure impedes line of sight or visibility to the sign face
label | be873cc5-8e6e-5033-b8f5-02ca37479b9a |  | note | (d) The sign is free of any graffiti or the aftermath of previous poor cleaning action
label | 870480e5-7368-5736-9af8-e026b6de43f2 |  | note | (e) Sign supports and foundations are sound and maintain correct sign presentation
label | d998f2bf-2647-5c02-a200-0838f0a48a7d |  | note | (f) The need for the sign still exists – for example a speed reduction has not negated the need for a
label | 0bcd6d83-0271-5aab-895a-3b5fe10d7e20 |  | note | posted curve warning speed
label | a2bc6004-8f1b-5bf1-b8f1-0c62f0e77666 |  | note | (g) Confirming that the physical sign and its structure remain suitable for purpose or note that some repair should be undertaken
label | 6d9a5250-b882-5b60-8488-bbc6d37c593d |  | note | (h) Any fluorescent sign, deemed to require a higher level of day time visibility through its fluorescing colour feature, maintains a satisfactory performance e.g. Signs for active users (schools, pedestrians, cyclists).
label | 9bf4c43d-4320-5b7d-86fd-a6f04ea73b01 |  | note | Verifying Document - Survey Checklist
label | 7e7c5ea2-d7c2-5bc8-af5d-7dbf9d5bfa14 |  | note | Frequency - Once per completed section of works
label | 13174261-434d-5db1-ac7e-1d3d16b5f2e1 |  | note | Inspection Type - Inspection
label | 743ea973-0ef5-5b66-986c-fa6efbd7fb7c |  | note | Inspection: Key - Inspection
label | 6f91540d-88c5-5b3b-8277-6696af5aaece |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 9.2.6 - Nighttime Survey
label | a4031a68-021b-551e-8eda-c7448a36b563 |  | note | Inspection Point: Quality Control Activity - Post construction survey
label | 065bd43e-9c0f-50f3-8c99-6cfe7bf1d2f2 |  | note | Acceptance Criteria - (a) Overall any sign or part of a traffic sign (eg guide sign), especially when set in a disadvantaged position, is performing suitable for purpose, exhibiting an even level of retroreflectivity across the face of the sign to ensure that an appropriate level of readability is achieved across the entire sign throughout the approach
label | db0526f1-b7d4-5076-93b0-a50ea06ea450 |  | note | (b) The orientation of the sign face is such that no specular (mirror) retroreflection creates an over bright glare effect that interferes with sign recognition/readability
label | 572f0424-028a-5d2d-bd7d-6a90cb3f05f1 |  | note | (c) At the threshold of retroreflectivity the traffic sign presents a level of visibility that ensures a driver becomes aware the sign is present – before actual readability is possible
label | 2c677f1c-6045-5c13-b4ed-8b28c5cb8130 |  | note | (d) That any previous maintenance completed during daylight hours has not damaged retroreflectivity at night – for example poor graffiti cleaning
label | b56ac1e0-7c56-5dab-b776-88ecc7def308 |  | note | (e) Traffic signs remain fully effective and suitable for the purpose for which they were installed
label | a520fbd8-999c-5fe8-b46d-eef5966a3c7e |  | note | Verifying Document - Survey Checklist
label | 0f796e09-b93b-5463-a4aa-cb8c7e607679 |  | note | Frequency - Once per completed section of works
label | 47708389-8076-53c3-b06d-d15570da684a |  | note | Inspection Type - Inspection
label | 4dda9212-1e4f-5d42-a37a-feedfd2f7805 |  | note | Inspection: Key - Inspection
label | fcd9d655-0753-5554-8af6-c550703fdaef |  | note | Inspection: By - PM/ER
checklist-sectioned |  |  | checklist | F2LSIP - ITP 10 - Rip Rap | itp |  |  |  | Yes | F2LSIP - ITP 10 - Rip Rap | 34bdbf07-26c5-462b-9621-a5f534d7fb5f
checkpoint-group |  |  | section | 10.0 - Rip Rap
checkpoint-status |  |  | checkpoint | Rip Rap
label | a05dcd5f-121d-59a6-bd2c-2d499891098c |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | 12bd98c4-4035-527e-809a-be13de9bfbb4 |  | note | Acceptance Criteria - All below requirements are met and approved by ER
label | 4e807d86-6cad-5d28-90ba-a7444875d8cc |  | note | Verifying Document - Referenced Item numbers as below
label | d5227873-fe0f-57fc-97fa-72b34a83d08f |  | note | Frequency - Once post construction
label | 0a297c85-1b36-5931-baef-2a6de50c2c8d |  | note | Inspection Type - Hold Point
label | 2ede9988-40de-55b3-bfc1-f1beee6a8066 |  | note | Inspection: Key - H
label | fe1a9dc9-002a-5c11-af0f-8f1d7c361498 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10.1 - Source Properties
checkpoint-status |  |  | checkpoint | 10.1.1 - Density
label | ae01e90c-4d1c-5ef5-afc4-123464305952 |  | note | Inspection Point: Quality Control Activity - Material Compliace Check
label | 90a441fd-9c4b-5b82-81cd-9413a2987bd6 |  | note | Acceptance Criteria - Density > 2.6t/m3 when tested in accordance with NZS 4407 1991 Test 3.7.2
label | d53331ab-341e-5594-9039-2ec9e1510e91 |  | note | Verifying Document - IANZ Lab Report
label | d6202af9-8125-523f-81bb-1bdba7f764ad |  | note | Frequency - Once per supplier
label | bf82827d-3de9-5b95-9c2e-0fb8f27055de |  | note | Inspection Type - Hold Point
label | 4d5379e4-715c-5eea-9f8a-2db0eb09124b |  | note | Inspection: Key - H
label | 03b4fa97-4c24-5bd9-acec-b8cb7681aac6 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1.2 - Crushing Resistance
label | a2478667-2c36-5410-a1dc-7b70732a6097 |  | note | Inspection Point: Quality Control Activity - Material Compliace Check
label | c465d5bf-0c47-53c6-8af7-9522ed160fa8 |  | note | Acceptance Criteria - CR > 150kN when tested in accordance with NZS 4407 1991 Test 3.10
label | 24698ff5-59d5-5090-bcd2-970a206dcfdf |  | note | Verifying Document - IANZ Lab Report
label | 53151093-6641-5596-88d4-3780ad6c9fa8 |  | note | Frequency - Once per supplier
label | bda6100c-cfcb-56db-85c6-08466ea45207 |  | note | Inspection Type - Hold Point
label | 2e7af380-54e7-5666-9910-398250d2db70 |  | note | Inspection: Key - H
label | 8b6c1a9d-3727-5b63-8b06-f4941a330ec7 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1.3 - Weathering Classification
label | 432efbcb-ee03-50f9-846e-e41b14ed6d71 |  | note | Inspection Point: Quality Control Activity - Material Compliace Check
label | 328856ee-afdb-5e49-8642-6afaa7396782 |  | note | Acceptance Criteria - AA, BA, AB or BB when tested in accordance with NZS 4407 1991 Test 3.11
label | 97941ad3-601f-56fb-b7e4-0eb75df358dc |  | note | Verifying Document - IANZ Lab Report
label | 9d202b22-4e7d-57cd-9bfd-739961be1917 |  | note | Frequency - Once per supplier
label | 40f278f1-7c2d-5c55-bcf5-e1c4a4265684 |  | note | Inspection Type - Hold Point
label | 98b00730-e249-527f-89f4-6971cdbee9e0 |  | note | Inspection: Key - H
label | 830106f2-d129-57e3-bd7b-4f3fa3924bc2 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1.4 - Abrasion Resistance
label | 9b435f6b-4f9e-5a8d-a90a-d9797985f599 |  | note | Inspection Point: Quality Control Activity - Material Compliace Check
label | ec647349-c63e-51da-abd8-e6012b60c3b6 |  | note | Acceptance Criteria - AR ≤ 26% when tested in accordance with NZS 4407 1991 Test 3.12
label | d5e7a90e-68dc-5911-9c57-95bd062bbf85 |  | note | Verifying Document - IANZ Lab Report
label | c5bc3c2b-ad3c-5623-9881-f4ae25530401 |  | note | Frequency - Once per supplier
label | 4248c4e6-c795-5bec-982c-2025d7c976e0 |  | note | Inspection Type - Hold Point
label | 70886a4a-1d08-5f5a-916f-81e4f2e3b486 |  | note | Inspection: Key - H
label | 6f197de5-ea51-5170-a924-d57419378bd4 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1.5 - Visual Check
label | 6ef36f21-9724-50b9-9b88-1914f7ca2517 |  | note | Inspection Point: Quality Control Activity - Material Compliace Check
label | 7a0e2a58-a1c4-524e-9cbc-752baac0271c |  | note | Acceptance Criteria - Rock shall be free from calcite intrusions and shall not be broken concrete or asphalt.
label | ff73db97-183b-5f09-bc82-895fd45cae04 |  | note | Verifying Document - IANZ Lab Report
label | 2b4b2c0e-229a-5f75-8374-db58cfadbeeb |  | note | Frequency - Once per supplier
label | 64b09954-2840-5ffd-8173-e0719b20852a |  | note | Inspection Type - Hold Point
label | f5ee3270-a03d-5094-ac77-7ead0d64f776 |  | note | Inspection: Key - H
label | b0aea0f9-175b-51cc-a6cb-f6af2c50c89d |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10.2 - Production Properties
checkpoint-status |  |  | checkpoint | 10.2.1 - Grading
label | f7d3c702-7f71-5293-a03d-1d265b21a7c6 |  | note | Inspection Point: Quality Control Activity - Material Compliance Check
label | ad423a68-50bc-5766-9129-abcb31766c7b |  | note | Acceptance Criteria - Rock shall be nominal D50 size shown on the drawings and shall be well graded as follows.
label | f12b40b2-dcdb-58cd-a803-592c857b18ff |  | note | – – – – – – – – – – – – – – – – – – – – –
label | d7e6750a-ff81-5d29-9398-c2234b2bd85d |  | note | Stone Size Range (m) ¦¦ Stone Weight Range (kilograms) ¦¦ % of Gradation smaller than
label | 101a5fc6-89e8-5e11-be41-49ad32eb62cf |  | note | – – – – – – – – – – – – – – – – – – – – –
label | c4473bc3-cfd4-5b1b-b20c-f9c3a6a604e6 |  | note | 1.5 D50 to 1.7 D50 ¦¦ 3.0 W50 to 5.0 W50 ¦¦ 100
label | e29bc9b2-1400-5515-8632-08dd9e167767 |  | note | 1.2 D50 to 1.4 D50 ¦¦ 2.0 W50 to 2.75 W50 ¦¦ 85
label | 1b7a1127-3699-5c11-92b0-2d6ff9a0a114 |  | note | 1.0 D50 to 1.4 D50 ¦¦ 1.0 W50 to 1.5 W50 ¦¦ 50
label | 73a173d8-9bad-555c-8613-3a1df8e47951 |  | note | 0.4 D50 to 0.6 D50 ¦¦ 0.1 W50 to 0.2 W50 ¦¦ 15
label | 6d539edc-d6c9-5848-b670-5323a2fe1abf |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 516c84e4-ebf4-54e0-882a-0d7d116e577a |  | note | ○ Please Add Bidim and AP150 Material Approval
label | a0ce0b10-5c04-56a8-93cb-129089328d59 |  | note | Verifying Document - IANZ Lab Report
label | 4bcea549-d6e4-5ee6-b135-97705bbbfc61 |  | note | Frequency - Once per supplier
label | 7182b3e0-efa7-5f5e-b061-747f63ce48e7 |  | note | Inspection Type - Hold Point
label | f1ee6039-e38b-56de-8a92-4e8148e252c3 |  | note | Inspection: Key - H
label | 796f5e57-2318-5b6f-a904-bcc123e9eb4c |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10.3 - Placement
checkpoint-status |  |  | checkpoint | 10.3.1 - Filter Cloth
label | baf8df3f-0086-5b40-ac76-3359338d3ea0 |  | note | Inspection Point: Quality Control Activity - Pre placement inspection
label | 745798e7-8da6-5afb-9e1a-6610c5048fbf |  | note | Acceptance Criteria - Filter cloth to be placed and securly pegged prior to placement, material to comply as per NZTA F7.
label | aab3e804-d1e7-58a8-869c-162553b7dc7a |  | note | Verifying Document - Site Checklist Form
label | f4a9aebc-0803-54b9-83cb-3549f12702c3 |  | note | Frequency - Once per Rip Rap bed
label | 802ba8d5-6f40-5935-8cdb-a644e265b8e8 |  | note | Inspection Type - Inspection / Review
label | 3eec357b-72ad-53bf-ae3e-60f7cd67046c |  | note | Inspection: Key - I / R
label | fb107bba-d2e4-5b66-985f-d289998517db |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 10.3.2 - Rock Placement
label | 16652594-ec74-5751-898f-8f52acb72bd7 |  | note | Inspection Point: Quality Control Activity - Post construction inspection
label | 272d3cab-32a4-5c13-b267-bac0cdc41faf |  | note | Acceptance Criteria - Rip Rap to be placed by machine or hand and not dumped.
label | 030188aa-4b0b-5ada-be53-03771c53d87b |  | note | ○ Placing to begin from the lowest point of bed in an unwatered state.
label | 32a236bf-975a-57e6-9f27-17dbeeab8206 |  | note | ○ No deformation of underlying surface during placement.
label | a179f19b-f34d-5ba1-8cba-fa44463606a4 |  | note | ○ Rocks should be placed so as not to deviate the bed/channel grade from the design drawings.
label | 0864100b-c4c9-5db8-8b99-7f1cdb741618 |  | note | ○ Rocks to be evenly distributed in size to lock togeather and minimise voids.
label | 21984c54-aebb-5400-9ace-d9804c954caf |  | note | Verifying Document - Site Checklist Form
label | d1d59b26-8b63-5c2d-910a-1d74fafa23da |  | note | Frequency - Once per Rip Rap bed
label | 150d185b-2f41-54c1-890b-a85a448a3961 |  | note | Inspection Type - Inspection / Review
label | 5093d86c-12ed-5243-9d39-c8d4b9f1c66d |  | note | Inspection: Key - I / R
label | 752049db-09e3-5c67-83f8-eaae070bfc83 |  | note | Inspection: By - PM/ER
checklist-flat |  |  | checklist | F2LSIP - ITP 01 - Documentation and Planning | itp |  |  |  | Yes | F2LSIP - ITP 01 - Documentation and Planning | 69b411ff-e7ba-4b03-a9a2-2ceea0d27445
checkpoint-status |  |  | checkpoint | 1 - Documentation and Planning
label | 2ff0d254-1d12-5c7d-8e1a-7d885dd6e855 |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | 09a2dc6c-8ac4-5e2d-929f-5af0dba72918 |  | note | Acceptance Criteria - All below HP Closed
label | ba0f3a80-ad5d-5a47-9e4a-7ae7542dc92d |  | note | Verifying Document - Referenced Item numbers as below
label | f96bf5eb-948d-5c6a-a34f-6d5e7522dc52 |  | note | Frequency - Once prior to works commencing
label | 43b47498-d564-5d84-8b9c-2066eb3e58aa |  | note | Inspection Type - Hold Point
label | f61173e3-6f88-51c3-8faf-a5629114dd84 |  | note | Inspection: Key - H
label | da2674d5-5b48-530b-b457-dbac2dafbd62 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Contract Obligation
label | 6f4c78ee-5869-53dd-a981-869239ef2a3c |  | note | Inspection Point: Quality Control Activity - Project Management Plan
label | 93f04f8b-10e3-5cd6-bb80-cdf346e7c7cf |  | note | Acceptance Criteria - Approved by CR
label | c1cfd858-2483-5ff8-88f5-1c124658b5e0 |  | note | Verifying Document - Signed CP
label | 653d4614-bb09-571e-b9e3-7b1e40c2eb83 |  | note | Frequency - Prior to Work Commencing
label | 9cbf1e48-eb2f-5c22-a742-aefa50f7673c |  | note | Inspection Type - Review
label | 801fa0e9-9673-5256-b7df-6cdc9c04abf3 |  | note | Inspection: Key - R
label | 87905d02-4eec-5082-ab7d-1fa99c9bef1f |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 1.2 - Contract Obligation
label | ed3d0f90-e067-557c-83a0-b4a12878fc00 |  | note | Inspection Point: Quality Control Activity - Health and Safety Management Plan
label | 9bea3519-5c91-5ade-8379-4d9aa7d4bedc |  | note | Acceptance Criteria - Approved by CR
label | bad3f088-0d9e-59da-af73-6b13476fee0a |  | note | Verifying Document - Signed HSMP
label | 0491f5d7-677b-5e5a-8d5b-c58ea489c133 |  | note | Frequency - Prior to Work Commencing
label | 2f2a50a1-87c0-5cad-a263-16d0e7cfef80 |  | note | Inspection Type - Review
label | c759ab7e-a4f1-5c41-b286-4a575d9343f3 |  | note | Inspection: Key - R
label | fb0d1604-b5fe-56d2-afd4-e7c728208666 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 1.3 - Contract Obligation
label | db9b29d2-53f7-55db-8474-4fdf43462721 |  | note | Inspection Point: Quality Control Activity - Quality Management Plan
label | d9757541-bbdf-586f-a3de-1c06373cdbcd |  | note | Acceptance Criteria - Approved by CR
label | 55f4538b-a243-535a-96e9-89934c84f96e |  | note | Verifying Document - Signed QMP
label | 79b6688c-a644-5a24-a8f4-401f16b1d323 |  | note | Frequency - Prior to Work Commencing
label | ae5ecd62-2fd4-5e81-a657-5421ef16a181 |  | note | Inspection Type - Review
label | b658ee8a-e80d-5ea8-a694-d30a86a6a613 |  | note | Inspection: Key - R
label | d6f4cbdb-fb27-5715-a61f-b44193290aad |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 1.4 - Contract Obligation
label | 94747fa6-0738-5d15-8a2d-63a3575082e0 |  | note | Inspection Point: Quality Control Activity - Communication Management Plan
label | 5734ba30-045f-5a59-a3da-86ae96c55a65 |  | note | Acceptance Criteria - Approved by CR
label | 63731e7c-81bc-59b8-bf38-a13e770f5339 |  | note | Verifying Document - Signed CSCMP
label | 77011a54-6ac2-5db7-abac-85156092875d |  | note | Frequency - Within 2 weeks of physical works commencing on site
label | eb72feae-ad4c-5c3c-a685-99bcbcc9d63b |  | note | Inspection Type - Review
label | a806029b-85a0-5443-be35-2450fc4c2dcb |  | note | Inspection: Key - R
label | 9b55ef3f-168f-5c77-8fe6-d3c5ff9c0ef7 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 1.5 - Contract Obligation
label | d9971d5a-7b5e-54df-9e07-97be70578914 |  | note | Inspection Point: Quality Control Activity - Environmental Management Plan
label | ee54f080-d9e4-589e-8166-dcae3f4ff591 |  | note | Acceptance Criteria - Approved by CR
label | 9c93574a-5ce0-5fdf-bd27-34c7ac73f977 |  | note | Verifying Document - Signed ESMP
label | 8e2d26f4-f9d7-5664-995e-d2ff62e270c0 |  | note | Frequency - Within 2 weeks of physical works commencing on site
label | be094b09-daf9-5bc9-a79f-1f92bb409eac |  | note | Inspection Type - Review
label | ea5c0d62-f662-52b4-80c5-b95042a1a4ae |  | note | Inspection: Key - R
label | f50df831-be6a-5aa4-9806-ac81f3f06713 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 1.5.1 - Contract Obligation
label | ac14ccb3-ac82-546a-a665-20f8d766f655 |  | note | Inspection Point: Quality Control Activity - Sediment Control Plan
label | bb5ff7c9-32af-5f6e-990d-d057b9d8b213 |  | note | Acceptance Criteria - Approved by CR
label | 86052151-afdb-5bd7-add3-85c86c3e3d3d |  | note | Verifying Document - Approved Control Plan
label | 5d40f3cd-93f0-5d4d-a2c4-14d8ac3e169e |  | note | Frequency - Prior to Work Commencing
label | 5467c879-15a8-5ca9-9159-c51327bb05d8 |  | note | Inspection Type - Hold Point
label | d47e8649-7be0-5a2a-87ae-5ce891e8baee |  | note | Inspection: Key - H
label | 17dbf1bc-5a18-526e-8a3f-c220d720f628 |  | note | Inspection: By - PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Contract Obligation
label | 0f5a5a30-1b4a-5750-ae07-cb8a40801a49 |  | note | Inspection Point: Quality Control Activity - Inspection and Testing Plan
label | 7d244bea-42a3-5e8a-98f5-2e37d0a7b5dd |  | note | Acceptance Criteria - Approved by CR
label | 5f12f290-e90d-5f15-8f19-c89ca77c3ea7 |  | note | Verifying Document - Approved ITP
label | 838f30ff-934d-5de4-8a4b-e171f2b1d880 |  | note | Frequency - Prior to Work Commencing
label | f9fe1cf6-5b8e-50b5-9024-cadf66666564 |  | note | Inspection Type - Review
label | 46855a41-f76d-5387-b835-469b57b2cf35 |  | note | Inspection: Key - R
label | 7710883d-8495-59a7-9936-bcf81aeb3d3c |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 1.7 - Contract Obligation
label | 1daac751-ea05-5c2b-89ee-4f3d87c03733 |  | note | Inspection Point: Quality Control Activity - Traffic Management Plan (TMP)
label | 528960f3-60c1-5431-be0e-31063f5d8e8b |  | note | Acceptance Criteria - Approved by TMC & CR
label | 27798c86-f72d-5a36-ad53-03168e8ef71d |  | note | Verifying Document - Approved TMP
label | 4c097c2c-1ea0-5e29-95a4-6a93a4f7145d |  | note | Frequency - Prior to Work Commencing
label | b1a233d8-7d9a-589e-b0d8-80d0e49c4bca |  | note | Inspection Type - Hold point
label | 5e0b0570-5d88-5e90-a915-dfa4f7cd1ef8 |  | note | Inspection: Key - H
label | 8b68babb-bdb2-5ff7-84ee-8b0205137ba9 |  | note | Inspection: By - PM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Contract Obligation
label | 08e7a151-e15f-5a67-acee-7d60e75f2554 |  | note | Inspection Point: Quality Control Activity - Construction Programme
label | 2ea5ffee-ec95-5848-8926-d028a3348e10 |  | note | Acceptance Criteria - Approved by CR
label | 50f049d6-7dc0-5687-a01c-c2d18dbf93cf |  | note | Verifying Document - Gantts Bar Chart
label | 1d05bddb-e07d-50b1-ac01-da7e413acae3 |  | note | Frequency - Prior to Work Commencing
label | 5d262fde-bd20-580c-8bf7-2e8ceca9a2fe |  | note | Inspection Type - Review
label | 20cad59f-6db5-5ce1-8326-8527fb7fd07d |  | note | Inspection: Key - R
label | c6e43567-6c3d-5cab-bf95-f725f781dd92 |  | note | Inspection: By - ER
checklist-sectioned |  |  | checklist | F2LSIP - ITP 11 - Concrete | itp |  |  |  | Yes | F2LSIP - ITP 11 - Concrete | 77404007-858c-45f3-9ca7-5124c893aeec
checkpoint-group |  |  | section | 11 - Drainage
checkpoint-status |  |  | checkpoint | Drainage
label | f84bb202-bf54-5e17-95e5-c3a2df607818 |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | 918ac157-8c1b-59d8-af99-a8aaa9934a58 |  | note | Acceptance Criteria - All below requirements are met and approved by CR
label | cb55d358-33f6-5b26-a92c-af18bc115f30 |  | note | Verifying Document - Referenced Item numbers as below
label | c11f2f52-d8ac-5a0f-9036-cb508b6aa166 |  | note | Frequency - Once post construction
label | 1d0dac1a-ba9f-55ca-b149-b57f802681ca |  | note | Inspection Type - Hold Point
label | 826327ba-5943-5b55-b117-bc3a2d412ef6 |  | note | Inspection: Key - H
label | 74e170d6-fb80-58a9-a956-8922b4d64a8c |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 11.1 - Materials
checkpoint-status |  |  | checkpoint | 11.1.1 - Plant Mix Concrete
label | 8be2d7ee-ba03-5d7f-9d92-ab163f5cb61e |  | note | Inspection Point: Quality Control Activity - Mix Design Review
label | cd21c3c4-6a81-5c8e-855f-9ac127f5f3ea |  | note | Acceptance Criteria - Meets Project TS 1 412.2 requirements and relevant mPa as required on drawings
label | d3d73ca5-d0ca-59ea-99a9-c57095c6767e |  | note | Verifying Document - Manufacturers Certificate
label | 38306266-1f9f-5cb9-9b51-f5dc99e785dc |  | note | Frequency - Prior to Pour
label | 82604f75-c2df-5da3-b2c1-d906abfa2e91 |  | note | Inspection Type - Review
label | 95d503d2-00ce-59e3-bad7-b1ac55d0d9b5 |  | note | Inspection: Key - R
label | e6651d04-d500-5366-afef-a0dbdd11012c |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 11.2 - Construction - In accordance with NZTA F/3 & NZS 3725
checkpoint-status |  |  | checkpoint | 11.2.1 - Pre-Pour Inspection _ NIB, Kerb & Dish Channel
label | 86bc7a47-d453-5abb-b877-028fd79581fb |  | note | Inspection Point: Quality Control Activity - Onsite Inspection and testing:
label | 25c087e2-a0dd-556f-b688-613ee92a5cff |  | note | ○ Witnessed Proof Roll
label | 92d38dbb-834d-504e-8384-951ec7401528 |  | note | ○ Clegg Testing
label | d9b8d22c-bbdc-5edc-a57f-2ec723f2d721 |  | note | Acceptance Criteria - Proof Roll shows no undue movement in Subbase
label | b55940af-ed62-5c0f-afed-a9cc1bb74213 |  | note | ○ Clegg Results > 20
label | a970c421-ec1c-5a14-ba92-39eb017119bd |  | note | ○ String Lines inspected by engineer onsite and approved.
label | caeeeb9d-bb66-5e48-ac78-a97f6319d309 |  | note | Verifying Document - Site Inspection Sheet and Clegg Record
label | 4f561ef0-a769-5413-8323-2cc9f4d61805 |  | note | Frequency - Once prior to each pour
label | d30ce0d7-48a7-5481-ab58-f9c02d4bf4fa |  | note | Inspection Type - Hold Point
label | 3e01f0de-f737-5f45-b5e2-66f4d98deda3 |  | note | Inspection: Key - H
label | bd8de394-beb1-5bd6-8a6a-95c1ae9a419d |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2.1 - Pre-Pour Inspection _ Roundabout & Central Island
label | 0c12e99b-81e5-5fe3-969b-656a5241c681 |  | note | Inspection Point: Quality Control Activity - Onsite Visual Inspection
label | a85b00d3-574b-5546-9300-f290315ec0aa |  | note | Acceptance Criteria - Visual Inspection of prepped surface showing tight uniform surface. All Subbase Pavement requirements passed as per ITP 4
label | cb7e405a-bff2-5cb5-9b17-f036aa4a2e08 |  | note | Verifying Document - Site Inspection Sheet and ITP Requirements
label | a2977501-7036-57cd-b719-3b4a4930befb |  | note | Frequency - Once prior to each pour
label | c9070c41-28df-55a6-afef-b9e5febb5589 |  | note | Inspection Type - Hold Point
label | ed4f891a-a4d4-5351-adcf-3b0b53f98128 |  | note | Inspection: Key - H
label | ca04b2e7-b283-511f-9f92-80cb75adf97c |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2.2 - Pre-Pour Reinforcing & boxing Inspection
label | 5a39df4c-f886-57d4-9383-de292e4f4963 |  | note | Inspection Point: Quality Control Activity - On-Site Visual Inspection
label | 9fa9bdac-2f45-54d3-b3bd-52ef52bcea6e |  | note | Acceptance Criteria - Reinforcing to be placed as per design with applicable cover as per TS1 and relevant specifications.
label | 1b62feaf-b778-5f72-ba86-4315ef143e6d |  | note | ○ Boxing to be set to design to ensure correct grade as per design.
label | d9e03c8b-1402-5578-9083-7eadb60513c6 |  | note | Verifying Document - Site Inspection Sheet
label | 50282c48-2a0d-5cec-a72a-c9c1cafa837b |  | note | Frequency - Once prior to each pour
label | 668dbf4c-ab84-5ab7-867e-0ef21425c398 |  | note | Inspection Type - Hold Point
label | 29f7a16f-9511-55cc-959e-d10390a9d2b3 |  | note | Inspection: Key - H
label | 29659ea8-1107-5ef8-8f0f-603b75100efb |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2.3 - Material Delivery
label | 4cf2b563-d9ea-5239-a320-cfde3cafbc4c |  | note | Inspection Point: Quality Control Activity - Maintain a delivery record for each batch of ready mixed concrete delivered to the works
label | 2176f3af-7f6e-5201-a558-68e4b58e586f |  | note | Acceptance Criteria - Concrete Dockets provided showing product delivered matches design as required.
label | cfde7525-8713-52a0-88bd-59a31c294cc9 |  | note | Verifying Document - Concrete Truck Docket
label | c39d78dc-c82d-50b0-94a3-279f1bb2858e |  | note | Frequency - Per Truck
label | b7243496-9c58-5239-b256-e3a7d7fe8c0d |  | note | Inspection Type - Witness Point
label | bab8d55e-1ed7-5a20-80f2-bb4035889752 |  | note | Inspection: Key - W
label | 39336e90-bb2c-5fd2-9b2d-c4cbe710ef01 |  | note | Inspection: By - PM/PS
checkpoint-status |  |  | checkpoint | 11.2.3 - Concrete Joints
label | 830c73e4-6f9f-5401-aad1-4a3ed902e7dd |  | note | Inspection Point: Onsite Visual Inspection
label | ab700fdb-7bba-50c7-bfca-d1348a1d4b0c |  | note | Acceptance Criteria - Construction/contraction joints to be constructed as per design and TS1 Specifications. Machine laid kerb and channel - Contraction Joints formed every 5m. Saw cutting within 24hours. Concrete Island Infills - Contraction Joints formed every 5m.
label | f5ce4816-8397-5fc3-9908-30686b77952e |  | note | Verifying Document - Site Inspection Sheet
label | 510519cb-d034-59c4-a611-8a7f279762e5 |  | note | Frequency - Post Construction
label | 8f55c8ad-cf7b-5f33-9530-653b24918b2d |  | note | Inspection Type - Witness Point
label | 86ea5a31-9dfb-595c-b0b9-2132c1ec7c07 |  | note | Inspection: Key - W
label | b0dfab2a-2213-58fc-be50-046474851612 |  | note | Inspection: By - PM/PS/ER
checkpoint-status |  |  | checkpoint | 11.2.4 - Survey As-Built
label | 4785a50f-359e-5dce-89cb-0d7f9b364be4 |  | note | Inspection Point: Quality Control Activity - Review of Data
label | 3815705c-d9b0-5ace-aeb0-760c798b2e15 |  | note | Acceptance Criteria - As-Builts show construction as per design, within tolerences set out in TS1 and relevant specifications.
label | 17b07d83-0c8e-5d76-9c16-bf6184431b7f |  | note | Verifying Document - As-Built 3d Data File
label | dcdd1417-ff9c-55c2-957d-1ca5ee3f7e0f |  | note | Frequency - Post Construction
label | 4d41a655-bcd1-531f-981f-661aff887a62 |  | note | Inspection Type - Hold Point
label | 1ad05f85-f067-5c59-ae04-9195792b2f19 |  | note | Inspection: Key - H
label | eec713be-4b37-5817-9ac5-3e9150d822fb |  | note | Inspection: By - PM/PS/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.2.5 - Post Construction Inspection
label | 40aa2a3b-5927-5ce0-b940-676cb629c15d |  | note | Inspection Point: Quality Control Activity - On-Site Visual Inspection
label | ac9dce5f-7e57-5159-88db-2851b419e33a |  | note | Acceptance Criteria - Finished concrete to be uniform and free of defects. Concrete Island Infill shall have a Class U5 Broomed Finish
label | 2913355a-9163-55c8-b2b4-7ea2cac2389e |  | note | Verifying Document - Site Inspection Sheet
label | 5364f7f1-02a3-5668-a897-2a27273c13be |  | note | Frequency - Post Construction
label | 361ac030-2cb8-5d19-a526-b1a419220a6a |  | note | Inspection Type - Hold Point
label | e03dfd2c-ca14-5fc7-9447-a987a751c847 |  | note | Inspection: Key - H
label | 071b0bae-05fa-5814-9a7e-d104f632d1ab |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 11.3 - Material Testing
checkpoint-status |  |  | checkpoint | 11.3.1 - Control tests from concrete plant
label | a0996f15-d9cc-5d26-80ce-10bf2ec07cfb |  | note | Inspection Point: Quality Control Activity - Project Technical Specification 13.10.7.4 & NZS 3104
label | 45f874d3-b7ae-581c-9902-2941ccddaaa5 |  | note | Acceptance Criteria - Test result by Ready-mix supplier
label | 9f96e56e-e3e7-515a-a535-5a2dadce5690 |  | note | Verifying Document - Prior concreting
label | 268e2832-6b85-516e-81d3-f999f860e824 |  | note | Frequency - Throughout Construction
label | be05fc90-5f47-5545-84f3-ec129dac4867 |  | note | Inspection Type - Hold Point
label | 6d97e3ce-d5bd-5c04-ab34-72b2dc76f31f |  | note | Inspection: Key - H
label | a9cd8268-7915-5bac-9d94-97bb301ecc63 |  | note | Inspection: By - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.3.2 - Compressive strength Test
label | b65df728-4e5f-50e3-b0cd-1b7c40c93f63 |  | note | Inspection Point: Quality Control Activity - Project Technical Specification 13.10.7.4 & NZS 3112
label | 5bbe5deb-77df-50a1-aad5-01b8d596e032 |  | note | Acceptance Criteria - Test Results from IANZ registered Laboratory. Cast in Channels: >20MPa Machine Laid Kerb and Channel: >25MPa Concrete Island Infill: >20Pa
label | ef7bf9d9-4b5e-5758-8e3a-726fa0c4ac55 |  | note | Verifying Document - During concreting
label | cdcbd2a4-70ec-576d-bf26-3ee3c3c4aeed |  | note | Frequency - One test per 50m3
label | f5226e81-869d-5876-b3d9-3d1ac944b00e |  | note | Inspection Type - Hold Point
label | 34d12ba4-20f7-5d75-a7f1-62ae8114b5e4 |  | note | Inspection: Key - H
label | 5ea4f443-e265-5382-b022-b0d32128ca7e |  | note | Inspection: By - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11.3.3 - Slump Test
label | d501e269-c632-5765-a259-7290f05f8d8a |  | note | Inspection Point: Quality Control Activity - Project Technical Specification 13.10.7.4 & NZS 3112:Part 1
label | 2dd75ff7-8832-5cdc-8ac9-6438d912635e |  | note | Acceptance Criteria - Test Results from IANZ registered Laboratory.
label | a6fe8810-69df-52aa-9d88-0d21a3097cf9 |  | note | Verifying Document - During concreting
label | 2c6761e2-4034-5eac-b1d6-0fab401e9f78 |  | note | Frequency - One test per 50m3
label | 6dfc48a2-4121-58fb-80d5-1ee557076933 |  | note | Inspection Type - Hold Point
label | 6027c5a6-b596-5410-bf1e-cd2b4b32f3b6 |  | note | Inspection: Key - H
label | 7c81e961-5242-5fda-a4c9-2636b13fb071 |  | note | Inspection: By - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | F2LSIP - ITP 06 - Road Barriers | itp |  |  |  | Yes | F2LSIP - ITP 06 - Road Barriers | 7dde947d-7988-4d6c-a73d-2cadca3f7556
checkpoint-group |  |  | section | 6.0 - Barriers
checkpoint-status |  |  | checkpoint | Barriers
label | b51debaf-5dd8-56ea-a144-59e012db7f8d |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | 1a5d8fe5-9f15-5ff7-9c32-589e8fa67c0d |  | note | Acceptance Criteria - All below requirements are met and approved by ER
label | 47386a93-2f76-53ac-aa0c-1744b62cdb97 |  | note | Verifying Document - Referenced Item numbers as below
label | 8ae2a1ca-4049-5862-a1cb-760e5faad2a8 |  | note | Frequency - Once post construction
label | 9b1d066b-92e0-5711-850c-5de2fb7fbac3 |  | note | Inspection Type - Hold Point
label | 8b9891cf-aedf-54fa-9d2b-d8a068c6b48f |  | note | Inspection: Key - H
label | 23a7bcbb-3527-575b-8c49-8c5dddc1ddaf |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.1 - Construction
checkpoint-status |  |  | checkpoint | 6.1.1 - Documentation Review
label | 7a235b35-41f5-5850-b6d8-65942ad04750 |  | note | Inspection Point: Quality Control Activity - Review
label | ffb39842-b27c-54d9-b079-16017ff91f0f |  | note | Acceptance Criteria - All barrier componants comply to the relevant specification as per NZTA M23.
label | d06dfb04-1f61-52aa-9a90-ea992ae08084 |  | note | Verifying Document - Manufacturers Certificates
label | 99a1bb99-a327-587d-a5bf-ab0419723522 |  | note | Frequency - Once per supplier
label | d7b445b0-5fd6-570e-b4e5-ba9cfda870ff |  | note | Inspection Type - Review
label | 4a9af5d3-abfd-5742-920f-cfad408bf0ca |  | note | Inspection: Key - R
label | 6d71e726-3cd4-59e8-addb-dc2b38311235 |  | note | Inspection: By - ER/PM
checkpoint-group |  |  | section | 6.2 - Construction
checkpoint-status |  |  | checkpoint | 6.2.1 - Design Revision as required
label | dd230cd6-75be-56f1-b879-a0918194fa4a |  | note | Inspection Point: Quality Control Activity - Design submission & review
label | e8191451-a5aa-546f-b419-f6b500b8b111 |  | note | Acceptance Criteria - Engineer to review and approve
label | 5cd12b48-468f-5e88-af8e-32560abeaa98 |  | note | Verifying Document - Revised design NTE/NTC
label | 19440b19-31e6-56ec-9093-4326deab33bd |  | note | Frequency - Once per design revision.
label | 3cb03adc-579d-5469-8eb1-2ed6af2f0296 |  | note | Inspection Type - Review
label | 8c262134-b6e3-5ff9-ae71-08b81e699dca |  | note | Inspection: Key - R
label | 9199a529-7581-5d56-82c0-c46c87f5bf76 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 6.2.2 - Barrier set out & review
label | 1818fa17-9841-520b-8f12-48a0449ca3e6 |  | note | Inspection Point: Quality Control Activity - Site inspection
label | 641bc773-b6e7-5fe4-b4f0-e4773e7a63bc |  | note | Acceptance Criteria - Engineer to review barrier setout onsite and approve.
label | 5f9784c4-d355-5616-ba28-4810821597e5 |  | note | Verifying Document - Ste inspection form
label | 3d88dd45-2dff-5677-95f7-993aed002a2e |  | note | Frequency - Once per barrier string
label | 94ee43d5-bc7c-59ee-bffb-f66fde61b343 |  | note | Inspection Type - Witness Point
label | 1d5e3271-a5d4-53d9-bf7f-b563ffdd99f7 |  | note | Inspection: Key - W
label | 71541f2e-7981-5fdf-b66e-3f3ea1f0effa |  | note | Inspection: By - ER/PM
checkpoint-status |  |  | checkpoint | 6.2.3 - Anchor Block Construction
label | 172723a8-eaa5-5f1f-a3c1-14ca59aac563 |  | note | Inspection Point: Quality Control Activity - Site Inspection
label | e6741647-1b80-5a05-8a56-aca4c806831b |  | note | Acceptance Criteria - Engineer to inspect excavated foundation prior to anchor block pour.
label | ad316464-21b5-57f3-b1e5-c26676b7ab6b |  | note | Verifying Document - Site inspection form
label | 32d46392-683d-5506-a7ca-13cb1ea75995 |  | note | Frequency - Once per anchor block
label | 76d5a1cd-7fa1-5291-9791-0041a6e53042 |  | note | Inspection Type - Hold Point
label | 01e94157-5fe0-5715-bf8f-e891dc678f3e |  | note | Inspection: Key - H
label | 012e0bf1-32b0-5b51-8ba4-51a30c078146 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.4 - Concrete Work
label | 99a2eac1-750b-5ab5-899f-e381d3b41fae |  | note | Inspection Point: Quality Control Activity - Site Inspection
label | 71e07e7a-7733-56aa-8ff4-df3bbd6fa8c1 |  | note | Acceptance Criteria - Concrete works shall be constructed to the line and levels detailed on the drawings, and finished to a smooth suface with no significant cracks, spalling or exposed reinforcing.
label | 9890e188-308d-5324-baa8-13d69b14a885 |  | note | ○ Concrete dockets to be provided to engineer.
label | 71ad8b26-4968-506a-b5a7-5e4b51dda4a0 |  | note | Verifying Document - Site inspection form
label | 940bc6f9-62dc-5f5e-b881-34127ba33344 |  | note | Frequency - Once per barrier string
label | f4ab5d3c-8a2f-5c82-be41-6a986d7680c5 |  | note | Inspection Type - Witness Point
label | ab595d47-4e5f-5581-b8d7-354d7fb0d24b |  | note | Inspection: Key - W
label | 6942806c-1b52-5177-b0d0-ec5f82cd8f78 |  | note | Inspection: By - ER/PM
checkpoint-status |  |  | checkpoint | 6.2.5 - Marker posts, reflectors and signage
label | 70706f12-9f84-52e2-b9c4-047963b05d3e |  | note | Inspection Point: Quality Control Activity - Site inspection
label | 20d75c10-bba1-5d27-b0a1-fc52da464c0d |  | note | Acceptance Criteria - Edge marker posts to be installed along w-beam at standard spacing intervals
label | c14a68bd-2c5d-5ace-972e-59d427f3a976 |  | note | ○ Wire rope barriers to have reflectorised top caps every 3rd post.
label | e6aef0bb-88e5-52f0-beb8-55b86d31b737 |  | note | ○ Leading end terminals to have Hazard/width marker where required
label | 7ef92471-7d95-5192-9d8d-d07a00ba9fe7 |  | note | ○ Wire rope barrier leading end terminals installed with RD6L signage
label | 796e55d3-0a65-5640-9fad-478693f48e16 |  | note | Verifying Document - Site inspection form
label | 59d89218-b289-503e-bd12-9f691a8a0e88 |  | note | Frequency - Once per barrier string
label | b11cef69-4764-5a1f-bc25-eebdfd84d00d |  | note | Inspection Type - Review
label | 078684cb-1a07-5900-a9f9-7ff37843e800 |  | note | Inspection: Key - R
label | f95bf465-b1a6-59d3-b4b7-36dd525253c0 |  | note | Inspection: By - ER/PM
checkpoint-status |  |  | checkpoint | 6.2.6 - WRB Pull Test
label | e462778f-09b5-5254-a02f-2bb44158314f |  | note | Inspection Point: Quality Control Activity - Witnessed pull test
label | 1b99ab3c-4abd-5c23-97a7-8d8ae1295468 |  | note | Acceptance Criteria - No visual damage to occur to posts or foundation as a result of the pull test. Any damage is to be rectified prior to sign off & string retested.
label | 965a7e8c-d9d6-5acd-903f-c30cc4bbee15 |  | note | Verifying Document - Site inspection form
label | 8a6bc5b2-2944-57e0-8750-82cb31ef0b00 |  | note | Frequency - Minimum one test / 100m
label | 3319ad1a-d08f-5442-bced-f234b48f3bae |  | note | Inspection Type - Witness Point
label | 0dcc8467-8fda-5d8c-88bb-b154a28fa202 |  | note | Inspection: Key - H
label | 49c6d833-f476-5c97-a5d3-25ee71b32a2e |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.7 - W-Beam Inspection
label | 7aeb6122-eaa2-5e4a-84d2-eb0a75c4693d |  | note | Inspection Point: Quality Control Activity - Check Sheet
label | b22e4563-8bbd-55ad-bee3-2e876642e925 |  | note | Acceptance Criteria - Contractor to provide end terminal check sheet signed by a suitably qualified person. Construction Review and Audit Form (RSHDS4) filed in QA File.
label | 49ac656d-dc7c-596a-bbf0-80a6d0ec4b2f |  | note | Verifying Document - Barrier Inspection form
label | 120d2746-aeb7-50ce-9845-d55e3acca263 |  | note | Frequency - One per end terminal
label | ef26d2c0-2d70-5eda-abef-29f662bbad4b |  | note | Inspection Type - Witness Point
label | 81d8e90c-8bfa-5538-87f5-15f6f6cbb2cf |  | note | Inspection: Key - W
label | 75ad75b7-becd-5ea7-9661-e1b17979fd7d |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 6.2.8 - As-Built
label | 9b1705d3-f8eb-5ab9-bff8-6e92520f16d0 |  | note | Inspection Point: Quality Control Activity - Survey As-Built
label | ffa1ed62-700d-5dd2-8fac-6a8ab5ffa81f |  | note | Acceptance Criteria - As-built to show Barrier constructed as per design and within tolerences as per m23
label | b2c3d96c-eb45-58ee-b0ee-79cc8e67bb4f |  | note | Verifying Document - As-Built Data
label | f1f4f31e-1ecf-5b82-a50f-f6d9dbd1bac9 |  | note | Frequency - Once Per String
label | fcefc214-9be1-5b05-9536-15ee01916152 |  | note | Inspection Type - Hold Point
label | 8e475c48-2823-5d46-af01-69de3081288f |  | note | Inspection: Key - H
label | edd486d1-affe-5eec-bc2b-056ebd49ceac |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | F2LSIP - ITP 05 - Lighting | itp |  |  |  | Yes | F2LSIP - ITP 05 - Lighting | 9a5fbbdd-2c65-4329-9179-9e5adbd10060
checkpoint-group |  |  | section | 5.0 - Lighting
checkpoint-status |  |  | checkpoint | Lighting
label | 5e7364df-0dc8-5049-a5e6-12b283beadd6 |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | bf6127c4-f532-5146-a972-42e5d1c81ddd |  | note | Acceptance Criteria - All below requirements are met and approved by CR
label | f8a2b0fa-7233-503a-bd58-8a9366c33c30 |  | note | Verifying Document - Referenced Item numbers as below
label | f9b1fb7f-1a7d-57b2-bbb5-80544e360572 |  | note | Frequency - Once post construction
label | 9392ab44-2300-5b51-9020-1cb92bc77c53 |  | note | Inspection Type - Hold Point
label | 460f3cdc-0d6c-56d4-b9a5-2cc98a4317a5 |  | note | Inspection: Key - H
label | 40db7e8f-83e5-538c-8862-54bfb8346b7a |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.1 - Technical Requirements
checkpoint-status |  |  | checkpoint | 5.1.1 - Electrical Installation undertaken by qualified & "approved" technician / Information to be provided by supplier
label | 540eaea0-6abe-5476-a158-2d9b0f148da2 |  | note | Inspection Point: Quality Control Activity - To be confirmed with Subcontractor prior
label | cb76dae7-824e-5419-afe1-2f66b0ea6a03 |  | note | Acceptance Criteria - Relevant qualification documentation provided by sub-contractor.
label | 0451d4e1-8846-5474-a538-bc4577168ecb |  | note | ○ Information to be provided by supplier
label | 573ace68-edff-5ffb-9177-3548ddfd6067 |  | note | The following information shall be supplied with the quotation, if requested:
label | 375f1f20-4660-570c-a8af-2501d945188c |  | note | (a) Fully detailed drawings showing a general arrangement, mounting height, outreach arm length, and base plate details, together with material specifications (including protective coating(s) where relevant), welding, fixing details, and construction tolerances.
label | f78e794e-ed69-56ae-9863-4d37d4b1ccea |  | note | (b) Method of assembly of the sections and base including lifting and installation procedures.
label | bc7cee5e-5439-5cf7-b49f-f8252a520cd5 |  | note | (c) Installation procedure including torque setting for holding down bolts and the maximum and minimum torque tolerance applicable.
label | 65119ee5-e256-5b55-aa72-4dec5a7c9ca3 |  | note | (d) Maintenance requirements for breakaway devices.
label | c7991285-50d3-5739-ba72-4e13d1c6978a |  | note | (e) Confirmation of specified intended life and details of any recommended maintenance to achieve this.
label | 0d938250-6595-5ea8-a4f4-3c80f59d5fde |  | note | (f) A suitable compliance certificate, e.g. Producer Statement Design (PS1).
label | 43176a65-a444-52b6-92ce-9a987e892a21 |  | note | This information may be lighting column type or wind zone specific and cover the general supply of the lighting columns. This generic information must be submitted initially by the supplier to the NZTA.
label | 703206ab-c899-5fb5-9cb4-6bdaa56ebd1b |  | note | Verifying Document - Qualifying Documents
label | 3cd96b9e-cad1-5469-95df-17aa906cd7ad |  | note | Frequency - Once Per Source/Supplier
label | fa7685ae-0efb-5738-a392-86fe0edec426 |  | note | Inspection Type - Review
label | 43017376-abc9-5d1d-b330-891c5e0ec227 |  | note | Inspection: Key - R
label | 89c66a9e-6f4a-55c6-bd9d-a8f6ccde64ca |  | note | Inspection: By - PM
checkpoint-status |  |  | checkpoint | 5.1.2 - Earthing
label | 26a5a842-cac7-553f-98db-31913ab4d3a8 |  | note | Inspection Point: Quality Control Activity - Inspection Post Install
label | 9be351f5-1bd5-58b5-99ee-7bd530767633 |  | note | Acceptance Criteria - Each pole to be separate installation, earthed using driven earth rod & M.E.N link - NZS3000
label | 5ecc4065-3a58-5bf4-8d18-4a54686a03fc |  | note | Verifying Document - Site Inspection Form
label | 43701244-1931-51b1-9ed9-4629852c9fc2 |  | note | Frequency - Once per pole installation
label | 0ba5ee2c-af60-596b-8b2b-dc57c159d8ad |  | note | Inspection Type - Witness Point
label | 1ee5065a-e18e-5d11-8ee5-0b20fab6cd37 |  | note | Inspection: Key - W
label | 825870fc-640e-5adb-bd45-0c87585b1c71 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 5.1.3 - Testing and Commissioning
label | 34d7cbd2-cc81-563c-8065-f7b76103f8f7 |  | note | Inspection Point: Quality Control Activity - Completed Post Install
label | 9d950ab8-e3c9-5674-8dd2-11478ca23808 |  | note | Acceptance Criteria - To be carried out in accordance with NZS3000 & NZTA M30
label | 8a26f611-1f2d-5563-aa5f-0679ca22cf1d |  | note | ○ Electrical test certificates for each lighting pole
label | d1b99c56-24be-5f21-b370-2829f651c751 |  | note | ○ Electrical Certificate of Compliance for the complete installation
label | 9f25a4bd-a070-52a2-8f5c-e1c5a996dde4 |  | note | ○ As Built information
label | 88bd61c2-11a6-5b92-9823-5f273fd3120a |  | note | ○ Completion Certificate (refer Appendix VI I of NZTA M30)
label | 18d70474-3765-5284-bd75-131b5138088b |  | note | ○ Any particular maintenance requirements (e.g., shear base poles)
label | f3807a00-a3f8-56c3-913d-8487289f8f36 |  | note | ○ Contractor to enter Ramm data for all installations
label | 7adc0a89-bad8-535c-a5bb-baa6e47f198e |  | note | Verifying Document - Relevant Documentation
label | cb94ae91-2123-515b-96c9-548414ce1eb4 |  | note | Frequency - Once per pole installation
label | aa0c3b3e-2ee0-5606-a907-fd01137bb17b |  | note | Inspection Type - Review
label | 0ae794e2-0cda-55dc-927d-b9077f5879da |  | note | Inspection: Key - R
label | 92c74246-1bbc-5e79-9b11-c094e75388b5 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 5.1.4 - Poles and Luminaries
label | e4a3da72-8537-50da-86de-4fd589dd33fd |  | note | Inspection Point: Quality Control Activity - Documentation provided Pre-Construction
label | d6a0c5a5-042b-5d6d-9b70-cb6f4ba477af |  | note | Acceptance Criteria - All lighting poles and luminaries to compley with NZTA M30, M26 & project technical specifications.
label | 1297845c-78c2-56b2-9394-cd0a2953b0f7 |  | note | Verifying Document - Manufacturers Certificates
label | 3cb8e0b9-b558-5dac-b6e7-06022119a5f4 |  | note | Frequency - Once Per Source/Supplier
label | 880ebb1b-7fd8-52d1-98e0-014d862cc914 |  | note | Inspection Type - Review
label | c7635baf-0681-55c7-a706-e4fa484cb1e3 |  | note | Inspection: Key - R
label | b304b26c-2ac2-5d42-b712-e0679aab577e |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 5.2 - Construction
checkpoint-status |  |  | checkpoint | 5.2.1 - Ducting & Cable Installation
label | 600768d0-1d91-5e7f-8e9b-95e2e0e570e4 |  | note | Inspection Point: Quality Control Activity - Trench Inspection
label | 3249d930-1fde-52b0-a7a7-2c18ceaba4c2 |  | note | Acceptance Criteria - Ducting to be installed as below where open trenching is possible
label | f41b66af-48c4-5c69-848c-5d9764b4a064 |  | note | ○ Required minimum thickness of separation 150mm
label | 10c4d492-5df7-568f-9ebd-986785e42efb |  | note | ○ Minimum cover depth from crown of ducting 700mm
label | 9a9cacb3-e121-5e28-9992-752483d53e47 |  | note | ○ Type of ducting required - Orange PVC 100mm duct
label | 833980e5-b468-52a3-8535-52a571d0ddda |  | note | ○ Warning tape required over ducting minimum 300mm above duct
label | 762241aa-e3da-5ae4-8a28-b7205af58fa5 |  | note | Verifying Document - Site Inspection Form
label | 5668c07f-2e4a-5f98-a26d-e1dbd5ebc6bc |  | note | Frequency - Once per tench installation
label | 2ee4597f-3fe3-5de8-aea7-37f714db23b1 |  | note | Inspection Type - Witness Point
label | 595ba12b-ffd1-584e-b59d-6d8dc4f4e796 |  | note | Inspection: Key - W
label | c18da813-a470-521d-af4f-517d237c9bc8 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 5.2.2 - Asbuilt of ducts
label | c2ba244c-4f8a-5e32-a78c-102f054af682 |  | note | Inspection Point: Quality Control Activity - Survey Asbuilt
label | 8b3d99dc-f3d6-59f2-a4bd-4659f05df1a4 |  | note | Acceptance Criteria - As-built location of ducting prior to backfilling as per design.
label | 51795b06-0b73-546e-8444-1eaf78aa80bb |  | note | Verifying Document - Suvey Records
label | 361b17d2-93ff-57ae-a844-e2b30a426316 |  | note | Frequency - Once per tench installation
label | 7979ea8e-f49b-5a81-bc5f-17b5c08fe138 |  | note | Inspection Type - Review
label | 46ed01dc-e348-5789-a55c-8394a0014069 |  | note | Inspection: Key - R
label | 486057c3-0a07-5520-aac5-d791b9aa53bf |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 5.2.3 - Trench Backfill
label | cc5068f2-1137-5634-9b4e-230656f5ca09 |  | note | Inspection Point: Quality Control Activity - Density
label | 096aeef8-0b54-5001-94e7-6ba5e8c7252e |  | note | Acceptance Criteria - Material is visually compact and tightly bound, and passes proof roll during subgrade inspection under ITP 2 Item 2.2.3
label | 6cd5547d-94f8-57fc-a875-5142d07a14ba |  | note | Verifying Document - Site Inspection Form
label | 54c4dffa-72b7-53c7-ad6b-c083d65fbec6 |  | note | Frequency - Once prior to subase placement
label | fdbcadf7-31c0-54d5-b18e-9e00b53614f9 |  | note | Inspection Type - Witness Point
label | 92e05346-15ad-5d33-844b-766f7a49f453 |  | note | Inspection: Key - W
label | d9f998c4-dca5-5297-8dff-aa1a1cf71980 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 5.2.4 - Pole & Luminaire Positioning / Add Identification Marking (NZTA M26 2.4)
label | b7380f4f-160c-5877-a454-d2b51db38e19 |  | note | Inspection Point: Quality Control Activity - Check setout prior to installation
label | b2f4e01b-7fdd-5f52-9865-0b55499c25e1 |  | note | Acceptance Criteria - Poles to be located a minimum of 1m behind kerb/edge of seal & at right angles (90°) to kerb lines and lane markings.
label | b5ea5526-dd1e-51bc-b6ae-941e059d05f3 |  | note | ○ When poles are set in place they shall be vertical to within 1°.
label | 401cc769-dc18-523c-b89d-c036b898a00d |  | note | ○ When each luminaire is installed it shall have the required tilt to within 2°
label | b0255aa6-7904-5d96-9068-cdc1646fb66f |  | note | ○ The axis of the luminaire beam shall be in a vertical plane to within 2°.
label | 000517ad-7d7f-54cc-963a-bb307190753e |  | note | ○ Columns shall be installed within +/- 100mm of the approved marked location both longitudinally and laterally. Height above finished ground level to ± 50mm of the manufacturer’s level.
label | 66551fca-7a12-5f6a-9a1e-b11047da5d9e |  | note | Identification Marking (NZTA M26 2.4)
label | 02c6d04d-ae2f-55e8-9dc5-2025406a8f78 |  | note | All lighting columns and outreach arms shall be clearly and durably marked with the following information:
label | c0a0087e-734f-553a-b736-1914db63a3f2 |  | note | ○ Name, identifying mark or symbol of the manufacturer
label | 342cdc5d-30d0-537e-8664-eaf800405e0f |  | note | ○ Year of manufacture (or at least the last two digits of the year in which the marking was affixed)
label | c073feb2-b5b3-5a08-a524-5c7d9931f9b2 |  | note | ○ Manufacturers model number or identification reference
label | 67f3d7c2-9854-5c87-b505-d7d92fee868f |  | note | ○ Impact classification and performance class (F if passively safe/frangible, blank otherwise).
label | 6ce70f30-af01-5f85-83fe-42cf2580517b |  | note | Verifying Document - Site Inspection Form
label | 9125d2b5-2740-50e8-820c-79f6d0b61539 |  | note | Frequency - Once per pole installation
label | 6b58b1ae-1524-5915-afb1-33e1ff143711 |  | note | Inspection Type - Inspection
label | 256cbf09-c5bc-5419-acb5-6173451d745d |  | note | Inspection: Key - I
label | 3921c72b-9c0c-56f3-884a-4217ab30b119 |  | note | Inspection: By - PM/PS/ER
checkpoint-status |  |  | checkpoint | 5.2.5 - Concrete
label | 75f05304-c83a-59ef-8446-301aa1e16d5c |  | note | Inspection Point: Quality Control Activity - Compressive Strength
label | a9d301f6-3033-5a85-9eb4-9b68ed9719ab |  | note | Acceptance Criteria - As per NZS 3112 - Concrete surrounding base to be minimum 20MPa at 28 days. Columns shall be installed as per the manufacturer’s recommendations.
label | 34bda7a2-f779-512d-937f-e5c0b67685c3 |  | note | Verifying Document - Compressive Strength Report
label | 4297112a-c105-52c5-a47e-c521b0f87e3c |  | note | Frequency - Once per days production
label | 15ea9a67-8ca8-524d-ba21-114564494e99 |  | note | Inspection Type - Review
label | 52789e46-50e8-5925-a295-625c71d4651b |  | note | Inspection: Key - R
label | 45300adc-32fb-50a6-ad00-f268f7f9df2c |  | note | Inspection: By - ER
checklist-sectioned |  |  | checklist | F2LSIP - ITP 08 - Road Marking & Deliniation | itp |  |  |  | Yes | F2LSIP - ITP 08 - Road Marking & Deliniation | c08fa776-72ae-4149-be66-0fad4c5f77ce
checkpoint-group |  |  | section | 8.0 - Road Marking & Deliniation
checkpoint-status |  |  | checkpoint | Road Marking & Deliniation
label | 9d530abd-42bd-54a2-816f-5685841c76b8 |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | ae4ccaf5-b018-5c19-91e0-ced2b0229bee |  | note | Acceptance Criteria - All below requirements are met and approved by ER
label | d489cb6b-76fc-526d-afe6-ebb57d1749ba |  | note | Verifying Document - Referenced Item numbers as below
label | 39363700-33aa-5ae4-8fbc-6df49ce648bf |  | note | Frequency - Once post construction
label | 254a7d2d-ceeb-50da-9a2f-5a6292f963dd |  | note | Inspection Type - Hold Point
label | 77804571-bf44-5f63-a866-32a70d64ee9c |  | note | Inspection: Key - H
label | af00ee26-0a26-5829-95cc-143e09f5f210 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8.1 - Materials - Pilot Spec M7
checkpoint-status |  |  | checkpoint | 8.1.1 - High Performance Roadmarking
label | b7debe72-b29d-5a71-a51c-5065944b8874 |  | note | Inspection Point: Quality Control Activity - Compliance Check
label | 4c1b7f61-fd7f-5f4c-8bcd-2b5f605332d1 |  | note | Acceptance Criteria - To Comply with TS1 & TNZ P12
label | 9a1801d0-cdd3-56db-b598-ddca9a09720b |  | note | Verifying Document - Manufacturers Cetificate
label | cf9cfade-d17c-5dd7-8530-6bad2c6dfe0c |  | note | Frequency - Once Per Supplier
label | 66642054-cc91-558e-b0be-dbd657805903 |  | note | Inspection Type - Review
label | 8d9a1ad7-8f8f-53b6-b073-20b610a64fd1 |  | note | Inspection: Key - R
label | e1038538-3cc3-5b51-9dac-02fc7adc51a2 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 8.1.2 - Audio Tactile Profiled Roadmarking
label | e0c63cf5-e715-5b31-8d93-6867e1ef5921 |  | note | Inspection Point: Quality Control Activity - Compliance Check
label | 1fa6312c-a047-5e50-96d1-8eb8f1efcc56 |  | note | Acceptance Criteria - To Comply with TS1 & TNZ M24
label | 6b1bf9cc-ffa7-5e5b-aaf0-215894b656df |  | note | Verifying Document - Manufacturers Cetificate
label | cae887d4-4da0-51ac-bf11-96fda6e95456 |  | note | Frequency - Once Per Supplier
label | dd11c4c2-39e0-55b6-a44f-83907661b668 |  | note | Inspection Type - Review
label | 7d181353-b5be-5ea4-ae63-81fa471b5be2 |  | note | Inspection: Key - R
label | 07c96095-7804-5819-8d46-a599b58a3294 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 8.1.3 - Raised Pavement Markers
label | 15360c63-7a2e-5543-b998-b2d329f4faa2 |  | note | Inspection Point: Quality Control Activity - Compliance Check
label | b4550b26-5528-58f2-80aa-83ad4804610b |  | note | Acceptance Criteria - To Comply with TS1 & M12
label | a5583017-3f4a-5682-b997-ab6ce7c0ca2e |  | note | Verifying Document - Manufacturers Cetificate
label | 58a662af-c40e-577f-a34f-4ff270bf57cf |  | note | Frequency - Once Per Supplier
label | d7685976-4aad-5066-b668-27d2bea78e67 |  | note | Inspection Type - Review
label | fb52db51-6a5b-537a-9274-7e917e1fb1f4 |  | note | Inspection: Key - R
label | 2b6e3e1f-3460-574f-a2c4-c7f73ffa0b30 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 8.1.4 - Edge Marker Posts
label | 77aa620c-03e9-560d-9d5f-17d33cd186bc |  | note | Inspection Point: Quality Control Activity - Compliance Check
label | 78e406e3-78d4-59a2-bbda-c325377b0e5e |  | note | Acceptance Criteria - To comply with TNZ T/12
label | 129a930b-e9de-5c58-8692-42b7a0b297ef |  | note | Verifying Document - Manufacturers Cetificate
label | 9068a384-289e-59c3-9d6c-dc50b49ed960 |  | note | Frequency - Once Per Supplier
label | 0abe165d-032c-5023-b8b6-a81eb7223a5a |  | note | Inspection Type - Review
label | 74fa24df-332d-5f80-856e-2be1bb0592f0 |  | note | Inspection: Key - R
label | 6d4431c1-7ec6-5003-a019-aa5ddcf3d411 |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 8.2 - Construction
checkpoint-status |  |  | checkpoint | 8.2.1 - Preparation
label | d2de9e30-9a43-511b-a8a2-ab105f595d60 |  | note | Inspection Point: Quality Control Activity - Onsite sweep and visual check
label | 65ae26fc-30a7-58ed-bbf1-b555eafd6766 |  | note | Acceptance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
label | 07739baf-6bae-5fb9-b8e8-7bf07cb0d44f |  | note | Verifying Document - Site Checklist
label | 7590e6bf-0940-5d80-a666-cfa962726284 |  | note | Frequency - Prior to all marking.
label | 59cda3e0-9ce5-51fe-a308-a4ab135a3dea |  | note | Inspection Type - Check / Review
label | 5585362b-8f25-503e-aa60-340bc4bad0c3 |  | note | Inspection: Key - C / R
label | c544c2c3-77a9-51dc-bc78-ae512c60212c |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 8.2.2 - High Performance & ATP Marking
label | fdd161ef-9a70-5ada-a0ab-ace02a9e1487 |  | note | Inspection Point: Quality Control Activity - Check
label | 0eaa89e0-8da5-5525-9086-836317cf36c1 |  | note | Acceptance Criteria - Paint applied minimum of 6 weeks prior to HP or ATP markings.
label | a057beae-5de4-5281-a529-3c8f459b6460 |  | note | ○ ATP to comply MOTSAM Part 2 Section 4.08 - Profiled Line Markings
label | 3b0efcf6-9b85-5986-82df-fc7e875bba77 |  | note | Verifying Document - Site Checklist
label | 498d14e4-60c5-5905-84db-0bf02fab5538 |  | note | Frequency - All marking.
label | ed5aa4a5-2dfe-5858-afeb-ebd36403ea9f |  | note | Inspection Type - Check / Review
label | 74b4751c-6ee6-503c-9fed-a91b283cba06 |  | note | Inspection: Key - C / R
label | b8a09998-e7b8-5913-a49c-eb601615acca |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 8.2.3 - Raised Pavement Markers
label | 3d727164-174b-5fa1-92e4-1a3a21d3936c |  | note | Inspection Point: Quality Control Activity - Check
label | f423dcb9-8844-5935-a1b9-4f846828cf08 |  | note | Acceptance Criteria - Installed as per drawings and in accordance with TNZ P14.
label | 9f8456a7-288b-595a-bb65-c21b569316bb |  | note | ○ Surface to be clean & dry prior to installation of RPM.
label | 3d10312b-8bdf-5793-8abf-b1f90ffbce7a |  | note | Verifying Document - Site Checklist
label | dc4da529-99f4-5e13-b205-9eb8e7997f1b |  | note | Frequency - All RPM
label | 2df6f21b-b7b1-5b1f-965d-3676fa81c7c0 |  | note | Inspection Type - Check / Review
label | 674f3ac6-b7d8-55a7-a9fa-b38629d6b5d2 |  | note | Inspection: Key - C / R
label | b10a7b41-1ff9-59cc-ac47-ae4a3e73de3f |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 8.2.4 - Edge Marker Posts
label | b22647b3-99f6-5945-9a87-d69e5959b918 |  | note | Inspection Point: Quality Control Activity - Check
label | 64d800ce-1d87-5607-9c41-2896d5ab5c27 |  | note | Acceptance Criteria - Installed in accordance with requirements of TNZ P16
label | a674e735-beef-5415-876f-8b7c6912a97e |  | note | ○ Application Rate of Paint - Dry Film Thickness
label | 41547949-776c-5e37-8285-0076055c7470 |  | note | ○ Material Records as per NZTA P12 - Section 16 QA Records
label | 17a0210d-d624-524c-b04e-b1403509f5b8 |  | note | Verifying Document - Site Checklist
label | 5c9892ae-5e83-5a8a-a772-f7ab794cc3a9 |  | note | Frequency - All Edge Markers
label | 2eb08606-b453-546f-b4c4-9b45b434ddde |  | note | Inspection Type - Check / Review
label | e1dbca0c-ef89-51a3-8be8-8407701a6521 |  | note | Inspection: Key - C / R
label | 37500df4-9659-5c60-948c-537265ce24ae |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 8.2.5 - As-Built Survey
label | 06fe9473-662b-5943-b8a2-b9348e11ec80 |  | note | Inspection Point: Quality Control Activity - Check
label | 30c77e35-20f2-57b5-82f7-9d7c8b9ac6c2 |  | note | Acceptance Criteria - Dimensional tolerance achieved in accordance with TS1
label | fbfbb327-56bc-5c79-ae5f-4bd193f934d5 |  | note | Verifying Document - Survey Records
label | 3a1fe311-6fd0-587b-870c-c5c848473b95 |  | note | Frequency - All Linemarking
label | 9b83a500-4e29-5a62-b13d-4b41b89f4733 |  | note | Inspection Type - Check / Review
label | 561e5778-fdac-5d8f-aa07-702d82f9e0d2 |  | note | Inspection: Key - C / R
label | 3412f232-2f91-5bf3-9787-914e1d2be681 |  | note | Inspection: By - PM/ER
checklist-sectioned |  |  | checklist | F2LSIP - ITP 07 - Sealing | itp |  |  |  | Yes | F2LSIP - ITP 07 - Sealing | d425488c-c498-4445-a3c2-36f0aeca200a
checkpoint-group |  |  | section | 7.0 - Sealing
checkpoint-status |  |  | checkpoint | Sealing
label | 999a494d-308f-59da-8177-7b4ec30e58d5 |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | 9f6da24d-e1ac-56ca-ac0c-1bde613d2a4c |  | note | Acceptance Criteria - All below requirements are met and approved by ER
label | 71f44c02-5d51-58cc-9700-7679e7bddf3d |  | note | Verifying Document - Referenced Item numbers as below
label | 74926791-0a37-5cbd-987b-c7269b0ad693 |  | note | Frequency - Once post construction
label | 8538c1fa-93e3-53f2-a760-39823c03a8c7 |  | note | Inspection Type - Hold Point
label | 0ca717f9-9ceb-54a9-9526-4ef3b3836147 |  | note | Inspection: Key - H
label | 6d7d2984-942b-5145-b50c-5bd97c86b98a |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7.1 - Bitumen Approval
checkpoint-status |  |  | checkpoint | 7.1.1 - NZTA M1: 2022: Bitumen Material Approval
label | 3930d22a-4bbc-5b0c-809c-a734081e1acf |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | 92ce3cce-b3f6-5d3c-a417-c172df875ff4 |  | note | Acceptance Criteria - Bitumen/binder compliant with NZTA M/1 - Table 5.1
label | 80b85b73-89c1-5eea-8a1d-431236f27407 |  | note | Verifying Document - Manufacturers Certificate
label | 23f009c4-db2a-5d1b-aca1-49e36c0422bf |  | note | Frequency - Minimum 5 working days prior to construction
label | 63940467-3d29-5910-9c4d-ff642a97560d |  | note | Inspection Type - Hold Point
label | 3dfc82bc-df15-5118-a9c4-f51cf3e1a8d9 |  | note | Inspection: Key - H
label | 2ccd747d-3d6d-54de-a096-13ac51715ec6 |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7.2 - Source Properties
checkpoint-status |  |  | checkpoint | 7.2.1 - NZTA M6: 2022: 4.2 Crushing Resistance
label | 4a7f556b-2f27-567b-b966-6891bff0ee98 |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | a7f8bf7f-a229-5d52-bf6f-e0fdf0810a4f |  | note | Acceptance Criteria - Maximum of 10% fines shall be produced under a load of 230kN.
label | 5f48000e-25a3-5da9-a876-94a7cb3cff3e |  | note | Verifying Document - IANZ Lab Report
label | 4ca0e6b0-4e8b-5173-b4f0-bd0f121b404d |  | note | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | 505757e9-ad6d-5ca2-848b-8dd9f6b6c275 |  | note | Inspection Type - Hold Point
label | 43c26c2e-cd8f-5199-a5bf-8491283ce3e9 |  | note | Inspection: Key - H
label | ee5314dc-8141-55bf-90f4-77eebae377a4 |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2.2 - NZTA M6: 2022: 4.3 Weathering Resistance
label | 93d5dcc7-e392-5043-b7ea-a6bd496301bf |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | 8ff7b245-9c86-5096-849c-7b91173fda08 |  | note | Acceptance Criteria - The aggregate shall have a quality index of AA or BA
label | b1767595-e14a-599c-9852-76a34870173d |  | note | Verifying Document - IANZ Lab Report
label | d5730c21-1d08-5705-a158-7867054aaa6f |  | note | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | aaac4c72-f31a-52f4-bc17-cc6ecbab91a8 |  | note | Inspection Type - Hold Point
label | b90b5976-47e4-556b-a24f-2d14535226a7 |  | note | Inspection: Key - H
label | fcfc4bb7-537e-57fd-8736-1447140873c9 |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2.3 - NZTA M6: 2022: 4.4 Weak Particles Test
label | 429505d1-6042-5739-be9d-a1986aa50d55 |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | 5863096c-fdc5-574f-9e44-a4286150e8b1 |  | note | Acceptance Criteria - Note - only required if source properties are disputed.
label | 65fea8b8-4a6d-51a1-9a84-bd9fcc4bb54f |  | note | ○ The aggregate shall have a maximum of 1% of unsound materials
label | d35e8d35-3ccf-58ce-86b0-f0865997cab5 |  | note | Verifying Document - IANZ Lab Report
label | 52e9b9b3-7b29-5e99-b811-6b349c8bedda |  | note | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | 18608e58-75be-5403-8d3a-32ca05cddc2d |  | note | Inspection Type - Hold Point
label | 8b241cee-4812-52a0-b81e-7c7d61067f56 |  | note | Inspection: Key - H
label | 351559b1-5f6a-5201-a7d4-024e9ce3b146 |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2.4 - NZTA M6: 2022: 4.6 Polished Stone Value
label | ff819963-9e51-5b63-9157-34cc589f42ff |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | baefed9e-c8f7-59bf-a3ef-251e0e4a2aff |  | note | Acceptance Criteria - Polished Stone Value (PSV) - compliant with NZTA M6: 2022: 4.6 & project requirements
label | aaf938de-4d64-5051-a47b-8bf9b1dd523d |  | note | Verifying Document - IANZ Lab Report
label | ade78e5e-d651-575a-b414-54b7fcc0bb78 |  | note | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | 8c0f6895-4feb-56bd-8a23-d8dbedf3b5fe |  | note | Inspection Type - Hold Point
label | 0ad461f8-262a-59c7-b884-0dd4e04bbb35 |  | note | Inspection: Key - H
label | f1b08326-e4da-5181-b866-ccf1bc51898f |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7.3 - Production Properties
checkpoint-no-status |  |  | checkpoint | Production Properties
label | a0ff8a11-79a4-5d8f-bf1e-1339d340324e |  | note | Acceptance Criteria - Grade 2, 3 & 4 Chip
checkpoint-status |  |  | checkpoint | 7.3.1 - NZTA M6: 2022: 5.1 Cleanness
label | e4e4d3d7-cb6c-58b2-a29b-a8c4e6ee38f0 |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | f0a0d078-c83d-5a8c-b90e-657ffc072764 |  | note | Acceptance Criteria - Cleaness of aggregate samples compliant with NZTA M6: 2022 5.2 Cleanness
label | 2efdd31b-0508-59c3-84cf-3b37da35ee40 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 72730b43-8b10-583b-9c2c-3efa63a6d169 |  | note | Chip Grade ¦¦ Minimum Cleaness Value
label | 21c8a682-a3b5-55cc-9e76-28b0c9f288d6 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 5db6da3e-f347-5bd3-a4c4-2a48ebae5924 |  | note | 2 ¦¦ 89
label | 2a60521d-54fb-527c-886a-99467698c0e4 |  | note | 3 ¦¦ 87
label | 45d913c4-86fa-5adc-a171-3e99c91ab852 |  | note | 4 ¦¦ 85
label | f2359b22-ee9a-5be4-9bc2-1f44ccb67611 |  | note | 5 ¦¦ Report only
label | 1edfd54a-9bd0-578c-b44b-5ddf9ff748f1 |  | note | 6 ¦¦ Report only
label | 80d4a0ea-ad8a-58ff-a376-c0ca160d5d14 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 00dcbcfb-6ce6-5794-8791-a69848c29926 |  | note | Verifying Document - IANZ Lab Report
label | b6ba7dc6-a05d-51e9-b53b-b9cd32b7ff53 |  | note | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | bba21f18-6f12-5f30-b8cf-fb4f2096311e |  | note | ○ 1 test per < 100m3;
label | 6717428b-d074-5ee5-86de-dbdaf92dfa08 |  | note | ○ 2 tests per 100-500m3; or
label | dec755cd-4d45-54cd-83e3-630f3e6d8df7 |  | note | ○ 3 tests per > 500m3
label | 942cc9d3-531a-5ae8-b5b8-4405a2952a63 |  | note | Inspection Type - Hold Point
label | 560c8bfd-810b-5a67-a76e-fe55dbb987df |  | note | Inspection: Key - H
label | a90f688f-5e74-5432-8a93-effb3130ea0b |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3.2 - NZTA M6: 2022: 5.2 Size and Shape
label | 0291a172-9098-58f4-bde6-8679553e1667 |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | af69ee9b-51aa-5338-a62b-5b2359de7c07 |  | note | Acceptance Criteria - Size and Shape of Aggregate Particles compliant with NZTA M6: 2022: 5.2 Size and Shape
label | 74071ae7-48ff-50fb-9d1b-1ea1fb3b56e0 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 09a9f457-4b90-5ad0-b528-9d5dc63d574c |  | note | Grade of Chip ¦¦ ALD (mm) ¦¦ % of Least Dimensions Within 2.5mm of ALD ¦¦ AGD/ALD Ratio ¦¦ % Passing 4.75mm Sieve ¦¦ % With at Least Two Broken Faces
label | 727e3ee3-5c36-5813-9c88-03b8b0f78a36 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 449d5c90-8ee7-5e8f-b6e2-3680a16ec1bc |  | note | 2 ¦¦ 9.5 - 12.0 ¦¦ 65 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 0154c6e3-c912-5f3a-9229-08553da97cd8 |  | note | 3 ¦¦ 7.5 - 10.0 ¦¦ 70 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 14801690-1342-5d0c-91a6-0c5364b9e9a5 |  | note | 4 ¦¦ 5.5 - 8.0 ¦¦ 75 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | bf974025-cda5-515c-a88f-775f217830b9 |  | note | 5 ¦¦ Report ¦¦ Report ¦¦ Report ¦¦ Report ¦¦ Report
label | bcbf5f1c-2f9c-5dda-9278-eea781d5208a |  | note | – – – – – – – – – – – – – – – – – – – – –
label | de5e3ebb-1f1f-5af5-8af9-98be2138f8f2 |  | note | Verifying Document - IANZ Lab Report
label | 22c318e1-6ed6-5790-853d-93124fd6babc |  | note | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | ddd60f16-78e7-571c-9e2f-6555c79b12e9 |  | note | ○ 1 test per < 100m3;
label | 26868683-b90c-59a7-98cb-5d5d56799c80 |  | note | ○ 2 tests per 100-500m3; or
label | 8bb7e310-c8ad-5cb4-bcce-2ce40eea7ddd |  | note | ○ 3 tests per > 500m3
label | a3f1104e-7169-5d6c-bd05-4f029b31db57 |  | note | Inspection Type - Hold Point
label | bc1c1a20-0b08-518b-a180-ce6e15946e2b |  | note | Inspection: Key - H
label | db111949-79c7-558e-b7bd-fc95823c39af |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7.4 - Production Properties
checkpoint-no-status |  |  | checkpoint | Production Properties
label | e524546d-e50f-5bbc-8816-6430b9b1c295 |  | note | Acceptance Criteria - Grade 5 & 6 Chip
checkpoint-status |  |  | checkpoint | 7.4.1 - NZTA M6: 2022 5.3 PSD
label | 0da10b2a-72fe-523e-b081-8640f58fc823 |  | note | Inspection Point: Quality Control Activity - Test Report Review
label | 163d4554-0e29-555b-a76b-7ef149a968de |  | note | Acceptance Criteria - Particle Size Distribution compliant with NZTA M6: 2022 5.1 Table 4
label | 31279ab4-ffd8-5575-b901-a20901d50a66 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 00a78c5c-c627-5b18-8703-5d479c9ad79d |  | note | Siege Size (mm) ¦¦ Percentage Passing Sieve (Grade 5 :: Grade 6)
label | 6e523ac2-460f-5acd-8829-a275a7aed441 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 969f758f-07c3-5e5a-9a09-d0eb5fa9eeb8 |  | note | 13.2 ¦¦ 100 :: -
label | 80c78a1f-058d-512b-95ab-e2ad770b92c9 |  | note | 9.5 ¦¦ 95 - 100 :: 100
label | e734535e-889d-54ab-a3f8-799eb28a70ea |  | note | 6.7 ¦¦ - :: 95 - 100
label | 4d8fe1ea-8cde-57fd-abc8-31db033199d6 |  | note | 4.75 ¦¦ 0 - 8 :: -
label | fd2424c0-5721-5dfe-9f0b-fb3096f7975a |  | note | 2.36 ¦¦ 0 - 2 :: 0 - 15
label | b4053518-edbc-523a-9cc0-6e2e662f6c4c |  | note | 0.300 ¦¦ 0 :: 0 - 8
label | bf44d65e-488e-54ea-afbb-b1a8b34042b4 |  | note | – – – – – – – – – – – – – – – – – – – – –
label | 80934642-51d8-5490-a4bc-f372bbfb7d4b |  | note | Verifying Document - IANZ Lab Report
label | 8190b7f3-4f1e-5d9f-9f8f-1bbb07652045 |  | note | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | f4a2a1db-5b22-5bb9-afc0-99e52248757c |  | note | ○ 1 test per < 100m3;
label | 03383e52-92ba-59e6-be48-dde3a06ef5a1 |  | note | ○ 2 tests per 100-500m3; or
label | c8f3cc2a-f7ee-5046-beda-9a2b6ad72fd0 |  | note | ○ 3 tests per > 500m3
label | ae2d1e8b-b6f6-592d-bd0d-2157600d7438 |  | note | Inspection Type - Hold Point
label | 3eab7945-c57e-58f9-9286-3b24777a46ee |  | note | Inspection: Key - H
label | 6be9d91b-b997-52ab-a858-930f10bc8143 |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7.5 - Pre-Construction
checkpoint-no-status |  |  | checkpoint | Pre-Construction
label | 0a86e3da-f4c7-521c-890f-29c29dd13376 |  | note | Acceptance Criteria - Require formal sign off record of previous layer prior to placment of next layer. DNZ to develop sign off sheet or approval system of work. Bitumen distributors shall possess a current Certificate of Compliance with the BCA E/2 Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
checkpoint-status |  |  | checkpoint | 7.5.1 - Chipseal Design Submission
label | 072389a3-af76-503d-8d62-3b8d6949f55b |  | note | Inspection Point: Quality Control Activity - Design Review
label | 52020c7a-5e8d-5a13-8f29-83066c14aa44 |  | note | Acceptance Criteria - Designer to approve sealing design, prior to sealing.
label | e177f1ad-8ece-5f31-92aa-832c8144ae4b |  | note | Verifying Document - NTC confirming acceptance
label | 3369cd99-4a19-57f7-a1b5-4c1a332f29ad |  | note | Frequency - Once per seal design
label | d4389f22-c08c-55c3-a340-0f396dbbb547 |  | note | Inspection Type - Hold Point
label | 34edcc67-4adb-53bb-a0b0-e7b68658d9e0 |  | note | Inspection: Key - H
label | e4c2e681-a7dc-5e78-b034-5ac645adcc5a |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5.2 - Pre-seal Inspection
label | 1988d7e2-26bb-5149-b129-a87f224f40e8 |  | note | Inspection Point: Quality Control Activity - Visual Site Inspection
label | e492e58b-e7ca-5f5d-b068-3f9a9bd91ee1 |  | note | Acceptance Criteria - Basecourse/Subbase (Membrane seal) - To be prepped to a tight, uniform surface, swept to remove any dust and other foreign objects.
label | d5aa68a9-ff5a-5b68-916f-49bcb86a5e00 |  | note | ○ Prime or previous seal - Full surface swept with a power broom to remove excess chip and any other foreign material. The Contractor shall give the Engineer 24 hours’ notice of its intention to seal
label | 7de8a0d5-7984-5e74-ae0f-b522a279fa44 |  | note | Verifying Document - Site Inspection Form
label | 1e96a862-f61e-563f-8aff-4b3e14e9d11f |  | note | Frequency - Prior to construction of sealing coat
label | 68ad3e9f-f3de-55e8-8a47-6dd597aec23a |  | note | Inspection Type - Hold Point
label | 1ed76c06-3c9b-55ad-abae-c16c71d46d9d |  | note | Inspection: Key - H
label | c43bda82-2d57-5b93-9885-368d81abcc01 |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5.3 - Pre-seal testing
label | e837eccc-07a4-50c6-b476-e0cfe4448e6f |  | note | Inspection Point: Quality Control Activity - Degree of Saturation test TNZB/02 Clause 12
label | e2311655-a884-5bc0-9bae-632fb9eb611b |  | note | Acceptance Criteria - Compliant as per TNZ B/02 Clause 12 DOS at each of minimim 5 points < 70%
label | 85b3debb-c7b4-5cb3-ae4b-1327894c3530 |  | note | Verifying Document - Testing results
label | 5dc92109-eba9-5833-921b-4b87ad426534 |  | note | Frequency - Minimum 5 tests per 1000m2
label | dd4662f7-e4d0-5fd5-874e-47d57fa974cf |  | note | Inspection Type - Hold Point
label | 240fbb2a-5fe5-5363-a06a-07c774a9a334 |  | note | Inspection: Key - H
label | 73979a7f-5c25-59e6-b2c0-e8e257279697 |  | note | Inspection: By - PM/ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7.6 - Construction
checkpoint-status |  |  | checkpoint | 7.6.1 - Working Temperature Prior to Spraying
label | 460b22f9-8cb2-534b-b18e-d721f5a5197d |  | note | Inspection Point: Quality Control Activity - Onsite check & Document
label | 46ed374e-4182-54ef-a0be-b3e5744c030d |  | note | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying shall be carried out when the pavement surface temperature is below 10 degrees C.
label | 342e01e5-9980-59d2-9abc-c7edc670acc4 |  | note | Verifying Document - Sealing Checklist
label | b0d6b3bb-e2b5-5f57-aae2-70a1b26ed343 |  | note | Frequency - Prior to Spraying
label | 008ee406-9cd9-5faf-a8f1-b335888f98be |  | note | Inspection Type - Review
label | 0bd66adb-fe0d-588f-9897-05c5daa36e33 |  | note | Inspection: Key - R
label | 243b322b-201b-518f-ad5a-cc1988188067 |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 7.6.2 - Application rate for Bituminous Seal
label | b75a4f93-b03d-5da2-9775-454165487eec |  | note | Inspection Point: Quality Control Activity - Onsite check & Document
label | 8f775708-8512-59d2-8258-a2ae56e2a793 |  | note | Acceptance Criteria - Sprayed Rate measured compliant with the Approved Seal Design
label | eff53065-4901-5603-a923-70505e53d565 |  | note | Verifying Document - Sealing Checklist
label | ee24571e-205f-5c19-b940-bdd15bf524ce |  | note | Frequency - Per spray run
label | d4f5e281-0c6d-553b-9d56-3f702a6460b0 |  | note | Inspection Type - Review
label | f18c7388-d6b2-5b18-81e2-1ac99b46b94a |  | note | Inspection: Key - R
label | b831f243-a9df-5a17-8a7b-98f7085b1772 |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 7.6.3 - Chip Spread Rate
label | 82de73ea-f0c4-5c58-8e92-902e0573bfbb |  | note | Inspection Point: Quality Control Activity - Onsite check & Document
label | 0d2cf5b3-5541-5f58-aa3c-ccf6e2c31597 |  | note | Acceptance Criteria - Sealing Records showing compliant spread rate of the chips based on C0213.5;TNZ P/3: 1995-21 Cl. 28
label | 31f73376-bcfd-586a-8342-1ec72201863f |  | note | Verifying Document - Sealing Checklist
label | 8215b81f-f5ab-57f8-a40b-92e018060102 |  | note | Frequency - 1 test per chip grade per 2,000m2 seal constructed
label | c4ff62d7-bb63-545e-a161-de0284ad51a4 |  | note | Inspection Type - Review
label | 0005a2a6-dde9-56c0-9f35-46c76ac38bec |  | note | Inspection: Key - R
label | 7d130de8-8ff8-55af-93d8-1d7c12e3bc0b |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 7.6.4 - Rolling Requirements
label | eea027b4-df04-52b7-9766-93af44d31a64 |  | note | Inspection Point: Quality Control Activity - Onsite check & Document
label | cf0aa14b-c338-5797-b30f-9193c62753a8 |  | note | Acceptance Criteria - Sealing Records showing compliant rolling requirements based on C0213.5;TNZ P/3: 1995-22 ROLLING
label | 42ade045-d6e3-5c22-aff5-4234999e501e |  | note | Verifying Document - Sealing Checklist
label | ad31ff22-1d07-5759-abf2-b02d2173e05e |  | note | Frequency - Per Shift
label | f16d8f62-c4e2-522e-8d48-feb7498061ce |  | note | Inspection Type - Review
label | 42e38622-98e5-51ae-8943-4e3cffa304d6 |  | note | Inspection: Key - R
label | e1bb4c24-6cc5-5352-8dc0-b11d5732e948 |  | note | Inspection: By - PM/ER
checkpoint-status |  |  | checkpoint | 7.6.5 - On Site Checks - Post PTR and Brooming
label | 568d1224-59a8-59ec-8562-0c8d84d62f03 |  | note | Inspection Point: Quality Control Activity - Onsite check & Document
label | 3ec0ecd6-7219-59da-b400-30fc90fb780b |  | note | Acceptance Criteria - Surface Compliant and Surplus chip removed
label | 6694731c-cb02-5244-bba5-7e8fa2361ebe |  | note | Verifying Document - Sealing Checklist
label | 69285f5f-8319-501e-b0b1-8ea40f0dc3bd |  | note | Frequency - Prior to construction of next layer/ Prior removal of the temporary speed restriction signs
label | 59468913-4bfd-58f9-a544-729a8d04f920 |  | note | Inspection Type - Review
label | ad0fe04d-ba1b-57d5-a0aa-639f3a23bb29 |  | note | Inspection: Key - R
label | 108d3990-693e-5c4b-aef6-9439314d7e7b |  | note | Inspection: By - PM/ER
checklist-sectioned |  |  | checklist | F2LSIP - ITP 04 - Pavements | itp |  |  |  | Yes | F2LSIP - ITP 04 - Pavements | dde760f8-2901-4394-8805-5dda7f5353e6
checkpoint-group |  |  | section | 4.0 - Pavements
checkpoint-status |  |  | checkpoint | Pavements
label | 99314952-3b94-5469-a25b-738540760b69 |  | note | Inspection Point: Quality Control Activity - Final Sign Off
label | e031cf41-054b-5812-aea5-583b42983bc6 |  | note | Acceptance Criteria - All below requirements are met and approved by CR
label | 1fe9454a-ab9b-5d5c-aa3a-e84ebf4aabf6 |  | note | Verifying Document - Referenced Item numbers as below
label | a4e86077-e204-5cde-a3d0-b4eb73a7fbb2 |  | note | Frequency - Once post construction
label | dc521582-823f-5683-a15a-53ef3212d441 |  | note | Inspection Type - Hold Point
label | c646bfe5-5b9d-5bdb-bc98-4546c187999c |  | note | Inspection: Key - H
label | 05d424f6-ab4d-5f4c-a3c0-5d33ef7cd308 |  | note | Inspection: By - ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.1 - Source Properties as per NZS 4407
checkpoint-no-status |  |  | checkpoint | Source Properties as per NZS 4407
label | 73cc3844-aa2a-5446-9bd9-417c56974477 |  | note | Acceptance Criteria - Subbase AP65
checkpoint-status |  |  | checkpoint | 4.1.1 - Crushing Resistance Test 3.10
label | c5f70a23-ab7b-5cec-b169-10c49e5fe7ab |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 78c3de67-df68-544e-a252-499a39e32ec4 |  | note | Acceptance Criteria - Under a load of 100 kN less than 10% fines passing 2.36mm sieve size shall be produced
label | 8ebab81d-6b25-55d8-aa80-f969393666e7 |  | note | Verifying Document - IANZ Lab Report
label | 00b27bf9-751d-5643-a2ee-8a0b0d296c69 |  | note | Frequency - Once Per Source/Supplier
label | 29ea62b8-a1a2-5d7c-b433-de0e2e08e4c3 |  | note | Inspection Type - Review
label | 265f36d6-1acb-5064-8010-b9f5ee441057 |  | note | Inspection: Key - R
label | 363be98d-f2b6-58ae-b096-0202a8ac975b |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.1.2 - Weathering Quality Index Test Test 3.11
label | 7095e01e-7b90-5ebe-848e-41abbe063bc7 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | f019a530-1b98-5a69-a176-8fac533fef61 |  | note | Acceptance Criteria - AA, AB, AC, BA, BB, or CA
label | ddf7387e-4cd2-54a3-9c0f-26e1aec5ad11 |  | note | Verifying Document - IANZ Lab Report
label | 11d5e587-c49e-5865-a653-152a4818cf3e |  | note | Frequency - Once Per Source/Supplier
label | 09047976-6f73-5c46-8c49-7ec70311beb9 |  | note | Inspection Type - Review
label | 49df8a4c-22b1-5e12-8549-9ec428b50863 |  | note | Inspection: Key - R
label | aa97480b-8e30-52d5-8f87-423d56d800a9 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.1.3 - Soaked CBR Test Test 3.15
label | 69fb55b5-bca2-572b-854d-0d994b9b2053 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | c2fe7023-fe17-5241-bcc5-eeb38e9e6457 |  | note | Acceptance Criteria - CBR ≥ 80%
label | d244d1f7-3388-52ca-9c58-bd916f642e28 |  | note | Verifying Document - IANZ Lab Report
label | 1716df53-7b0c-5c22-bf4d-6d97d66440a6 |  | note | Frequency - Once Per Source/Supplier
label | 3f2ddfea-4150-5acb-87a0-055396f5a5e3 |  | note | Inspection Type - Review
label | 2aafbd72-5abb-5705-9720-381c99922942 |  | note | Inspection: Key - R
label | 124148bd-fc91-52b4-8699-04c5a677bfab |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.2 - Production Properties as per NZS 4407
checkpoint-no-status |  |  | checkpoint | Production Properties as per NZS 4407
label | cbddf4a2-9ee5-54c7-a627-f5507d5db4c7 |  | note | Acceptance Criteria - Subbase AP65
checkpoint-status |  |  | checkpoint | 4.2.1 - Quality of Fines - SE 3.6 - CI 3.5 - PI 3.4
label | a1f0451d-e9ae-5261-a19e-b99dda2e2f2d |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | fa1539f6-4117-5f29-a5e0-976a4a78146e |  | note | Acceptance Criteria - SE ≥ 25, CI ≤ 3, PI ≤ 6
label | f69a7f99-df05-5773-898c-417a73b05646 |  | note | Verifying Document - IANZ Lab Report
label | de197b2a-1155-5d6b-86ed-3b0a3fd85dab |  | note | Frequency - Once Per Source/Supplier
label | c12456da-77b3-59ba-9949-b90efbd60d78 |  | note | Inspection Type - Review
label | b9106b9d-2226-5c8e-908a-572db463dede |  | note | Inspection: Key - R
label | b3e8acf2-db01-5d0d-8881-73e1157b74a2 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.2.2 - Broken Face Content Test 3.14
label | 580dce8d-5341-5e81-acee-d923e6adbab6 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | fa94b273-c2b7-565d-a30e-1a20341d2130 |  | note | Acceptance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 60% by weight shall have two or more broken faces.
label | e1596381-324d-59b2-b340-cde003eeea08 |  | note | Verifying Document - IANZ Lab Report
label | 4551c726-58f0-5b85-b1b8-bf5f48395b85 |  | note | Frequency - Once Per Source/Supplier
label | 0d9f4530-1368-5c1a-91f4-964a13d939e2 |  | note | Inspection Type - Review
label | 69ca83c7-ff3f-5c61-9235-00bc7f1354a6 |  | note | Inspection: Key - R
label | 9d4bf5d0-d11e-5a68-9e29-d511472de9a4 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.2.3 - Particle Size Distribution Test 3.8.1
label | 60a4ec7b-bf54-5602-97c4-57e2c04e8d75 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 09d2e2c0-e7d3-5723-94a0-e75cae20a535 |  | note | Acceptance Criteria - As per Table to A506.2.1
label | 4ff49667-8578-5029-b682-be73045b6e43 |  | note | Verifying Document - IANZ Lab Report
label | af38757e-d7ec-51c8-bfd7-aedacc557584 |  | note | Frequency - Once Per Source/Supplier
label | 664803a6-b341-5c72-9ac6-423998701546 |  | note | Inspection Type - Review
label | c0dba56c-dd9e-5d27-9d8d-03c401c1bbc8 |  | note | Inspection: Key - R
label | 5ecf75a2-a08c-5b46-9fa0-82306c9b023d |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 4.3 - Source Properties as per NZTA M-4
checkpoint-no-status |  |  | checkpoint | Source Properties as per NZTA M-4
label | c97434ac-5fc0-58fa-b271-67714e47b561 |  | note | Acceptance Criteria - Basecourse AP40
checkpoint-status |  |  | checkpoint | 4.3.1 - Crushing Resistance Test 3.1
label | a07ec69f-2f4b-5c86-9769-3c8a702279a6 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 1fc0a6d7-95db-599d-8785-687e5a3b05c9 |  | note | Acceptance Criteria - Under 130kN load < 10% fines passing 2.36mm sieve.
label | 2b9f2519-8cc4-5370-bc10-2ef20d9f11ea |  | note | Verifying Document - IANZ Lab Report
label | 4b9ff4ea-9fcb-5166-99c4-6500fa832c45 |  | note | Frequency - Once per 10,000m3
label | 9548e54a-9561-5321-8ad0-b38d5ac3e718 |  | note | Inspection Type - Review
label | f08812bb-01d6-56e6-8868-44c0dd2c1c3d |  | note | Inspection: Key - R
label | 1c131781-5bbe-5d2a-8e9d-90ea8faa8bd9 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.3.2 - Weathering Quality Index Test 3.11
label | 2420c72c-36a4-55a4-af92-a18957b65aa1 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 30a32171-efdd-5976-bbe8-7d719b0e09b1 |  | note | Acceptance Criteria - AA,AB,BA,BB,CA
label | 780545b8-f93a-5e13-afb5-b76aa557943e |  | note | Verifying Document - IANZ Lab Report
label | f7a6b926-4cc1-53cb-9a56-9225a87e6552 |  | note | Frequency - Once per 10,000m3
label | d75e4c56-54a2-541f-982f-ce7b86822d29 |  | note | Inspection Type - Review
label | 7391d165-bcf4-5527-b8bd-fc92e8357538 |  | note | Inspection: Key - R
label | fd136d27-a4fa-56de-99a3-72764dd82d1b |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.3.3 - California Bearing Ratio Test 3.15
label | 078a9820-98cc-5495-9436-1aaf5e8dadd1 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 5bae0bb9-d0c8-5178-9294-c9c78228942c |  | note | Acceptance Criteria - Not less than 80%
label | 0ba4745a-9a50-5139-ad21-94d075b55543 |  | note | Verifying Document - IANZ Lab Report
label | d8e530ee-01d4-5725-bbda-3f92cdd33309 |  | note | Frequency - Once per 10,000m3
label | 4b02cb17-9c8f-5bb4-8c3b-091b260e4b6a |  | note | Inspection Type - Review
label | 0a1bfd70-3743-5678-9709-35196f5f1fac |  | note | Inspection: Key - R
label | 65aaad7a-12b7-5536-9fa7-c7b61f60db4a |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 4.4 - Production Properties as per NZTA M-4
checkpoint-no-status |  |  | checkpoint | Production Properties as per NZTA M-4
label | 3ddb25ed-f5f7-5aa1-9183-38eeb6c9a6da |  | note | Acceptance Criteria - Basecourse AP40
checkpoint-status |  |  | checkpoint | 4.4.1 - Quality of Fines - SE 3.6 - CI 3.5 - PI 3.4
label | 06202c4e-5d6a-5fb3-ae83-72e7fab4c01a |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 988ba629-46f9-5ff7-8f60-fac77cfdf60d |  | note | Acceptance Criteria - SE ≥ 40, CI ≤ 3, PI ≤ 5
label | 43952437-370d-5170-954f-8ccad0454250 |  | note | Verifying Document - IANZ Lab Report
label | 56a86efa-db22-5b9a-aed4-34e70dff862f |  | note | Frequency - Lot Size =
label | c9372153-9f74-5dca-bb1f-c98ef72e1c8e |  | note | ○ < 400m2 = 2 Samples
label | 49569234-899b-5569-8242-68f885315445 |  | note | ○ 400 to 1500m2 = 3 Samples
label | aa43e504-a173-5e12-869b-19395b7887b7 |  | note | ○ 1500 to 4000m3 = 4 Samples
label | 22039c25-90f6-5896-801a-cc268a636fa9 |  | note | Inspection Type - Review
label | 5f3a83a2-5886-5d85-bbc3-fe6e83790693 |  | note | Inspection: Key - R
label | c99f9e8e-d967-50de-8388-615bfdc32778 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.4.2 - Broken Face Content Test 3.14
label | c8aacbe3-d0cc-5f2f-b55d-dcff79cba695 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | de6d4705-74e4-578c-8199-8c4d85114b95 |  | note | Acceptance Criteria - 19mm - 37.5mm - NOT LESS THAN 70%
label | f9ea7339-9c1d-5c64-a205-0f777cd63a8a |  | note | ○ 9.5mm - 19.0mm - NOT LESS THAN 70%
label | 03a0f2cd-8d91-5cbd-b485-dd8cf053a155 |  | note | ○ 4.75mm - 9.5mm - NOT LESS THAN 70%
label | b88649d3-ed65-5e18-a7a3-2f5b05d936f3 |  | note | Verifying Document - IANZ Lab Report
label | 32205d55-8f75-573a-8692-b9888d194183 |  | note | Frequency - Lot Size =
label | bdc98621-d642-5b8a-b66f-0036eb9a1110 |  | note | ○ < 400m2 = 2 Samples
label | 53b1c018-7d69-595a-b8bc-4fa5d94b3f00 |  | note | ○ 400 to 1500m2 = 3 Samples
label | 4a0a643a-a928-5aa9-a5ff-2f38afaf091e |  | note | ○ 1500 to 4000m3 = 4 Samples
label | 80dc92fd-e688-5437-9c29-cbc3189439a3 |  | note | Inspection Type - Review
label | 77377f55-52f6-5ea6-94cf-5c1aba12605d |  | note | Inspection: Key - R
label | 5cbb660e-a773-50b6-9002-235719f3e772 |  | note | Inspection: By - ER
checkpoint-status |  |  | checkpoint | 4.4.3 - Particle Size Distribution Test 3.8.1
label | 7b0f4bb1-df78-5110-b83b-06072fd01c91 |  | note | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | 3947dc84-111b-5412-b798-ccbd737a0ba6 |  | note | Acceptance Criteria - As per NZTA M/4 AP40 PSD Requirements
label | bc2f0715-79f1-53aa-b91b-7aaa2a1766d1 |  | note | Verifying Document - IANZ Lab Report
label | 817dfc61-b196-5222-887c-1c990c33f401 |  | note | Frequency - Lot Size =
label | 84f5a69a-2fef-5553-9894-092645b64905 |  | note | ○ < 400m2 = 2 Samples
label | f4a36df9-b7f5-5d43-9cd8-49707f0515a6 |  | note | ○ 400 to 1500m2 = 3 Samples
label | 264dcee0-26ec-5d3e-810f-30bd6b03f7d1 |  | note | ○ 1500 to 4000m3 = 4 Samples
label | 8974d9a7-a765-5dff-8041-5379f5d631bd |  | note | Inspection Type - Review
label | cb6f474e-c1d3-5e0b-98a7-b36bbe8dfae1 |  | note | Inspection: Key - R
label | faa23e8f-b913-5072-addb-46620587fce7 |  | note | Inspection: By - ER
checkpoint-group |  |  | section | 4.5 - Pavement Construction
checkpoint-no-status |  |  | checkpoint | Pavement Construction
label | 5a943e93-b4b3-562a-9ed0-831a7740eb81 |  | note | Acceptance Criteria - Require formal sign off record of previous layer prior to placment of next layer. DNZ to develop sign off sheet or approval system of work.
checkpoint-status |  |  | checkpoint | 4.5.1 - Visual inspection of final trimmed subgrade surface
label | 5ed0a90a-af0b-511a-92d6-04887959e885 |  | note | Inspection Point: Quality Control Activity - Pre pavement construction visual inspection
label | 1f437c71-a35d-583f-8801-10114ca4432d |  | note | Acceptance Criteria - Entire surface to be firm, uniform and smooth.
label | 7c536bf5-18da-54a2-99b3-49b0670373d4 |  | note | Verifying Document - Site Inspection Form
label | 7eb3eee4-5eec-5f11-9672-9e416f7821fd |  | note | Frequency - Once per construction area
label | 8b4247ce-dbe0-5b8b-9e9d-4d6e7e9af9c3 |  | note | Inspection Type - Witness Point
label | b0572551-11dd-5ebc-81cb-64fa31817e5d |  | note | Inspection: Key - W
label | c2264362-3ede-569c-b4b5-8ee59e90351c |  | note | Inspection: By - PM & ER
checkpoint-status |  |  | checkpoint | 4.5.2 - Survey Setout
label | 3c468a73-4ba4-57d7-82f9-a1e01fafadf6 |  | note | Inspection Point: Quality Control Activity - Height Check
label | 5e7d51f8-2c1f-5bea-a9d9-1dea06c19362 |  | note | Acceptance Criteria - Check to ensure pegs are still sitting at correct height from initial set out. Target MDD to be approved prior to Construction. Lab MDD Reports to be submitted for Approval.
label | 50e78ee1-bce1-56c5-a3f7-640a27d35eb5 |  | note | Verifying Document - Visual
label | 8b4e8498-6dd2-5a6c-a2e7-e6368807e594 |  | note | Frequency - Prior to subbase construction
label | b2669b1b-6699-5710-a5d8-ca806654d823 |  | note | Inspection Type - Check
label | ee9e5e9e-3cb3-5ca4-bca7-dd70e4b93acb |  | note | Inspection: Key - C
label | 026146f3-d947-517f-bed9-ce8de19ee374 |  | note | Inspection: By - SV
checkpoint-status |  |  | checkpoint | 4.5.3 - Subbase Compaction
label | 27228a24-8eaf-53b5-88c4-c6940bd19f0e |  | note | Inspection Point: Quality Control Activity - NDM - Dry Density
label | 4e2c7259-4ee3-5a68-80bb-00fe4ae8bbb5 |  | note | Acceptance Criteria - Mean DD ≥ 95% of MDD, Minimum DD ≥ 92% of MDD
label | c34b9df2-37c0-5835-9355-adba667e3a95 |  | note | Verifying Document - IANZ Lab & Report, NDM Report
label | 3c553075-4d58-5033-b5de-6a9605eb7397 |  | note | Frequency - MDD to be determind per 5000m2 of material laid.
label | b90fccb0-3cb7-51e2-a21b-d1ab7d946b9b |  | note | ○ Compacted layer to be tested in 1000m2 lots, at randomly generated locations.
label | fdc81900-0f0a-5eb3-a283-8d44061d3cb6 |  | note | Inspection Type - Hold Point
label | 473866b7-c9fc-5ec8-b031-f4d5cb5fa9de |  | note | Inspection: Key - H
label | ce69399c-be95-5714-983e-26ad4ece1726 |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5.4 - Subbase Deflection
label | e302683d-e38c-5a90-bc3d-d80743f03175 |  | note | Inspection Point: Quality Control Activity - Benklemen Beam Test
label | a77434f5-b28c-50b8-abe9-dd79667d579f |  | note | Acceptance Criteria - Maximum Deflections of not more than (see surfacing notes)
label | 4f37fc30-c4d3-5d8c-ab12-b2c6ab4e02a9 |  | note | Verifying Document - IANZ Report and Truck Weightbridge Docket (where applicable)
label | 389352a2-122b-5b57-981b-9e98faf2575f |  | note | Frequency - 10m Intervals - alternating wheel paths
label | 7dc3a20e-6e9e-5a97-b439-0d501c6ee537 |  | note | Inspection Type - Hold Point
label | f7fbc745-6f10-5da5-8339-c3f64ea068ce |  | note | Inspection: Key - H
label | 08a0a77d-dd35-5cd3-9930-3d8d4a60c902 |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5.5 - Level Compliance
label | 4e8f4da1-1f6e-574a-b33c-520bf235b75e |  | note | Inspection Point: Quality Control Activity - Survey As-built
label | 547bbb68-0f9c-54f5-a9c6-8ce0e3504b99 |  | note | Acceptance Criteria - Subbase level to be within +5mm / - 25mm of design
label | 7b16264e-8d9b-531b-b5d8-f2578c1bc29d |  | note | Verifying Document - 20m Survey Cross Sections
label | 490b3d4a-eb3d-5f49-aa54-3ec4c5be2ce4 |  | note | Frequency - 20m Cross Sections
label | cfa612ff-c4f5-5d49-8b82-ba6526bee1de |  | note | Inspection Type - Witness Point
label | c54b4125-75e7-5998-b0a4-71c2fce5b7af |  | note | Inspection: Key - W
label | 402f578d-4235-5326-abce-1988dc77529a |  | note | Inspection: By - PM & ER
checkpoint-status |  |  | checkpoint | 4.5.6 - Basecourse Compaction
label | f52d3f1f-8595-59aa-948c-2d4dcfb38cfa |  | note | Inspection Point: Quality Control Activity - NDM - Dry Density
label | 46a03462-d274-50b3-aa91-47bbdec8b862 |  | note | Acceptance Criteria - Mean DD ≥ 98% of MDD, Minimum DD ≥ 95% of MDD
label | aadaf353-15bb-5091-a956-c2f4af6328be |  | note | Verifying Document - IANZ Lab & Report, NDM Report
label | bbbd6e33-43f8-5808-9c80-0e0661a36b20 |  | note | Frequency - MDD to be determind per 5000m2 of material laid.
label | 032df665-6e6d-5184-a330-77611718ceab |  | note | ○ Compacted layer to be tested in 1000m2 lots, at randomly generated locations.
label | a85bffbe-4add-55ef-b9aa-11797c9a3568 |  | note | Inspection Type - Hold Point
label | f9de22a5-aabb-5e50-91aa-ca79c1c07254 |  | note | Inspection: Key - H
label | 097f5828-980c-54d4-8c0e-30ae52cb5028 |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5.7 - Basecourse Deflections
label | 8fd7ada7-1bb0-5547-9e98-82ea3034d1db |  | note | Inspection Point: Quality Control Activity - Benklemen Beam Test
label | 22aa3d10-2b9e-5159-9f4a-bb5faaf49b47 |  | note | Acceptance Criteria - Only Required if subbase BB not completed - Engineer to advise target
label | 647de660-7d1f-5c21-855c-95c8d1c3cbab |  | note | Verifying Document - IANZ Report and Truck Weightbridge Docket (where applicable)
label | c6ac99ed-4dd5-5542-bae6-b1235901f0dc |  | note | Frequency - 10m Intervals - alternating wheel paths
label | e8f9b4c9-5f94-5aa4-89da-14e146e67d5a |  | note | Inspection Type - Hold Point
label | e81a2169-edac-57bc-bfe7-6cb4abc1a3df |  | note | Inspection: Key - H
label | 54ba5546-1939-57c7-bb95-9a3a7d9309cd |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5.8 - Final Surface Shape & Levels
label | 1f79a297-e1c6-5d54-b4aa-72484866b27c |  | note | Inspection Point: Quality Control Activity - Straight Edge, Survey As-built
label | 3a6368cc-0c20-5dcb-96c3-98e4e5ab9ac0 |  | note | Acceptance Criteria - Pavement shall not deviate greater than 10mm under a 3m straight edge.
label | f405308a-d1bc-565e-942d-69dc319bf4ea |  | note | ○ No area of pavement shall pond water where grade is greater than 1%.
label | ee62c3e8-f178-57f4-b978-25391f859878 |  | note | ○ Pavement to be within +15mm / -5mm of design levels (or +/- 5mm against the lip of a channel)
label | 47be9865-78b4-52ba-8f1f-450b781631e1 |  | note | Verifying Document - Straight Edge Sheet, Site Inspection Form, 20m Survey Cross Sections
label | 6d68541a-9dcd-5895-bc80-ab339d374087 |  | note | Frequency - Once per construction area, 20m Cross Sections
label | d30394aa-7435-5ae8-aee4-67a5ca6aed77 |  | note | Inspection Type - Hold Point
label | 92990419-c69d-5fb6-be21-b5893b7d6080 |  | note | Inspection: Key - H
label | c3d2eab8-2a97-5729-98ff-cf6365bd4c2b |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5.9 - Final Surface Visual Inspection
label | cbad2382-dd00-5037-989d-da9908543668 |  | note | Inspection Point: Quality Control Activity - Onsite Surface Inspection
label | 7efdab7f-a492-5cad-97f8-c7a387824916 |  | note | Acceptance Criteria - Shall present a swpet, tightly consolidated surface in which:
label | 2df01f9b-115e-53d9-b267-d2f2f5165782 |  | note | ○ Large aggregate is exposed to the surface & held in place with a matrix of smaller agregates.
label | 81fa0d52-4067-5562-96fa-2db5b5590ec9 |  | note | ○ Smaller aggregate is held in place by fines material
label | 02216856-d29e-58a5-8304-0fe09a199ef3 |  | note | ○ Matrix does not displace under normal trafficing or sweeping.
label | c6473b50-5573-512e-b8f9-f21aab66b452 |  | note | Verifying Document - Site Inspection Form
label | 34df9e7d-36ba-5df2-a294-8b1939a5f930 |  | note | Frequency - Once per construction area
label | 4d5270b4-7faf-5d04-b20b-5f1f587332b7 |  | note | Inspection Type - Hold Point
label | 1aa7b5e3-7b80-581a-a5cb-e7699e87dbb7 |  | note | Inspection: Key - H
label | 9ebd2c08-6f1c-5959-84bd-ef6620d0957e |  | note | Inspection: By - PM & ER
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT