## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 134.75 - 1.0 PRE-CONSTRUCTION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 01.0 PRE-CONSTRUCTION
section | 1.0 PRE-CONSTRUCTION
checkpoint | 1.01 - Check IFC Drawings
label | DRAWING / SPECIFICATION REF.: Kiwirail – North Auckland Line Recovery 136km Construction Issue (Rev A)
label | SPECIFICATION DETAIL SUMMARY: Ensure latest revision is being used
label | ACCEPTANCE CRITERIA: Correct drawings
label | TEST SPEC AND FREQUENCY: Prior to works, updated accordingly based on formal correspondence
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Controlled IFC drawings being used – Checkpoint on QA
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): Internal
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 2.0 BULK EARTHWORKS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 02.0 BULK EARTHWORKS
section | 2.0 BULK EARTHWORKS
checkpoint | 2.01 - Source Selection Criteria - Ballast
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.1; Table 2.1
label | SPECIFICATION DETAIL SUMMARY: Ballast shall comply with the requirements of KiwiRail C-ST-FO-4110 Formation, v.1 March 2019.
label | ○ If existing ballast material is proposed by the contractor to be stripped and re-used in construction, the ballast stockpile shall be inspected and approved by the Engineer prior to reinstatement.
label | ACCEPTANCE CRITERIA: Ballast material shall meet the requirements stated in document T-SP- MM-60140 Supply of Crushed and Screened Stone Ballast
label | TEST SPEC AND FREQUENCY: Spec and frequency must comply with Kiwirail C-ST- FO-4110
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.02 - Source Selection Criteria - Sub-ballast (GAP40)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.2;Table 2.1
label | SPECIFICATION DETAIL SUMMARY: The GAP40 shall comply with the NZTA M/4 specification for basecourse aggregate.
label | Fill materials shall be sourced from areas of cut or from alternative sources. If the Contractor wishes to propose materials from alternative sources then they shall provide details of such sources for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Allowable Particle Size: < 40 mm
label | ○ (1*) Percentage Fines (0.07mm): <7%
label | ○ (2*) Weathering Quality Index: The aggregate shall have a quality index > or = to CA
label | ○ (3*) Crushing Resistance Test: <10% fines passing 2.36 mm sieve under test load of 130 kN
label | ○ (4*) Broken Face Content: 50% for >37.5 mm fraction and 19 mm – 37.5 mm fraction
label | TEST SPEC AND FREQUENCY: Min. 2 tests per source
label | 1* = Testing method NZS 4402:1986 Test 2.8.1
label | 2* = Testing method NZS 4407:2015 Test 3.11
label | 3* = Testing method NZS 4407:2015 Test 3.10
label | 4* = Testing method NZS 4407:2015 Test 3.14
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.03 - Source Selection Criteria - Structural Fill/Hardfill GAP65
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.5; Table 2.1
label | SPECIFICATION DETAIL SUMMARY: Defines a well graded aggregate, with slightly weathered to unweathered fragments of rock up to maximum 65 mm characteristic dimension and which is relatively free of fines and other mineral matter such that when compacted the rock fragments can achieve point-to-point contact.
label | ○ Fill materials shall be sourced from areas of cut or from alternative sources. If the Contractor wishes to propose materials from alternative sources then they shall provide details of such sources for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Allowable Particle Size: < 65 mm
label | ○ (1*) Percentage Fines (0.07mm): <7%
label | ○ (2*) Weathering Quality Index: The aggregate shall have a quality index > or = to CA
label | ○ (3*) Crushing Resistance Test: <10% fines passing 2.36 mm sieve under test load of 130 kN
label | ○ (4*) Broken Face Content: 50% for >37.5 mm fraction and 19 mm – 37.5 mm fraction
label | TEST SPEC AND FREQUENCY: Min. 2 tests per source
label | 1* = Testing method NZS 4402:1986 Test 2.8.1
label | 2* = Testing method NZS 4407:2015 Test 3.11
label | 3* = Testing method NZS 4407:2015 Test 3.10
label | 4* = Testing method NZS 4407:2015 Test 3.14
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.04 - Source Selection Criteria - Rockfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.6; Table 2.1
label | SPECIFICATION DETAIL SUMMARY: Defines a well graded aggregate with slightly weathered to unweathered fragments of rock up to maximum 300 mm characteristic dimension and which is relatively free of fines and other mineral matter such that when compacted the rock fragments can achieve point-to-point contact.
label | ○ Fill materials shall be sourced from areas of cut or from alternative sources. If the Contractor wishes to propose materials from alternative sources then they shall provide details of such sources for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Allowable Particle Size: < or = 300mm
label | ○ (1*) Percentage Fines: nil
label | ○ (2*) Weathering Quality Index: The aggregate shall have a quality index > or = to CA
label | ○ (3*) Crushing Resistance Test: <10% fines passing 2.36 mm sieve under test load of 130 kN
label | ○ (4*) Broken Face Content: nil
label | TEST SPEC AND FREQUENCY: Min. 2 tests per source
label | 2* = Testing method NZS 4407:2015 Test 3.11
label | 3* = Testing method NZS 4407:2015 Test 3.10
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.05 - Earthworks Tolerances
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.4.9
label | SPECIFICATION DETAIL SUMMARY: All earthworks shall adhere to the lines, levels and grades shown on drawings or Engineer’s instruction. Accuracy of surfaces under metal courses or concrete structures must preserve min. thicknesses of overlying layers.
label | ACCEPTANCE CRITERIA: Tolerances shall otherwise be as follows:
label | ○ Subgrade surfaces 0mm to - 30mm
label | ○ Batters 0mm to +100mm
label | ○ Rockfill surfaces ±200mm
label | ○ Other surfaces 0mm to + 75mm
label | TEST SPEC AND FREQUENCY: For every section of earthworks completed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.06 - Inspection of stripped surface
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.4.10
label | SPECIFICATION DETAIL SUMMARY: The Engineer must be notified before any cut or fill begins.
label | ○ The Engineer will inspect the stripped surface and decide if additional excavation, undercutting, backfilling, or other works such as drainage are needed.
label | ○ No cut or fill can proceed in the area until the Engineer approves the commencement after necessary inspections and approvals have been completed.
label | ACCEPTANCE CRITERIA: The Engineer inspects and approves the stripped surface and any required works. No cut or fill is allowed until the Engineer gives approval.
label | TEST SPEC AND FREQUENCY: Inspect prior to any cut or fill begins
label | ○ Re-inspect after cut (prior to fill)
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineers approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Standards and Testing - General
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9
label | SPECIFICATION DETAIL SUMMARY: General Testing – The locations and levels of all in-situ tests shall be recorded within 0.2m horizontally and 0.1m vertically
label | ○ All testing, both in-situ and laboratory, is to be carried out using an IANZ accredited testing organisation. Full details of the proposed testing organisation(s) shall be submitted to the Engineer for their approval.
label | ACCEPTANCE CRITERIA: General Testing – The locations and levels of all in-situ tests shall be recorded within 0.2m horizontally and 0.1m vertically
label | ○ All testing, both in-situ and laboratory, is to be carried out using an IANZ accredited testing organisation. Full details of the proposed testing organisation(s) shall be submitted to the Engineer for their approval.
label | TEST SPEC AND FREQUENCY: For all compaction testing completed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineers approval of the proposed testing organization
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.08 - General Undercutting (Outside the track formation area)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.5.6
label | SPECIFICATION DETAIL SUMMARY: The requirements for general undercutting outside the track formation area, i.e. within gullies, for the fill foundations and below areas of cut
label | ○ All organic materials, other unsuitables, materials with an undrained shear strength of less than 75 kPa or less than 3 blows per 100 mm using a Scala penetrometer to 1.5 m depth, or otherwise shown on the drawings, or instructed by the Engineer, shall be undercut.
label | ○ The depth of the undercut in materials will be specified by the Engineer when the material at the subgrade level has been exposed and evaluated.
label | ACCEPTANCE CRITERIA: Shear Vane: Target Criteria: No individual reading less than 75 kPa
label | Or
label | ○ Scala Penetrometer: Target Criteria: 3 blows/100mm to a depth of 1.5m
label | TEST SPEC AND FREQUENCY: Shear vane and/or Scala testing, Frequency not specified – Engineer to confirm
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Written instruction by the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Formation Undercutting
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.5.7
label | SPECIFICATION DETAIL SUMMARY: Undercuts are required if the foundation soils do not meet the minimum design requirements.
label | ○ Prior to the placement of any fill the foundation shall be inspected and approved by the Engineer.
label | ○ Two stages to expedite testing and decision making on extents of undercut:
label | – 1) Initial testing using the Scala penetrometer probes to a minimum of 1.5 m depth below the base of the foundation.
label | – 2) Further testing to be undertaken after excavation to the depth of the proposed undercut surface (where required) using local test pitting or full excavation of identified soft soil then undertake Scala penetrometer and shear vane testing to confirm strength of founding layers and extent/depth of any remaining softer material and/or depth to competent material.
label | ACCEPTANCE CRITERIA: Rail Embankments
label | ○ Shear vane – No individual reading less than 80 kPa and average reading >100 kPa.
label | ○ Scala - 3 blows/100mm (for cohesive soils); 5 blows/100mm (for granular soils)
label | ○ Formation for ballast and trackset Scala/Shear vane – equivalent CBR value as set out in C-ST-FO-4110.
label | TEST SPEC AND FREQUENCY: Rail Embankments:
label | ○ Shear Vane: 1 test per 5m x 5m grid and minimum of 6 tests.
label | ○ Scala Penetrometer: 1 test per 5m x 5m grid and minimum of 6 tests.
label | ○ Formation for ballast and track set:
label | ○ Shear Vane / Scala Penetrometer: Three tests every 5m length of track
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Conditioning and Spreading of Fill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.7.2
label | SPECIFICATION DETAIL SUMMARY: Before fill is placed in any area, the Contractor shall notify the Engineer that the fill foundation has been stripped, drained, including subsoil drains and prepared as required by the drawings and Specification and is ready for the Engineer’s inspection and approval.
label | ACCEPTANCE CRITERIA: The fill foundation has been stripped, drained, including subsoil drains and prepared as required by the drawings and Specification.
label | TEST SPEC AND FREQUENCY: Engineer to inspect and approve before fill is placed in any area
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Pre-Construction Compaction Testing
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.3
label | SPECIFICATION DETAIL SUMMARY: Before placing any fill the Contractor shall carry out lab testing on any material to be used for testing to confirm the max dry density and optimum water content of each material type.
label | ACCEPTANCE CRITERIA: Test results shall be provided to the Geotech Engineer to confirm the target dry densities and water contents for each material
label | TEST SPEC AND FREQUENCY: Testing shall be undertaken by an IANZ accredited testing organization and undertaken according to the standards outline in Table 2.3
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: IANZ test results, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.12 - Compaction Requirements – Buttress Fill (cohesive)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.5, Table 2.4
label | SPECIFICATION DETAIL SUMMARY: Fill materials shall be compacted so as to achieve the minimum target criteria. Should any test result fail to meet the min. target criteria the Contractor shall propose remedial measures for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Shear Vane: Target Criteria: Average reading over 10 consecutive readings shall not be less than 100 kPa with no individual readings less than 80 kPa.
label | ○ In-situ Dry Density: Target Criteria: ≥ 95% Maximum Dry Density.
label | ○ Air Voids: Target Criteria: Average reading over 10 consecutive readings shall not exceed 6%, with no single reading exceeding 8%.
label | TEST SPEC AND FREQUENCY: Shear Vane: Minimum Test Frequency: 1 set per 250 m3 of fill.
label | ○ In-situ Dry Density: Minimum Test Frequency: 1 set of NDM test per 250 m2 of fill lift
label | ○ Air Voids: Minimum Test Frequency: 1 set of NDM test per 250 m2 of fill lift
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), IANZ test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.13 - Compaction Requirements – Sub- ballast (GAP40)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.5, Table 2.5
label | SPECIFICATION DETAIL SUMMARY: Before placing any fill the Contractor shall carry out lab testing on any material to be used for testing to confirm the max dry density and optimum water content of each material type.
label | ACCEPTANCE CRITERIA: In-situ Dry Density: Target Criteria: ≥ 98% Maximum Dry Density.
label | ○ Clegg Hammer Test: Target Criteria: Single test minimum clegg impact value ≥ 18. Average CIV ≥ 22 (over 5 consecutive tests)
label | TEST SPEC AND FREQUENCY: • In-situ Dry Density: Minimum Test Frequency: 1 set of NDM test per 50 m2 of fill lift.
label | ○ Clegg Hammer Test: Minimum Test Frequency: 1 test per 50 m2 of fill lift.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), IANZ test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.14 - Compaction Requirements – Structural Fill / Hardfill (GAP65) / Rockfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.5, Table 2.5
label | SPECIFICATION DETAIL SUMMARY: Fill materials shall be compacted so as to achieve the minimum target criteria. Should any test result fail to meet the min. target criteria the Contractor shall propose remedial measures for the Engineer’s approval
label | ACCEPTANCE CRITERIA: In-situ Dry Density: Target Criteria: ≥ 95% Maximum Dry Density.
label | ○ Clegg Hammer Test: Target Criteria: Single test minimum clegg impact value ≥ 18. Average CIV ≥ 22 (over 5 consecutive tests) (equivalent CBR of >15%).
label | TEST SPEC AND FREQUENCY: In-situ Dry Density: Minimum Test Frequency: 1 set of NDM test per 50 m2 of fill lift and every 1m lift. Minimum of 3 tests per approach embankment.
label | ○ Clegg Hammer Test: Minimum Test Frequency: 1 test per 50 m2 of fill lift.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), IANZ test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.15 - Grassing
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.12
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall submit to the Engineer for approval their proposed seed mixture fertiliser type and respective application rates prior to commencement of the grassing
label | ACCEPTANCE CRITERIA: Engineer to approve the proposed seed mixture fertiliser type and respective application rates
label | TEST SPEC AND FREQUENCY: Prior to commencement of grassing
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Specification for the seed mixture fertiliser type & application rate, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checklist | CH 134.75 - 3.0 GEOSYNTHETICS SPECIFICATION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 03.0 GEOSYNTHETICS SPECIFICATION
section | 3.0 GEOSYNTHETICS SPECIFICATION
checkpoint | 3.01 - Pre-commencement
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 3.3.1
label | SPECIFICATION DETAIL SUMMARY: Before any geosynthetic installation is commenced, or fill is placed in any area, the Contractor shall advise the Engineer
label | ACCEPTANCE CRITERIA: The Contractor shall be responsible for the correct setting out of the work and shall see that the specified locations, orientations, lengths, depths, spacings, and levels are strictly adhered to. Engineer to confirm requirements.
label | TEST SPEC AND FREQUENCY: Before any geosynthetic installation is commenced, or fill is placed in any area, the Contractor shall advise the Engineer, with at least one working days’ notice
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 3.02 - Geogrid
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 3.4.1
label | SPECIFICATION DETAIL SUMMARY: Specific geogrid reinforcement types are shown on the drawings. Alternative, equivalent geogrids may be approved by the Engineer. The alternative geogrids shall have similar performance characteristics equivalent to or better those of the specified materials.
label | ACCEPTANCE CRITERIA: The following information shall be provided to the Engineer to allow approval of the proposed alternative geogrids:
label | ○ Roll widths
label | ○ Minimum overlap width between rolls
label | ○ Characteristics initial strength
label | ○ Material reduction factor – creep rupture
label | ○ Creep limited strength based on creep rupture
label | ○ Material reduction factor – installation damage in sand and gravel
label | ○ Material reduction factor – environmental effects at 100 years design life
label | ○ Long term design strengths in sand and gravel (at 100 years design life)
label | ○ Coefficient of interaction for pullout
label | ○ Coefficient of direct sliding
label | TEST SPEC AND FREQUENCY: Engineer to approve prior to use of alternative geogrid
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation from the Engineer, Geogrid Spec
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 3.03 - Separation Geotextile
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 3.4.2
label | SPECIFICATION DETAIL SUMMARY: Specific separation geotextile types are shown on the drawings. Alternative, equivalent geotextiles may be approved by the Engineer. Separation geotextile shall be non-woven, needle-punched geotextile that have similar performance characteristics equivalent to or better than those of the specified materials and shall meets the requirements of TNZ F/7:2003
label | ACCEPTANCE CRITERIA: Specification for Geotextile Wrapped Aggregate Subsoil Drain Construction as follows:
label | 1) Filtration Class 2, Strength Class B for separation under or within embankments (including drainage blanket applications)
label | 2) Filtration Class 1, Strength Class C for separation behind the reinforced slope facing (e.g. Green Terramesh units or similar)
label | 3) Filtration Class 1, Strength Class D for separation under rockfill in embankments (including drainage blanket applications)
label | TEST SPEC AND FREQUENCY: Engineer to approve prior to use of alternative geotextiles
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation from the Engineer, Geogrid Spec
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 3.04 - Tolerances
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 3.5.5
label | SPECIFICATION DETAIL SUMMARY: The front facing of the slope shall be aligned so that the front face varies not more than 100 mm from a 5 m straight edge held horizontally and vertically.
label | ○ Curved slopes shall be constructed with a uniform angular change so that the slope presents an evenly curved surface pleasing to the eye. The maximum horizontal gap between adjacent geogrids at the slope face shall be 10 mm.
label | ACCEPTANCE CRITERIA: Front face varies not more than 100 mm from a 5 m straight edge held horizontally and vertically.
label | ○ The maximum horizontal gap between adjacent geogrids at the slope face shall be 10 mm.
label | TEST SPEC AND FREQUENCY: For every section of geosynthetic installed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 3.05 - Quality Assurance – information to be supplied
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 3.7, Table 3.1
label | SPECIFICATION DETAIL SUMMARY: On delivery of geosynthetics, the Contractor is to provide the following information:
label | ○ Product name
label | ○ Name and address of producer/supplier
label | ○ Manufacturer’s compliance certificate
label | ACCEPTANCE CRITERIA: The following information to be supplied:
label | ○ Geosynthetics:
label | 1 - Product Name
label | 2 - Name and Address of producer/supplier
label | 3 - Manufacturer’s compliance certificate
label | ○ Separation Geotextile:
label | 4 - Checklist for directional placement, tensioning, laps, spacing, damage
label | ○ Geogrid:
label | 5 - Checklist for directional placement, tensioning, laps, spacing, damage
label | TEST SPEC AND FREQUENCY: Min. frequency:
label | 1 - Check each lot (1 roll)
label | 2 - Check each lot (1 roll)
label | 3 - Check each lot (1 roll)
label | 4 - 1 checklist per 100m2 of geosynthetic installed
label | 5 - 1 checklist per geosynthetic is installed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Dockets, Compliance Certificate
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 3.06 - Quality Assurance – Material Testing
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 3.7, Table 3.2
label | SPECIFICATION DETAIL SUMMARY: Testing requirements as per Table 3.2 of the Specifications
label | ACCEPTANCE CRITERIA: Geogrid – Tensile strength (Machine Direction) – ISO10319
label | TEST SPEC AND FREQUENCY: 1 test per batch – min. tensile strength shall be shown on the drawings
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Test results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 4.0 SUBSOIL DRAINAGE – COUNTERFORT DRAINS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 04.0 SUBSOIL DRAINAGE – COUNTERFORT DRAINS
section | 4.0 SUBSOIL DRAINAGE – COUNTERFORT DRAINS
checkpoint | 4.01 - Pre-commencement
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.3
label | SPECIFICATION DETAIL SUMMARY: Before any subsoil or bored inclined drain installation is commenced or fill is placed in any area the Contractor shall advise the Engineer.
label | ACCEPTANCE CRITERIA: The Contractor shall be responsible for the correct setting out of the work and shall see that the specified locations, gradients, depths and levels are strictly adhered to.
label | TEST SPEC AND FREQUENCY: Engineer to be given at least one working days’ notice, so that they may inspect the area and confirm the requirements.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.02 - Materials – Drainage Pipe
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.1.1
label | SPECIFICATION DETAIL SUMMARY: Drainage pipe material as per spec and or drawings or as instructed by the Engineer
label | ACCEPTANCE CRITERIA: Counterfort drainage pipes shall generally be 100 mm diameter. SDR 11 HDPE pipe, or as shown on the drawings or as instructed by the Engineer.
label | ○ The pipes shall be slotted as specified on the drawings with the slots carefully formed to 2 mm width (+/- 0.2 mm) and clear of all debris and swarf. The drainpipes shall comply with the relevant specifications referred to in TNZ F/2.
label | TEST SPEC AND FREQUENCY: Visual inspection and check pipe matches spec and or drawings prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Material Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.03 - Materials – Filter Material and Backfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.1.2
label | SPECIFICATION DETAIL SUMMARY: The counterfort drain pipe shall be surrounded and immediately overlain by filter materials as defined in TNZ F/2 and Table 4.1
label | ACCEPTANCE CRITERIA: Filter material shall be placed in the trench to the thickness shown on the drawings or as instructed by the Engineer.
label | ○ Backfill material for the remainder of the trench shall be either clean well graded 40/20 or 20/7 material; or filter material as defnied in TNZ F/2 and Table 4.1, or as instructed by the Engineer
label | – – – – – – – – – – – – – – – – – –
label | Table 4.1 Grading of backfill
label | Test sieve aperture ¦¦ Percentage passing
label | – – – – – – – – – – – – – – – – – –
label | 53 mm ¦¦ 100
label | 13.2 mm ¦¦ 10 maximum
label | 4.75 mm ¦¦ 0
label | – – – – – – – – – – – – – – – – – –
label | TEST SPEC AND FREQUENCY: Visual inspection and check materials match spec and or drawings and or Engineers instruction
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Material Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.04 - Trench Excavation
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.2
label | SPECIFICATION DETAIL SUMMARY: Trench grade and depth as shown on the drawings or as instructed by the Engineer.
label | ACCEPTANCE CRITERIA: Trench widths shall be a minimum of 300 mm increasing to a minimum of 600 mm for trenches greater than 1 m deep.
label | ○ Trenches shall be excavated to depth/grade as shown on drawings or as instructed by the Engineer
label | TEST SPEC AND FREQUENCY: For every section of trench excavated
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.05 - Bedding and Installation of Drainage Pipe
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.3
label | SPECIFICATION DETAIL SUMMARY: Installation of pipe and bedding material as per spec and or drawings
label | ACCEPTANCE CRITERIA: The drainage pipe lengths shall be joined following the manufacturer’s instructions or as approved by the Engineer, with the pipe jointing such as to leave a smooth flush internal surface. Min. 75mm of filter material which completely surrounds the drainage pipe.
label | TEST SPEC AND FREQUENCY: For every section of pipe installed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.06 - Backfilling
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.4
label | SPECIFICATION DETAIL SUMMARY: Contractor to propose, for the Engineers approval, a method of compaction and testing procedures to demonstrate that relative density has been achieved.
label | ACCEPTANCE CRITERIA: The drain pipe installation shall be inspected and approved prior to backfilling.
label | ○ Backfill above the filter material shall be carefully placed in 300mm layers and compacted into a min Relative Density of 70%
label | TEST SPEC AND FREQUENCY: Method of compaction and testing to be reviewed by the Engineer
label | ○ Each length of pipe installed to be inspected and approved by the Engineer
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Compaction methodology
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checklist | CH 134.75 - 5.0 SUBSOIL DRAINAGE – COLLECTOR DRAIN | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 05.0 SUBSOIL DRAINAGE – COLLECTOR DRAIN
section | 5.0 SUBSOIL DRAINAGE – COLLECTOR DRAIN
checkpoint | 5.01 - Materials – Drainage Pipe
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.1.1
label | SPECIFICATION DETAIL SUMMARY: Drainage pipe material as per spec and or drawings or as instructed by the Engineer
label | ACCEPTANCE CRITERIA: Collector drain pipes shall generally be 100 mm diameter SDR 11 HDPE pipe, or as shown on the drawings or as instructed by the Engineer. The pipes shall not be slotted unless shown otherwise on the drawings. The drain pipes and any connectors shall comply with the relevant specifications referred to in TNZ F/2.
label | TEST SPEC AND FREQUENCY: Prior to use of material on site
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Material Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 5.02 - Materials – Filter Material and Backfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.5.1.2
label | SPECIFICATION DETAIL SUMMARY: Filter and backfill materials as per spec and or drawings or as instructed by the Engineer.
label | ACCEPTANCE CRITERIA: Collector drain pipe shall be surrounded and immediately overlain by filter materials as defined in TNZ F/2 and Table 4.1
label | ○ Filter material shall be placed in the trench to the thickness shown on the drawings or as instructed by the Engineer.
label | – – – – – – – – – – – – – – – – – –
label | Table 4.1 Grading of backfill
label | Test sieve aperture ¦¦ Percentage passing
label | – – – – – – – – – – – – – – – – – –
label | 53 mm ¦¦ 100
label | 13.2 mm ¦¦ 10 maximum
label | 4.75 mm ¦¦ 0
label | – – – – – – – – – – – – – – – – – –
label | TEST SPEC AND FREQUENCY: Prior to use of material o site
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Material Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 5.03 - Trench Excavation
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.5.2.2
label | SPECIFICATION DETAIL SUMMARY: Trench grade and depth as shown on the drawings or as instructed by the Engineer.
label | ACCEPTANCE CRITERIA: Trench widths shall be a minimum of 300 mm increasing to a minimum of 600 mm for trenches greater than 1 m deep.
label | ○ Trenches shall be excavated to depth/grade as shown on drawings or as instructed by the Engineer
label | TEST SPEC AND FREQUENCY: For every section of trench excavated
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 5.04 - Bedding and Installation of Drainage Pipe
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.3
label | SPECIFICATION DETAIL SUMMARY: Installation of pipe and bedding material as per spec and or drawings
label | ACCEPTANCE CRITERIA: The drainage pipe lengths shall be joined following the manufacturer’s instructions or as approved by the Engineer, with the pipe jointing such as to leave a smooth flush internal surface.
label | ○ The collector drain pipes shall be joined using “T” junctions to counterfort drain pipes at locations shown on the drawings or as instructed by the Engineer, Min. 75mm of filter material which completely surrounds the collector drain pipe.
label | TEST SPEC AND FREQUENCY: For every section of pipe installed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 5.05 - Backfilling
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.4
label | SPECIFICATION DETAIL SUMMARY: Backfilling of each section shall follow on immediately after installing the drain pipe and filter material
label | ACCEPTANCE CRITERIA: The collector drain pipe and connections with counterfort drainpipes shall be inspected and approved prior to backfilling.
label | ○ Backfill above the filter material shall be carefully placed in 300mm layers and lightly compacted into place using an excavator bucket or similar approved.
label | TEST SPEC AND FREQUENCY: Each length of pipe and connection(s) installed to be inspected and approved by the Engineer
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Compaction methodology
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checklist | CH 134.75 - 6.0 SUBSOIL DRAINAGE - OUTLET STRUCTURES | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 06.0 SUBSOIL DRAINAGE - OUTLET STRUCTURES
section | 6.0 SUBSOIL DRAINAGE - OUTLET STRUCTURES
checkpoint | 6.01 - Materials & Construction
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.6
label | SPECIFICATION DETAIL SUMMARY: Materials used and construction as per drawings or in other sections of this spec.
label | ACCEPTANCE CRITERIA: Materials to be used for the outlet structures shall be as specified on the drawings or in other sections of this Specification.
label | ○ Outlet structure shall be constructed in accordance with the drawings and relevant sections of this Specs.
label | TEST SPEC AND FREQUENCY: For every section of outlet structure
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, Dockets, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 7.0 SUBSOIL DRAINAGE - TRACKSIDE DRAINS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 07.0 SUBSOIL DRAINAGE - TRACKSIDE DRAINS
section | 7.0 SUBSOIL DRAINAGE - TRACKSIDE DRAINS
checkpoint | 7.01 - Materials & Construction
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.7
label | SPECIFICATION DETAIL SUMMARY: Materials used and construction as per drawings and in accordance with Kiwirail Standards.
label | ACCEPTANCE CRITERIA: Materials to be used for the trackside drain shall be as specified on the drawings and in accordance with KiwiRail Standards Corridor Drainage C- ST-CD-4102.
label | ○ Trackside drains shall be constructed in accordance with KiwiRail Standards Corridor Drainage C-ST-CD-4102.
label | TEST SPEC AND FREQUENCY: For every section of trackside drain
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, Dockets, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 8.0 GROUND ANCHORS - BARS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 08.0 GROUND ANCHORS - BARS
section | 8.0 GROUND ANCHORS - BARS
checkpoint | 8.01 - Anchor Bars
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.3.1.1
label | SPECIFICATION DETAIL SUMMARY: All anchors bars should be grade 500E as specified in the drawings. Mill certs shall be submitted to the Engineer for each batch.
label | ACCEPTANCE CRITERIA: All anchors bars should be grade 500E as specified in the drawings. Mill certs shall be submitted to the Engineer for each batch of bar showing the ultimate late, the yield, and percentage of elongation at yield load and the modulus of elasticity. Bar shall be hot dip galv with min. coating thickness of 600gm/m2
label | TEST SPEC AND FREQUENCY: For each batch of bar
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Mill certs, Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.02 - Cement Grout
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.3.2
label | SPECIFICATION DETAIL SUMMARY: Cement used for grouting shall comprise fresh Portland Cement complying with NZS3122 : 1995, water and approved additives. The proportions of cement, water and additives shall conform to NZS 3109 to produce a cement-rich grout having a standard-cured compressive strength of not less than 20 MPa at 7 days and 40 MPa at 28 days when tested in accordance with NZS 3112.
label | ACCEPTANCE CRITERIA: Cement for grouting must have a compressive strength of not less than 20 MPa at 7 days and 40 MPa at 28 days.
label | ○ Sand or other materials shall not be used unless approved by the Engineer.
label | TEST SPEC AND FREQUENCY: Compressive testing at 7 and 28 days for each batch of concrete poured
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Dockets, QA Checksheet(s), Lab Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.03 - Anchor Fabrication
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.4.1
label | SPECIFICATION DETAIL SUMMARY: Anchors shall be fabricated under controlled (factory) conditions in accordance with the approved method statement including the shop/fabrication drawings), using organisations and persons experienced in that type of work.
label | ACCEPTANCE CRITERIA: The fabricated anchors will be inspected by the Engineer prior to installation. Any anchor which is in any way damaged or fails to meet the specified requirements will be rejected
label | TEST SPEC AND FREQUENCY: Inspection by Engineer prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.04 - Drilling Logs
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.4.2
label | SPECIFICATION DETAIL SUMMARY: The Contractor must use suitable equipment and techniques for the site, drillholes must be 150mm in diameter, air drilling unless approved by the Engineer, and polymer drilling fluids should not be used.
label | ACCEPTANCE CRITERIA: Drillholes must be performed according to drawings or Engineer's instructions, within 2° alignment
label | The summary log shall record at least the following:
label | ○ Ground anchor number and type
label | ○ Date and time of the start and finish of the drilling
label | ○ Length, diameter and inclination of the hole
label | ○ Method of drilling hole
label | ○ Ground conditions encountered and ease of drilling
label | ○ Depth at which rock was encountered
label | ○ Any water encountered
label | ○ Location and extent of air loss
label | ○ Problems such as caving that occurred during drilling and any drilling fluid, flushing medium or casing used
label | ○ Length of casing used
label | ○ Date and time of clearing out the hole
label | ○ Length of bar installed and any as built details which vary from those shown on the Drawings
label | ○ Date and time of grouting
label | ○ Nominal and actual volume of grout placed
label | TEST SPEC AND FREQUENCY: Drilling logs provided within 1 working day of completion of drilling hole.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Drilling Log
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.05 - Installation
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.4.3
label | SPECIFICATION DETAIL SUMMARY: Before anchor installation, clean the drillhole with air and wait for approval from the Engineer. Install anchors according to fabricator's recommendations and Contractor's method statement, ensuring fixed length is within the specified anchorage zone.
label | ○ Handle equipment to prevent damage to anchor strands and corrosion protection.
label | ○ Provide centralizers if needed. Keep individual anchor records for installation dates and problems.
label | ACCEPTANCE CRITERIA: Installation of an anchor will not be permitted until the relevant drillhole log has been approved by the Engineer.
label | TEST SPEC AND FREQUENCY: Engineer to approve drillhole log prior to install
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.06 - Grouting
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.4.4
label | SPECIFICATION DETAIL SUMMARY: The grouting equipment must produce homogenous grout free of lumps and undispersed cement, with a pumping system featuring valves and calibrated pressure gauges for continuous grout circulation and pumping with an accuracy of +/- 0.1 MPa grout pressure, following the Contractor's approved method statement.
label | ACCEPTANCE CRITERIA: The grouting procedures shall be as per the Contractor’s approved method statement and shall conform to the requirements of BS 8081.
label | ○ The Contractor shall keep records of all grouting works. The information provided shall be as listed in the Contractor’s method statement but as a minimum shall not be less than specified in BS 8081.
label | TEST SPEC AND FREQUENCY: Records provided to the Engineer within 1 working day of completion of each and every any stage of grouting
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Grout Records
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.07 - Stressing (Lock off)
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.5
label | SPECIFICATION DETAIL SUMMARY: After completion of backfilling behind the wall and around the ground anchor, and following the Engineer’s written approval, the anchor headworks shall be completed with the anchor plate and nut installed.
label | ACCEPTANCE CRITERIA: The anchor nut shall then be tightened and locked off to 25 kN
label | TEST SPEC AND FREQUENCY: Following Engineer’s approval
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.08 - Ground Anchor Acceptance Test – 83.84km only
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.6.1
label | SPECIFICATION DETAIL SUMMARY: One acceptance test is required during construction for the ground anchors at 83.84 km site only.
label | ○ Acceptance tests shall be carried out on anchors forming part of the permanent works as a measure of quality control.
label | ACCEPTANCE CRITERIA: The testing will be in accordance with BS 8081:2015 and ISO 22477-5:2018.
label | ○ Test anchors must be axially loaded, either by cutting the slope perpendicular to the anchor or using a stressing chair. If a ground anchor fails acceptance testing, the Contractor informs the Engineer and conducts additional testing.
label | TEST SPEC AND FREQUENCY: The Contractor shall give the Engineer at least 2 working days’ notice of testing to be carried out. The Engineer will be present during the testing.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval, Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.09 - Anchor Stressing & Testing
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.6.2
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall keep records of all anchor stressing and testing.
label | ACCEPTANCE CRITERIA: The information provided shall be as listed in the Contractor’s method statement but as a minimum shall not be less than specified in BS 8081.
label | TEST SPEC AND FREQUENCY: The Engineer must receive stressing records and test results for a specific anchor within 5 working days of its completion.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Stress and Test Records
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.10 - Acceptance Load Test
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 5.6.3
label | SPECIFICATION DETAIL SUMMARY: The objectives of the acceptance load tests are to take any “slack” out of the installed anchor system and to demonstrate that installed anchors are able to provide at least the design working load capacity.
label | ○ Loading Procedure as outlined in Table 5.1 of the Specifications 5.6.3.3
label | ACCEPTANCE CRITERIA: The creep rate α for acceptance test shall be checked according to Annex A of ISO 22477-5:2018.
label | – – – – – – – – – – – – – – – – – –
label | α = (sb-sa)/log(tb/ta) <2 mm where: sa is the displacement of the anchor head at the time ta;
label | sb is the displacement of the anchor head at the time tb; ta is the start of the respective time interval; and
label | tb is the end of the respective time interval.
label | The ground anchor with creep rates exceeding the above criteria will be deemed to have failed.
label | – – – – – – – – – – – – – – – – – –
label | TEST SPEC AND FREQUENCY: The tests shall be carried out on all the installed anchor and at a location to be agreed by the Engineer on site.
label | ○ Acceptance ground anchor tests shall be undertaken prior to placement of the timber lagging
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Acceptance Test Results, Written confirmation of Engineer’s approval,
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checklist | CH 134.75 - 9.0 GROUND ANCHORS – TIE-BACK | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 09.0 GROUND ANCHORS – TIE-BACK
section | 9.0 GROUND ANCHORS – TIE-BACK
checkpoint | 9.01 - Anchor Bars
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.3.1.1
label | SPECIFICATION DETAIL SUMMARY: All anchors bars should be grade 500, complting to the requirements of BS 8081 and BS 5986. Mill certs shall be submitted to the Engineer for each batch.
label | ACCEPTANCE CRITERIA: Mill certs shall be submitted to the Engineer for each batch of bar showing the ultimate late, the yield, and percentage of elongation at yield load and the modulus of elasticity. Bar shall be hot dip galv with min. coating thickness of 600gm/m2
label | TEST SPEC AND FREQUENCY: For each batch of bar
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Mill certs, Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 9.02 - Cement Grout
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.3.2
label | SPECIFICATION DETAIL SUMMARY: Cement used for grouting shall comprise fresh Portland Cement complying with NZS3122 : 1995, water and approved additives. The proportions of cement, water and additives shall conform to NZS 3109 to produce a cement-rich grout having a standard-cured compressive strength of not less than 20 MPa at 7 days and 35 MPa at 28 days when tested in accordance with NZS 3112.
label | ACCEPTANCE CRITERIA: Cement for grouting must have a compressive strength of not less than 20 MPa at 7 days and 30 MPa at 28 days.
label | ○ Sand or other materials shall not be used unless approved by the Engineer. Water cement ratio shall not be less than 0.4
label | TEST SPEC AND FREQUENCY: Compressive testing at 7 and 28 days for each batch of concrete poured
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Dockets, Lab Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 9.03 - Deadman Anchor Blocks
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.1
label | SPECIFICATION DETAIL SUMMARY: Deadman anchor block excavation should follow the drawings' levels and dimensions, with appropriate plant used to avoid disturbance. Temporary support or battering of excavation sides is approved by the Engineer. Reinforcing steel should be placed, and the sides and base cleaned of loose or softened material. The completed excavation and reinforcing steel must be inspected and approved before placing concrete, and the backfill must comply with the Specification and drawings.
label | ACCEPTANCE CRITERIA: Excavation and reinforcing steel comply with the drawings. Engineer to inspect and approve before placing concrete
label | TEST SPEC AND FREQUENCY: Pre-pour inspection prior to concrete pour
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation of Engineer’s Approval, Phoros, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.04 - Tie-back Anchor Fabrication
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.2
label | SPECIFICATION DETAIL SUMMARY: Anchors shall be fabricated under controlled (factory) conditions in accordance with the approved method statement including the shop/fabrication drawings), using organisations and persons experienced in that type of work.
label | ACCEPTANCE CRITERIA: The fabricated anchors will be inspected by the Engineer prior to installation. Any anchor which is in any way damaged or fails to meet the specified requirements will be rejected
label | TEST SPEC AND FREQUENCY: Inspection by Engineer prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.05 - Tie-back Anchor Installation
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.3
label | SPECIFICATION DETAIL SUMMARY: The installation of a tie-back anchor bar must follow the drawings or the Engineer's instructions, with the contractor marking the alignment for approval. The trench must be excavated to the required depths and minimize damage.
label | ○ The bar, wrapped in Densotape and uPVC duct, should be connected to the deadman anchor and anchor headworks. The contractor must maintain records of the installation date and any issues encountered.
label | ACCEPTANCE CRITERIA: Installation of a tie-back anchor bar must follow the drawings or the Engineer’s instructions.
label | ○ Engineer to approve aligment
label | TEST SPEC AND FREQUENCY: Inspection by Engineer prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.06 - Deadman ground beam and anchor bar backfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.3
label | SPECIFICATION DETAIL SUMMARY: After the deadman ground beam reaches its design strength, the excavation around it and the tie-back anchor bar trench must be backfilled with approved material, following the Engineer's approval. This backfilling must be carried out in a controlled manner, ensuring the deadman and tie-back anchor bar are not disturbed or damaged.
label | ACCEPTANCE CRITERIA: Approved backfill material to be used. Backfilling to be carried out to the Engineer’s approval
label | TEST SPEC AND FREQUENCY: Engineers approval Prior to backfill
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s methodology and approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.07 - Stressing (Lock off)
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 6.5.1
label | SPECIFICATION DETAIL SUMMARY: After completion of backfilling behind the wall and around the ground anchor, and following the Engineer’s written approval, the anchor headworks shall be completed with the anchor plate and nut installed.
label | ACCEPTANCE CRITERIA: The anchor nut shall then be tightened and locked off to 25 kN
label | TEST SPEC AND FREQUENCY: Following Engineer’s approval
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 10.0 PILE SPECIFICATIONS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 10.0 PILE SPECIFICATIONS
section | 10.0 PILE SPECIFICATIONS
checkpoint | 10.01 - Preliminary, Site Datum, and Grid References
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 7.1.1 & 7.1.2
label | SPECIFICATION DETAIL SUMMARY: The Auckland Structural Group's Piling Specification Rev G, dated 12 March 2002, is used for piling construction, with project- specific requirements modifying it. Drawings show levels in NZVD2016 Vertical Datum.
label | ACCEPTANCE CRITERIA: The Auckland Structural Group (ASG) Piling Specification Rev G, dated 12 March 2002, is to be used for piling construction, with project-specific requirements modifying it.
label | ○ All levels shown on the Drawings are in terms of NZVD2016 Vertical Datum. Pile locations are shown on the Drawings.
label | TEST SPEC AND FREQUENCY: Prior to construction of piles
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 10.02 - Method Statement
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 7.1.4
label | SPECIFICATION DETAIL SUMMARY: The method statement shall describe all proposed equipment, and detail the construction sequence including but not limited to:
label | ○ Programme of the works, detailing the timing and sequence of individual portions of the works;
label | ○ Full details of the installation plant to be used, including manufacturer’s information and proof of servicing/recent upkeep;
label | ○ Full details of proposed plant set-up and loading throughout the works to inform on the local tability during the construction;
label | ○ Proposed phasing of excavation/filling operations such that the design stresses in the piles (and any supporting frames) are not exceeded;
label | ○ (Driven piles) Pile driving methodology and equipment for driving piles;
label | ○ A contingency plan to be adopted in the event of encountering obstructions, to minimise disruption and delay; and,
label | ○ Example Pile Construction Card.
label | ACCEPTANCE CRITERIA: Acceptance of Method Statement by the Engineer
label | TEST SPEC AND FREQUENCY: At least two weeks prior to construction of piles
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Method Statement
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.03 - Tolerances
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 7.1.5
label | SPECIFICATION DETAIL SUMMARY: Tolerances specified shall apply for the construction of the piles unless otherwise specified on the drawings or agreed with the Engineer
label | ACCEPTANCE CRITERIA: The following tolerances shall applyt, unless otherwise:
label | ○ Position of pile head (at underside of cap) shall not vary more than -25/+ 75 mm horizontally (- towards rail / + away from rail) and +/- 25 mm vertically from the true position as specified on the drawings.
label | ○ The maximum permitted deviation of the piles from the vertical, at any depth, shall not be greater than 1H:75V deviation from the vertical.
label | TEST SPEC AND FREQUENCY: Tolerances to be inspected during construction of each pile
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 10.04 - Inspections
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 7.1.7
label | SPECIFICATION DETAIL SUMMARY: The Engineer is required to have the opportunity to observe all phases of piling operations and inspect specific items, including driving piles and required testing.
label | ○ They must have access to all parts of the works included in the contract and be given at least three working days' notice when work is ready for inspection or testing. The Contractor must arrange inspection facilities and replace or rectify defective or unsuitable parts or materials at their expense, as per the Principal's contract documents.
label | ACCEPTANCE CRITERIA: Engineer must be given opportunity to observe all phases of the piling operation.
label | ○ The Engineer shall have at all reasonable times access to all parts of the works included in the Contract.
label | TEST SPEC AND FREQUENCY: Engineer given at least 3 working days’ notice of when work is ready for inspection or testing
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Written Confirmation of Engineers Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 10.05 - Producer Statements
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 7.1.9
label | SPECIFICATION DETAIL SUMMARY: Producer Statement – Construction (PS3) are required for each structure for the construction of the piles, with relevant construction records.
label | ACCEPTANCE CRITERIA: PS3 submission for each structure of the construction of the piles with relevant records
label | TEST SPEC AND FREQUENCY: Post construction
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Producer Statement (PS3)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 10.06 - Pile Embedment
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 7.2.4
label | SPECIFICATION DETAIL SUMMARY: Set cards (showing sets and rebound) shall be inspected by the Engineer and embedment depth agreed upon.
label | ACCEPTANCE CRITERIA: Sets and embedment agreed with the Engineer
label | TEST SPEC AND FREQUENCY: Agreed with Engineer prior to driving pile
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation of Engineers Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.07 - Piling Records
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 7.2.6
label | SPECIFICATION DETAIL SUMMARY: The piling record must be submitted on professionally formatted, clearly typed documents and only accepted after verification by the Engineer or the nominated site representative:
label | ○ The date and time of installation.
label | ○ Sequence of driving (if driving in groups)
label | ○ The level of the bed at the commencement of operations.
label | ○ The pile number or location.
label | ○ The type and size of the piling hammer.
label | ○ The type and condition of the piling helmet and packing.
label | ○ Details of any variations in the penetration resistance.
label | ○ Any apparent deviation from specified location and inclination
label | ○ The length of the complete pitched pile.
label | ○ The toe level of the pile before and after driving.
label | ○ The distance driven.
label | ○ The distance drilled.
label | ○ The level of the top of the rock.
label | ○ The set at 0.5 m intervals over the last 3 m of driving.
label | ○ The final set and rebound (averaged over the last 10 blows).
label | ○ Details of any interruption to driving
label | ACCEPTANCE CRITERIA: Review cards by the Engineer
label | TEST SPEC AND FREQUENCY: Records provided to the Engineer within 24 hours of pile completion
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Piling Records
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 11.0 STRUCTURAL SPECIFICATION – CONCRETE WORKS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 11.0 STRUCTURAL SPECIFICATION – CONCRETE WORKS
section | 11.0 STRUCTURAL SPECIFICATION – CONCRETE WORKS
checkpoint | 11.01 - Aggregates
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.3.2
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall provide the Engineer with details of the types and source of supply of the aggregates
label | ACCEPTANCE CRITERIA: Fine and coarse aggregates shall comply with the requirements of NZS 3121 and NZS 3111. The maximum size of coarse aggregate shall be 19 mm.
label | ○ Proposed aggregates are non-reactive as defined in clause 6.1 of the CCANZ report no. TR3, Alkali Silica Reaction: Minimising the Risk of Damage to Concrete : Guidance Notes and Recommended Practice (2 no. edn) 2003.
label | ○ Once approval has been obtained for the aggregates to be used, neither the quality nor source shall vary without the prior approval of the Engineer.
label | TEST SPEC AND FREQUENCY: At least two weeks before work is to commence.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Mix Design (Aggregate source)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.02 - Reinforcing Steel
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.3.8
label | SPECIFICATION DETAIL SUMMARY: Reinforcing bars to comply with specifications
label | ACCEPTANCE CRITERIA: Reinforcing bars shall be higher ductility plain carbon steel grade 300E or 500E as shown on the drawings, and shall comply with AS/NZS 4671
label | ○ Grade 250N or grade 500N reinforcement is permitted where specifically indicated on the drawings.
label | ○ Grade 250L or 500L is not permitted.
label | TEST SPEC AND FREQUENCY: For every reinforcing bar(s) used
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.03 - Concrete Mix Design (from a non approved ready mix concrete producer)
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.4.1
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall supply to the Engineer details of the concrete mix design for approval. These shall include the following:
label | (a) weights of aggregates and water
label | (b) cement weight
label | (c) water/cement ratio by weight
label | (d) target slump
label | (e) target compressive strength
label | (f) admixtures
label | (g) concrete grade
label | (h) mix designation
label | ACCEPTANCE CRITERIA: Engineer to approve mix design prior to commencement of concrete works
label | TEST SPEC AND FREQUENCY: At least two weeks notice
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Mix Design
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.04 - Concrete Mix Design (from an audited NZRMCA plant)
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.4.2
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall advise the Engineer of the mix details, concrete supplier and provide all supporting documentation if requested to do so to confirm the audit status of the ready mix plant.
label | ACCEPTANCE CRITERIA: Engineer to review and approve mix design if requested to do so
label | TEST SPEC AND FREQUENCY: Upon request of the Engineer
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Mix Design
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.05 - Delivery Records
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.4.2
label | SPECIFICATION DETAIL SUMMARY: Records shall be kept at the bacthing plant for each batch incl the following:
label | (i) Batch number and docket number which can be referred back to the batch plant
label | (ii) Specified slump
label | (iii) Mix designation (minimum strength, aggregate size and admixtures)
label | (iv) Specified strength
label | (v) Date and time of mixing
label | (vi) Quantity delivered
label | (vii) Actual weight and type of cement, fine and coarse aggregate, weight of free water and hence the free water / cement ratio.
label | ACCEPTANCE CRITERIA: Records must meet the approved Mix Design
label | TEST SPEC AND FREQUENCY: Records for each batch of concrete ordered
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Concrete Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.06 - Testing – Slump Test
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.6.2
label | SPECIFICATION DETAIL SUMMARY: The results of slump tests taken on samples of concrete supervised by the Engineer at the point of delivery shall be the only basis for defining the slump of the mixes supplied.
label | ACCEPTANCE CRITERIA: Tolerances for slump shall be in accordance with Table 9.1 (Snippet below).
label | – – – – – – – – – – – – – – – – – –
label | Table 9.1: Concrete mixes
label | Grade designation ¦¦ Maximum aggregate size (mm) ¦¦ Specified compressive strength (MPa) ¦¦ Method of placement ¦¦ Specified slump (mm) ¦¦ General location ¦¦ Additional data
label | – – – – – – – – – – – – – – – – – –
label | 30 (normal mix) ¦¦ 19 ¦¦ 30 ¦¦ NBC ¦¦ 100 ¦¦ Deadman anchor ¦¦ ++ Max shrinkage 750 microstrains at 56 days
label | 17.5 (normal mix) ¦¦ 19 ¦¦ 17.5 ¦¦ Gravity ¦¦ 100 ¦¦ Site concrete ¦¦ Mix approval not required
label | – – – – – – – – – – – – – – – – – –
label | TEST SPEC AND FREQUENCY: At least one slump test on each bach of concrete
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: In-situ Slump Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.07 - Testing – Compressive Strength Test
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.6.2
label | SPECIFICATION DETAIL SUMMARY: Compressive testing to be undertaken
label | ACCEPTANCE CRITERIA: Three specimens tested at 28 days and another at 7 days (if required). Test results must comply with the parameters set on the approved mix design
label | TEST SPEC AND FREQUENCY: Three compressive strength specimens shall be moulded for each 75m3 of concrete placed.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Compressive Strength Lab Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.08 - Testing – air entrainment
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.6.5
label | SPECIFICATION DETAIL SUMMARY: Air entrainment tests shall be carried out in accordance with NZS 3104 clause 2.15.3.1 and percentage of air entrained determined in accordance with NZS 3112 Part 1.
label | ACCEPTANCE CRITERIA: Air entrainment values for the work shall be between 3% and 6% for concrete with nominal aggregate size greater than 20 mm, and 4 to 8% for 10 to 20 mm nominal aggregate size.
label | TEST SPEC AND FREQUENCY: At least one test on each bach of concrete
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Lab Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.09 - Testing - Reinforcement
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.6.5
label | SPECIFICATION DETAIL SUMMARY: The contractor is required to provide a steel manufacturer's test certificate for each reinforcement material grade supplied. Independent testing shall also be carried out by the Contractor:
label | ○ One tensile and two bend tests shall be carried out on a random sample of every bar size, type and grade, for every 250 tonnes batch of reinforcing steel delivered to the site, with a minimum of one series of tests for each bars size, type and grade. The tests shall be carried out in accordance with AS/NZS 4671, by an independent TELARC registered testing laboratory and the samples shall be selected by the Engineer.
label | ACCEPTANCE CRITERIA: Reinforcing steel shall be deemed acceptable if it complies fully with the requirements of AS/NZS 4671
label | TEST SPEC AND FREQUENCY: Prior to use of reinforcement
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Test certificates, Tensile and Bend Tests Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.10 - Concrete Placing
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.7.4
label | SPECIFICATION DETAIL SUMMARY: Engineer or rep to be advised before any concrete is placed to inspect the formwork and reinforcement
label | ACCEPTANCE CRITERIA: Engineer or rep to approve pre-pour inspection
label | TEST SPEC AND FREQUENCY: At least 48 hours before concrete placement
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Written Confirmation of Engineer’s/Rep Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.11 - Curing Compounds
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.7.8.4
label | SPECIFICATION DETAIL SUMMARY: Curing compound details shall be approved in writing by the Engineer, such details shall be accompanied by test certificates to show that the compound will give satisfactory results for the proposed application
label | ACCEPTANCE CRITERIA: The compound shall be applied in strict accordance with the Manufacturer’s Specification and shall be applied as soon as the surface water has disappeared
label | TEST SPEC AND FREQUENCY: At least 6 days prior to use of curing compound
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Curing Compound Spec Sheet, Confirmation of Engineer’s/Rep Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.12 - Cast-in items
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.8.1
label | SPECIFICATION DETAIL SUMMARY: Holding down bolts and inserts shall be secured and fixed before the concrete is placed or, if shown on the drawings or if directed by the Engineer, recesses or blockouts shall be made in the concrete and the holding down bolts or inserts shall be grouted in place, or embedded in the second-stage concrete
label | ACCEPTANCE CRITERIA: The position tolerance on cast-in items shall be as follows:
label | ○ bolts and inserts +/- 10 mm
label | ○ All cast-in items shall meet the durability requirements of the New Zealand Building Code.
label | TEST SPEC AND FREQUENCY: Visual check prior to concrete placement
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.13 - Construction Joint
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.9.1
label | SPECIFICATION DETAIL SUMMARY: Construction joints shall be formed in the position shown on the drawings unless a change is approved by the Engineer
label | ACCEPTANCE CRITERIA: Construction joints shall be formed in the position shown on the drawings unless a change is approved by the Engineer
label | TEST SPEC AND FREQUENCY: Contractor to confirm joint locations with Engineer prior to concrete pour
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.14 - Sealants
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.9.3
label | SPECIFICATION DETAIL SUMMARY: Joints show on the drawings shall be sealed, with works undertaken in accordance with manufacturer’s instructions and by an experienced applicator.
label | ○ Contractor shall submit details of the proposed sealant and applicator to the approval of the Engineer
label | ACCEPTANCE CRITERIA: Engineer to approve proposed sealant and applicator
label | TEST SPEC AND FREQUENCY: Prior to sealant works
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Joint material spec, Applicator’s credentials, Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.15 - Tolerances and Surface Finishes
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.10
label | SPECIFICATION DETAIL SUMMARY: All concrete work shall be set out and constructed to achieve the structural tolerances specified in The Specs & drawings.
label | ACCEPTANCE CRITERIA: Surface finish as follows:
label | ○ Below Ground (surfaces not seen) Finish: F1 U1
label | ○ Surfaces in contract with water Finish: F5 U4
label | ○ All channels Finish: F4 U3
label | TEST SPEC AND FREQUENCY: For every concrete pour
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 11.16 - Concrete Repair
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.11
label | SPECIFICATION DETAIL SUMMARY: Contractor shall advise the Engineer of the presence of any defective concrete
label | ACCEPTANCE CRITERIA: Repair of imperfections to be completed within 7 days of removal of forms.
label | ○ Engineer to approve repair methods and materials used
label | TEST SPEC AND FREQUENCY: For concrete works that require repair
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Material Specs, Repair Methodology, Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.17 - Slab on Grade
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.12
label | SPECIFICATION DETAIL SUMMARY: The Contractor must adhere to minimum requirements before placing concrete ground slabs, compact the subgrade using a footpath roller or plate compactor, obtain Engineer's approval before hardfill is placed, and remove soft spots as directed.
label | ACCEPTANCE CRITERIA: Engineer to inspect and approve subgrade before hardfill is placed
label | TEST SPEC AND FREQUENCY: Before placing concrete ground slabs
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11.18 - Shop Drawings
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.1.14
label | SPECIFICATION DETAIL SUMMARY: The Contractor is required to create shop drawings for precast units and concrete metal work, which must be submitted to the Engineer for approval before commencing operations. The Contractor is responsible for the accuracy of these drawings, ensuring competent tradesmen can fabricate structures to the dimensions and standards specified in the specifications.
label | ACCEPTANCE CRITERIA: Shop drawings reviewed and approved by Engineer
label | TEST SPEC AND FREQUENCY: Prior to fabrication or pre- cast units and metal work cast into concrete
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Shop Drawings, Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checklist | CH 134.75 - 12.0 STRUCTURAL SPECIFICATION – STRUCTURAL STEELWORK & METALWORK | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 12.0 STRUCTURAL SPECIFICATION – STRUCTURAL STEELWORK & METALWORK
section | 12.0 STRUCTURAL SPECIFICATION – STRUCTURAL STEELWORK & METALWORK
checkpoint | 12.01 - Origin of Steel
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.5
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall submit steel source steel list as described in the SCNZ Report to the Design Engineer for review.
label | ACCEPTANCE CRITERIA: Evidence of conformity meeting the requirements of the SCNZ Report shall be submitted to the Construction Reviewer for review
label | TEST SPEC AND FREQUENCY: Prior to procurement of steel
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Steel Source List
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 12.02 - Inspections
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.7
label | SPECIFICATION DETAIL SUMMARY: The contractor must inform the Engineer of shop work commencement in advance, offer necessary assistance for material observation, and ensure reasonable access to work locations. The contractor must cooperate with the Engineer in arranging inspections and keeping them informed about all stages of work.
label | ACCEPTANCE CRITERIA: Engineer to provide approval of inspection.
label | TEST SPEC AND FREQUENCY: The following inspections are required by the Engineer:
label | ○ Random inspection during the fabrication process;
label | ○ After completion of fabrication and application of all protective coatings; and
label | ○ After erection in final location in the works.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12.03 - Bolts, Nuts, and Washers
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.8.3
label | SPECIFICATION DETAIL SUMMARY: The contractor must ensure the bolt, nut, and washer set have correct markings, and unmarked bolts should not be used. If no certification is provided, the Engineer may reject the bolts or request testing in accordance with AS/NZS 1252 Appendix A
label | ACCEPTANCE CRITERIA: If there is no certification provided the Engineer may reject the bolts and nuts or request them to be tested in accordance with AS/NZS 1252 App
label | TEST SPEC AND FREQUENCY: Prior to use of bolts, nuts, and washers.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Certification for the bolts and nuts
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 12.04 - Fabrication
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.10.1
label | SPECIFICATION DETAIL SUMMARY: The Engineer approves all quality control and checking procedures, and after a component's fabrication and erection, the Contractor must promptly provide the Engineer with the results of all quality control checks for that component.
label | ACCEPTANCE CRITERIA: Engineer to approve quality control and checking procedures
label | TEST SPEC AND FREQUENCY: Prior to and during fabrication
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QC and Checking Procedures, Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12.05 - Tolerances
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.10.2
label | SPECIFICATION DETAIL SUMMARY: General Tolerances Straightness length/500 Structural dimensions + 3 mm
label | ○ Plan position of structural members + 5 mm Level of structural members + 5 mm.
label | ACCEPTANCE CRITERIA: Fabrication tolerances shall not be exceeded.
label | ○ If the assembled item's tolerance doesn't meet the clause, the Contractor and Engineer must agree on a method for achieving acceptable tolerances
label | TEST SPEC AND FREQUENCY: For every section of steelwork and metalwork installed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 12.06 - Welding
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.10.17
label | SPECIFICATION DETAIL SUMMARY: Before any welding is commenced, the Contractor shall advise the Engineer so that they may have an opportunity to inspect any of the prepared surfaces.
label | ACCEPTANCE CRITERIA: Surfaces cleaned, prepared, and preppred for welding
label | TEST SPEC AND FREQUENCY: Before any welding is commenced
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Email trails
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 12.07 - Weld Quality Control
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.10.17
label | SPECIFICATION DETAIL SUMMARY: An independent Welding Inspector will conduct all necessary inspections, tests, and reports, including NDT testing, for welding defects, and must be qualified to AS/NZS1554.
label | ○ The Welding Inspector must be approved by the Designer, and their details, including company, technical qualifications, and curriculum vitae
label | ACCEPTANCE CRITERIA: The Welding Inspector shall record all details of its inspections and shall submit a weekly written report covering progress, testing, rework and welding quality matters for that week.
label | ○ Welding procedure sheets shall be prepared by the fabricator and approved by the Welding Inspector.
label | TEST SPEC AND FREQUENCY: Inspector details must be submitted two weeks before commencing structural steelwork fabrication.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Welding Procedure Sheets, Written Confirmation from Welding Inspector
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12.08 - Corrosion Protection
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.13.3
label | SPECIFICATION DETAIL SUMMARY: Corrosion protection shall be fabricated and erected in accordance with a quality plan meeting the requirements of AS/NZS9002
label | ○ Applicators shall have in place formal written quality assurance procedures appropriate to the scope of work, prior to commencing work on application of the corrosion protection system.
label | ACCEPTANCE CRITERIA: The Quality Plan shall allow for the engagement of an independent Corrosion Protection Inspector to carry out inspections and coating thickness measurements and provide corresponding reports in accordance section 11 of AS/NZS 2312.
label | TEST SPEC AND FREQUENCY: Prior to fabrication of corrosion protection
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Quality Plan, Written Confirmation from Corrosion Protection Inspector
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12.09 - Storage and Handling
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.14.2
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall lay down the steelwork on the site at the position agreed with the Engineer
label | ACCEPTANCE CRITERIA: Prior to erection all steelwork shall be cleaned as necessary to the satisfaction of the Engineer.
label | TEST SPEC AND FREQUENCY: Prior to erection of steelwork
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, Written Confirmation from Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 12.10 - Erection Method
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 9.2.14.3
label | SPECIFICATION DETAIL SUMMARY: A detailed method statement shall be prepared covering structural steel erection
label | ACCEPTANCE CRITERIA: Engineer to review and approve method statement prior to erection of steel on site
label | TEST SPEC AND FREQUENCY: 2 weeks before commencing structural steel erection on site
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Method Statement, Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checklist | CH 134.75 - 13.0 CIVIL SPECIFICATION – PIPES & ASSOCIATED WORKS (GRAVITY DRAINAGE SYSTEM) | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 13.0 CIVIL SPECIFICATION – PIPES & ASSOCIATED WORKS (GRAVITY DRAINAGE SYSTEM)
section | 13.0 CIVIL SPECIFICATION – PIPES & ASSOCIATED WORKS (GRAVITY DRAINAGE SYSTEM)
checkpoint | 13.01 - Manhole Foundation
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.1.3.3.2
label | SPECIFICATION DETAIL SUMMARY: The manhole structure shall be constructed or placed on a levelling course placed on top of the subgrade material.
label | ○ The levelling course shall comprise a 100 mm minimum layer of compacted approved AP20 granular material or concrete.
label | ACCEPTANCE CRITERIA: The suitability of the subgrade material shall be confirmed by the Engineer
label | TEST SPEC AND FREQUENCY: Prior to placement of levelling course
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Test Result(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.02 - Manhole Testing
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.1.3.3.3
label | SPECIFICATION DETAIL SUMMARY: The Engineer may require a watertightness test to be carried out at manholes.
label | ACCEPTANCE CRITERIA: The manhole shall be considered watertight if the drop does not exceed 0.2 litre per square metre of internal cross-section area per metre depth of the manhole.
label | TEST SPEC AND FREQUENCY: Upon request
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Test Result, Photos, Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 13.03 - Transport, Handling, and Storage of Materials
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.1.4.2
label | SPECIFICATION DETAIL SUMMARY: Materials will be inspected by the Engineer, at their discretion, upon delivery to Site or as soon thereafter as practicable.
label | ACCEPTANCE CRITERIA: Damaged or unsatisfactory materials noted at that time will be marked and the Contractor shall either replace the item or if the Engineer permits, repair the defect in an approved manner.
label | TEST SPEC AND FREQUENCY: At the Engineer’s discretion
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation of Engineer’s Acceptance
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 13.04 - Tolerance
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.1.4.5
label | SPECIFICATION DETAIL SUMMARY: For all culverts:
label | ○ An overall slope tolerance of + / - 0.5% is acceptable for installed culvert unless absolute maximum or minimum grades are stated on the Drawings.
label | ○ Each separate pipe shall be individually set to line and within 10 mm of the invert levels shown on the Drawings provided that the deviation from a string line extending over two pipe lengths shall not exceed 10 mm.
label | ○ No sections of pipe shall be laid with an adverse (negative) grade unless shown otherwise onthe Drawings
label | ACCEPTANCE CRITERIA: Tolerances are adhered to
label | TEST SPEC AND FREQUENCY: For every section of pipe laid
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 14.0 CIVIL SPECIFICATION – TRENCHING, BEDDING, AND BACKFILLING | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 14.0 CIVIL SPECIFICATION – TRENCHING, BEDDING, AND BACKFILLING
section | 14.0 CIVIL SPECIFICATION – TRENCHING, BEDDING, AND BACKFILLING
checkpoint | 14.01 - Trenching
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.2.5.1.1
label | SPECIFICATION DETAIL SUMMARY: Trench excavation to be carried out in accordance with KiwiRail Civil Engineering Standard Culverts C-ST-CD-4103 Section 7.1.2.
label | ACCEPTANCE CRITERIA: Excavation in line with KiwiRail Civil Engineering Standard Culverts C-ST-CD- 4103 Section 7.1.2.
label | TEST SPEC AND FREQUENCY: For every section of trench
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 14.02 - Unsuitable Foundation
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.2.5.1.4
label | SPECIFICATION DETAIL SUMMARY: If trench bottom material isn't suitable for pipe foundation, Contractor must over- excavate upon receipt of order from the Engineer, and backfill with approved material.
label | ACCEPTANCE CRITERIA: Over excavation required if trench invert is less than the CBR values in Table 10.1 (snippet below).
label | ○ Replacement material tested for strength using Clegg Hammer or Scala and shall achieve equivalent CBR strength values given in Table 10.1.
label | – – – – – – – – – – – – – – – – – –
label | Table 10.1 Trench invert strengths
label | Trench situation ¦¦ Minimum required CBR value at trench design invert level
label | – – – – – – – – – – – – – – – – – –
label | In non road areas ¦¦ 3.5
label | In permanent road areas with depth to trench invert less than 0.6 m ¦¦ 5
label | As in 2, but with depth to trench invert greater than 0.6 m ¦¦ 3.5
label | Beneath temporary construction haul roads ¦¦ add 3 to the above permanent road case CBR's
label | – – – – – – – – – – – – – – – – – –
label | TEST SPEC AND FREQUENCY: • For pipe diameters < 1,000 mm: testing at 10 m maximum centres for each placed layer.
label | ○ For pipe diameters 1,000 mm to 1500 mm: testing at 5 m maximum centres for each placed layer.
label | ○ For pipe diameters > 1,500 mm: testing at 2.5 m centres for each placed layer.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Clegg and or Scala Test Results, Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 14.03 - Pipe Bedding & Support
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.2.5.2
label | SPECIFICATION DETAIL SUMMARY: Pipe bedding to be carried out in accordance with KiwiRail Civil Engineering Standard Culverts C-STCD-4103 Section 7.1.3.
label | ACCEPTANCE CRITERIA: Pipe bedding in line with KiwiRail Civil Engineering Standard Culverts C-STCD- 4103 Section 7.1.3
label | TEST SPEC AND FREQUENCY: For every section of pipe bedding and support
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheets, Photos, Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 14.04 - Backfilling
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.2.5.2
label | SPECIFICATION DETAIL SUMMARY: Backfilling to be carried out in accordance with KiwiRail Civil Engineering Standard Culverts C-ST-CD-4103 Section 7.1.3.
label | ACCEPTANCE CRITERIA: Backfilling in line with KiwiRail Civil Engineering Standard Culverts C-STCD- 4103 Section 7.1.3
label | TEST SPEC AND FREQUENCY: For every section pipe backfilled
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheets, Photos, Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checklist | CH 134.75 - 15.0 CIVIL SPECIFICATION – TRENCHLESS METHODS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.75 - 15.0 CIVIL SPECIFICATION – TRENCHLESS METHODS
section | 15.0 CIVIL SPECIFICATION – TRENCHLESS METHODS
checkpoint | 15.01 - Rock Armour Grading
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.4.3.1.1
label | SPECIFICATION DETAIL SUMMARY: Rock armour material shall be well graded as indicated on the drawings.
label | ACCEPTANCE CRITERIA: Poorly graded or gap graded armour rock shall not be permitted except as approved by the Engineer.
label | TEST SPEC AND FREQUENCY: For every section of rock armour
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Rock Specifications
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 15.02 - Rock Armour - Placement
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.4.4.4
label | SPECIFICATION DETAIL SUMMARY: The placement method of armour and underlayers directly on geotextile filter fabric shall be approved by the Engineer prior to placement
label | ACCEPTANCE CRITERIA: Engineer to approve methodology
label | TEST SPEC AND FREQUENCY: Prior to rock armour placement
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Method Statement, Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15.03 - Tolerances
label | DRAWING / SPECIFICATION REF.: T+T NALRecovery Specifications: 10.4.5.2
label | SPECIFICATION DETAIL SUMMARY: Rock materials must be placed according to the drawings' levels, dimensions, and slopes, and the surface profile must be measured using the specified tolerances:
label | ○ Subgrade levels -0.1 m to +0.1 m
label | ○ Armour underlayer thickness (average per profile): -0.1 m to +0.2 m
label | ○ Armour rock thickness (average per profile):
label | ○ 0.1 m to +0.5 m
label | ACCEPTANCE CRITERIA: Tolerances are adhered to
label | TEST SPEC AND FREQUENCY: For every section of rock material placed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T