## Project Structure
Folder Structure | [5 empty] | Checklists
Site QA
9781 Brighton Grammar
Switchboard
|  |  | MSSB-B-01 |  |  | MSSB checklist
|  |  | MSSB-B-02 |  |  | MSSB checklist
|  |  | MSSB-G-01 |  |  | MSSB checklist
|  |  | MSSB-G-02 |  |  | MSSB checklist
|  |  | MSSB-G-03 |  |  | MSSB checklist
|  |  | MSSB-L1-01 |  |  | MSSB checklist
|  |  | MSSB-L1-02 |  |  | MSSB checklist
|  |  | MSSB-RF-01 |  |  | MSSB checklist
|  |  | MSSB-RF-02 |  |  | MSSB checklist
Variable Speed Drives
|  |  | VSD-CPSF-1 |  |  | VSD checklist
|  |  | VSD-CPEF-1 |  |  | VSD checklist
|  |  | VSD-KSF-1 |  |  | VSD checklist
|  |  | VSD-KEF-01 |  |  | VSD checklist
|  |  | VSD-EF-B-02 (DEU-01) |  |  | VSD checklist
|  |  | VSD-EF-R1 |  |  | VSD checklist
|  |  | VSD-EF-R2 |  |  | VSD checklist
|  |  | VSD-EF-R3 |  |  | VSD checklist
|  |  | VSD-EF-R4 |  |  | VSD checklist
|  |  | VSD-EF-R5 |  |  | VSD checklist
|  |  | VSD-EF-R6 |  |  | VSD checklist
|  |  | VSD-EF-R8 |  |  | VSD checklist
|  |  | VSD-FCEF-01 |  |  | VSD checklist
Ventilation Fans
|  |  | EF-B-01 |  |  | Ventilation Fans checklist
|  |  | EF-B-03 |  |  | Ventilation Fans checklist
|  |  | EF-B-04 |  |  | Ventilation Fans checklist
|  |  | EF-B-05 |  |  | Ventilation Fans checklist
|  |  | TEF-G-1 |  |  | Ventilation Fans checklist
|  |  | EF-G-01 |  |  | Ventilation Fans checklist
|  |  | EF-G-02 |  |  | Ventilation Fans checklist
|  |  | EF-G-03 |  |  | Ventilation Fans checklist
|  |  | TEF-R2 |  |  | Ventilation Fans checklist
|  |  | EF-R7 |  |  | Ventilation Fans checklist
|  |  | SAF-R1 |  |  | Ventilation Fans checklist
|  |  | TEF-R1 |  |  | Ventilation Fans checklist
|  |  | TEF-R3 |  |  | Ventilation Fans checklist
ERV / HRV Unit
|  |  | HRU-G.01 |  |  | ERV / HRV Checklist
|  |  | HRU-G.02 |  |  | ERV / HRV Checklist
|  |  | HRU-G.03 |  |  | ERV / HRV Checklist
|  |  | HRU-G.04 |  |  | ERV / HRV Checklist
|  |  | HRU-G.05 |  |  | ERV / HRV Checklist
|  |  | HRU-G.06 |  |  | ERV / HRV Checklist
|  |  | HRU-G.07 |  |  | ERV / HRV Checklist
|  |  | HRU-G.08 |  |  | ERV / HRV Checklist
|  |  | HRU-G.09 |  |  | ERV / HRV Checklist
|  |  | HRU-G.10 |  |  | ERV / HRV Checklist
|  |  | HRU-G.11 |  |  | ERV / HRV Checklist
|  |  | HRU-G.12 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.01 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.02 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.03 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.04 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.05 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.06 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.07 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.08 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.09A |  |  | ERV / HRV Checklist
|  |  | HRU-L1.09B |  |  | ERV / HRV Checklist
|  |  | HRU-L1.10 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.11 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.13 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.14 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.15 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.16 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.17 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.19 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.20 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.21 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.22 |  |  | ERV / HRV Checklist
|  |  | HRU-L1.23 |  |  | ERV / HRV Checklist
|  |  | HRU-L2.01A |  |  | ERV / HRV Checklist
|  |  | HRU-L2.01B |  |  | ERV / HRV Checklist
|  |  | AHU-R1 |  |  | ERV / HRV Checklist
VRF / Split AC Unit
Admin
Ground Floor
[5 empty] | OU-G-01 | AC Condensor checklist
[5 empty] | BS-G-01 | Branch Box checklist
[5 empty] | AC-G.01 | FCU-AC checklist
[5 empty] | AC-G.02 | FCU-AC checklist
[5 empty] | AC-G.04 | FCU-AC checklist
[5 empty] | AC-G.05 | FCU-AC checklist
[5 empty] | AC-G.06 | FCU-AC checklist
[5 empty] | AC-G.07 | FCU-AC checklist
[5 empty] | AC-G.08A | FCU-AC checklist
[5 empty] | AC-G.08B | FCU-AC checklist
[5 empty] | AC-G.08C | FCU-AC checklist
Labs
Ground Floor
[5 empty] | OU-G-02 | AC Condensor checklist
[5 empty] | BS-G-02 | Branch Box checklist
[5 empty] | AC-G.15A | FCU-AC checklist
[5 empty] | AC-G.15B | FCU-AC checklist
[5 empty] | AC-G.16 | FCU-AC checklist
[5 empty] | AC-G.17 | FCU-AC checklist
Labs
Ground Floor
[5 empty] | OU-G-03 | AC Condensor checklist
[5 empty] | BS-G-03 | Branch Box checklist
[5 empty] | AC-G.14 | FCU-AC checklist
[5 empty] | AC-G.18 | FCU-AC checklist
[5 empty] | AC-G.19 | FCU-AC checklist
[5 empty] | AC-G.20 | FCU-AC checklist
Labs
Ground Floor
[5 empty] | OU-G-04 | AC Condensor checklist
[5 empty] | BS-G-04 | Branch Box checklist
[5 empty] | AC-G.09 | FCU-AC checklist
[5 empty] | AC-G.11 | FCU-AC checklist
[5 empty] | AC-G.12 | FCU-AC checklist
[5 empty] | AC-G.13 | FCU-AC checklist
[5 empty] | AC-G.22 | FCU-AC checklist
[5 empty] | AC-G.23 | FCU-AC checklist
Café
Ground Floor
[5 empty] | OU-G-05 | AC Condensor checklist
[5 empty] | BS-G-05 | Branch Box checklist
[5 empty] | AC-G.10A | FCU-AC checklist
[5 empty] | AC-G.10B | FCU-AC checklist
[5 empty] | AC-G.10C | FCU-AC checklist
[5 empty] | AC-G.10D | FCU-AC checklist
[5 empty] | AC-G.10E | FCU-AC checklist
[5 empty] | AC-G.24 | FCU-AC checklist
Science
Level 1
[5 empty] | OU-L1-01 | AC Condensor checklist
[5 empty] | BS-L1-01 | Branch Box checklist
[5 empty] | AC-L1.01 | FCU-AC checklist
[5 empty] | AC-L1.04 | FCU-AC checklist
[5 empty] | AC-L1.06 | FCU-AC checklist
[5 empty] | AC-L1.07 | FCU-AC checklist
Science
Level 1
[5 empty] | OU-L1-02 | AC Condensor checklist
[5 empty] | BS-L1-02 | Branch Box checklist
[5 empty] | AC-L1.02 | FCU-AC checklist
[5 empty] | AC-L1.03A | FCU-AC checklist
[5 empty] | AC-L1.03B | FCU-AC checklist
[5 empty] | AC-L1.05 | FCU-AC checklist
[5 empty] | AC-L1.08 | FCU-AC checklist
Science
Level 1
[5 empty] | OU-L1-03 | AC Condensor checklist
[5 empty] | BS-L1-03 | Branch Box checklist
[5 empty] | AC-L1.09A | FCU-AC checklist
[5 empty] | AC-L1.09B | FCU-AC checklist
[5 empty] | AC-L1.11 | FCU-AC checklist
[5 empty] | AC-L1.13 | FCU-AC checklist
[5 empty] | AC-L1.16 | FCU-AC checklist
Science
Level 1
[5 empty] | OU-L1-04 | AC Condensor checklist
[5 empty] | BS-L1-04 | Branch Box checklist
[5 empty] | AC-L1.10 | FCU-AC checklist
[5 empty] | AC-L1.14 | FCU-AC checklist
[5 empty] | AC-L1.15 | FCU-AC checklist
[5 empty] | AC-L1.17 | FCU-AC checklist
[5 empty] | AC-L1.18 | FCU-AC checklist
[5 empty] | AC-L1.19 | FCU-AC checklist
Science
Level 1
[5 empty] | OU-L1-05 | AC Condensor checklist
[5 empty] | BS-L1-05 | Branch Box checklist
[5 empty] | AC-L1.20 | FCU-AC checklist
[5 empty] | AC-L1.21 | FCU-AC checklist
[5 empty] | AC-L1.22 | FCU-AC checklist
[5 empty] | AC-L1.23 | FCU-AC checklist
[5 empty] | AC-L1.24 | FCU-AC checklist
[5 empty] | AC-L1.25 | FCU-AC checklist
[5 empty] | AC-L1.26 | FCU-AC checklist
Level 2
Level 2
[5 empty] | OU-L2-01 | AC Condensor checklist
[5 empty] | BS-L2-01 | Branch Box checklist
[5 empty] | AC-L2.01A | FCU-AC checklist
[5 empty] | AC-L2.01B | FCU-AC checklist
[5 empty] | AC-L2.02 | FCU-AC checklist
Solar Inverter
Basement
[5 empty] | IU-B-01 | FCU-AC checklist
[5 empty] | CU-B-01 | AC Condensor checklist
Comms Room
Ground Floor
[5 empty] | IU-G-01 | FCU-AC checklist
[5 empty] | CU-R1 | AC Condensor checklist
[5 empty] | IU-L1-01 | FCU-AC checklist
[5 empty] | CU-R2 | AC Condensor checklist
Fire Damper
[5 empty] | FD-B-1 | Fire Damper checklist
[5 empty] | FD-B-2 | Fire Damper checklist
[5 empty] | FD-B-3 | Fire Damper checklist
[5 empty] | FD-B-4 | Fire Damper checklist
[5 empty] | FD-B-5 | Fire Damper checklist
[5 empty] | FD-B-6 | Fire Damper checklist
[5 empty] | FD-B-7 | Fire Damper checklist
[5 empty] | FD-B-8 | Fire Damper checklist
[5 empty] | FD-B-9 | Fire Damper checklist
[5 empty] | FD-B-10 | Fire Damper checklist
[5 empty] | FD-G-1 | Fire Damper checklist
[5 empty] | FD-G-2 | Fire Damper checklist
[5 empty] | FD-G-3 | Fire Damper checklist
[5 empty] | FD-G-3A | Fire Damper checklist
[5 empty] | FD-G-4 | Fire Damper checklist
[5 empty] | FD-L1-1 | Fire Damper checklist
[5 empty] | FD-L1-2 | Fire Damper checklist
[5 empty] | FD-L1-3 | Fire Damper checklist
[5 empty] | FD-L1-4 | Fire Damper checklist
[5 empty] | FD-L1-5 | Fire Damper checklist
[5 empty] | FD-L1-6 | Fire Damper checklist
[5 empty] | FD-L1-7 | Fire Damper checklist
[5 empty] | FD-L1-8 | Fire Damper checklist
[5 empty] | FD-L1-9 | Fire Damper checklist
Seismic
Basement
|  |  |  | Duct run CPEF-01 |  | Seismic checklist
|  |  |  | Duct run CPSF-01 |  | Seismic checklist
Seismic checklist
Ground
Duct
[5 empty] | General | Seismic checklist
[5 empty] | M110 | Seismic checklist
[5 empty] | M104 | Seismic checklist
[5 empty] | Risers | Seismic checklist
Equipment
[5 empty] | HRU-G.01 | Seismic checklist
[5 empty] | HRU-G.02 | Seismic checklist
[5 empty] | HRU-G.03 | Seismic checklist
[5 empty] | HRU-G.04 | Seismic checklist
[5 empty] | HRU-G.05 | Seismic checklist
[5 empty] | HRU-G.06 | Seismic checklist
[5 empty] | HRU-G.07 | Seismic checklist
[5 empty] | HRU-G.08 | Seismic checklist
[5 empty] | HRU-G.09 | Seismic checklist
[5 empty] | HRU-G.10 | Seismic checklist
[5 empty] | HRU-G.11 | Seismic checklist
[5 empty] | HRU-G.12 | Seismic checklist
[5 empty] | TEF-G-01 | Seismic checklist
[5 empty] | BS-G-01 | Seismic checklist
[5 empty] | AC-G.01 | Seismic checklist
[5 empty] | AC-G.02 | Seismic checklist
[5 empty] | AC-G.04 | Seismic checklist
[5 empty] | AC-G.05 | Seismic checklist
[5 empty] | AC-G.06 | Seismic checklist
[5 empty] | AC-G.07 | Seismic checklist
[5 empty] | AC-G.08A | Seismic checklist
[5 empty] | AC-G.08B | Seismic checklist
[5 empty] | AC-G.08C | Seismic checklist
[5 empty] | BS-G-05 | Seismic checklist
[5 empty] | AC-G.10A | Seismic checklist
[5 empty] | AC-G.10B | Seismic checklist
[5 empty] | AC-G.10C | Seismic checklist
[5 empty] | AC-G.10D | Seismic checklist
[5 empty] | AC-G.10E | Seismic checklist
[5 empty] | AC-G.24 | Seismic checklist
[5 empty] | BS-G-04 | Seismic checklist
[5 empty] | AC-G.09 | Seismic checklist
[5 empty] | AC-G.11 | Seismic checklist
[5 empty] | AC-G.12 | Seismic checklist
[5 empty] | AC-G.13 | Seismic checklist
[5 empty] | AC-G.22 | Seismic checklist
[5 empty] | AC-G.23 | Seismic checklist
[5 empty] | BS-G-02 | Seismic checklist
[5 empty] | AC-G.15A | Seismic checklist
[5 empty] | AC-G.15B | Seismic checklist
[5 empty] | AC-G.16 | Seismic checklist
[5 empty] | AC-G.17 | Seismic checklist
[5 empty] | BS-G-03 | Seismic checklist
[5 empty] | AC-G.14 | Seismic checklist
[5 empty] | AC-G.18 | Seismic checklist
[5 empty] | AC-G.19 | Seismic checklist
[5 empty] | AC-G.20 | Seismic checklist
[5 empty] | KSF-1 | Seismic checklist
[5 empty] | ATT-G1 | Seismic checklist
[5 empty] | ATT-G2 | Seismic checklist
Level 1
Duct
[5 empty] | General | Seismic checklist
[5 empty] | Risers M204 | Seismic checklist
[5 empty] | Risers M208 | Seismic checklist
[5 empty] | Fume Risers M209 | Seismic checklist
Roof
[5 empty] | Fans | Seismic checklist
[5 empty] | Condensers | Seismic checklist
[5 empty] | Risers upper roof | Seismic checklist
Equipment
[5 empty] | HRU-L1.01 | Seismic checklist
[5 empty] | HRU-L1.02 | Seismic checklist
[5 empty] | HRU-L1.03 | Seismic checklist
[5 empty] | HRU-L1.04 | Seismic checklist
[5 empty] | HRU-L1.05 | Seismic checklist
[5 empty] | HRU-L1.06 | Seismic checklist
[5 empty] | HRU-L1.07 | Seismic checklist
[5 empty] | HRU-L1.08 | Seismic checklist
[5 empty] | HRU-L1.09A | Seismic checklist
[5 empty] | HRU-L1.09B | Seismic checklist
[5 empty] | HRU-L1.10 | Seismic checklist
[5 empty] | HRU-L1.11 | Seismic checklist
[5 empty] | HRU-L1.13 | Seismic checklist
[5 empty] | HRU-L1.14 | Seismic checklist
[5 empty] | HRU-L1.15 | Seismic checklist
[5 empty] | HRU-L1.16 | Seismic checklist
[5 empty] | HRU-L1.17 | Seismic checklist
[5 empty] | HRU-L1.19 | Seismic checklist
[5 empty] | HRU-L1.20 | Seismic checklist
[5 empty] | HRU-L1.21 | Seismic checklist
[5 empty] | HRU-L1.22 | Seismic checklist
[5 empty] | HRU-L1.23 | Seismic checklist
[5 empty] | BS-L1-01 | Seismic checklist
[5 empty] | AC-L1.01 | Seismic checklist
[5 empty] | AC-L1.04 | Seismic checklist
[5 empty] | AC-L1.06 | Seismic checklist
[5 empty] | AC-L1.07 | Seismic checklist
[5 empty] | BS-L1-02 | Seismic checklist
[5 empty] | AC-L1.02 | Seismic checklist
[5 empty] | AC-L1.03A | Seismic checklist
[5 empty] | AC-L1.03B | Seismic checklist
[5 empty] | AC-L1.05 | Seismic checklist
[5 empty] | AC-L1.08 | Seismic checklist
[5 empty] | BS-L1-03 | Seismic checklist
[5 empty] | AC-L1.09A | Seismic checklist
[5 empty] | AC-L1.09B | Seismic checklist
[5 empty] | AC-L1.11 | Seismic checklist
[5 empty] | AC-L1.13 | Seismic checklist
[5 empty] | AC-L1.16 | Seismic checklist
[5 empty] | BS-L1-04 | Seismic checklist
[5 empty] | AC-L1.10 | Seismic checklist
[5 empty] | AC-L1.14 | Seismic checklist
[5 empty] | AC-L1.15 | Seismic checklist
[5 empty] | AC-L1.17 | Seismic checklist
[5 empty] | AC-L1.18 | Seismic checklist
[5 empty] | AC-L1.19 | Seismic checklist
[5 empty] | BS-L1-05 | Seismic checklist
[5 empty] | AC-L1.20 | Seismic checklist
[5 empty] | AC-L1.21 | Seismic checklist
[5 empty] | AC-L1.22 | Seismic checklist
[5 empty] | AC-L1.23 | Seismic checklist
[5 empty] | AC-L1.24 | Seismic checklist
[5 empty] | AC-L1.25 | Seismic checklist
[5 empty] | AC-L1.26 | Seismic checklist
[5 empty] | BS-L2-01 | Seismic checklist
[5 empty] | AC-L2.01A | Seismic checklist
[5 empty] | AC-L2.01B | Seismic checklist
[5 empty] | AC-L2.02 | Seismic checklist
Green star
|  |  |  | Photo identification |  | Greenstar checklist

## Checklists
type | name | values
checklist | MSSB checklist
checkpoint | MSSB mounted in position
checkpoint | MSSB labelled correctly
checkpoint | Required clearance provided to MSSB
checkpoint | Cables connected into MSSB and all terminated and labelled
checkpoint | Main power connected to MSSB
checkpoint | MSSB energisation form provided to builder
checkpoint | Fire interface cable supplied & fitted off.
checkpoint | MSSB commissioned and operational
checklist | Fire Damper checklist
checkpoint | Fire damper installed correctly
checkpoint | Fire damper labelled
checkpoint | Fire damper sealed correctly
checkpoint | Photo required of installation
Drop test
checklist | Ventilation Fans checklist
checkpoint | Technical data from Unit, Motor & drives match equipment schedules |  | Solid ductwork install complete and levelled
checkpoint | Equipment Identification labels installed. |  | All flexible/canvas ductwork connections installed
checkpoint | All components installed as per Mechanical shop drawings |  | Fan installed into position and correctly aligned/Level and in direction of flow
checkpoint | Transport bolts and packing material Removed |  | Vibration isolation installed
checkpoint | Mounting and anti vibration mounts installed |  | Dampers installed to duct (NRD, VC, FD, MVCD) Correctly
checkpoint | Fan & motor rotate freely
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Electrical connections complete and Mains power available |  | All items correctly insulated if required
checkpoint | Control wiring complete including any local operating controllers |  | Fire Shutdown cable roughed in
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC |  | VSD installed to Fan including electrical and controls
checkpoint | Mechanical electrical contractor has verified operating voltage & amps |  | Works area tidy and clean of debris
checkpoint | Fan rotation verified by electrical contractor |  | General area inspection for defects
checkpoint | Controls functionality programmed and operational |  | Solid ductwork capped, covered, sealed and seams weatherproofed
checkpoint | System is ready to be put into manual / automatic operation. |  | Overflashings installed and weatherproofed
checkpoint | System has been commissioned & balanced. |  | Filters installed and are removable
checkpoint | Fire interface connected and operational |  | Electrical installation fitted off
checkpoint | System correctly operational & placed into Automatic service. |  | Control works fitted off including all sensors, controllers
Fire Shutdown connected
checklist | AC Condensor checklist |  | Grilles/louvres installed if required
checkpoint | Technical data from Unit,Motor & drives match equipment schedules |  | labels installed
checkpoint | All components installed as per Mechanical shop drawings |  | Take photp of Fan model and serial name plate
checkpoint | Equipment Identification labels installed. |  | All dampers are fully open
checkpoint | Transport bolts and packing material Removed |  | Works area tidy and clean of debris
checkpoint | Mounting and anti vibration mounts installed |  | General area inspection for defects
checkpoint | Condensate drains / safety trays connected and tested for correct operation |  | Equipment ready for commissioning
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | Branch Box checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | FCU-AC checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | ERV / HRV Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Fans & Motors rotate freely
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | VSD checklist
checkpoint | Technical data from VSD matches equipment schedules
checkpoint | VSD mounted in position
checkpoint | VSD labelled correctly
checkpoint | Cables connected into VSD and all terminated
checkpoint | Main power connected to MSSB
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | VSD has been commissioned programmed & Parameter list recorded.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | Seismic checklist
checkpoint | Seismic installed as design
checkpoint | Seismic location/drawing
Seismic photos
checklist | Greenstar checklist
checkpoint | PVC pipe
reciepts
Solvents/silicon
Solid Duct plastic wrapped