## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | External Wall Framing Checklist |  | External Wall Framing Checklist | 18a0bc1e-1e65-4a3c-9cb2-59f228401eb3
| checkpoint | Installer details entered
685431b5-7d44-59f1-b02c-2a6e1d10ce18 | textbox | Installer:
| checkpoint | 1) All relevant drawings and revision numbers checked and attached.
| checkpoint | 2) Timber delivery dockets checked and correct on arrival.
845a1d29-be41-596c-b76c-4d05477bc422 | tickbox | All timber dockets attached
| checkpoint | 3) Timber delivered are well stored and protected.
| checkpoint | 4) DPC installed, checked, and correct as per specifications.
| checkpoint | 5) Wall locations checked, correct, and approved as per latest revised drawing.
| checkpoint | 6) Fixings and hold down bolts checked and correct.
| checkpoint | 7) All openings (doors/windows, etc) checked, correct and approved.
| checkpoint | 8) Wall type checked (straight and plumb) and within tolerance.
| checkpoint | 9) 20mm clearance zone required between the threaded rod and structure above
| checkpoint | 10) All relevant nogs (service, and special fixtures) installed, checked and correct.
| checkpoint | 11) Moisture reading checked, recorded and acceptable.
| checkpoint | 12) All wall framing checks completed and inspections carried out.
| checkpoint | 13) Report sent to client.
| checklist | Fire Door Post-Installation Check |  | Fire Door Post-Installation Check | f377388d-3ae1-4103-a40f-5f6873798483
| section | Details
| checkpoint | All relevant drawings and revision numbers checked and attached.
| checkpoint | Door is fully operational.
| checkpoint | Door jambs are level and direction of door correct.
| checkpoint | Correct fixings used and installed at correct centres.
| checkpoint | Door gap around door leaf within tolerance as per manufacturer’s specifications.
| checkpoint | Fireseal around door installed correctly.
| checkpoint | Floor clearance is correct.
| checkpoint | Installer details.
| checkpoint | Post-Installation checked completed.
| signoff | Add signature
| checklist | Fire Door Pre-Installation Check |  | Fire Door Pre-Installation Check | e97d47e9-2eb5-463d-b47b-dca34fd121a1
| section | Details
| checkpoint | Installation can be carried out in accordance with finish floor product thickness.
| checkpoint | Door opening area (slab) is level with door jamb area.
| checkpoint | Wall framing opening size checked and correct.
| checkpoint | The dimensions of the door frame and panel are in accordance to Hawkins’ order.
| checkpoint | Door frame and panel are free from any defects and damages upon receiving from Hawkins.
| checkpoint | Pre-Installation checked completed
| signoff | Add signature
3d74aca7-9982-41b5-af05-64628c0c022f | checklist | GIB Lining |  | GIB Lining | 09c5b30a-1d41-40ec-8951-c6cf4888d147
2b82be1e-a147-4847-b765-c7c3763943cb | checkpoint | Installer details entered
60e19cfd-c818-5ba6-9681-96548b8a7ceb | textbox | Installer:
6d5e1cf1-2418-40a0-8b29-f2adf8cf7e3d | checkpoint | All relevant drawings and revision numbers checked and attached/commented
73f33e0c-369c-4284-9f54-16005ef29c4a | checkpoint | Area ready for GIB install
5476ccc3-a922-445e-b269-8916cc64f868 | checkpoint | Insulation installed
6724bf1a-4c59-419f-b701-194e7672ba84 | checkpoint | General photos, comments and observations during install
48a8002c-4618-499b-a8f5-40c79e3bc5d0 | checkpoint | Correct lining checked and approved and area specifics checked
62dae2f3-24e9-4e75-9059-e804301194dd | checkpoint | Correct fixings used and installed at correct centres
d0cc8a9f-b39c-478c-9c61-97604e8ba568 | checkpoint | Any bracing elements completed to design specification
3f794aa9-9f60-40df-aa8f-1e77dd88c208 | checkpoint | In long unbroken partitions or wall runs, control joints are required at 12 metres centres in either direction
4f1d5afc-4f66-4bb4-a353-766563d460f9 | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
89e42923-042f-476e-931f-a0920b93538c | checkpoint | GIB Lining report sent through to client
| checklist | GIB Weatherline |  | GIB Weatherline | 82bb4d25-8e87-4d58-a5d7-26eb510d4f58
| checkpoint | All relevant KCL drawings and revision numbers checked and attached
| checkpoint | Installation location
06d42236-35d0-5a47-bb38-1c82482586e0 | tickbox | Timber Frame 800mm x 300mm
aef1f987-cc4f-5db1-b90d-e1bc56c32125 | tickbox | Steel Studs 300mm x 300mm
| checkpoint | Correct fasteners used and installed at correct centres
| checkpoint | Fasteners – 12mm from the edges and 18mm from ends
| checkpoint | Fasteners – 200mm centres along sheet end butt joints
| checkpoint | Are screws over driven? If YES, install a new screw fixing 25mm away and adjacent to the over driven screw.
| checkpoint | Is the GIB installed hard up against the floor.
| checkpoint | Installer details
5132182e-2717-5353-8c19-51fb8318db5d | textbox | Installer:
| checklist | Prefab Module Fabrication |  | Prefab Module Fabrication | 2b34b135-5d64-4738-884c-40c7228726a0
| section | Details
| checkpoint | Panel Numbers
| checkpoint | Date Check
| checkpoint | Installers Details
| checkpoint | Fixing used checked and correct
| checkpoint | Panel constructed checked (straight, plumb and square)
| checkpoint | All window openings checked and correct
| checkpoint | Gib Weatherline – correct fixings used and installed at correct centres
| checkpoint | WrapShield – all installation as per manufacturer’s specs; overlaps must be a minimum of 80mm on horizontal and vertical seams, VaproLiqui-Flash applied evenly at least 50mm onto the face and at least 25mm out along all sides of the penetration and all air bubbles must be smooth out to ensure full adhesion.
f1830bff-e028-5d3e-b117-001f178e3e3a | note | All panel checks completed and inspections carried out.
| signoff | ANT Steel Frame Check/Signoff
| checkpoint | Livefirm Signoff
| checkpoint | Report sent through to Hawkins
| checklist | Prefab Module Installation / Post Installation |  | Prefab Module Installation / Post Installation | b7c62ddf-458d-4bc5-8791-5fdbab72e897
| section | Prefab Module Installation
| checkpoint | Prefab module received and damaged free
| checkpoint | Setup completed and clearly marked and ready for installation
| checkpoint | Installed in correct centres location with adequate seating (each stud with packers)
| checkpoint | Correct centres and fixing used on steel structure and floor
| checkpoint | Prefab module installation completed (check location, height and level)
| signoff | Request Signoff
| section | Prefab Module Post Installation
| checkpoint | Window opening location checked and correct
| checkpoint | Drossbach fully grouted
| checkpoint | Correct type of grout used
| checkpoint | Simpson tie bolt checked and tighten
| signoff | Request Signoff
a841648e-e155-4245-ae76-575fcac4ad1f | checklist | QA - Base Set Out Checklist |  | QA - Base Set Out Checklist | f676fe1a-e1b3-4bb2-aff5-fe04a1de5678
| checkpoint | Installer details entered
79fee405-71e1-592b-b400-7252f4b7d727 | textbox | Installer:
2a789262-deb8-4ee6-ab14-acb3f2173991 | checkpoint | All relevant drawings and revision numbers checked and attached/commented
144d20c0-ec31-4140-a31d-56a99473f698 | checkpoint | Set out points and Datum to be established by surveyor
b41edaf8-208b-4878-bb5e-c5f9fd1d5781 | checkpoint | Obtain written confirmation from surveyor
fd0bb3a2-9a83-4ee5-a8e9-7eba95fbc3ab | checkpoint | Send Report to client
| checklist | QA - Concrete Pour Checklist |  | QA - Concrete Pour Checklist | 49933a36-eed0-4c74-9bc0-0a99e2f8a614
| section | Installer Details
| checkpoint | Installer details entered
a9da33ce-75dd-5c2a-b115-ab772fbb2eac | textbox | Installer:
| section | Pre-Formwork and Embedded Items
| checkpoint | Drawing numbers and revisions
| checkpoint | Pre Formwork Inspection
20e0d790-fe28-5745-a64f-dbdab164e6e2 | button | Cover to reinforcement | Pass,Fail,N/A
77f9f72e-fde0-5d54-893e-072dd14b63b4 | button | Dimension/Thickness according to design | Pass,Fail,N/A
| signoff | Request for signoff
| section | Post-Formwork and Embedded Items
| checkpoint | Grids and RLs clearly marked for reference
| checkpoint | Reinforcing approved by contractor
| checkpoint | Formwork - location, heights, falls, and dimensions checked and accurate
| checkpoint | Formwork sufficiently fixed and braced
| checkpoint | Any rebates/nibs/cast in items are correctly positioned, sized and appropriately fixed in place
8ad88f85-ba18-5a78-8315-48094e284c19 | tickbox | Hold down bolts checked and correct
de638392-fe4b-52b6-82f3-f62db2d821fa | tickbox | Precast panel starters checked and correct
| checkpoint | Service penetrations formed correctly and locations checked/correct
| checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc)
| checkpoint | Any control joints/stop ends installed accurately and correctly braced
| checkpoint | Waterproofing approved by contractor
| checkpoint | DPM & connection to other waterproofing completed
| checkpoint | Any additional formwork photos and observations
| checkpoint | All formwork elements completed and ready for concrete pour (Livefirm’s own excess debris removed)
| checkpoint | Slump test / Spread test (only applicable to special mix)
| checkpoint | Signoff Request sent to Livefirm senior site manager
| signoff | Signoff Request sent to Livefirm senior site manager
| checkpoint | Signoff Request sent to Hawkins from Livefirm senior site manager
| signoff | Signoff Request sent to Hawkins from Livefirm senior site manager
| section | Placement Method
| checkpoint | Placement methodology confirmed and necessary plant and equipment on site
d486df44-034a-529d-8902-3317a89a21ce | textbox | Date of pour
9870f572-e54b-5272-adc5-689e94fbb34f | textbox | Who is placing the concrete
| checkpoint | Concrete ordered – correct mix and strength
cd2e3c1e-1665-540d-9690-8418d857c98c | textbox | Mix
955aa592-22ea-5067-9420-87c7ff99bb31 | textbox | Strength
620ef230-e4e0-580d-a373-18b04303d3ad | textbox | Summary of proposed cement mix date and revision checked
a32e7f09-374d-5f95-91b5-de97629cb7e6 | textbox | Structural services specifications number and revision checked
| checkpoint | Height and falls checked / confirmed before placement
| checkpoint | Cover correct to specification
| checkpoint | Concrete pump priming grout slurry is pumped to waste
| checkpoint | All concrete checked and correct on arrival (mix and strength)
5d47a110-5184-5157-b37f-967cf41a1dfd | textbox | All concrete dockets attached
| checkpoint | General photos and observations of concrete placement attached
| checkpoint | Heights and falls checked / confirmed after placement
| checkpoint | Any curing compound applied correctly
| checkpoint | Concrete placement completed - specified level of finish achieved
| checkpoint | Area left clean and tidy
| checkpoint | Report sent to client
| signoff | Request for signoff
| section | Post-Pour Checks
| checkpoint | Any remedial work completed
| checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
| checkpoint | Report sent to client
fc5fc549-6091-488e-9513-c0c8922d44dc | checklist | QA - Precast Erection Checklist |  | Precast Erection Checklist | 35a129f3-bdb7-43fe-a0ba-8a328fb21eb9
| section | Installer Details
| checkpoint | Installer details entered
65db7f28-ba53-5d38-8021-a5bd8f4f34b4 | textbox | Installer:
61886a01-a1fb-4516-9e93-eaa1baf2f363 | section | Component
c993d19e-f34e-4a1d-8623-242e08451678 | checkpoint | Component Specified
65db7f28-ba53-5d38-8021-a5bd8f4f34b4 | dropdown | Select | Beam,Double T,Dycore,Rib,Slab,Staircase,Wall
8f6d7f14-c88a-5b12-ab5b-ccc19b88a6df | textbox | If other please specify
ef0fa217-8b42-4623-9a28-54d83ac4b033 | section | Drawing & Instruction
e139ce8f-eeb8-43d3-bb0e-85971fd406dd | checkpoint | Drawing References
dab72bfe-ea2c-5673-a2eb-12af9827fb1a | textbox | 1
adb306a7-e1fa-561c-8fe5-e0b1a4314a7d | textbox | 2
4431912b-436d-557d-a09f-d7a25e5a9bdc | textbox | 3
df3bdf06-5ab1-53e8-8b52-db988cc2c4d5 | textbox | 4
560312a8-b755-4eb4-9b9b-c584c6342a45 | section | Setting Out/Starter bar/Shore loading/Fixing
962413fd-dc82-4309-8ac4-34eeed2b50d9 | checkpoint | Survey mark
a60f0d7c-d2f8-42bd-aec1-ea676fdc4140 | checkpoint | Grids & Offsets
14148c21-a1b3-4a84-8b75-d5c2ca36bb6d | checkpoint | Datums
188a59ad-9ced-4a34-bb61-7b99239e3663 | checkpoint | Starter bar
560d74cd-4d99-462f-9e20-60a46b34fe75 | checkpoint | Shore Loading
d672f8f0-3c75-494e-9e4c-5ad433fe38b1 | checkpoint | Propping
4e4bcab7-70fa-4e73-84c0-79c815560f8e | checkpoint | Safety bolt
c9a58ac6-251f-5d6e-baf3-8804464ffd95 | textbox | Bolt size :
301048ac-5785-574a-9755-826c7fa1256c | textbox | Bolt type :
ac6d9b46-fc1c-46bb-b461-34589f3ad70b | section | Precast Items
8908b511-6888-4f4d-a952-d0da16170005 | checkpoint | Dimensions
4676117c-01d4-4210-9710-a4512112821d | section | Pre-Erection Meeting
d8d78ecd-2631-42ba-ad29-9f49bb964061 | checkpoint | Complete
6e5ad12d-53b5-5100-ae55-b6adb99000be | textbox | List all who are present
68bea212-be1a-4475-aa39-acf208686abf | section | Signoffs
c018d182-3ec9-4a45-a374-8d5b275db3a9 | checkpoint | Work to Proceed
| checklist | Roof Checklist |  | Roof Checklist | 118a32f5-7fbe-43cc-b97a-54b683fab474
| section | Battens
| checkpoint | Timber treatment correct as per spec
| checkpoint | Timber spacings are correct
| checkpoint | Fixings installed with correct fixing pattern
| section | Plywood
| checkpoint | Plywood is correct thickness (17mm)
| checkpoint | Fixings installed with correct fixing pattern
| checkpoint | Correct fixing used and installed at correct centres
| checkpoint | Correct adhesive used
| checkpoint | Sheets installed in staggered pattern
| checkpoint | No gaps between sheets
| section | Completion and Handover
| checkpoint | All framing completed correctly within tolerance in respective area
| checkpoint | Report sent through to client
| checklist | Soffit |  | Soffit | 8350c61f-2098-4335-8000-8201307b0886
| section | Details
| checkpoint | All relevant drawings and revision numbers checked.
| checkpoint | Timber frame specifications.
| checkpoint | All joists are installed at correct centres.
| checkpoint | Correct fixing used and installed at correct centres
| checkpoint | Soffit lined with GIB weatherline completed correctly according to manufacturer’s specifications.
| checkpoint | Installer’s details.
c9667501-ac7a-57ab-99cc-4dff6da01a07 | textbox | Installer:
66ef80ee-c709-4d8a-b27c-5e41afe69dac | checklist | Wall Framing Checks |  | Wall Framing Checks | d075bc65-860f-4fc9-ba17-d7c7d52695b5
242b4a2d-b6ea-4b9f-9b82-44c97e7664cb | checkpoint | Installer details entered
71f8d068-5761-57e6-b5c5-9d03600b65d5 | textbox | Installer:
edb252a7-e90b-466f-bce4-a1e4f5291978 | checkpoint | All relevant drawings and revision numbers checked and attached
0a7a108a-19ad-451b-934b-f7b12947377b | checkpoint | Drawing no. and revision
ad916d8f-5cd2-4f09-a24f-c45390255cdb | checkpoint | DPC installed, checked and correct as per specification
ed5387dd-2423-4123-b7f7-46304e373532 | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
af766c46-1afc-47c9-a5d5-8cd6ce68795d | checkpoint | Fixings and hold down bolts checked and correct
729bd163-422e-47d5-9ef0-a1597a81c079 | checkpoint | All openings (doors / windows etc) checked, correct and approved
ca10f7e4-86da-4169-b4eb-c904171e4a53 | checkpoint | Deflection heads type installed and correct
02bbad7e-8c32-494e-b8df-b2648d8c6846 | checkpoint | Wall type checked (straight and plumb) and within tolerance
f7f65abf-1434-4bd1-a7fc-1ca3ed03938c | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
cfbb253e-1152-4b43-92d7-8be62659867f | checkpoint | All other nogs checked and approved
d7335047-3825-4433-b754-b2936fa3f825 | checkpoint | Moisture reading checked, recorded and acceptable
5444ef0f-94a8-4e52-85d3-3dc006644d70 | checkpoint | A control joint is required where there is a split between the underlying structure with a break in the top and bottom plate
ec2c3681-ddd7-4d45-84c1-4ac865741a38 | checkpoint | All wall framing checks completed & Inspections carried out
bc4bec8e-9ade-4506-8897-668fde1d1a4f | checkpoint | Relevant inspections completed and attached
cb7f00af-8484-47d0-a0a4-b30e6faa2703 | checkpoint | Report sent to client
| checklist | WrapShield |  | WrapShield | c18de092-4fd7-4a83-94e5-3b064d708527
| checkpoint | Installer details entered
249aea3a-4077-5d94-9725-c3c277f15604 | textbox | Installer:
| checkpoint | Substrate must be dry, clean and free of any contaminants.
| checkpoint | All overlaps must be a minimum of 80mm on horizontal and vertical seams.
| checkpoint | Inside and outside vertical corners should be at minimum 150mm of overlap.
| checkpoint | All installation must be with the lower courses lapped under the upper courses.
| checkpoint | All air bubbles must be smooth out to ensure full adhesion.
| checkpoint | Apply VaproLiqui-Flash evenly at least 50mm onto the face and at least 25mm out along all sides of the penetration.