## Lot Register
ITP# | Lot ID | Status | NCR?
01 | MS1 | Open
| MS2 | Open
| MS3 | Open
| MS4 | Open
| MS5 | Open
| Swale 12 | Open
| Swale 9 | Open
| Swale 7 | Open
| Swale 10-2 | Open
| Swale 8-2 | Open
| Pit 1 | Open
| Pit 2 | Open
| Pit 3 | Open
| Culvert 5 | Open
| Culvert 4 | Open
| Swale 2 | Open
| Culvert 2 | Open
| Culvert 3 | Open
02 | swale 3 | Open
| swale 5 | Open
| swale 9 | Open
| swale 11 | Open
| swale 13 | Open
| swale 14 | Open
| swale 6 | Open
| MS1 | Open
| MS2 | Open
| MS3 | Open
| MS4 | Open
| MS5 | Open
03 | Culvert 1 | Open
| Culvert 2 | Open
| Culvert 3 | Open
| Culvert 4 | Open
| Culvert 5 | Open
| Swale 1 | Open
| Swale 2 | Open
| Swale 8-1 | Open
| Swale 10-1 | Open
| Swale 12 | Open

## ITP - Overarching Checklist
type |  | name | Note for CONQA | Need one copy of this checklist for the project.
checklist |  | RCCE - SMP Implementation Project - Overarching Checklist | Project Name: | STORMWATER MANAGEMENT PLAN IMPLEMENTATION PROJECT
section |  | Preliminary Sign-offs | Stage: | Package 1 - CONSTRUCTION
Checkpoint | PASS / FAIL / N/A | Approval of Quality Management Plan (QMP) | Our Reference: | 189
textbox |  | (Upload QMP here) | Client: | Byron Shire Council (BSC)
signoff |  | HOLD POINT - QMP reviewed and accepted by BSC Representative | Client Reference: | 2024-2089
Checkpoint | PASS / FAIL / N/A | Approval of Traffic Management Plan (TMP)
textbox |  | (Upload TMP here)
signoff |  | HOLD POINT - TMP reviewed and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Safety Management Plan (SMP)
textbox |  | (Upload SMP here)
signoff |  | HOLD POINT - SMP reviewed and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Inspection Test Plans (ITPs)
textbox |  | (Upload ITPs here)
signoff |  | HOLD POINT - ITPs reviewed and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Decommissioning Plan (DP)
textbox |  | (Upload DP here)
signoff |  | HOLD POINT - DP reviewed and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Precommencement Survey
textbox |  | (Upload Precommencement Survey here)
signoff |  | HOLD POINT - Precommencement Survey reviewed and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Services Survey
textbox |  | (Upload Services Survey here)
signoff |  | HOLD POINT - Services Survey reviewed and accepted by BSC Representative
section |  | Material Sign-offs
Checkpoint | PASS / FAIL / N/A | Approval of Seperation Geotextile material
textbox |  | (Upload Evidence / Certification of Seperation Geotextile material used here)
signoff |  | HOLD POINT - Seperation Geotextile material accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Rip-rap material
textbox |  | (Upload Evidence / Certification of Rip-rap material used here)
signoff |  | HOLD POINT - Rip Rap material accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of GCCM material
textbox |  | (Upload Evidence / Certification of GCCM material used here)
signoff |  | HOLD POINT - GCCM material accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Trench Drainage material
textbox |  | (Upload Evidence / Certification of Trench Drainage material used here)
signoff |  | HOLD POINT - Trench Drainage material accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Certification of Pre-cast Units
textbox |  | (Upload Certification of Compliance for pre-cast units here)
signoff |  | HOLD POINT - Pre-cast Units accepted by RCCE PM or Engineer & BSC Representative
section |  | Completion of Works Sign-offs
Checkpoint | PASS / FAIL / N/A | Acceptance of Works As-Excecuted (WAE)
textbox |  | (Upload WAE here)
signoff |  | HOLD POINT - WAE accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Acceptance of CCTV
textbox |  | (Upload CCTV files here)
signoff |  | HOLD POINT - CCTV accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | All NCRs closed
textbox |  | (Upload NCR Register here)
signoff |  | HOLD POINT - All NCRs closed and accepted by BSC Representative
signoff |  | RCCE - PM to sign and close out Lot

## 189 - ITP Lot Checklist-RAW
type |  | name | Note for CONQA | This is checklist that includes all items, I have then removed what is not required for the releveant ITP checklist is relating to
checklist |  | RCCE - SMP Implementation Project - Lot Checklist - FULL | Project Name: | STORMWATER MANAGEMENT PLAN IMPLEMENTATION PROJECT
section |  | Lot Details | Stage: | Package 1 - CONSTRUCTION
textbox |  | Lot No. | Our Reference: | 189
textbox |  | Lot ID. | Client: | Byron Shire Council (BSC)
textbox |  | Lot Description | Client Reference: | 2024-2089
Checkpoint | PASS / FAIL / N/A | Lot Checklist to be complete in conjunction with pre-approved Project-specific ITPs
section |  | Formation Survey
Checkpoint | PASS / FAIL / N/A | Approval of Formation Survey
textbox |  | (Upload Formation Survey here)
signoff |  | HOLD POINT - Formation Survey reviewed and accepted by BSC Representative
section |  | Erosion & Sediment Control
Checkpoint | PASS / FAIL / N/A | ERSED Installed
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - ERSED accepted by RCCE Supervisor (or other representative)
section |  | Construction & Installation
Checkpoint | PASS / FAIL / N/A | Approval of Seperation Geotextile Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Seperation Geotextile Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of GCCM Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - GCCM Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of HDPE Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - HDPE Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Culvert / Pit Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Culvert / Pit Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Inspection
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Foundation inspected and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Testing
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - Foundation testing signed off by RCCE Supervisor
signoff |  | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
Checkpoint | PASS / FAIL / N/A | Concrete Pre-pour Inspection
textbox |  | (Upload photos of pre-pour & any commentary here)
signoff |  | HOLD POINT - Pre-pour accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Geometry Measured
textbox |  | (Upload photos of geometry & any commentary here)
signoff |  | SIGNOFF - Geometry measured and signed off by RCCE Supervisor
signoff |  | SIGNOFF - Geometry measured and witnessed by BSC Representative (Optional)
section |  | Non-Conformance Reporting - IF APPLICABLE
Checkpoint | PASS / FAIL / N/A | Non-Conformance Reported
textbox |  | (Upload additional photos & any commentary here, including remedial measures)
signoff |  | SIGNOFF - RCCE Representative resolved NCR
signoff |  | HOLD POINT - NCR resolved and accepted by BSC Representative
section |  | Other
Checkpoint | PASS / FAIL / N/A | Other
textbox |  | (Upload additional photos & any commentary here)
signoff |  | SIGNOFF - Signoff by RCCE Supervisor relating to any additional commentary.
section |  | Lot Closure
Checkpoint |  | Were any Non-Conformances reported
textbox |  | details of NCR and remediation measures required
Checkpoint |  | NCR Closed?
signoff |  | RCCE - Supervisor or PM remediated and closed NCR
Checkpoint |  | Acceptance of Works within Lot
textbox |  | (Upload completion photos here)
signoff |  | HOLD POINT - Lot accepted by BSC Representative
signoff |  | RCCE - PM to sign and close out Lot

## 189 - ITP-01-Checklist
type |  | name |  | Note for CONQA | A copy of this checksheet will be required to be replicated for each Lot
checklist |  | RCCE - SMP Implementation Project - ITP-01-Drainage Structures-CHECKLIST |  | Project Name: | STORMWATER MANAGEMENT PLAN IMPLEMENTATION PROJECT
section |  | Lot Details |  | Stage: | Package 1 - CONSTRUCTION
textbox |  | Lot No. |  | Our Reference: | 189
textbox |  | Lot ID. |  | Client: | Byron Shire Council (BSC)
textbox |  | Lot Description |  | Client Reference: | 2024-2089
Checkpoint | PASS / FAIL / N/A | Lot Checklist to be complete in conjunction with pre-approved ITP-01-Drainage Structures
section |  | Formation Survey
Checkpoint | PASS / FAIL / N/A | Approval of Formation Survey
textbox |  | (Upload Formation Survey here)
signoff |  | HOLD POINT - Formation Survey reviewed and accepted by BSC Representative
section |  | Erosion & Sediment Control
Checkpoint | PASS / FAIL / N/A | ERSED Installed
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - ERSED accepted by RCCE Supervisor (or other representative)
section |  | Construction & Installation | rows to be removed hidden VV
Checkpoint | PASS / FAIL / N/A | Approval of Seperation Geotextile Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Seperation Geotextile Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of GCCM Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - GCCM Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of HDPE Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - HDPE Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Culvert / Pit Installation | rowsto be removed hidden ^^
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Culvert / Pit Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Inspection
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Foundation inspected and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Testing
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - Foundation testing signed off by RCCE Supervisor
signoff |  | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
Checkpoint | PASS / FAIL / N/A | Concrete Pre-pour Inspection
textbox |  | (Upload photos of pre-pour & any commentary here)
signoff |  | HOLD POINT - Pre-pour accepted by BSC Representative | rows to be removed hidden VV
Checkpoint | PASS / FAIL / N/A | Geometry Measured
textbox |  | (Upload photos of geometry & any commentary here)
signoff |  | SIGNOFF - Geometry measured and signed off by RCCE Supervisor
signoff |  | SIGNOFF - Geometry measured and witnessed by BSC Representative (Optional)
section |  | Non-Conformance Reporting - IF APPLICABLE | rowsto be removed hidden ^^
Checkpoint | PASS / FAIL / N/A | Non-Conformance Reported
textbox |  | (Upload additional photos & any commentary here, including remedial measures)
signoff |  | SIGNOFF - RCCE Representative resolved NCR
signoff |  | HOLD POINT - NCR resolved and accepted by BSC Representative
section |  | Other
Checkpoint | PASS / FAIL / N/A | Other
textbox |  | (Upload additional photos & any commentary here)
signoff |  | SIGNOFF - Signoff by RCCE Supervisor relating to any additional commentary.
section |  | Lot Closure
Checkpoint |  | Were any Non-Conformances reported
textbox |  | details of NCR and remediation measures required
Checkpoint |  | NCR Closed?
signoff |  | RCCE - Supervisor or PM remediated and closed NCR
Checkpoint |  | Acceptance of Works within Lot
textbox |  | (Upload completion photos here)
signoff |  | HOLD POINT - Lot accepted by BSC Representative
signoff |  | RCCE - PM to sign and close out Lot

## 189 - ITP-02-Checlist
type |  | name |  | Note for CONQA | This is checklist that includes all items, I have then removed what is not required for the releveant ITP checklist is relating to
checklist |  | RCCE - SMP Implementation Project - ITP-02-Open Drains-CHECKLIST |  | Project Name: | STORMWATER MANAGEMENT PLAN IMPLEMENTATION PROJECT
section |  | Lot Details |  | Stage: | Package 1 - CONSTRUCTION
textbox |  | Lot No. |  | Our Reference: | 189
textbox |  | Lot ID. |  | Client: | Byron Shire Council (BSC)
textbox |  | Lot Description |  | Client Reference: | 2024-2089
Checkpoint | PASS / FAIL / N/A | Lot Checklist to be complete in conjunction with pre-approved ITP-02-Open Drains
section |  | Formation Survey
Checkpoint | PASS / FAIL / N/A | Approval of Formation Survey
textbox |  | (Upload Formation Survey here)
signoff |  | HOLD POINT - Formation Survey reviewed and accepted by BSC Representative
section |  | Erosion & Sediment Control
Checkpoint | PASS / FAIL / N/A | ERSED Installed
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - ERSED accepted by RCCE Supervisor (or other representative)
section |  | Construction & Installation
Checkpoint | PASS / FAIL / N/A | Approval of Seperation Geotextile Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Seperation Geotextile Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of GCCM Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - GCCM Installation accepted by BSC Representative | rows to be removed hidden VV
Checkpoint | PASS / FAIL / N/A | Approval of HDPE Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - HDPE Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Culvert / Pit Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Culvert / Pit Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Inspection | rowsto be removed hidden ^^
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Foundation inspected and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Testing
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - Foundation testing signed off by RCCE Supervisor
signoff |  | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
Checkpoint | PASS / FAIL / N/A | Concrete Pre-pour Inspection
textbox |  | (Upload photos of pre-pour & any commentary here)
signoff |  | HOLD POINT - Pre-pour accepted by BSC Representative |  | rows to be removed hidden VV
Checkpoint | PASS / FAIL / N/A | Geometry Measured
textbox |  | (Upload photos of geometry & any commentary here)
signoff |  | SIGNOFF - Geometry measured and signed off by RCCE Supervisor
signoff |  | SIGNOFF - Geometry measured and witnessed by BSC Representative (Optional)
section |  | Non-Conformance Reporting - IF APPLICABLE |  | rowsto be removed hidden ^^
Checkpoint | PASS / FAIL / N/A | Non-Conformance Reported
textbox |  | (Upload additional photos & any commentary here, including remedial measures)
signoff |  | SIGNOFF - RCCE Representative resolved NCR
signoff |  | HOLD POINT - NCR resolved and accepted by BSC Representative
section |  | Other
Checkpoint | PASS / FAIL / N/A | Other
textbox |  | (Upload additional photos & any commentary here)
signoff |  | SIGNOFF - Signoff by RCCE Supervisor relating to any additional commentary.
section |  | Lot Closure
Checkpoint |  | Were any Non-Conformances reported
textbox |  | details of NCR and remediation measures required
Checkpoint |  | NCR Closed?
signoff |  | RCCE - Supervisor or PM remediated and closed NCR
Checkpoint |  | Acceptance of Works within Lot
textbox |  | (Upload completion photos here)
signoff |  | HOLD POINT - Lot accepted by BSC Representative
signoff |  | RCCE - PM to sign and close out Lot

## 189 - ITP-03-Checklist
type |  | name |  | Note for CONQA | This is checklist that includes all items, I have then removed what is not required for the releveant ITP checklist is relating to
checklist |  | RCCE - SMP Implementation Project - ITP-03-Pipe Drainage-CHECKLIST |  | Project Name: | STORMWATER MANAGEMENT PLAN IMPLEMENTATION PROJECT
section |  | Lot Details |  | Stage: | Package 1 - CONSTRUCTION
textbox |  | Lot No. |  | Our Reference: | 189
textbox |  | Lot ID. |  | Client: | Byron Shire Council (BSC)
textbox |  | Lot Description |  | Client Reference: | 2024-2089
Checkpoint | PASS / FAIL / N/A | Lot Checklist to be complete in conjunction with pre-approved ITP-03-Pipe Drainage
section |  | Formation Survey
Checkpoint | PASS / FAIL / N/A | Approval of Formation Survey
textbox |  | (Upload Formation Survey here)
signoff |  | HOLD POINT - Formation Survey reviewed and accepted by BSC Representative
section |  | Erosion & Sediment Control
Checkpoint | PASS / FAIL / N/A | ERSED Installed
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - ERSED accepted by RCCE Supervisor (or other representative)
section |  | Construction & Installation
Checkpoint | PASS / FAIL / N/A | Approval of Seperation Geotextile Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Seperation Geotextile Installation accepted by BSC Representative | rows to be removed hidden VV
Checkpoint | PASS / FAIL / N/A | Approval of GCCM Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - GCCM Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of HDPE Installation | rowsto be removed hidden ^^
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - HDPE Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Approval of Culvert / Pit Installation
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Culvert / Pit Installation accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Inspection
textbox |  | (Upload photos & any commentary here)
signoff |  | HOLD POINT - Foundation inspected and accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Foundation Testing
textbox |  | (Upload photos & any commentary here)
signoff |  | SIGNOFF - Foundation testing signed off by RCCE Supervisor
signoff |  | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional) | rows to be removed hidden VV
Checkpoint | PASS / FAIL / N/A | Concrete Pre-pour Inspection
textbox |  | (Upload photos of pre-pour & any commentary here)
signoff |  | HOLD POINT - Pre-pour accepted by BSC Representative
Checkpoint | PASS / FAIL / N/A | Geometry Measured | rowsto be removed hidden ^^
textbox |  | (Upload photos of geometry & any commentary here)
signoff |  | SIGNOFF - Geometry measured and signed off by RCCE Supervisor
signoff |  | SIGNOFF - Geometry measured and witnessed by BSC Representative (Optional)
section |  | Non-Conformance Reporting - IF APPLICABLE
Checkpoint | PASS / FAIL / N/A | Non-Conformance Reported
textbox |  | (Upload additional photos & any commentary here, including remedial measures)
signoff |  | SIGNOFF - RCCE Representative resolved NCR
signoff |  | HOLD POINT - NCR resolved and accepted by BSC Representative
section |  | Other
Checkpoint | PASS / FAIL / N/A | Other
textbox |  | (Upload additional photos & any commentary here)
signoff |  | SIGNOFF - Signoff by RCCE Supervisor relating to any additional commentary.
section |  | Lot Closure
Checkpoint |  | Were any Non-Conformances reported
textbox |  | details of NCR and remediation measures required
Checkpoint |  | NCR Closed?
signoff |  | RCCE - Supervisor or PM remediated and closed NCR
Checkpoint |  | Acceptance of Works within Lot
textbox |  | (Upload completion photos here)
signoff |  | HOLD POINT - Lot accepted by BSC Representative
signoff |  | RCCE - PM to sign and close out Lot