## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Overarching Checklist | [5 empty] | RCCE - SMP Implementation Project - Overarching Checklist
section | Preliminary Sign-offs
checkpoint | Approval of Quality Management Plan (QMP)
label | (Upload QMP here)
signoff | HOLD POINT - QMP reviewed and accepted by BSC Representative
checkpoint | Approval of Traffic Management Plan (TMP)
label | (Upload TMP here)
signoff | HOLD POINT - TMP reviewed and accepted by BSC Representative
checkpoint | Approval of Safety Management Plan (SMP)
label | (Upload SMP here)
signoff | HOLD POINT - SMP reviewed and accepted by BSC Representative
checkpoint | Approval of Inspection Test Plans (ITPs)
label | (Upload ITPs here)
signoff | HOLD POINT - ITPs reviewed and accepted by BSC Representative
checkpoint | Approval of Decommissioning Plan (DP)
label | (Upload DP here)
signoff | HOLD POINT - DP reviewed and accepted by BSC Representative
checkpoint | Approval of Precommencement Survey
label | (Upload Precommencement Survey here)
signoff | HOLD POINT - Precommencement Survey reviewed and accepted by BSC Representative
checkpoint | Approval of Services Survey
label | (Upload Services Survey here)
signoff | HOLD POINT - Services Survey reviewed and accepted by BSC Representative
section | Material Sign-offs
checkpoint | Approval of Seperation Geotextile material
label | (Upload Evidence / Certification of Seperation Geotextile material used here)
signoff | HOLD POINT - Seperation Geotextile material accepted by BSC Representative
checkpoint | Approval of Rip-rap material
label | (Upload Evidence / Certification of Rip-rap material used here)
signoff | HOLD POINT - Rip Rap material accepted by BSC Representative
checkpoint | Approval of GCCM material
label | (Upload Evidence / Certification of GCCM material used here)
signoff | HOLD POINT - GCCM material accepted by BSC Representative
checkpoint | Approval of Trench Drainage material
label | (Upload Evidence / Certification of Trench Drainage material used here)
signoff | HOLD POINT - Trench Drainage material accepted by BSC Representative
checkpoint | Certification of Pre-cast Units
label | (Upload Certification of Compliance for pre-cast units here)
signoff | HOLD POINT - Pre-cast Units accepted by RCCE PM or Engineer & BSC Representative
section | Completion of Works Sign-offs
checkpoint | Acceptance of Works As-Excecuted (WAE)
label | (Upload WAE here)
signoff | HOLD POINT - WAE accepted by BSC Representative
checkpoint | Acceptance of CCTV
label | (Upload CCTV files here)
signoff | HOLD POINT - CCTV accepted by BSC Representative
checkpoint | All NCRs closed
label | (Upload NCR Register here)
signoff | HOLD POINT - All NCRs closed and accepted by BSC Representative
checkpoint | RCCE - PM to sign and close out Lot
signoff | RCCE - PM to sign and close out Lot
checklist | ITP-01-Drainage Structures-Checklist-(Lot ID##) | [5 empty] | RCCE - SMP Implementation Project - ITP-01-Drainage Structures-CHECKLIST
section | Lot Details
checkpoint-no-status | Lot Details
textbox | Lot No.
textbox | Lot ID.
textbox | Lot Description
checkpoint | Lot Checklist to be complete in conjunction with pre-approved ITP-01-Drainage Structures
section | Formation Survey
checkpoint | Approval of Formation Survey
label | (Upload Formation Survey here)
signoff | HOLD POINT - Formation Survey reviewed and accepted by BSC Representative
section | Erosion & Sediment Control
checkpoint | ERSED Installed
textbox | (Upload photos & any commentary here)
signoff | SIGNOFF - ERSED accepted by RCCE Supervisor (or other representative)
section | Construction & Installation
checkpoint | Approval of Culvert / Pit Installation
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - Culvert / Pit Installation accepted by BSC Representative
checkpoint | Foundation Inspection
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - Foundation inspected and accepted by BSC Representative
checkpoint | Foundation Testing
textbox | (Upload photos & any commentary here)
signoff | SIGNOFF - Foundation testing signed off by RCCE Supervisor
checkpoint | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
signoff | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
checkpoint | Concrete Pre-pour Inspection
textbox | (Upload photos of pre-pour & any commentary here)
signoff | HOLD POINT - Pre-pour accepted by BSC Representative
section | Non-Conformance Reporting - IF APPLICABLE
checkpoint | Non-Conformance Reported
textbox | (Upload additional photos & any commentary here, including remedial measures)
signoff | SIGNOFF - RCCE Representative resolved NCR
checkpoint | HOLD POINT - NCR resolved and accepted by BSC Representative
signoff | HOLD POINT - NCR resolved and accepted by BSC Representative
section | Other
checkpoint | Other
textbox | (Upload additional photos & any commentary here)
signoff | SIGNOFF - Signoff by RCCE Supervisor relating to any additional commentary.
section | Lot Closure
checkpoint | Were any Non-Conformances reported
textbox | details of NCR and remediation measures required
checkpoint | NCR Closed?
signoff | RCCE - Supervisor or PM remediated and closed NCR
checkpoint | Acceptance of Works within Lot
label | (Upload completion photos here)
signoff | HOLD POINT - Lot accepted by BSC Representative
checkpoint | RCCE - PM to sign and close out Lot
signoff | RCCE - PM to sign and close out Lot
checklist | ITP-02-Open Drains-Checklist-(Lot ID##) | [5 empty] | RCCE - SMP Implementation Project - ITP-02-Open Drains-CHECKLIST
section | Lot Details
checkpoint-no-status | Lot Details
textbox | Lot No.
textbox | Lot ID.
textbox | Lot Description
checkpoint | Lot Checklist to be complete in conjunction with pre-approved ITP-02-Open Drains
section | Formation Survey
checkpoint | Approval of Formation Survey
label | (Upload Formation Survey here)
signoff | HOLD POINT - Formation Survey reviewed and accepted by BSC Representative
section | Erosion & Sediment Control
checkpoint | ERSED Installed
textbox | (Upload photos & any commentary here)
signoff | SIGNOFF - ERSED accepted by RCCE Supervisor (or other representative)
section | Construction & Installation
checkpoint | Approval of Seperation Geotextile Installation
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - Seperation Geotextile Installation accepted by BSC Representative
checkpoint | Approval of GCCM Installation
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - GCCM Installation accepted by BSC Representative
checkpoint | Foundation Inspection
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - Foundation inspected and accepted by BSC Representative
checkpoint | Foundation Testing
textbox | (Upload photos & any commentary here)
signoff | SIGNOFF - Foundation testing signed off by RCCE Supervisor
checkpoint | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
signoff | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
checkpoint | Concrete Pre-pour Inspection
textbox | (Upload photos of pre-pour & any commentary here)
signoff | HOLD POINT - Pre-pour accepted by BSC Representative
section | Non-Conformance Reporting - IF APPLICABLE
checkpoint | Non-Conformance Reported
textbox | (Upload additional photos & any commentary here, including remedial measures)
signoff | SIGNOFF - RCCE Representative resolved NCR
checkpoint | HOLD POINT - NCR resolved and accepted by BSC Representative
signoff | HOLD POINT - NCR resolved and accepted by BSC Representative
section | Other
checkpoint | Other
textbox | (Upload additional photos & any commentary here)
signoff | SIGNOFF - Signoff by RCCE Supervisor relating to any additional commentary.
section | Lot Closure
checkpoint | Were any Non-Conformances reported
textbox | details of NCR and remediation measures required
checkpoint | NCR Closed?
signoff | RCCE - Supervisor or PM remediated and closed NCR
checkpoint | Acceptance of Works within Lot
label | (Upload completion photos here)
signoff | HOLD POINT - Lot accepted by BSC Representative
checkpoint | RCCE - PM to sign and close out Lot
signoff | RCCE - PM to sign and close out Lot
checklist | ITP-03-Pipe Drainage-Checklist-(Lot ID##) | [5 empty] | RCCE - SMP Implementation Project - ITP-03-Pipe Drainage-CHECKLIST
section | Lot Details
checkpoint-no-status | Lot Details
textbox | Lot No.
textbox | Lot ID.
textbox | Lot Description
checkpoint | Lot Checklist to be complete in conjunction with pre-approved ITP-03-Pipe Drainage
section | Formation Survey
checkpoint | Approval of Formation Survey
label | (Upload Formation Survey here)
signoff | HOLD POINT - Formation Survey reviewed and accepted by BSC Representative
section | Erosion & Sediment Control
checkpoint | ERSED Installed
textbox | (Upload photos & any commentary here)
signoff | SIGNOFF - ERSED accepted by RCCE Supervisor (or other representative)
section | Construction & Installation
checkpoint | Approval of Seperation Geotextile Installation
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - Seperation Geotextile Installation accepted by BSC Representative
checkpoint | Approval of HDPE Installation
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - HDPE Installation accepted by BSC Representative
checkpoint | Approval of Culvert / Pit Installation
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - Culvert / Pit Installation accepted by BSC Representative
checkpoint | Foundation Inspection
textbox | (Upload photos & any commentary here)
signoff | HOLD POINT - Foundation inspected and accepted by BSC Representative
checkpoint | Foundation Testing
textbox | (Upload photos & any commentary here)
signoff | SIGNOFF - Foundation testing signed off by RCCE Supervisor
checkpoint | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
signoff | SIGNOFF - Foundation testing witnessed by BSC Representative (Optional)
checkpoint | Geometry Measured
textbox | (Upload photos of geometry & any commentary here)
signoff | SIGNOFF - Geometry measured and signed off by RCCE Supervisor
checkpoint | SIGNOFF - Geometry measured and witnessed by BSC Representative (Optional)
signoff | SIGNOFF - Geometry measured and witnessed by BSC Representative (Optional)
section | Non-Conformance Reporting - IF APPLICABLE
checkpoint | Non-Conformance Reported
textbox | (Upload additional photos & any commentary here, including remedial measures)
signoff | SIGNOFF - RCCE Representative resolved NCR
checkpoint | HOLD POINT - NCR resolved and accepted by BSC Representative
signoff | HOLD POINT - NCR resolved and accepted by BSC Representative
section | Other
checkpoint | Other
textbox | (Upload additional photos & any commentary here)
signoff | SIGNOFF - Signoff by RCCE Supervisor relating to any additional commentary.
section | Lot Closure
checkpoint | Were any Non-Conformances reported
textbox | details of NCR and remediation measures required
checkpoint | NCR Closed?
signoff | RCCE - Supervisor or PM remediated and closed NCR
checkpoint | Acceptance of Works within Lot
label | (Upload completion photos here)
signoff | HOLD POINT - Lot accepted by BSC Representative
checkpoint | RCCE - PM to sign and close out Lot
signoff | RCCE - PM to sign and close out Lot