## QA Folder Structure
QA Folder Structure |  |  | Checklists | Checklists
Manufacturing / Off-site QA
Site QA
Area 03A (Porte Cochere)
| Shop Drawing - SKP-QIMR-201 | 3AW 20 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3AW 41 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3AW 70 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3AW 88 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3AW 95 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3AW 102 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
Area 03B (Level 6 Balcony)
| Shop Drawing - SKP-QIMR-202 | 3BW 09 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3BW 20 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3BW 35 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3BW 53 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3BW 72 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3BW 92 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 3BC 06 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
Area 04A (Level 6 External Deck Soffit)
| Shop Drawing - SKP-QIMR-203 | 4AC 11 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 4AC 28 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 4AC 50 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 4AC 65 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 4AC 77 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 4AC 90 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
Area 04B (Level6 External Deck Wall)
| Shop Drawing - SKP-QIMR-204 | 4BC 10 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
Area 06A (Link to Bancroft Ceilings)
| Shop Drawing - SKP-QIMR-205 | 6AC TA | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6AC TB | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6AC 34 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6AC 45 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
Area 07 (Link to Bancroft Wall)
| Shop Drawing - SKP-QIMR-206 | 7C 05 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 7C 35 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 7C 51 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 7C 55 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 7C 86 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 7C 134 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 7C 146 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 7C 151 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
Area 06B (Link to CBCRC Celilings)
| Shop Drawing - SKP-QIMR-207 | 6BC 02 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6BC 14 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6BC 32 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6BC 54 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6BC TA | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
|  | 6BC TB | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
Area 06C (Link to CBCRC Walls)
|  | 6CC 05 | ONSITE - Installation of Facade System | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist

## ITPs Checklists
type | name | values
checklist | OFFSITE - Fabrication of 3mm Solid Mondoclad Checklist
section | Pre-fabrication
checkpoint | Ensure CNC machine operator daily checklist has been undertaken
checkpoint | Nest summary and site drawings provided by programmer, file number printed on paperwork corresponds with file programmed in CNC
checkpoint | Check currency of Drawings and Approved
checkpoint | Check Mondoclad 3mm pre-finished sheet is selected.
label | Insert photo of inkjet writing on back of sheet showing product, colour and batch number
checkpoint | Colour and sheet size corresponds with fabrication drawings and nesting.
checkpoint | Sheets are not bent, scratched or damaged before placing on CNC table
checkpoint | No metal filings located on CNC table or sheets prior to placing sheet on bed. Compressed air used to remove any debris
section | Machining
checkpoint | Fluid levels, suction pressures and functions are optimum. Correct tooling is selected and utilized
checkpoint | Ensure Minimum route depth thickness is maintained at Mondoclad recommendations
checkpoint | Panel numbers engraved into back of panel correspond with file numbers and fabrication drawings
checkpoint | Panels are checked off as machined once machining has terminated
checkpoint | Panels stacked neatly on edge on A frame back to back - face to face.
section | Fabrication
checkpoint | Correct tooling used to fold edges of panels. Panel returns folded neatly and square
checkpoint | Panel cleaned of any excess cutting lubricant or foreign debris. Back of panel is cleaned at panel stiffener and perimeter angle extrusion locations, as are perimeter angle extrusions and stiffener contact surfaces as per DOW recommendations and ITP completed.
checkpoint | Correct sized mill finished aluminum 20x20x3 EA 6351 -T6 run full length of perimeter folds and finish no more than 30mm from edge of panel.
checkpoint | 20x3EA cleaned with clean cloth and isopropanol prior to structural silicone and structural spacer tape application. Continuous 7mm wide x 6mm high structural glazing spacer tape applied down the length of the 20x3EA flush with the backside of the uptuned edge of angle. Dowsil 795 Structural Silicon used to adhere perimeter angle to back of panel. Dowsil 795 to be applied continuously maintaining 6mm thick x 13mm wide bead adjacent to structural glazing spacer tape. 20x3EA applied firmly to back of cladding panel and snug against folded claddding panel return.
checkpoint | Continuous mill finished 20x3 EA perimenter angle connected to folded cladding return fold via Hobson 4.8mm dia stainless steel rivets at max 300mm centers
checkpoint | Correct sizes angle cleated selected and installed to match engraving on back of panel (32mmx20mmx3mm mill finished 6351-T6 alumnium angle cleats @ 150mm long or 25mmx20mmx3 mill finished 6351-T6 alumnium @ 75mm long) located around perimeter of panel. Cleats fixed through cladding panel perimeter fold and 20x3EA via 4.8mm dia stainless steel rivets. Rivets at 100mm spacing to 150mm long cleats and 50mm spacing for 75mm cleats. Rivet spacings generally not greater than 300mm. Cleats to have 9mm dia oversized expansion holes drilled at required centers and edge distances.
checkpoint | Correct RHS stiffener selected - 76.2mm x 25.4mm x 2.4mm RHS 6351-T6 Mill Finish. Stifffner is cleaned with clean cloth and isopropanol prior to structural silicone and structural spacer tape application. Continuous 6mm wide x 6mm high structural glazing spacer tape applied continuously down the length of each side of contact face of the RHS stiffener min 10mm from edge. Dowsil 795 Structural Silicon used to adhere perimeter angle to back of panel. Dowsil 795 to be applied continuously maintaining min 6mm thick x 13mm wide bead adjacent to strucutral glazing spacer tape. RHS stiffener applied firmly to back of cladding panel fitting neatly between perimeter 20x3EA.
checkpoint | 75x25x3 UA Mill finished cleats are located either side of stiffener (x1 per side) Angle cleats are attached to RHS stiffeners via x2 4.8mm dia stainless steel rivets (x2 each side) Angle cleats are fixed to 32x20x3 UA and perimeter 20x3 EA via x2 4.8mm stainless steel rivets (x1 per angle cleat leg).
label | Insert images of DOWSIL 795 been applied as per above detail. ALSO INSERT IMAGE SHOWING BATCH NUMBER OF PRODUCT.
label | Insert photo of completed panel showing stiffener spacings (use tape measure) and general arrangement.
section | Packing
checkpoint | Panels stacked neatly back to back - face to face with protective foam placed between panel faces for transport
checkpoint | Ensure panel numbers are marked off as complete
checkpoint | Panels are secured and wrapped ready for transport
checkpoint | Remove rubbish from work area. Clean workshop for next shift
checklist | ONSITE - Installation of Facade System
section | Pre-constructions and Removal of existing ACP and top hat framing.
checkpoint | Existing condition of surrounding surfaces and finished is documented and photo evidence is obtained and emailed through to Skypanel Management
checkpoint | Removal of sealant in a safe manner, place into bin/bags for disposal and tidy work area.
checkpoint | Removal of composite panels in a safe manner from facade, move to lay down area and secured ensuring work area kept tidy.
label | Take photo where the panel was removed from (from a distance) as to be able to be able to be clearly identifiable.
checkpoint | Removed composite panels stacked neatly in recycling bin for recycling.
section | Assessment of Structure and Aluminium Framing Installation
checkpoint | Visually check existing structure for condition. Identify any visible cracked welds, missing fixtures and connections and take photo graphic evidence
checkpoint | Identify existing structure. Capture images with tape measure showing type, size, spans, centers and connections at selected locations
label | Insert Photos showing exisitng structure showing member sizing, spans, centers & connections at selected locations and general structure at location.
checkpoint | Install Air Barrier ensuring material is lapped and sealed to all adjacent strcutures
label | Insert photos of air seal installed correctly.
checkpoint | Refer to design documents to ensure tophat span design sizes are not going to be exceeded for the project. 40mm Tophat max span 1200mm at 1100mm, 37mm Tophat max span 1100mm at 600mm spacing on Bancroft Wall. 22.5mm tophat span max 1000mm on Porte Cochere
checkpoint | Ensure Structural Improvements are impelmented as per Blight Tanner documentation
checkpoint | Check fixings types of aluminium subframe into structure: Fixings to be stainless steel 12ga Tek screws min (No 10ga screws to be used or retained). Fixings into concrete to be Seismic rated Stainless Steel Wedge Anchors with min 55mm embedment
checkpoint | Ensure aluminium frames setout reflects shop drawing setout are installed plumb, level and are packed to suit existing build out as required with aluminium packers
checkpoint | Prior to commencement of cladding installation: Ensure other services are complete: Ensure all framing requirements are met and Enngineers have signed off as complete prior to installing cladding panels or air barrier.
label | Insert Photos showing completed aluminum framing with components identified showing spans, tophat sizes, fixings at selected locations
section | Installation of 3mm Mondoclad Cladding
checkpoint | Ensure cladding material and colour is correct by referencing shop drawings - Mondoclad 3mm solid aluminum
checkpoint | Ensure appropriate stiffeners are located in back of panel as per BT Design documents & Skypanel Shop drawings
checkpoint | Ensure specific stiffener details are achieved as noted in corner situations i.e. High wind corner stiffener support connection
checkpoint | Ensure 3mm aluminum mill finished angles are installed with strucutural silicone to the back of panels to support all corner folds as per BT documents
checkpoint | Ensure rivet fixing of Z bracket to panel return edges spaced no more than 300mm apart
checkpoint | Ensure panels are defect free with no scratches and dents
checkpoint | Install cladding panels by mechanically fixing through angle cleat brackets to tophat support framing with 12ga stainless steel SDS screws at nominated fixing centers.
checkpoint | Ensure all panels are installed in the same direction as indicated on the protective film
checkpoint | Ensure panel joint consistancy is maintianed
checkpoint | Ensure panels are installed plumb, square and true, and within Skypanel tolerances
checkpoint | Ensure panels are installed in correct positions by checking engraving on back of sheet corresponds with position on shop drawings
label | Insert Photos of installed panel, panel widths, junctions, 12ga bi metal screws and fixing centers at selected locations
section | Caulking of panels
checkpoint | Ensure closed cell backing rod is applied correctly
checkpoint | Ensure Black Dowsil 791 sealant is installed correctly and consistently. Min depth of sealant to be 8mm
checkpoint | Ensure all penetrations are caulked
checkpoint | Ensure plastic film is removed and caulking and glue residues are properly cleaned from cladding surface
label | Insert photos of sealed panels at selected locations
holdpoint | Hold Point - Approval of caulking required by Buildcorp before demobilising from area