## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Under Floor Heating & Tiling – Internal Areas |  |  |  |  | Yes | ITP-022A Under Floor Heating & Tiling – Internal Areas | 008d3867-23de-4cd6-9731-e2cf0522b7da
checkpoint-group |  |  | section | Underfloor Heating (do not start until Waterproofing ITP completed). Prior to Tiling Install
checkpoint-status |  |  | checkpoint | Waterproofing ITP has been completed
checkpoint-status |  |  | checkpoint | Confirm bathroom receives heating upgrade
checkpoint-status |  |  | checkpoint | Confirm power supply
checkpoint-status |  |  | checkpoint | UFH to use Devi brand – lay heat matts
checkpoint-status |  |  | checkpoint | Controller/thermostat mounted adjacent to light switch (Devi touch controller)
checkpoint-status |  |  | checkpoint | Devi guard alarm installed – ITP received by subcontractor
checkpoint-status |  |  | checkpoint | Testing completed:
boolean | 86a922a0-3d21-4d3e-93c4-5acab87458ad |  | tickbox | Prior to tiling
boolean | bef300e9-6d92-466c-91c2-9da504128548 |  | tickbox | After tiling
boolean | aabe08f9-a6f6-4703-b207-d27cf3b8b2bd |  | tickbox | After livening / apartment handover
checkpoint-group |  |  | section | Tiling - Prior to Works
checkpoint-status |  |  | checkpoint | Confirm scheme for unit from Apartments Finishes Schedule & upload architectural drawing.
checkpoint-status |  |  | checkpoint | Confirm tile set out prior to tiling, number and location of cut tiles with architect. Number of cut tiles to be minimised & to be no less than half size of tile.
checkpoint-status |  |  | checkpoint | Confirm tiles are from the same batch.
checkpoint-status |  |  | checkpoint | Confirm all services and accessories are in place
checkpoint-status |  |  | checkpoint | Confirm Tile Floor Finish level.
checkpoint-status |  |  | checkpoint | Confirm all floor wastes are plugged during tiling works.
checkpoint-status |  |  | checkpoint | Confirm aluminium angle is not damaged or misaligned & installed at door threshold.
holdpoint |  |  | signoff | HOLD POINT – Ensure waterproofing is not damaged. OK to proceed with Tiling works.
checkpoint-group |  |  | section | Tiling - During Works
checkpoint-status |  |  | checkpoint | Confirm sand/cement using Ardex x56 adhesive
checkpoint-status |  |  | checkpoint | Confirm maximum tile and tile bed thickness at door threshold works with other floor finishes.
checkpoint-status |  |  | checkpoint | Confirm installation of floor wastes is flush with or 1mm below floor tile level.
checkpoint-status |  |  | checkpoint | Stop wall and floor tiles 2-3mm short of edges and fill with resilient caulking compound.
checkpoint-status |  |  | checkpoint | Floor tiles laid to falls – min 1:100.
checkpoint-status |  |  | checkpoint | Confirm all joints are aligned.
checkpoint-status |  |  | checkpoint | Confirm colour of grout is consistent and uniform – Ardex FSDD 1-4mm with Ardex grout booster.
checkpoint-status |  |  | checkpoint | Confirm all tile edges line up and are plumb.
checkpoint-status |  |  | checkpoint | Confirm all silicon jointing provided to all floor/wall tile junctions.
checkpoint-status |  |  | checkpoint | Confirm all excess silicon is removed from tiles and adjoining surfaces.
checkpoint-status |  |  | checkpoint | Subcontractor ITP received.
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Waterproofing Concrete Checklist | itp |  |  |  | Yes | Add Waterproofing - Concrete ITP | 05d4778b-26dc-4186-b476-9587587c1f4e
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Confirm all previous trades have completed works:
boolean | 5f764610-3306-4624-be15-3dcf6d9fb20f |  | tickbox | Formwork stripped
boolean | 31455bc1-d9b2-4f21-aef4-6964df079287 |  | tickbox | Panels installed and grouted
boolean | 1fa42d10-c4df-4ba8-b33b-9d276e770ce1 |  | tickbox | Service penetrations installed
checkpoint-status |  |  | checkpoint | Confirm RL of substrate Check rebate heights and length
boolean | 10bbc949-72b4-4aca-9252-a3e9e16a11e3 |  | tickbox | Check rebate heights and length
boolean | 18cfce36-03cb-433f-a43a-c4d06bf56058 |  | tickbox | Check high and low points on canopy/gutter
checkpoint-status |  |  | checkpoint | Confirm subgrade/substrate is flat, level and free of any sharp protrusions, signed off by water proofing contractor.
checkpoint-status |  |  | checkpoint | Confirm substrate material complies to specification EG. fixings as per Deboer data sheet
checkpoint-status |  |  | checkpoint | Drawing attached of area where works are to be completed including grid lines for reference.
checkpoint-status |  |  | checkpoint | Confirm all penetrations are present and in the correct location, Drawing attached.
checkpoint-status |  |  | checkpoint | Confirm all installer’s tickets are on record.
checkpoint-status |  |  | checkpoint | Confirm falls to waste/outlets have been formed.
checkpoint-status |  |  | checkpoint | Have ILD been notified to install conductive mesh
checkpoint-status |  |  | checkpoint | Confirm weather is appropriate for installation.
checkpoint-status |  |  | checkpoint | Handover to Subcontractor Received
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Have correct minimum lap been completed consistently and heavy rolled/welded?
checkpoint-status |  |  | checkpoint | Have sealant to joints in substrate been applied to specification
checkpoint-status |  |  | checkpoint | Have Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
checkpoint-status |  |  | checkpoint | Have penetration (pipe, soak pit, overflow) detail been followed, fillet installed and liquid membrane/sealants in place as per drawing and specification.
checkpoint-status |  |  | checkpoint | Has protection sheet been installed where needed
checkpoint-status |  |  | checkpoint | Have membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct primer or adhesives used as per specification.
checkpoint-status |  |  | checkpoint | Cap sheet and base sheets fully boned together, no areas of delamination.
checkpoint-status |  |  | checkpoint | No sign of overheating/excessive bitumen bleed
checkpoint-status |  |  | checkpoint | Cap sheet and base sheets laps offset satisfactorily, lay build up to specification
checkpoint-status |  |  | checkpoint | Has membrane been extended for lapping details
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Has membrane been inspected for imperfections and signed off by subcontractor.
checkpoint-status |  |  | checkpoint | Is all installation as per manufacturer’s specifications and NZ standards?
checkpoint-status |  |  | checkpoint | Has Membrane been cleaned and all patches completed?
checkpoint-status |  |  | checkpoint | Check opening dimensions to be compliant with shop drawings E.g KFI suite
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off/Subcontractor ITP Sign-off
label | 5bc5b1ca-f4b3-45cd-8c90-2d6bb59e9482 |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Waterproofing Checklist | itp |  |  |  | Yes | Add Waterproofing ITP | 12d35ae5-bed5-4f2b-9521-4da49a615fb3
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Confirm RL of subgrade and all compaction tests completed.
checkpoint-status |  |  | checkpoint | Confirm subgrade/substrate is flat, level and free of any sharp protrusions, signed off by water proofing contractor.
checkpoint-status |  |  | checkpoint | Confirm substrate material complies to specification
checkpoint-status |  |  | checkpoint | Drawing attached of area where works are to be completed including grid lines for reference.
checkpoint-status |  |  | checkpoint | Confirm all penetrations are present and in the correct location, Drawing attached.
checkpoint-status |  |  | checkpoint | Confirm all installer’s tickets are on record.
checkpoint-status |  |  | checkpoint | Confirm drainage ITP is signed off and completed.
checkpoint-status |  |  | checkpoint | Confirm falls to waste/outlets have been formed.
checkpoint-status |  |  | checkpoint | Confirm weather is appropriate for installation.
checkpoint-group |  |  | section | HOLD POINT - In ground Drainage ITP signed off and completed
checkpoint-status |  |  | checkpoint | HOLD POINT - In ground Drainage ITP signed off and completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Have correct minimum lap been completed consistently and heavy rolled/welded?
checkpoint-status |  |  | checkpoint | Have sealant to joints in substrate been applied to specification
checkpoint-status |  |  | checkpoint | Have pile cap details been followed as per drawing and specification.
checkpoint-status |  |  | checkpoint | Have Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
checkpoint-status |  |  | checkpoint | Have penetration (pipe, soak pit, overflow) detail been followed, fillet installed and liquid membrane/sealants in place as per drawing and specification.
checkpoint-status |  |  | checkpoint | Has protection sheet been installed where needed
checkpoint-status |  |  | checkpoint | Have membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct primer or adhesives used as per specification.
checkpoint-status |  |  | checkpoint | Cap sheet and base sheets fully boned together, no areas of delamination.
checkpoint-status |  |  | checkpoint | No sign of overheating/excessive bitumen bleed
checkpoint-status |  |  | checkpoint | Cap sheet and base sheets laps offset satisfactorily, lay build up to specification
checkpoint-status |  |  | checkpoint | Has membrane been extended for lapping details
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Has membrane been inspected for imperfections and signed off by subcontractor.
checkpoint-status |  |  | checkpoint | Is all installation as per manufacturer’s specifications and NZ standards?
checkpoint-status |  |  | checkpoint | Has Membrane been cleaned and all patches completed?
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off/Subcontractor ITP Sign-off
label | 5bc5b1ca-f4b3-45cd-8c90-2d6bb59e9482 |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Electrical/Security/Data First Fix Checklist | itp |  |  |  | Yes | Electrical/Security/Data First Fix Checklist | 1394f85b-ef7c-460e-8918-9161c951a379
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any cable/conduit penetrating Fire rated walls are sealed both sides with Intumescent fire mastic to spec.
checkpoint-status |  |  | checkpoint | Confirm any cable/conduit penetrating Fire rated walls Sign off by Fire subcontractor
checkpoint-status |  |  | checkpoint | Confirm cabling not bunched excessively through penetration.
checkpoint-status |  |  | checkpoint | Confirm fire rated boxes installed and sealed to approve detail.
checkpoint-group |  |  | section | HOLD POINT - OK to proceed to electrical services
checkpoint-group |  |  | section | Electrical Services
checkpoint-status |  |  | checkpoint | Confirm Cable tray support
checkpoint-status |  |  | checkpoint | Confirm height and location of all outlet from architect’s drawings. TV/Data/Power/Light/security
checkpoint-status |  |  | checkpoint | Confirm wiring for switches are in place.
checkpoint-status |  |  | checkpoint | Confirm TV and GPO locations in place.
checkpoint-status |  |  | checkpoint | Confirm location of bathroom GPO has been coordinated with joinery shop drawings.
checkpoint-status |  |  | checkpoint | Confirm light allocations as per the drawings.
checkpoint-status |  |  | checkpoint | Confirm data cable is installed.
checkpoint-status |  |  | checkpoint | Confirm location of DB board has been coordinated with kitchen shop drawings.
checkpoint-status |  |  | checkpoint | Confirm intercom wiring in place.
checkpoint-status |  |  | checkpoint | Confirm wiring to kitchen appliances in place as per kitchen joinery shop drawing:
checkpoint-status |  |  | checkpoint | Confirm wiring to external lights confirmed.
checkpoint-status |  |  | checkpoint | Confirm wiring to FCU and exhaust motors in place.
checkpoint-status |  |  | checkpoint | Confirm fire speaker cabling is installed.
checkpoint-status |  |  | checkpoint | Confirm adaptable unit requirements if applicable.
checkpoint-status |  |  | checkpoint | Confirm security cabling is installed.
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
checklist-sectioned |  |  | checklist | Balustrades |  |  |  |  | Yes | ITP-034 Balustrades | 1476cfd3-cf45-4853-844a-c2d122757fe5
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Confirm correct balustrade type as per architectural drawings.
label | 9b5e3f1a-1603-466c-8eb2-d84f70ebbf6d |  | note | Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Confirm glass is correct thickness and type
checkpoint-status |  |  | checkpoint | Confirm posts are correct colour
checkpoint-status |  |  | checkpoint | Subcontractor has assessed and inspected work face
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm that adjoining balustrades have common level or line.
checkpoint-status |  |  | checkpoint | Confirm all posts or fixings are grouted with non-shrink epoxy grout (where applicable) as per specification
checkpoint-status |  |  | checkpoint | Confirm base plate installed to posts/fixings and any required sealing is complete.
checkpoint-status |  |  | checkpoint | Confirm all aluminum is powder coated as specified and approved fixings are being used suitable for the environment they are in
label | b1f4c940-30ba-402f-b74e-97c57b894c43 |  | note | Refer Architectural drawings & specification
checkpoint-status |  |  | checkpoint | Post centers as per shop drawings
checkpoint-status |  |  | checkpoint | Confirm top rail is installed as specified
label | d92487e6-1e21-487e-8697-4f51a1e5b609 |  | note | Refer Architectural drawings & specification
checkpoint-status |  |  | checkpoint | Confirm balustrades are installed as per approved shop drawings and complies with the building code
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Inspection - |  |  |  |  | Yes | Add Consultant Inspection Checklist | 1a9dd234-0f75-47f3-aadb-bad57e06e75c
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of Inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Type of Inspection:
text | 534f8c4f-3a28-4d0b-8e31-2e870fe2cb87 |  | textbox | Area inspection relates to
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | b4ff21c8-e458-474a-a19a-1cbce0361c6d |  | textbox | Corrective Actions Required
checklist-sectioned |  |  | checklist | BGT Site Report - |  |  |  |  | Yes | BGT Site Visit Report | 1c32aa80-bee4-4232-ad4f-506577919b18
checkpoint-group |  |  | section | Site Details
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
label | 1b5aefea-2449-4634-bb3c-c4646ef9014c |  | note | Company - Ganellen
label | c03ca78a-0e0a-4139-8f3b-2dfc715133ae |  | note | Project: Horizon Apartments
label | 47f3df78-060c-48c8-8e49-0fc2e59122de |  | note | Attention - Timothy Barrow
label | 4a724786-de18-4d53-86a0-58d0ec7a7f0e |  | note | Email - t.barrow@ganellen.com
label | 51033c9c-9108-4153-b953-710100e16340 |  | note | Author - Max Su
label | bae63165-d3d4-459a-a5b6-6f1a5fa36c96 |  | note | Job No - 12303
text | aefec857-00a3-453e-8c0b-490768fd627a |  | textbox | SVR #
label | 3fe56a5b-2d19-40db-9a7b-6f784ad90473 |  | note | Site Address - 250 Kepa Road, Mission Bay, Auckland
checkpoint-group |  |  | section | Inspection Details
checkpoint-status |  |  | checkpoint | All Inspection Details Inputted Below
text | c19e23b7-94bd-45fa-9afa-eb4323ed82aa |  | textbox | DATE & TIME OF INSPECTION:
label | 2823d2f7-01db-4ed4-beae-3d4930c8c4f8 |  | note | CONSTRUCTION SUPERVISOR PRESENT:
boolean | a2c08b6e-8064-47e7-bdd9-c16eb07dd9e4 |  | tickbox | Timothy Barrow
text | bac49365-a24f-48b7-b2eb-4f51ec298fc7 |  | textbox | Other - Specify below
text | 06cc81b8-39b6-415a-a2bd-5c109d10f531 |  | textbox | WORK ELEMENT BEING MONITORED:
button | fa542d24-375c-4575-ae78-984b4475f214 |  | button | HAS CONTRACTOR PRE-INSPECTION QA CHECK BEEN VIEWED: | No,Yes
label | 01d5b97c-8ae9-4408-8115-7e9bc210a549 |  | note | LEVEL OF MONITORING - CM3
text | 9ffb8fdc-d54c-4e0a-be75-305ea16c9d0a |  | textbox | REMEDIAL ITEMS THAT REQUIRE DESIGN REVIEW (Reference Remedial Items below)
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | HEALTH AND SAFETY: (Any observed H&S Issues that require action by the Contractor)
checkpoint-status |  |  | checkpoint | DRAWING OR BGT CAN REFERENCE:
checkpoint-status |  |  | checkpoint | Works accepted may proceed, reinspection required to defective elements (If Failed - Works Cannot Proceed)
label | 57facece-71a4-432a-b4e5-81d18ae7645d |  | note | Photographic evidence to close out remedial items is required prior to pouring concrete or completing works. Proceeding without the engineer’s approval is at the Contractor’s risk
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Observations - Any relevant observations recorded and closed out appropriately
checklist-flat |  |  | checklist | Observation: |  |  |  |  | Yes | BGT - Add Observation / Remedial Item | 2453a912-183c-4ad1-b06d-5c264e2ab42b
checkpoint-status |  |  | checkpoint | Observation/Remedial Status - To be passed by BGT engineer once satisfied
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Observation Description
holdpoint |  |  | signoff | Request BGT Signoff
checklist-sectioned |  |  | checklist | Structural Steel Installation ITP | itp |  |  |  | Yes | Structural Steel Install ITP | 29909f25-b825-4470-bebf-8b91a7aa85a0
checkpoint-group |  |  | section | Prior to Erection
checkpoint-status |  |  | checkpoint | Heights for concrete beams / piles to be checked.
label | 0420e6c4-cfe7-47d0-8ba3-511a8b137559 |  | note | Responsible Inspectorate - Site Engineer
label | f4b6d190-b8d9-4fbd-8e65-5af814c0f5f9 |  | note | Acceptance Criteria - Concrete tolerances.
label | fff7e541-8833-47b5-9bc3-2e3a167d264a |  | note | Method - Visual Measure.
label | 26968923-c6aa-47b4-9799-c259e6786fcc |  | note | Frequency - Prior to installation of columns
label | d33c89e1-ca09-4844-ab68-875a0a6fea7e |  | note | Verifying Record - N/A
checkpoint-status |  |  | checkpoint | Hold Down Bolts Surveyed and As-Built dimensions checked.
label | 7a50eff9-31d4-43a3-b16b-dbaeb144f567 |  | note | Responsible Inspectorate - Site Engineer
label | df1dfc0e-30ff-468a-aa8d-978746b20893 |  | note | Acceptance Criteria - "+- 10mm tolerance. Column baseplate templates installed."
label | 88f08b21-ec3f-4c41-8b7b-c44dfc1f9797 |  | note | Method - Visual Measure.
label | fe26459b-76a3-4c57-8d06-e28fd2634c9e |  | note | Frequency - One-off.
label | 89fe3a6b-9845-46af-83e4-15be19f7369a |  | note | Verifying Document - Survey records.
checkpoint-status |  |  | checkpoint | Correct packing to underside of Columns.
label | a36eac30-aa12-454f-b51c-0913c75ef6ae |  | note | Responsible Inspectorate - Site Engineer
label | b09a00a9-c632-49ae-af1f-588b0292b031 |  | note | Acceptance Criteria - Allow for 15mm grouting post-installation.
label | 81a871c1-81f3-473d-93c8-c0a94b9de936 |  | note | Method - Visual Measure.
label | 07423201-03d6-4db9-8a2b-d5eaf904fcc5 |  | note | Frequency - Prior to installation of columns
label | 0fefc932-2dda-4652-918c-44b87a256ef7 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | Steel tolerances e.g. beam pre-camber.
label | 3144d873-f9b4-4adf-8603-c64642eaddae |  | note | Responsible Inspectorate - Site Engineer
label | cd5e8bcb-93fc-40a7-9f22-702d468777f1 |  | note | Acceptance Criteria - "NZS3404:1997 NZS3404:2009"
label | 198081cf-1aee-4460-b844-48e8b8489456 |  | note | Method - Visual Measure.
label | 2a3d0eb4-d88d-49ce-af58-86207acef739 |  | note | Frequency - Per member.
label | 9b82c427-2e91-4170-b2b0-dcb9d19b3166 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | Steel connections to be checked off shop drawings.
label | ad258ac1-065e-41f8-a4e1-9dde3a89859e |  | note | Responsible Inspectorate - Site Engineer
label | 50488491-ab27-41a4-9982-e71646bfa4ca |  | note | Acceptance Criteria - As-built comparison.
label | 3cc17250-0ce0-4239-b1f0-4ca63db74d90 |  | note | Method - Visual Measure.
label | 9c05d700-113f-4dc7-a8b3-6fe092e24d57 |  | note | Frequency - Per member.
label | 2a56cc78-5083-4922-b3dc-b0ced816bc2e |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | Weights to be reviewed and lifting gear to be inspected prior to any lifts.
label | a4f3c5de-d63b-4aa6-9269-78841a3bf993 |  | note | Responsible Inspectorate - Site Engineer
label | 13cf623d-d203-47d7-90a2-ce99603be734 |  | note | Acceptance Criteria - Dogman & Crane Driver satisfied.
label | 5c241e7f-c94c-4c70-bf12-05a60d670a30 |  | note | Method - Visual.
label | 60dfcdb0-636a-49c0-8e28-288922f3dbbf |  | note | Frequency - Day before installation
label | af400f70-0748-4901-8dcb-229665262c64 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | Tag lines must be secured to all structural steel to be installed.
label | db9ef40e-5aba-42d7-b370-a3654ef0eb30 |  | note | Responsible Inspectorate - Site Engineer
label | 91652edf-8967-4dc1-977a-0bd452ead741 |  | note | Acceptance Criteria - Dogman & Crane Driver satisfied.
label | c877c3ef-f0ff-4ac4-b68d-714987adb8c9 |  | note | Method - Visual
label | 411952d1-d25f-4e13-ae88-0fb27b558f48 |  | note | Frequency - Per load.
label | c3104149-4786-4c8f-b3d8-2077b557bde8 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | HOLD POINT - Lifting may commence once all of the above has been completed.
checkpoint-group |  |  | section | HOLD POINT - Lifting may commence once all of the above has been completed.
checkpoint-status |  |  | checkpoint | Approval to proceed
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | All steelwork checked for plumb, level and alignment. Top Of Steel level check. Confirm F.F.L. reflects documented floor levels.
checkpoint-status |  |  | checkpoint | All bolts to be M20 Grade 8.8S, U.N.O.
checkpoint-status |  |  | checkpoint | All bolt connections checked / inspected.
checkpoint-status |  |  | checkpoint | All welds are to be 6mm fillet all around category SP, U.N.O.
checkpoint-status |  |  | checkpoint | All washer plates need to be site welded after aligning, U.N.O.
checkpoint-status |  |  | checkpoint | All weld connections checked / inspected as per specification.
checkpoint-group |  |  | section | After Erection
checkpoint-status |  |  | checkpoint | Propping for structural steel installed if required.
label | b434fb89-5fc3-48f3-8839-0918aa6e8b73 |  | note | Responsible Inspectorate - Site Engineer
label | 0471efd5-2188-4bd4-abd4-ed584c1edf09 |  | note | Acceptance Criteria - As per Task Analysis.
label | f7268bbb-8a4c-433f-a19c-16e4925cabe9 |  | note | Method - Visual.
label | e27461b0-f787-4548-81d7-693f50b44e91 |  | note | Frequency - Per element.
label | 69bcc811-5fef-4167-83b5-582dd2c78e2e |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | All steelwork checked for plumb, level and alignment. Top Of Steel level check. Confirm F.F.L. reflects documented floor levels.
label | 34141a4d-a3bf-4e19-a9f8-e3eb176c8d05 |  | note | Responsible Inspectorate - Site Engineer
label | 186d4979-425a-46be-8a07-93dce632c9e3 |  | note | Acceptance Criteria - Subcontractor installation ITP received.
label | 5765a4eb-9141-41e2-b602-13bec165e531 |  | note | Method - Approval.
label | ccaab211-5961-41e4-96e9-7d168dce64cc |  | note | Frequency - Per zone.
label | 6a15f2f8-f9b0-44e1-89f0-9a4c02ce919a |  | note | Verifying Document - QA sheet.
checkpoint-status |  |  | checkpoint | All bolts to be M20 Grade 8.8S, U.N.O.
label | 0881fbe6-ab9d-4948-a2ae-6c7bafeb1cfd |  | note | Responsible Inspectorate - Site Engineer
label | a67f79f6-133a-47c4-8fd3-b0ececfad094 |  | note | Acceptance Criteria - N/A
label | 79e19950-93b9-49e0-8dc6-661faad51df7 |  | note | Method - Approval.
label | 1871cc43-e30d-4919-a45d-4c0d1be27d52 |  | note | Frequency - Each bolted connection
label | 3be819f1-1a48-4d9b-b5ee-1c3fae7caee4 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | All bolt connections checked / inspected.
label | fa141b30-90d6-40c2-a078-0be3985d8148 |  | note | Responsible Inspectorate - Site Engineer
label | 61f5b702-378f-4ea9-ae9d-984947b018d9 |  | note | Acceptance Criteria - As per specification.
label | 2c8bbdee-269b-44f7-9a97-0777d8fc6663 |  | note | Method - Approval.
label | 2c206e10-c08d-46db-b017-05a72fb2b7fc |  | note | Frequency - Each bolted connection
label | 126c0a1d-3d1e-4a60-84d7-e332baeb3c12 |  | note | Verifying Document - Inspection reports.
checkpoint-status |  |  | checkpoint | All welds are to be 6mm fillet all around category SP, U.N.O.
label | 82e8e6c0-b0ed-422c-b62a-b319cc38640c |  | note | Responsible Inspectorate - Site Engineer
label | 74746f57-e393-4a8a-86ea-08b63609c3bf |  | note | Acceptance Criteria - N/A
label | fcb9ac0a-6da9-427f-aae4-ffef4692d938 |  | note | Method - Approval.
label | 4e657cee-5271-470d-9698-b2e90da8c989 |  | note | Frequency - Each welded connection
label | e083eb10-ff95-4c3d-9c4d-f1b44962a087 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | All washer plates need to be site welded after aligning, U.N.O.
label | 347fcc7b-62e7-4045-83eb-d48f82771563 |  | note | Responsible Inspectorate - Site Engineer
label | a75a8770-2ef2-483a-93ca-dc67ec3691bd |  | note | Acceptance Criteria - N/A
label | 9c4d5ce6-1dd0-4175-a0a1-4368a079bfa5 |  | note | Method - Approval.
label | 489170dd-2778-4312-87af-a52a31cd4d69 |  | note | Frequency - Each Column Baseplate.
label | 0c0eeb63-6bcb-4175-9017-7cb688d81674 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | All weld connections checked / inspected as per specification.
label | 3415461e-0bb4-435a-a217-147854001ad2 |  | note | Responsible Inspectorate - Site Engineer
label | 028d84f2-1bb6-4f67-a42d-48dfa9b3cca0 |  | note | Acceptance Criteria - As per specification.
label | cb6c9e67-aa08-44cd-b99e-1c5e0ffdba9e |  | note | Method - Approval.
label | 024084e8-ef29-4f53-892e-b1e8ee2d9659 |  | note | Frequency - Each welded connection
label | 02ddcf79-48e4-44b6-bfab-9564c77e632d |  | note | Verifying Document - Inspection reports.
checkpoint-group |  |  | section | HOLD POINT - Verify verticality Verify tensioning of bolts Verify Inspections
checkpoint-status |  |  | checkpoint | Approval to proceed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | After Erection Cont.
checkpoint-status |  |  | checkpoint | Obtain all necessary sign off prior to grouting base plates.
label | 5fbb39e3-ff76-4c6f-b980-6688d11cfe8c |  | note | Responsible Inspectorate - Site Engineer
label | 3f26354b-e3b8-4f3c-a7eb-d3c24c2a4d3b |  | note | Acceptance Criteria - As per specification.
label | 1cc17819-e4f3-43af-a6d8-7aca49b133ee |  | note | Method - Approval.
label | ba887ade-c676-40ad-848b-3d935508a3d0 |  | note | Frequency - Each column.
label | 17c2c687-af5e-45c4-8ad0-e019a8e95ebd |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | Grouting of base plates. QA check sheet received.
label | 226116af-83da-42c2-9b2f-6af06dd36ddd |  | note | Responsible Inspectorate - Site Engineer
label | 13b7039e-46cc-41f3-8719-538e8f585523 |  | note | Acceptance Criteria - Sika Grout 212HP – 80MPa Strength.
label | f805f599-75b2-41e8-8a24-59a4aa70f378 |  | note | Method - Lab test.
label | 7aeea200-647b-437d-b53b-0531457c9d86 |  | note | Frequency - 1 set of samples for every 15 grouted baseplates.
label | bc872db0-bc6f-4403-99df-b7521b24a493 |  | note | Verifying Document - Independent Reports.
checkpoint-status |  |  | checkpoint | Confirm services penetrations match shop drawings.
label | b6b97b4b-1479-4991-b800-444f374091be |  | note | Responsible Inspectorate - Site Engineer
label | 749071cc-dd80-487a-a122-efbabc514bf4 |  | note | Acceptance Criteria -
label | c03e79af-dc75-4baf-9c48-6ea9c05a1b97 |  | note | Method - Visual.
label | 90618af1-8e82-4001-bb69-d411d51ca994 |  | note | Frequency - Each beam.
label | d78ada4a-ea60-4c12-9bdd-d9d512b8aedf |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | Confirm coatings/cover are as per specification. Confirm if coating touch up is required.
label | f6cde832-4f5a-41de-9dcb-2565f03ac2ec |  | note | Responsible Inspectorate - Site Engineer
label | 86f0050c-6694-47c5-be83-dae035f4d69c |  | note | Acceptance Criteria - N/A
label | 16bc166b-0c16-4933-81af-800310250341 |  | note | Method - N/A
label | d40f775a-5b87-4c22-bf7d-a055ec41f27f |  | note | Frequency - N/A
label | 9d4629b9-4d35-4350-b984-f9a4433c8911 |  | note | Verifying Document - N/A
checkpoint-status |  |  | checkpoint | PS3 for installation.
label | c80da9b0-1fa6-49be-ac68-a11cf3e5199a |  | note | Responsible Inspectorate - Site Engineer
label | ee1f81f2-a682-4ea2-acf4-06e654da9163 |  | note | Acceptance Criteria - Received and signed.
label | 7f952165-3652-4299-824f-ed13f654fe1b |  | note | Method - Approval.
label | 69a7b0af-77b9-4481-8d77-c17c15c7943a |  | note | Frequency - Each month.
label | f875109a-f7c1-4158-a633-2763e1ed41e9 |  | note | Verifying Document - PS3.
checkpoint-group |  |  | section | Subcontractor ITP Signoff
checkpoint-status |  |  | checkpoint | Subcontractor ITP Signoff
label | 5c4e37d0-0c64-489f-b1f0-7cf8b4ef176d |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Trade Contractor Signoff
checklist-sectioned |  |  | checklist | Internal Partitioning | itp |  |  |  | Yes | 05) Add Internal Partitioning ITP | 30c63fa1-4260-4b7a-a75a-3f18f7377471
checkpoint-group |  |  | section | Pre-Construction Tasks
checkpoint-status |  |  | checkpoint | Check Materials ordered/delivered
checkpoint-status |  |  | checkpoint | Check Current Architectural drawings to work from
checkpoint-status |  |  | checkpoint | Area clear and dry
checkpoint-status |  |  | checkpoint | Check Concrete slab levels and shear walls splatters/over pours
checkpoint-status |  |  | checkpoint | Check bathrooms set downs levelled and grinded 40mm set down
checkpoint-status |  |  | checkpoint | Fill Shear wall hobs
checkpoint-status |  |  | checkpoint | Remove pins in Comflor angle
checkpoint-status |  |  | checkpoint | Grid lines installed
checkpoint-status |  |  | checkpoint | +1m above FFL RL level datum marked on shear walls / core walls
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to steel framing
checkpoint-group |  |  | section | During Installation
checkpoint-status |  |  | checkpoint | Bottom plate DPC installed
checkpoint-status |  |  | checkpoint | Working of correct drawings - CATPLAN checks
checkpoint-status |  |  | checkpoint | Check gauge of materials / screws used
checkpoint-status |  |  | checkpoint | Checking spacing between studs "400mm crs for IT and Corridors " & "600mm crs for Internal walls"
checkpoint-status |  |  | checkpoint | Rondo fast track: "1 run at 100mm down from top plus 2 intermediate runs on IT/Corridor walls" & "1 run at 100mm down from top"
checkpoint-status |  |  | checkpoint | 32mm 6.5g metal pin anchor either side of door on bottom track
checkpoint-status |  |  | checkpoint | Confirm door openings with schedule
checkpoint-status |  |  | checkpoint | Head track completed as per details
checkpoint-status |  |  | checkpoint | Timber fillet installed inside door studs in all doors
checkpoint-status |  |  | checkpoint | Check fixings bottom and top tracks 17mm trackmaster 600mm spacing
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to nogs
checkpoint-status |  |  | checkpoint | Check no H3.2 CCA treated timber being used
checkpoint-status |  |  | checkpoint | Kitchens
checkpoint-status |  |  | checkpoint | Bathrooms
checkpoint-status |  |  | checkpoint | Wardrobes
checkpoint-status |  |  | checkpoint | Media unit
checkpoint-status |  |  | checkpoint | Laundry
checkpoint-status |  |  | checkpoint | Hot water cylinder
checkpoint-status |  |  | checkpoint | Plinth (HWC)
checkpoint-status |  |  | checkpoint | Services ply
checkpoint-status |  |  | checkpoint | Attach subcontractors ITPs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off/Subcontractor ITP Sign-off
label | 5bc5b1ca-f4b3-45cd-8c90-2d6bb59e9482 |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Mechanical Services First Fix Checklist | itp |  |  |  | Yes | Mechanical Services First Fix Checklist | 33c77c82-0699-4d5a-b339-c11aff3485f4
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any duct penetrating fire-rated walls or shafts are sealed/fire rated to manufacture spec
checkpoint-status |  |  | checkpoint | Confirm access for fire damper adequate i.e. access panel in duct or access panel.
checkpoint-status |  |  | checkpoint | Confirm fire damper installed in line of wall.
checkpoint-status |  |  | checkpoint | Confirm fire dampers installed as per manufacturer’s requirement and have access panels
checkpoint-status |  |  | checkpoint | Fire damper approval. Data sheet cited and signed.
checkpoint-group |  |  | section | HOLD POINT - OK to proceed to Acoustic Requirements
checkpoint-group |  |  | section | Acoustic Requirement
checkpoint-status |  |  | checkpoint | Confirm that the AC fan coil unit is vibration isolated with in shear rubber mount or springs from the structure and ductwork
checkpoint-status |  |  | checkpoint | Confirm toilet/laundry/kitchen exhaust fans are vibration isolated with in shear rubber mounts
checkpoint-status |  |  | checkpoint | Confirm sheet metal ductwork has inner acoustic lining if required
checkpoint-group |  |  | section | HOLD POINT - OK to proceed to Mechanical Services
checkpoint-group |  |  | section | Performance Requirements - Prior to Sheeting Walls
checkpoint-status |  |  | checkpoint | Confirm all flexible and sheet metal ducting has been installed as per drawings
checkpoint-status |  |  | checkpoint | Confirm wiring of AC controls are located as per architectural requirements.
checkpoint-status |  |  | checkpoint | Confirm all supply and return piping from riser to FCU in place and charged.
checkpoint-status |  |  | checkpoint | Confirm no flexible ductwork is torn or damaged.
checkpoint-status |  |  | checkpoint | Confirm sealing of flexible connections between kitchen/ toilet exhaust fan and metal ducting (mechanically fixed required).
checkpoint-status |  |  | checkpoint | Confirm electrical panel and filters are accessible on FCU from access panel for future inspections.
checkpoint-status |  |  | checkpoint | Confirm spreaders are installed to flexible duct hanging system to prevent squashing of flexi.
checkpoint-status |  |  | checkpoint | Confirm all equipment is wired and complete (Ready for making active).
checkpoint-status |  |  | checkpoint | Confirm all condensate drains and trays (incl. safety tray have been connected to hydraulic wastes and wet tested.
checkpoint-status |  |  | checkpoint | Confirm all refrigerant or condenser water testing required has been carried out (Attach test sheet). Insulated as required.
checkpoint-status |  |  | checkpoint | Confirm all ceiling and bulkhead plenum boxes have been installed as per RCP drawings. crosscheck with windows and facade drawings
checkpoint-status |  |  | checkpoint | Confirm access panel locations marked out and identified on slab below (review arch RCP location). Ensure clear access to controls and filters.
checkpoint-status |  |  | checkpoint | Confirm all pipework is supported correctly with uni-strut/timber blocks/ saddles and insulation. Drainage has fallen to tundish.
checkpoint-status |  |  | checkpoint | Confirm all Dampers are fully open.
checkpoint-status |  |  | checkpoint | Check quality and position of electronic dampers and controls.
checkpoint-status |  |  | checkpoint | Confirm type and colour of external grill and louvre is fit for purpose, check all penetrations
checkpoint-status |  |  | checkpoint | Check paint specs and fixing methodology for external louvres/grills
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
checklist-sectioned |  |  | checklist | Windows and Doors |  |  |  |  | Yes | ITP-020 Windows and Doors | 35b95e5f-8249-4090-8dbd-077ed5a017a9
checkpoint-group |  |  | section | Pre-construction
checkpoint-status |  |  | checkpoint | Inspected and accepted the work area and surfaces ready to commence work
checkpoint-status |  |  | checkpoint | Confirmed Site storage requirements, packaging and preservation
checkpoint-status |  |  | checkpoint | Confirmed material handling schedule
checkpoint-status |  |  | checkpoint | Gridlines set-out by surveyor
checkpoint-status |  |  | checkpoint | Shop drawings approved
boolean | adc4fd75-5fa0-4d3c-af62-9d7e5f40ebee |  | tickbox | Attach drawing
checkpoint-group |  |  | section | Opening Handover
checkpoint-status |  |  | checkpoint | Timber head constructed and flashing tape installed as per manufacturers guidelines
checkpoint-status |  |  | checkpoint | Check set down to correct level & size. Are rebates for sill as per shop drawing
checkpoint-status |  |  | checkpoint | Confirm all side lifting eyes been patched
checkpoint-status |  |  | checkpoint | Confirm the panel been sealed as per façade/architectural spec
checkpoint-status |  |  | checkpoint | Confirm waterproofing is installed as per manufacturers requirements
checkpoint-status |  |  | checkpoint | Rough Opening Height & Width as per shop drawing. Tolerance 0mm to +10mm
checkpoint-status |  |  | checkpoint | Rough opening position from Grid as per shop drawing. +/- 10mm
checkpoint-status |  |  | checkpoint | Opening surface is level and clean
checkpoint-status |  |  | checkpoint | S/C inspected and opening handed over
checkpoint-group |  |  | section | Window & Door Suite Installation
checkpoint-status |  |  | checkpoint | Aluminium angle for rear air seal installed back of PC panel
checkpoint-status |  |  | checkpoint | Saddle flashing are fixed in place and fully sealed against WP membrane & side edge of precast spandrel
checkpoint-status |  |  | checkpoint | Frame fixed plumb, level and heads in alignment
checkpoint-status |  |  | checkpoint | Packers installed as per shop drawings
checkpoint-status |  |  | checkpoint | Orientation of glass panel installed correctly
checkpoint-status |  |  | checkpoint | Bead & head flashing securely fixed, ready for soffit interface
checkpoint-status |  |  | checkpoint | Rear air seal installed with no over spill and residue.
checkpoint-group |  |  | section | Interface Finish
checkpoint-status |  |  | checkpoint | Negative detail (internal wall) correctly installed
checkpoint-status |  |  | checkpoint | Ensure interface schedule is checked for specific details
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Removal of temporary fixings, spacers & packers
checkpoint-status |  |  | checkpoint | Panel cleaned to remove installation marks
checkpoint-status |  |  | checkpoint | Panel surface are defects free
checkpoint-group |  |  | section | Final Inspection
checkpoint-status |  |  | checkpoint | All defects complete and “signed off”
checkpoint-status |  |  | checkpoint | Obtain all balcony slider keys
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Fire Services Rough In Checklist | itp |  |  |  | Yes | Fire Services Rough In Checklist | 398dd901-7475-490e-ac70-d9a990e4eac3
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any pipework and cabling penetrating partition walls are fire sealed
checkpoint-status |  |  | checkpoint | Confirm pipe works are supported, anchors hangers and clips
checkpoint-status |  |  | checkpoint | Confirm sprinkler pipework installed as per drawings.
checkpoint-status |  |  | checkpoint | Confirm if any drenchers required have been installed.
checkpoint-status |  |  | checkpoint | Confirm apartment and balcony sprinkler head brackets are installed to ceiling grids.
checkpoint-status |  |  | checkpoint | Confirm pipework pressure test (Attach subcontractor sign off).
checkpoint-status |  |  | checkpoint | Confirm installation for fire electrical speakers and detectors.
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
checkpoint-group |  |  | section | HOLD POINT - OK to proceed to Plasterboard Sheeting
checklist-sectioned |  |  | checklist | Hydraulic Rough In Checklist | itp |  |  |  | Yes | Hydraulic Rough In Checklist | 42004e22-fe45-4cec-ab3b-1dd4536f682e
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Intumescent fire collars inspected and installed as per manufacturers details
checkpoint-status |  |  | checkpoint | Fire collars sealed around penetrations
checkpoint-group |  |  | section | HOLD POINT - OK to proceed to Hydraulic Services
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to Hydraulic Services
checkpoint-group |  |  | section | Hydraulic Servies - Prior to Sheeting Walls
checkpoint-status |  |  | checkpoint | Confirm all materials comply with specs.
checkpoint-status |  |  | checkpoint | All pipes supports, anchors, hangers and clips
checkpoint-status |  |  | checkpoint | Confirm all pipes not damaged or leaking prior to lagging and joints are glued
checkpoint-status |  |  | checkpoint | All pipe work acoustically lagged and wrapped in accordance with Acoustic Specification.
label | 73f66d99-8468-40b8-9717-4228be51904d |  | note | Confirm hot water/cold water supply to:
boolean | 4ff30b6f-cda4-428d-93e1-5e2fa916b3f1 |  | tickbox | Kitchen
boolean | 53eb2fb4-3d82-40ea-8c0d-de1953cd9546 |  | tickbox | Bathroom
boolean | e6937cf8-3d9f-47e3-996a-7a9e190ba129 |  | tickbox | Ensuite
boolean | e1a4546d-c9e9-40ea-9877-f72c74473932 |  | tickbox | Laundry
checkpoint-status |  |  | checkpoint | Confirm water and gas point
checkpoint-status |  |  | checkpoint | Confirm kitchen rough in is as per kitchen shop drawing.
checkpoint-status |  |  | checkpoint | Confirm location of gas meter as per Kitchen Shop Drawing.
text | 0a49ed6b-790b-4faf-8634-2843c4decbfd |  | textbox | Kitchen Type:
checkpoint-status |  |  | checkpoint | Confirm A/C tundish location has been supplied and trap prefilled.
checkpoint-group |  |  | section | Confirm the following heights and location from architectural detail drawings:
checkpoint-status |  |  | checkpoint | Confirm the following heights and location from architectural detail drawings:
text | e737fa03-0809-4e45-abf6-4728294767fc |  | textbox | Shower head:
text | e7abd5a9-5725-4224-87f6-b261b7b93f66 |  | textbox | Shower mixer:
text | ae33a55b-0dae-4942-b072-649cf6729ffd |  | textbox | Shower drain:
text | 96cb74f7-413f-4d8a-99e5-812cc148a7a6 |  | textbox | Bathroom basin:
text | 22ff70a5-82e9-4a33-8cd8-443cce43274c |  | textbox | Bathroom drain:
checkpoint-group |  |  | section | Confirm following test been undertaken (attached sign off)
checkpoint-status |  |  | checkpoint | Confirm following test been undertaken (attached sign off)
boolean | 01701b8e-18e9-4c29-9413-2b0c0bb9e5ba |  | tickbox | Hydraulic Services - Prior to Sheeting Walls
boolean | 182bc9d5-e842-4d5e-99c9-907fc1bbc218 |  | tickbox | Confirm all pipes not damaged or leaking prior to lagging and joints are glued
boolean | 0ee76b9a-f0c5-47c1-94bb-fb6d4ecb62a8 |  | tickbox | Confirm all materials comply with specs.
boolean | c791edd4-6f50-4431-83c7-450bcb0795e1 |  | tickbox | Pressure test for water and gas
boolean | 189a07c3-4b55-4cb8-934d-5e4dac09309c |  | tickbox | Confirm hot water/cold water supply to:
boolean | 948dc3ae-07d8-472b-b96c-8199e50f137b |  | tickbox | All pipes supports, anchors, hangers and clips
boolean | f692bbc6-608b-4f59-a36f-54b724923f00 |  | tickbox | Drainage pipework
checkpoint-status |  |  | checkpoint | Confirm supply pipes have been charged
checkpoint-status |  |  | checkpoint | Confirm rough-in of wet area fixtures as per layout.
checkpoint-status |  |  | checkpoint | Confirm bath has been installed level and correct RL and protected.
checkpoint-status |  |  | checkpoint | Confirm bath protection
checkpoint-status |  |  | checkpoint | Confirm downpipe type, color and location
checkpoint-status |  |  | checkpoint | Confirm tap location to balcony's
checkpoint-status |  |  | checkpoint | Confirm drainage accommodates mech condensate pipe
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checklist-sectioned |  |  | checklist | Aluminum Louvres |  |  |  |  | Yes | ITP-027 Aluminum Louvres | 5585317d-73f9-43c4-8faa-55eb6697737f
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Inspected and accepted the work area and surfaces ready to commence work
checkpoint-status |  |  | checkpoint | Confirmed Site storage requirements, packaging and preservation
checkpoint-status |  |  | checkpoint | All site measures for opening sizes complete prior to manufacture
label | 61e27261-0d16-4d68-8aad-c66cd17d747f |  | note | Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Colour samples issued for approval and signed off
label | f9090d61-3e11-4285-845b-70f897b3c376 |  | note | Refer sample sign off
checkpoint-status |  |  | checkpoint | All windows and doors delivered to site to be correct colour, grade and thickness
checkpoint-status |  |  | checkpoint | Shop drawings approved
boolean | 466cb686-7991-456c-811a-faa9e36a516c |  | tickbox | Attach file
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Waterproof membrane laid and dry prior to install
checkpoint-status |  |  | checkpoint | Louvers installed correct distances from envelopes to comply with façade /architectural specification
checkpoint-status |  |  | checkpoint | Louvers installed in locations as per drawings and are correct sizes
checkpoint-status |  |  | checkpoint | All fixings installed – rigid and louver does not rattle
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | No visible defects and signed off by Ganellen
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Plasterboard and Linings |  |  |  |  | Yes | ITP-025 Plasterboard and Linings | 591df470-bc02-41b1-8bf7-3650d5081c05
checkpoint-group |  |  | section | Pre-Line - Full Heightwalls
checkpoint-status |  |  | checkpoint | Confirm all services first fix ITPs closed out for area;
boolean | 572f6797-776d-4a73-81c1-df75c81bb9f0 |  | tickbox | Mechanical
boolean | ac9b35df-2bee-4fce-8a46-4ef979dad148 |  | tickbox | Hydraulic
boolean | a3f02079-f6e0-4e0e-9d3e-76b5403fbcf3 |  | tickbox | Gas
boolean | b103b75c-4a85-47ad-98d4-4734186fd96a |  | tickbox | Fire Sprinklers
boolean | 6594a4f4-8f1d-492f-a323-3231aac82960 |  | tickbox | Fire Alarms
boolean | 1f7e227e-9ec0-438d-855d-7fc77b7bd326 |  | tickbox | Electrical
boolean | 60729f4f-8b30-4948-b491-f471fc76d0b7 |  | tickbox | Data
boolean | dae4f7a7-be1f-4579-9d7a-8910236e1ed3 |  | tickbox | Security
boolean | 7f037084-1962-44e2-ae8b-bcbc95c686ff |  | tickbox | Intercom
checkpoint-status |  |  | checkpoint | Confirm all noggings / timber fixings installed for joinery / fittings fit off;
boolean | 51b96eae-5d29-455b-8fda-39eec547b6a9 |  | tickbox | Kitchen
boolean | 303801ea-2942-450e-bbf4-b8f4a3c50c2c |  | tickbox | Joinery
boolean | 0e8fa9ae-c267-491e-ace1-22bc47046c0f |  | tickbox | Bathroom Fixture and hardware
boolean | 0c9d0198-19c0-4bcd-88c3-ef5f976fadaf |  | tickbox | Vanities
boolean | ec7af725-2fed-48b6-9f09-2197239571f2 |  | tickbox | TV hangers
boolean | 864da3b9-ce23-45c0-9c82-f7eb1a6c0e6e |  | tickbox | Other
checkpoint-status |  |  | checkpoint | Confirm all box around services complete for passive fire – separate signoff required from passive fire contractor / service contractor
checkpoint-status |  |  | checkpoint | Confirm all intumescent paint sign off
checkpoint-status |  |  | checkpoint | Confirm thermal / acoustic insulation installed
checkpoint-status |  |  | checkpoint | Confirm door frames installed true, plumb and correct orientation
checkpoint-status |  |  | checkpoint | Pre-line inspections;
boolean | 2d413fb1-129b-4d83-a0aa-2081030ccdde |  | tickbox | Service Consultants
boolean | 1f1eadc5-f8ba-46f3-a39a-9d1d630a356d |  | tickbox | Engineer (if engineers detail supplied for wall framing)
boolean | 596f5e4b-858a-4846-bb0f-94368650cdd9 |  | tickbox | Architect
boolean | f1c2b376-a31e-4a52-a98e-7a3b81e58c7f |  | tickbox | Acoustic Consultant
boolean | 020de8da-bc9e-465f-82c9-84e1d700191b |  | tickbox | Fire Engineer
boolean | 0506e893-7983-40e8-aeec-90715003c959 |  | tickbox | Council
checkpoint-status |  |  | checkpoint | Check S/C drawings latest revisions and confirm wall types
holdpoint |  |  | signoff | HOLD POINT – ALL INSPECTIONS COMPLETE INCLUDING COUNCIL PRE-LINE INSPECTION
checkpoint-group |  |  | section | Pre-Line Ceiling
checkpoint-status |  |  | checkpoint | Full height wall linings complete
checkpoint-status |  |  | checkpoint | All fire walls fire sealed
checkpoint-status |  |  | checkpoint | All service penetrations through wall fire sealed
checkpoint-status |  |  | checkpoint | Lined fire walls inspected;
boolean | 561ea73d-6316-44eb-bd1d-6aee5fd6e1b8 |  | tickbox | Fire Engineer
boolean | 9fb7e6b2-59f1-412a-99cc-2800bb77309a |  | tickbox | Council
boolean | 626382a0-861f-4c45-9f5e-958252eca3f8 |  | tickbox | Architect
checkpoint-status |  |  | checkpoint | Ceiling grid installed correct RL
checkpoint-status |  |  | checkpoint | Ceiling bulkheads square / level
checkpoint-status |  |  | checkpoint | Suspended ceiling seismic restraints installed as detailed
checkpoint-status |  |  | checkpoint | All services seismic restraint installed
checkpoint-status |  |  | checkpoint | 50mm seismic clearance between all services, ceiling frame
checkpoint-status |  |  | checkpoint | Confirm ceiling access hatches installed in correct locations for fire dampers and mechanical equipment
checkpoint-status |  |  | checkpoint | Confirm ceiling furring channels do not clash with other services (e.g. downlights, sprinklers, grilles, sprinkler head)
checkpoint-status |  |  | checkpoint | Final services sign off required
checkpoint-status |  |  | checkpoint | Ceiling height partitions installed and braced (may need more checks for non -full height walls)
checkpoint-status |  |  | checkpoint | Confirm ceiling and wall insulation installed (acoustic / thermal)
checkpoint-status |  |  | checkpoint | Attach sub-contractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | GRC |  |  |  |  | Yes | GRC | 5ee1b0e3-dbf4-4ff5-9620-26f4a257b862
checkpoint-group |  |  | section | Fabrication Tasks
checkpoint-status |  |  | checkpoint | Confirm all shop drawings submitted are approved.
checkpoint-status |  |  | checkpoint | Confirm that structural engineer has been notified of pour schedule / programme for required inspections prior to any fabrication for confirmation of bar size, layout and cover etc..
checkpoint-status |  |  | checkpoint | Remedials completed from engineers inspection.
checkpoint-status |  |  | checkpoint | Check all cast ins are in correct location (e.g. weld plates and inserts).
checkpoint-status |  |  | checkpoint | Post pour panel finish accepted
boolean | 772429ed-7282-4307-9d4f-b14342139de4 |  | tickbox | Attach photo
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT proceed only if items above are completed
checkpoint-group |  |  | section | Materials Receiving Tasks
checkpoint-status |  |  | checkpoint | Confirm that materials delivered to site are in conformance with drawings and specification
boolean | 1879d478-e58b-4ecf-b46b-1d135dc61951 |  | tickbox | Attach panel certificate where required
checkpoint-status |  |  | checkpoint | Confirmed site unloading and set down / storage of materials.
checkpoint-status |  |  | checkpoint | Confirm all panels are undamaged.
boolean | 60984a54-f6b0-418f-98f3-78dac991d8e8 |  | tickbox | Attach photo
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT proceed only if items above are completed
checkpoint-group |  |  | section | Pre - Erection Tasks
checkpoint-status |  |  | checkpoint | Check all dowels and starters are as per shop drawings
checkpoint-status |  |  | checkpoint | Base level / Setting out checked. Verify setting pads / shims are correct material
checkpoint-status |  |  | checkpoint | Confirmed construction sequencing / handling and lifting points correctly located and to correct loading factor.
checkpoint-status |  |  | checkpoint | Ensure all props are readily available prior to install
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT SECONDARY GANELLEN SIGN OFF REQUIRED
checkpoint-group |  |  | section | Erection Tasks
checkpoint-status |  |  | checkpoint | All shim packers in place as per drawings. Confirm check on dry packing.
checkpoint-status |  |  | checkpoint | Intermittently check verticality, alignment and level as panels progress including dowel pins
checkpoint-status |  |  | checkpoint | Check all temporary bracing as per shop drawings and Engineers requirements
checkpoint-status |  |  | checkpoint | Obtain any sign off necessary from Structural Engineer prior to grouting. Attach certificate- See specification for requirement
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT SECONDARY GANELLEN SIGN OFF REQUIRED
checkpoint-group |  |  | section | Erection Tasks Cont.
checkpoint-status |  |  | checkpoint | Confirm all grouting complete (perform check to confirm full depth)
checkpoint-status |  |  | checkpoint | Check all joint and connection details as per drawings. (rebar, weld and cast in-situ joint connections)
checkpoint-group |  |  | section | Final Inspection Tasks
checkpoint-status |  |  | checkpoint | All defects complete and signed off, also check that no visible cracks or damage
checklist-sectioned |  |  | checklist | Suspended Slab ITP | itp |  |  |  | Yes | Add Suspended Slab ITP | 61244a9e-7f70-46a5-82d3-c30d149ab9ee
checkpoint-group |  |  | section | Prior to Erection
checkpoint-status |  |  | checkpoint | For construction shop drawings consultant sign-off received
checkpoint-status |  |  | checkpoint | QA and post pour checks complete
checkpoint-status |  |  | checkpoint | Materials handling and access equipment checked
checkpoint-status |  |  | checkpoint | Received Structural handover
label | 8b258dc2-e6a9-4eb5-b97d-879ffc6d4e53 |  | note | Acceptance Criteria - QA Received
label | 81a871c1-81f3-473d-93c8-c0a94b9de936 |  | note | Method - N/A
label | b09a00a9-c632-49ae-af1f-588b0292b031 |  | note | Frequency - N/A
checkpoint-status |  |  | checkpoint | Static Lines / Handrails installed
label | 9f85b9e0-fdfb-4747-b84f-ced79f2ad9d6 |  | note | Acceptance Criteria - H&S:Preventions of Falls
label | 02ddd17e-f679-48f5-9506-a78067d357e2 |  | note | Method - Approval
checkpoint-status |  |  | checkpoint | Grid lines available and set out
checkpoint-status |  |  | checkpoint | Propping and/or temporary works installed
label | 76745c63-4c56-4e6a-8b64-7ade08d9ff13 |  | note | Acceptance Criteria - As per Temporary Works Design
label | c64819e4-7e07-45e6-9dc5-7180768164af |  | note | Method - Visual
checkpoint-status |  |  | checkpoint | Confirm RL of bearing platform/structure
checkpoint-group |  |  | section | PHOTO HOLD POINT
checkpoint-status |  |  | checkpoint | PHOTO HOLD POINT – proceed only if above items are completed
checkpoint-group |  |  | section | After Erection
checkpoint-status |  |  | checkpoint | Flooring system installed as per shop drawings. Confirm all set outs are correct
label | 198081cf-1aee-4460-b844-48e8b8489456 |  | note | Method - Visual.
checkpoint-status |  |  | checkpoint | End bearing is achieved
label | 50488491-ab27-41a4-9982-e71646bfa4ca |  | note | Acceptance Criteria - As per shop drawing requirements
label | 21a7aa0e-c3b0-4bf0-a998-7c5a93c24ad4 |  | note | Method - Approval
checkpoint-status |  |  | checkpoint | Shear Studs
label | 91652edf-8967-4dc1-977a-0bd452ead741 |  | note | Acceptance Criteria - As per shop drawings and specifications
checkpoint-status |  |  | checkpoint | Third inspection completed if required
label | 51afd004-ca73-48ef-8c9d-5f7eeb7c53bd |  | note | Acceptance Criteria - As required (e.g. shear studs)
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | SIGN OFF HOLD POINT – SUBCONTRACTOR SIGN OFF RECEIVED
checkpoint-group |  |  | section | Formwork Tasks
checkpoint-status |  |  | checkpoint | Inspect formwork is secure, straight and true
checkpoint-status |  |  | checkpoint | Construction joint installed as per plans / agreed methodology.
checkpoint-status |  |  | checkpoint | Set downs and falls as per documentation
checkpoint-status |  |  | checkpoint | Plug all gaps
checkpoint-group |  |  | section | Reinforcing Tasks
checkpoint-status |  |  | checkpoint | Confirm all starter bars reinforcing have been installed as per shop drawings and specification (size/grade/type/lap)
text | 8ebb76d0-baff-4b2f-b96a-c272d120e63a |  | textbox | Size:
text | 651ae466-97bd-4cc8-a738-45d159238bdc |  | textbox | Grade:
text | 3e5ca3db-95c7-46ab-923c-c117859a5cd6 |  | textbox | Type:
text | 8ea139d0-4405-4bc1-9cfc-36179c5fb484 |  | textbox | Lap:
text | f4802474-c5e8-419b-b22d-e11d006a547b |  | textbox | Cover:
checkpoint-status |  |  | checkpoint | Confirm starter bars to columns and walls installed in correct location as per shop drawing & specification
checkpoint-status |  |  | checkpoint | Obtain signoff from steel fixer prior to inspection
checkpoint-group |  |  | section | Services & Cast In Item tasks
checkpoint-status |  |  | checkpoint | Confirm any welding is complete and cast in items installed (structural steel/façade/services)
checkpoint-status |  |  | checkpoint | Confirm Services installation is complete and secure (Inspection Plans). Ensure reinforcement out of core concrete zones
checkpoint-group |  |  | section | Third Party Inspection
checkpoint-status |  |  | checkpoint | Engineer Inspection Completed
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | SIGN OFF HOLD POINT – SECONDARY GANELLEN & S/C SIGN OFF RECEIVED
checkpoint-group |  |  | section | Concrete Tasks
checkpoint-status |  |  | checkpoint | Confirm Concrete order/ specification requirements. Including second person measure. Request Strength test as required
checkpoint-status |  |  | checkpoint | Ganellen check on laser set-up for concrete pour off datum
checkpoint-status |  |  | checkpoint | Obtain concrete delivery/supply docket and review
checkpoint-status |  |  | checkpoint | Confirm surface finish is in line with specification
checkpoint-status |  |  | checkpoint | Curing/ monitoring as per specification
checkpoint-status |  |  | checkpoint | Saw cuts as per specification and drawings and drawings
checkpoint-status |  |  | checkpoint | Confirm surfaces have had concrete removed and cleaned for subsequent trade
checkpoint-status |  |  | checkpoint | Post concrete pour survey grid to confirm slab within acceptable tolerances.
checkpoint-status |  |  | checkpoint | Temporary works until slab pour in place and floor cured
label | b52bc307-0345-4f56-b8f1-122a2168b834 |  | note | Acceptance Criteria - As per manufacturers specifications
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Observations
checklist-sectioned |  |  | checklist | Kitchen Joinery |  |  |  |  | Yes | ITP-023A Kitchen Joinery | 612ac5b5-c330-4320-926b-036cda7034c7
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Kickboard to be installed after flooring is completed
checkpoint-status |  |  | checkpoint | Confirm as-built dimensions of space
boolean | 1727664b-b32f-43e4-9dc0-1ac0e7ac4808 |  | tickbox | Bulkhead
boolean | c1fc42e1-da1c-48c1-9583-c99493c497b8 |  | tickbox | Walls – check against shop drawings
checkpoint-status |  |  | checkpoint | Confirm all services installed and undamaged
checkpoint-status |  |  | checkpoint | Slab clean, free of debris and even
checkpoint-status |  |  | checkpoint | First coat of painting complete
holdpoint |  |  | signoff | HOLD POINT – proceed once above tasks have been completed
checkpoint-group |  |  | section | Pre-Installation
checkpoint-status |  |  | checkpoint | Ensure access requirements through site are clear and accessible
checkpoint-status |  |  | checkpoint | Entry into apartment confirmed
checkpoint-status |  |  | checkpoint | Upload apartment specific shop drawings
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Site measure bench tops / trim on site
checkpoint-status |  |  | checkpoint | Second fix services
boolean | 4d2c8b5a-609c-4812-a2d9-3d9f4e616532 |  | tickbox | Electrical
boolean | 48a9a7f0-10a4-4392-973a-004ac044a132 |  | tickbox | Mechanical
boolean | 119751a5-d18a-490d-abda-2c48f3d41316 |  | tickbox | Hydraulics
checkpoint-status |  |  | checkpoint | Install doors / draws
checkpoint-status |  |  | checkpoint | Check operation of all hinges
checkpoint-status |  |  | checkpoint | Confirm alignment of doors / draws
checkpoint-status |  |  | checkpoint | Subcontractor ITP uploaded
checkpoint-status |  |  | checkpoint | Protection installed
checkpoint-status |  |  | checkpoint | Splashback installed
checkpoint-status |  |  | checkpoint | Architectural inspection completed
holdpoint |  |  | signoff | HOLD POINT – GANELLEN to Inspect
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | P - | itp |  |  |  | Yes | Add Precast Panel QA | 66313b9e-fc24-43d9-b4d1-ef2ae024558b
checkpoint-group |  |  | section | Fabrication Tasks
checkpoint-status |  |  | checkpoint | Confirm all shop drawings submitted are approved.
checkpoint-status |  |  | checkpoint | Confirm that structural engineer has been notified of pour schedule / programme for required inspections prior to any fabrication for confirmation of bar size, layout and cover etc..
checkpoint-status |  |  | checkpoint | Remedials completed from engineers inspection.
checkpoint-status |  |  | checkpoint | Check all cast ins are in correct location (e.g. weld plates and inserts).
checkpoint-status |  |  | checkpoint | Post pour panel finish accepted
boolean | 960ef329-4b93-4039-ab23-a83ba6ca1628 |  | tickbox | Attach photo
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT – proceed only if items above are completed
checkpoint-group |  |  | section | Materials Receiving Tasks
checkpoint-status |  |  | checkpoint | Confirm that materials delivered to site are in conformance with drawings and specification
boolean | a8789353-43c1-40d8-ab37-dd642265cd8a |  | tickbox | Attach panel certificate where required
checkpoint-status |  |  | checkpoint | Confirmed site unloading and set down / storage of materials.
checkpoint-status |  |  | checkpoint | Confirm all panels are undamaged.
boolean | 20fba1d9-22de-4138-9288-12bef254c23e |  | tickbox | Attach photo
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT – proceed only if items above are completed
checkpoint-group |  |  | section | Pre - Erection Tasks
checkpoint-status |  |  | checkpoint | Check all dowels and starters are as per shop drawings
checkpoint-status |  |  | checkpoint | Base level / Setting out checked. Verify setting pads / shims are correct material
checkpoint-status |  |  | checkpoint | Confirmed construction sequencing / handling and lifting points correctly located and to correct loading factor.
checkpoint-status |  |  | checkpoint | Ensure all props are readily available prior to install
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT – SECONDARY GANELLEN SIGN OFF REQUIRED
checkpoint-group |  |  | section | Erection Tasks
checkpoint-status |  |  | checkpoint | All shim packers in place as per drawings. Confirm check on dry packing.
checkpoint-status |  |  | checkpoint | Intermittently check verticality, alignment and level as panels progress including dowel pins
checkpoint-status |  |  | checkpoint | Check all temporary bracing as per shop drawings and Engineers requirements
checkpoint-status |  |  | checkpoint | Obtain any sign off necessary from Structural Engineer prior to grouting. Attach certificate- See specification for requirement
checkpoint-group |  |  | section | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT – SECONDARY GANELLEN SIGN OFF REQUIRED
checkpoint-group |  |  | section | Erection Tasks Cont.
checkpoint-status |  |  | checkpoint | Confirm all grouting complete – (perform check to confirm full depth)
checkpoint-status |  |  | checkpoint | Check all joint and connection details as per drawings. (rebar, weld and cast in-situ joint connections)
checkpoint-group |  |  | section | Final Inspection Tasks
checkpoint-status |  |  | checkpoint | All defects complete and signed off, also check that no visible cracks or damage
folder-progress |  | Unknown tags: itp | checklist | Insitu Concrete Checklist - | itp |  |  |  | Yes | Add Insitu Concrete Pour Checklist | 983e38dc-d135-4bd4-9fc0-53e1d0153ed8
checklist-flat |  |  | checklist-flat | Pre-commencement Tasks
checklist-flat |  |  | checklist-flat | PHOTO HOLD POINT
checklist-sectioned |  |  | checklist-sectioned | Pre-pour Tasks
checklist-flat |  |  | checklist-flat | HOLD POINTS
checklist-flat |  |  | checklist-flat | Placement
checklist-flat |  |  | checklist-flat | Concrete Tasks
checklist-sectioned |  |  | checklist | Mechanical Services First Fix Checklist | itp |  |  |  | Yes | 04) Add Mechanical ITP | 992d36f1-ebf3-4088-a670-336949896444
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any duct penetrating fire-rated walls or shafts are sealed/fire rated to manufacture spec
checkpoint-status |  |  | checkpoint | Confirm access for fire damper adequate i.e. access panel in duct or access panel.
checkpoint-status |  |  | checkpoint | Confirm fire damper installed in line of wall.
checkpoint-status |  |  | checkpoint | Confirm fire dampers installed as per manufacturer’s requirement and have access panels
checkpoint-status |  |  | checkpoint | Fire damper approval. Data sheet cited and signed.
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to Acoustic Requirements
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Acoustic Requirement
checkpoint-status |  |  | checkpoint | Confirm that the AC fan coil unit is vibration isolated with in shear rubber mount or springs from the structure and ductwork
checkpoint-status |  |  | checkpoint | Confirm toilet/laundry/kitchen exhaust fans are vibration isolated with in shear rubber mounts
checkpoint-status |  |  | checkpoint | Confirm sheet metal ductwork has inner acoustic lining if required
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to Mechanical Services
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Performance Requirements - Prior to Sheeting Walls
checkpoint-status |  |  | checkpoint | Confirm all flexible and sheet metal ducting has been installed as per drawings
checkpoint-status |  |  | checkpoint | Confirm wiring of AC controls are located as per architectural requirements.
checkpoint-status |  |  | checkpoint | Confirm all supply and return piping from riser to FCU in place and charged.
checkpoint-status |  |  | checkpoint | Confirm no flexible ductwork is torn or damaged.
checkpoint-status |  |  | checkpoint | Confirm sealing of flexible connections between kitchen/ toilet exhaust fan and metal ducting (mechanically fixed required).
checkpoint-status |  |  | checkpoint | Confirm electrical panel and filters are accessible on FCU from access panel for future inspections.
checkpoint-status |  |  | checkpoint | Confirm spreaders are installed to flexible duct hanging system to prevent squashing of flexi.
checkpoint-status |  |  | checkpoint | Confirm all equipment is wired and complete (Ready for making active).
checkpoint-status |  |  | checkpoint | Confirm all condensate drains and trays (incl. safety tray have been connected to hydraulic wastes and wet tested.
checkpoint-status |  |  | checkpoint | Confirm all refrigerant or condenser water testing required has been carried out (Attach test sheet). Insulated as required.
checkpoint-status |  |  | checkpoint | Confirm all ceiling and bulkhead plenum boxes have been installed as per RCP drawings. crosscheck with windows and facade drawings
checkpoint-status |  |  | checkpoint | Confirm access panel locations marked out and identified on slab below (review arch RCP location). Ensure clear access to controls and filters.
checkpoint-status |  |  | checkpoint | Confirm all pipework is supported correctly with uni-strut/timber blocks/ saddles and insulation. Drainage has fallen to tundish.
checkpoint-status |  |  | checkpoint | Confirm all Dampers are fully open.
checkpoint-status |  |  | checkpoint | Check quality and position of electronic dampers and controls.
checkpoint-status |  |  | checkpoint | Confirm type and colour of external grill and louvre is fit for purpose, check all penetrations
checkpoint-status |  |  | checkpoint | Check paint specs and fixing methodology for external louvres/grills
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
label | 5bc5b1ca-f4b3-45cd-8c90-2d6bb59e9482 |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | SVR: |  |  |  |  | Yes | Add SVR | 9db656e7-a979-4e1c-9db0-40f2c5bf5600
checkpoint-group |  |  | section | SVR Details
checkpoint-status |  |  | checkpoint | SVR Details Complete
text | d6eed151-0e5b-4167-aec8-7d72ada85c3b |  | textbox | Date
text | c42bc9c5-b27a-420f-b4ef-aff104f81f3f |  | textbox | Area(s)
checklist-flat |  |  | checklist | Minor Variation - |  |  |  |  | Yes | Add Council Minor Variation Checklist | a6447db9-6962-4a5d-96ce-c6be91a8c9aa
checkpoint-status |  |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | d83c76ad-c2c4-422a-b3d0-5e46ac4be24f |  | note | PASS above checkpoint when variation is approved
label | ab21c4bc-c773-43ee-88d7-f338c674ee92 |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of application
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Reason for application
text | 4ce69a81-cba4-4eac-b963-ff28392bbaf5 |  | textbox | Date of approval / acceptance
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council approval of minor variation attached
checklist-sectioned |  |  | checklist | Fire Services Rough In Checklist | itp |  |  |  | Yes | 01) Add Fire ITP | a801c7f8-1816-450a-8dac-766e985dd202
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any pipework and cabling penetrating partition walls are fire sealed
checkpoint-status |  |  | checkpoint | Confirm pipe works are supported, anchors hangers and clips
checkpoint-status |  |  | checkpoint | Confirm sprinkler pipework installed as per drawings.
checkpoint-status |  |  | checkpoint | Confirm if any drenchers required have been installed.
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off/Subcontractor ITP Sign-off
label | 5bc5b1ca-f4b3-45cd-8c90-2d6bb59e9482 |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Confirm apartment and balcony sprinkler head brackets are installed to ceiling grids.
checkpoint-status |  |  | checkpoint | Confirm pipework pressure test (Attach subcontractor sign off).
checkpoint-status |  |  | checkpoint | Confirm installation for fire electrical speakers and detectors.
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to Plasterboard Sheeting
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Façade - Roofing ITP |  |  |  |  | Yes | Façade - Roofing ITP | abb55615-2069-4190-aef6-abf2d095ffcf
checkpoint-group |  |  | section | Pre-Construction Tasks
checkpoint-status |  |  | checkpoint | Manufacturers information and samples provided for approval where required
checkpoint-status |  |  | checkpoint | Confirm all height access requirements and check against contractors method statement
checkpoint-group |  |  | section | Materials Receiving Tasks
checkpoint-status |  |  | checkpoint | Confirm that materials delivered to site are in conformance with drawings and specification documentation. Q.A. sheets (if required) must be signed off during delivery
checkpoint-group |  |  | section | Pre-Installation Tasks
checkpoint-status |  |  | checkpoint | Work area and surfaces ready to commence work. Structure inspected and accepted. Hot works permit issued where necessary. Safe access has been provided to sub-contractor to commence works.
checkpoint-status |  |  | checkpoint | Confirm all gutter lengths / heights and all outlets / overflows in correct locations. Also confirm all outlets are correct diameter and are fully sealed and tested. Confirm all penetrations in correct locations.
checkpoint-group |  |  | section | Installation Tasks
checkpoint-status |  |  | checkpoint | Confirm all insulation requirement have been met as per specification, confirm install and required separations have been adhered to
checkpoint-status |  |  | checkpoint | Carry out staged inspections to confirm all materials are fitted undamaged and all fixings / flashings detail correct
checkpoint-status |  |  | checkpoint | Confirm all substrate is in place for any additional fixings (safety, aerials, fixings, flashings, service penetrations, etc.)
checkpoint-status |  |  | checkpoint | Check all flashing / upstand waterproofing details are in accordance with specification and drawings
checkpoint-status |  |  | checkpoint | Confirm all gutters have correct clear width (sheeting overhand) and all outlets formed correctly. Visual check only
checkpoint-status |  |  | checkpoint | Confirm all connection details are true and correct (roof and parapet details)
checkpoint-status |  |  | checkpoint | Fall Arrest System installed
checkpoint-status |  |  | checkpoint | Roof cleaned down of all excess materials and left in final condition
checkpoint-group |  |  | section | Final Inspection Tasks
checkpoint-status |  |  | checkpoint | All defects complete and signed off and also check for no visible damage
checkpoint-status |  |  | checkpoint | Check watertightness of installed roof as per NZ standard. Check all screws in place
checkpoint-status |  |  | checkpoint | Confirm correct fixings used in regard to wind loads, weatherproofing, etc.
checkpoint-status |  |  | checkpoint | Sign Off
text | 7df99c7c-0564-47ad-b17c-1de9a7ded8ee |  | textbox | Viewed By:
checklist-sectioned |  |  | checklist | Hydraulic Rough In Checklist | itp |  |  |  | Yes | 02) Add Hydraulic ITP | abc87cc6-8a5c-47dc-b88d-0eb5ea0858dc
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Intumescent fire collars inspected and installed as per manufacturers details
checkpoint-status |  |  | checkpoint | Fire collars sealed around penetrations
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to Hydraulic Services
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Hydraulic Servies - Prior to Sheeting Walls
checkpoint-status |  |  | checkpoint | Confirm all materials comply with specs.
checkpoint-status |  |  | checkpoint | All pipes supports, anchors, hangers and clips
checkpoint-status |  |  | checkpoint | Confirm all pipes not damaged or leaking prior to lagging and joints are glued
checkpoint-status |  |  | checkpoint | All pipe work acoustically lagged and wrapped in accordance with Acoustic Specification.
label | 73f66d99-8468-40b8-9717-4228be51904d |  | note | Confirm hot water/cold water supply to:
boolean | 4ff30b6f-cda4-428d-93e1-5e2fa916b3f1 |  | tickbox | Kitchen
boolean | 53eb2fb4-3d82-40ea-8c0d-de1953cd9546 |  | tickbox | Bathroom
boolean | e6937cf8-3d9f-47e3-996a-7a9e190ba129 |  | tickbox | Ensuite
boolean | e1a4546d-c9e9-40ea-9877-f72c74473932 |  | tickbox | Laundry
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off/Subcontractor ITP Sign-off
label | 5bc5b1ca-f4b3-45cd-8c90-2d6bb59e9482 |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Confirm water and gas point
checkpoint-status |  |  | checkpoint | Confirm kitchen rough in is as per kitchen shop drawing.
checkpoint-status |  |  | checkpoint | Confirm location of gas meter as per Kitchen Shop Drawing.
text | 0a49ed6b-790b-4faf-8634-2843c4decbfd |  | textbox | Kitchen Type:
text | 4263b54e-1e80-4b88-88e2-87f6ebc5ef0c |  | textbox | Drawing #
checkpoint-status |  |  | checkpoint | Confirm A/C tundish location has been supplied and trap prefilled.
checkpoint-status |  |  | checkpoint | Confirm the following heights and location from architectural detail drawings:
text | e737fa03-0809-4e45-abf6-4728294767fc |  | textbox | Shower head:
text | e7abd5a9-5725-4224-87f6-b261b7b93f66 |  | textbox | Shower mixer:
text | ae33a55b-0dae-4942-b072-649cf6729ffd |  | textbox | Shower drain:
text | 96cb74f7-413f-4d8a-99e5-812cc148a7a6 |  | textbox | Bathroom basin:
text | 22ff70a5-82e9-4a33-8cd8-443cce43274c |  | textbox | Bathroom drain:
checkpoint-status |  |  | checkpoint | Confirm following test been undertaken (attached sign off)
boolean | c791edd4-6f50-4431-83c7-450bcb0795e1 |  | tickbox | Pressure test for water and gas
boolean | f692bbc6-608b-4f59-a36f-54b724923f00 |  | tickbox | Drainage pipework
checkpoint-status |  |  | checkpoint | Confirm supply pipes have been charged
checkpoint-status |  |  | checkpoint | Confirm rough-in of wet area fixtures as per layout.
checkpoint-status |  |  | checkpoint | Confirm bath has been installed level and correct RL and protected.
checkpoint-status |  |  | checkpoint | Confirm bath protection
checkpoint-status |  |  | checkpoint | Confirm downpipe type, color and location
checkpoint-status |  |  | checkpoint | Confirm tap location to balcony's
checkpoint-status |  |  | checkpoint | Confirm drainage accommodates mech condensate pipe
checklist-sectioned |  |  | checklist | Masonry / Blockwork – CF King | itp |  |  |  | Yes | Masonry-Blockwork ITP | af8125be-1d94-4a9b-8c76-8452061a51b5
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Inspected and accepted the work area and surfaces and structure ready to commence work.
checkpoint-status |  |  | checkpoint | Confirm set out of walls as per Architectural Drawings.
label | 88f08b21-ec3f-4c41-8b7b-c44dfc1f9797 |  | note | Records - Architectural Drawings
checkpoint-status |  |  | checkpoint | Confirmed Site storage requirements for bricks/blocks, mortar and sundries.
checkpoint-status |  |  | checkpoint | Confirm starter bars / dowels are in the correct position.
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | All damp proof course built in.
checkpoint-status |  |  | checkpoint | All flashings and wall ties built in.
checkpoint-status |  |  | checkpoint | All cavities clean and clear.
checkpoint-status |  |  | checkpoint | Gaps closed below soffit overhead beams.
checkpoint-status |  |  | checkpoint | Completed sills and header courses.
checkpoint-status |  |  | checkpoint | Final brick/block clean.
checkpoint-status |  |  | checkpoint | Reinforcing completed as per drawings
checkpoint-status |  |  | checkpoint | Cast-in items installed as per drawings
checkpoint-status |  |  | checkpoint | Engineers sign off completed
checkpoint-group |  |  | section | Concrete Works
checkpoint-status |  |  | checkpoint | Correct mix ordered as per specification
label | 0881fbe6-ab9d-4948-a2ae-6c7bafeb1cfd |  | note | Records - Concrete Dockets
checkpoint-status |  |  | checkpoint | Bond beams poured as per drawings
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
checkpoint-status |  |  | checkpoint | Subcontractor ITP Signoff
label | 5c4e37d0-0c64-489f-b1f0-7cf8b4ef176d |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Trade Contractor Signoff
checkpoint-status |  | Not allowed as a child of checklist-sectioned. | checkpoint | Subcontractor ITP Signoff
label | 5c4e37d0-0c64-489f-b1f0-7cf8b4ef176d |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Trade Contractor Signoff
checklist-sectioned |  |  | checklist | Waterproofing – Internal Areas |  |  |  |  | Yes | ITP-024A Waterproofing – Internal Areas | d65e3a55-8ff1-432b-86b8-663fde6d1c3e
checkpoint-group |  |  | section | Surface Preparation
checkpoint-status |  |  | checkpoint | Floor wastes are free of waste material and are in correct location, flush and grinded down.
checkpoint-status |  |  | checkpoint | Confirm concrete floor slab 100% clean, free of water, dirt dust.
checkpoint-status |  |  | checkpoint | Confirm primer (Ardex multiprime) used to floors and walls is as per manufacturers requirements.
boolean | ce7c722e-dc25-4faf-8e93-eb9460bab1b2 |  | tickbox | Minimum drying time 1 hour
boolean | 86396efc-1929-4d4a-b552-3d56f7f118b6 |  | tickbox | 1 litre = 6m2
checkpoint-status |  |  | checkpoint | Correct fall has been made in wet areas. Levelling compound Ardex LQ92
boolean | e9e65ce3-63f4-4bcb-9ef5-92dd04cfc194 |  | tickbox | Do not use below 10° or above 35°
boolean | ebebf551-b62e-4484-8e04-713d8bbcb60b |  | tickbox | Do not exceed 25mm
boolean | b8c24b3d-035c-4d60-a24a-534146a4cecc |  | tickbox | 4 litres of water per 20kg bag
boolean | 1e6e1261-066f-4a96-888f-0bc3198b72ec |  | tickbox | Aggregate can be added for larger depths
checkpoint-status |  |  | checkpoint | Confirm RLs on levelling compound in relation to floor wastes/falls/door clearance
holdpoint |  |  | signoff | HOLD POINT - acoustic map
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm sealant at wall/floor junction and wall/wall junction, as per manufacturer’s requirements.
checkpoint-status |  |  | checkpoint | Use neutral cure silicone to perimeter as bond breaker and any gaps
checkpoint-status |  |  | checkpoint | Use Ardex x56 adhesive – apply with 3mm notch towel
checkpoint-status |  |  | checkpoint | Install Ardex DS40 acoustic matt
checkpoint-status |  |  | checkpoint | Lay fleece side into mortar bed
checkpoint-status |  |  | checkpoint | Lay in brick pattern
holdpoint |  |  | signoff | HOLD POINT - WATERPROOFING
checkpoint-status |  |  | checkpoint | Floor membrane:
checkpoint-status |  |  | checkpoint | Floors and upturn 150mm at wall as per manufacturer’s requirements.
boolean | 88bcfedf-abe7-4141-a97a-257b25326126 |  | tickbox | Install first coat to floors and upturn 150mm at walls and 800mm in shower recess
checkpoint-status |  |  | checkpoint | Install second coat min. 2 hours after first product. Ardex WPM 002 0.6 – 0.9mm per coat
checkpoint-status |  |  | checkpoint | Apply neutral cure sealant to vertical and horizontal joints/corners
checkpoint-status |  |  | checkpoint | Dress into floor waste
holdpoint |  |  | signoff | HOLD POINT - flood testing
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Flood testing:
checkpoint-status |  |  | checkpoint | Fill floors with water to height of door angle
checkpoint-status |  |  | checkpoint | Leave for 24 hours
checkpoint-status |  |  | checkpoint | Confirm no leaks
checkpoint-status |  |  | checkpoint | If leaks were found – re-tank and confirm which area and flood test again.
checkpoint-status |  |  | checkpoint | Subcontractor ITP received
holdpoint |  |  | signoff | HOLD POINT - OK to proceed
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Waterproofing |  |  |  |  | Yes | ITP-012 Waterproofing | d99306ca-f344-40f7-84db-688861aaa988
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Confirm RL of subgrade and all compaction tests completed.
checkpoint-status |  |  | checkpoint | Confirm subgrade/substrate is flat, level and free of any sharp protrusions, signed off by water proofing contractor.
checkpoint-status |  |  | checkpoint | Confirm substrate material complies to specification
checkpoint-status |  |  | checkpoint | Drawing attached of area where works are to be completed including grid lines for reference.
checkpoint-status |  |  | checkpoint | Confirm all penetrations are present and in the correct location, Drawing attached.
checkpoint-status |  |  | checkpoint | Confirm all installer’s tickets are on record.
checkpoint-status |  |  | checkpoint | Confirm drainage ITP is signed off and completed.
checkpoint-status |  |  | checkpoint | Confirm falls to waste/outlets have been formed.
checkpoint-status |  |  | checkpoint | Confirm weather is appropriate for installation.
holdpoint |  |  | signoff | HOLD POINT – In ground Drainage ITP signed off and completed.
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Have correct minimum lap been completed consistently and heavy rolled/welded?
checkpoint-status |  |  | checkpoint | Have sealant to joints in substrate been applied to specification
checkpoint-status |  |  | checkpoint | Have pile cap details been followed as per drawing and specification.
checkpoint-status |  |  | checkpoint | Have Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
checkpoint-status |  |  | checkpoint | Have penetration (pipe, soak pit, overflow) detail been followed, fillet installed and liquid membrane/sealants in place as per drawing and specification.
checkpoint-status |  |  | checkpoint | Has protection sheet been installed where needed
checkpoint-status |  |  | checkpoint | Have membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct primer or adhesives used as per specification.
checkpoint-status |  |  | checkpoint | Cap sheet and base sheets fully boned together, no areas of delamination.
checkpoint-status |  |  | checkpoint | No sign of overheating/excessive bitumen bleed
checkpoint-status |  |  | checkpoint | Cap sheet and base sheets laps offset satisfactorily, lay build up to specification
checkpoint-status |  |  | checkpoint | Has membrane been extended for lapping details
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Has membrane been inspected for imperfections and signed off by subcontractor.
checkpoint-status |  |  | checkpoint | Is all installation as per manufacturer’s specifications and NZ standards?
checkpoint-status |  |  | checkpoint | Has Membrane been cleaned and all patches completed?
checkpoint-status |  |  | checkpoint | Attach subcontractor/ Supplier QA documents.
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Below Ground Services | itp |  |  |  | Yes | Below Ground Services ITP | e0bcbe9e-2a6d-4dcf-9652-823a76808e39
checkpoint-group |  |  | section | Installation Tasks
checkpoint-status |  |  | checkpoint | Confirm detailed survey of existing ground levels and location of. all exisiting services has been carried out
checkpoint-status |  |  | checkpoint | Confirm permit to dig documentation is on site, and required authorities have been notified
checkpoint-status |  |  | checkpoint | Confirm RL and location of trenches (attach marked up services plan for records)
checkpoint-status |  |  | checkpoint | Confirm layout, runs and invert levels of all below ground service runs
checkpoint-status |  |  | checkpoint | Ensure temporary pumps are in place as required and that no discharge of water onto public right of way. Check specification for requirements
checkpoint-status |  |  | checkpoint | Ensure any conducts / power feeds required are installed
checkpoint-status |  |  | checkpoint | Confirm material / diameter / branch connections/joints of all pipework as per specification
checkpoint-status |  |  | checkpoint | Confirm correct bedding material being used under all pipework
checkpoint-status |  |  | checkpoint | Inspection and sign off by consultant / Council placement, line & level, cleanliness of all pipework as works progress. Ensure photographic evidence on file
checkpoint-status |  |  | checkpoint | Carry out all tests and inspections of exposed works including signoff as necessary
checkpoint-status |  |  | checkpoint | HOLD POINT - Ganellan as-built check of line / level and position prior to backfilling
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Ensure all fill materials is in accordance with specifications
checkpoint-status |  |  | checkpoint | Ensure all warning tape installed as per local authority requirements
checkpoint-status |  |  | checkpoint | Ensure no reinforement is altered during installations of services
checkpoint-group |  |  | section | Post Installation Tasks
checkpoint-status |  |  | checkpoint | Ensure all areas level and clean with no open trenches or spoil
checkpoint-status |  |  | checkpoint | Ensure all upstands are capped and clearly marked as per as-built drawing on record for future connections
checkpoint-status |  |  | checkpoint | Confirm all tests carried out to satisfactory results and all records provided to Engineer for sign-off as per contract specification
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign off
checkpoint-status |  |  | checkpoint | Ganellen Sign Off
checklist-sectioned |  |  | checklist | Electrical/Security/Data First Fix Checklist | itp |  |  |  | Yes | 03) Add Electrical ITP | e5d726b4-9efb-41f6-ab71-87e66dbef197
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any cable/conduit penetrating Fire rated walls are sealed both sides with Intumescent fire mastic to spec.
checkpoint-status |  |  | checkpoint | Confirm any cable/conduit penetrating Fire rated walls Sign off by Fire subcontractor
checkpoint-status |  |  | checkpoint | Confirm cabling not bunched excessively through penetration.
checkpoint-status |  |  | checkpoint | Confirm fire rated boxes installed and sealed to approve detail.
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to electrical services
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Electrical Services
checkpoint-status |  |  | checkpoint | Confirm Cable tray support
checkpoint-status |  |  | checkpoint | Confirm height and location of all outlet from architect’s drawings. TV/Data/Power/Light/security
checkpoint-status |  |  | checkpoint | Confirm wiring for switches are in place.
checkpoint-status |  |  | checkpoint | Confirm TV and GPO locations in place.
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off/Subcontractor ITP Sign-off
label | 5bc5b1ca-f4b3-45cd-8c90-2d6bb59e9482 |  | note | The subcontractor acknowledges that all work and documentation provided has been competed in accordance with the relevant drawings and specifications, and that all information provided in the Inspection Test Plan (whether on site/offsite/hard copy/Conqa) is true and correct.
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Confirm location of bathroom GPO has been coordinated with joinery shop drawings.
checkpoint-status |  |  | checkpoint | Confirm light allocations as per the drawings.
checkpoint-status |  |  | checkpoint | Confirm data cable is installed.
checkpoint-status |  |  | checkpoint | Confirm location of DB board has been coordinated with kitchen shop drawings.
checkpoint-status |  |  | checkpoint | Confirm intercom wiring in place.
checkpoint-status |  |  | checkpoint | Confirm wiring to kitchen appliances in place as per kitchen joinery shop drawing:
checkpoint-status |  |  | checkpoint | Confirm wiring to external lights confirmed.
checkpoint-status |  |  | checkpoint | Confirm wiring to FCU and exhaust motors in place.
checkpoint-status |  |  | checkpoint | Confirm fire speaker cabling is installed.
checkpoint-status |  |  | checkpoint | Confirm adaptable unit requirements if applicable.
checkpoint-status |  |  | checkpoint | Confirm security cabling is installed.
checklist-sectioned |  |  | checklist | Insitu Piles | itp |  |  |  | Yes | Insitu Piles Checklist | e6594840-9d48-43c7-9771-b3b421261b4b
checkpoint-group |  |  | section | Preliminary Tasks
checkpoint-status |  |  | checkpoint | Confirm Pile installation plan including methodology, material and equipment submitted
label | ed02e98b-d35f-43bf-a914-962102a3d166 |  | note | Sub-Contract signing
checkpoint-group |  |  | section | Site Start Up Tasks
checkpoint-status |  |  | checkpoint | Confirm full services and utilities check by subcontractor. Permit to work in place
label | 6d5aa22d-2520-449e-a4d3-dd2b59e43529 |  | note | Prior to mobilization
checkpoint-status |  |  | checkpoint | Confirm an adequate site surface has been established for a safe working platform and check periodically once installation is underway.
label | 4a4a32b2-7711-4715-80ff-e5d2a1c533fc |  | note | 1 week prior and intermittently after
checkpoint-status |  |  | checkpoint | Confirm all piles to be set out in accordance with design requirements and appropriate procedures taken to protect adjacent services, structures etc.
label | cb9f67b9-b307-4209-bfe4-85f47980787a |  | note | Prior to installation of 1st pile
checkpoint-group |  |  | section | Construction Tasks
checkpoint-status |  |  | checkpoint | Confirm correct equipment is in place to check the verticality and position of rig, and that the mast is vertical in both axes prior to construction of each pile
label | 876a0bae-1f4a-4834-b0b6-92766746b04c |  | note | Prior to installation of 1st pile and periodically after
checkpoint-status |  |  | checkpoint | Confirm pile construction has not been carried out within the specified distance of newly cast piles until concrete has attained the strength specified. Refer to installation methodology provided.
label | 596c3123-498d-4d89-8f5b-046dccaed3c9 |  | note | Each pile
checkpoint-status |  |  | checkpoint | Confirm that pile depth has been checked at completion of boring. Toe level to at or below target depth
text | 577706e0-260d-422c-858c-74604a53a6bf |  | textbox |  |  |  | m depth
label | 91e7a94c-69f2-412a-af0d-dcf884a4f315 |  | note | Each pile
checkpoint-status |  |  | checkpoint | Sight delivery dockets to confirm all in accordance with engineers specification.
label | 9f3413eb-89f6-4b78-a094-d7dd6b5979b3 |  | note | Each concrete delivery
checkpoint-status |  |  | checkpoint | Confirm that subcontractor has checked that steel is not excessively rusted, cage has been sturdily constructed and that the correct cage has been installed for each pile.
label | d43ba92d-d206-443e-aa42-9b280a238098 |  | note | Each reinf. Cage batch
checkpoint-status |  |  | checkpoint | Dimensional check, length, bar diameter, nr of bars. Make sure compliant with technical package.
label | d53567b8-a0a8-4d29-a471-6d2547cf41bc |  | note | Random control check
checkpoint-status |  |  | checkpoint | CCTV of piles conducted prior to pour. Engineer notified prior to camera survey.
label | 60fb71c8-cc0b-4c17-a995-d55e0b761dff |  | note | Random control check
checkpoint-status |  |  | checkpoint | Check cage has been installed at the correct level and is centralised, ensure cover requirements are met. All as per specification and documents.
label | dfac77ab-4de3-4a67-bc39-8f0dcd4a3a98 |  | note | Random control check
checkpoint-status |  |  | checkpoint | Obtain Engineers site reports and signoff as required.
label | 33187509-e334-4c92-a40e-97d4db504f31 |  | note | As per Contract
checkpoint-status |  |  | checkpoint | Confirm top of piles have been trimmed to elevations indicated on design drawings prior to construction of pile caps.
label | 7cfa3530-415a-4824-b8e6-37b5a7107a60 |  | note | After completion of installation
checkpoint-group |  |  | section | Post Construction Tasks
checkpoint-status |  |  | checkpoint | Obtain as-built drawings to confirm grid layout is completely in accordance with all drawings and specifications (all within tolerance)
label | df83e005-7ec3-4f93-b627-a098fad80bab |  | note | After completion
checkpoint-status |  |  | checkpoint | All data and records required provided to Structural Engineer after completion of pile installation (as per required contract specification). Include any Engineer’s site reports and sign off.
label | bd8de0ca-97c8-4b2e-8556-adaff9e49bf9 |  | note | After completion of works
checkpoint-status |  |  | checkpoint | Dynamic pile testing (if required by the contract) carried out as per specification requirements. Written pile test results submitted for acceptance. Obtain sign off from Structural Engineer. (Attach certificate)
label | 4d46f90d-184e-40fc-b475-1e0134d49aa0 |  | note | As per contract requirements
checkpoint-status |  |  | checkpoint | Confirm all inspections as identified on the cover page have been undertaken
label | 836335dd-4580-4abd-b2f2-92e5d733c82a |  | note | After Completion
checklist-flat |  |  | checklist | Remedial: |  |  |  |  | Yes | Add Remedial Observation | eb67332b-741e-4d51-9dbe-0e20c5f492e2
checkpoint-status |  |  | checkpoint | Remedial Complete
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Action Required
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Observation Reference (if applicable)
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Location
holdpoint |  |  | signoff | Request Signoff