## ITP Tree
THE ALBERTON - ITP TREE
| 1. CIVIL |  |  | 2. STRUCTURAL |  |  |  |  | 3. FAÇADE |  |  | 4. SERVICES |  |  |  | 5. FIT-OUT
|  | BUILDINGS (6No.) A - F | a. SUBGRADES |  |  | BUILDINGS (6No.) A - F |  |  |  | BUILDINGS (6No.) A - F |  |  | BUILDINGS (6No.) A - F |  |  |  | BUILDINGS (6No.) A - F
|  | ROADS (4No.) A - D |  |  |  |  | a. FOUNDATIONS |  |  |  | b. ALUMINIUM FRAMED GLAZING
[14 empty] | HOUSES 1 - 121 |  |  |  | HOUSES 1 - 121
|  |  | b. DRAINGE |  |  |  | b. SLABS ON GRADE |  |  |  | c. ALUMINIUM CLADDING
[15 empty] | a. INTERNAL FRAMING / SERVICES / LININGS |  |  |  | a. FRAMING & LININGS
|  |  | c. ROADS |  |  |  | c. SUSPENDED SLABS |  |  |  | d. RENDER TO CONCRETE MASONRY UNITS
b. WET AREAS
[7 empty] | d. BLOCK WALLS |  |  |  | e. BRICK VENEER
c. KITCHENS
[7 empty] | e. RETAINING WALLS & WATERPROOFING | Per Area |  |  | f. FACADE CARPENTRY
d. WARDROBES
[7 empty] | f. STRUCTUAL STEEL |  |  |  | g. CANOPY
e. APPLIANCES
[7 empty] | g. CARPENTRY |  |  |  | h. ROOFS, GUTTERS, CAPPINGS AND FLASHINGS
f. DOORS AND HARDWARE
i. METAL CLADDING
g. FLOORING
b. WATERPROOFING TO BALCONIES
| DEVELOP ITP |  |  |  | HOUSE NUMBERING DISTRIBUTION PER BUILDING:
ITP READY FOR REVIEW
| ITP UPLOADED |  |  |  |  | BUILDING A - 1 - 25
BUILDING B - 26 - 45
BUILDING C - 46 - 71
BUILDING D - 72 - 85
BUILDING E - 86 - 95
BUILDING F - 96 - 121
|  | CIVIL | STRUCTURAL | FAÇADE |  | SERVICES | FIT-OUT |  |  | External works
|  | Groundwork | Blockwork | Aluminium awnings |  | Electrical | Appliances |  |  | Fencing
|  | Drainage | Carpentry | Aluminium Cladding |  | Fire services | Balustrades and hand rails |  |  | Hardscaping
|  |  | Composite flooring | Brickwork |  | Hydraulic | Ceiling Framing |  |  | Landscaping
|  |  | Scaffolding | Grouting and sealant |  | Insulation | Door hardware |  |  | Linemarking
|  |  | Structural steel | Render |  | Interior framing | Doors and frames |  |  | Leterboxes
|  |  | Structure | Windows & Doors |  | Mechanical | Final clean
[6 empty] | Passive fire | Flooring
[6 empty] | Waterproofing | Joinery
Plasterboard, stopping, painting
Roller door
Shower tray
Tiling
Undefloor heating
Wardrobes

## Trade List
TRADE | Subcontractor
Demolition | KIDD
Groundworks
Drainage
Structure & Reinforcement | Conset
Grouting & Sealant | Sunbuild
Blockwork & Brickwork | RGC
Structural Steel | Jaycee
Waterproofing | MPM
Metal Roofing & Cladding | ACMF
Carpentry | FZ Group
Interior Framing - ceiling | Metro
Plasterboard / Stopping / Painting | Steg
Insulation | Goldtex
Awnings | Aluminium Tehcnology
Render | Nexus
Windows & Doors | Lancom
Garage Doors | Glideaway
Doors & Frames | Best Doors
Aluminium GS Door Type | Home Plus
Door Hardware | KnK Hardware
Joinery | Cabtec
Wardrobe | Boston Wardrobes
Metalwork/Letterboxes | Mitre 10
Ballustrades and Handrails | Unex
Carpet and vinyl | Flooring Direct
Shower Tray | Newline
Tiling | Asian Tilers
Composite flooring | Composite Floor Decks Ltd
Appliances Supply & Install | F&P
Hydraulic Services | Express Plumbing
Electrical Services | RSB
Mechanical Services | Airmaster
Underfloor Heating | Warmup
Fire Service | The Fire Guys
Passive Fire
Fencing
Landscaping | Mace
Hardscaping
Scaffold & Propping
Flashings
Surveying | Surveyworx
Site Security | ATF
Linemarking | KP Group Ltd

## 1.a. Subgrades
Subgrade base
Expose building sub-base
Geotech Eng inspection report received- and close-out
Geotech Eng Inspection of sub-base and proof rolling prior to filling
Building Subgrade build-up
GL and datum provided
Geogrid (Tensar TX160) installed as per civil details
Placement of hardfill layer compacted as per design
Drainage piping installed under foundation level
Platforms spot checks heights and location
Subgrade Sign-off
Subgrade QA and test results received
Geotech Eng Inspection of subgrade and proof rolling report received and close-out

## 1b. Drainage
Pre-start
Locates done on site – confirm no clash with pre-existing underground services
Appropriate permits in place
GL and datum provided
Upload drawings / check services depths, confirm location, filling/digging
Clear work area
TA / SSSP documentation in place
Trenching
Delineation of area
Benching appropriate for ground conditions
Safety of trenching conditions and edge protection
Civil Eng inspection report received and close-out if unsuitable subgrade conditions exist
Client notified of rock trenching
Installation
Confirm correct bedding material being used and spot check RL’s
Pipes installed and correct junctions/connections
Civil Eng inspection report received and close-out for first pipe run
Council sign-off through audit system
Backfilling
Appropriate backfill material
Backfill and compact as per Civil spec
Civil Eng inspection report received and close-out
Post backfilling
Internal manhole works
Splitters and benching completed
Civil Eng inspection
Soakholes
Civil Eng Inspection of selection of rock bore installation, report received and close-out
Civil Eng inspection of selected of soakage testing
Council inspection report received and close-out – as-built plan required
Drainage QA and as built received

## 2.a. Footings
Pre-start – HOLD POINT
QA for sub-grade and relevant services received
GL and datum provided
Clear work area
Geotechnical Eng inspection report received and closed-out
Relevant Drawings uploaded
Pre-pour
Formwork signoff/QA
Check levels and dimensions
Waterproof sign off/QA
Reo sign off/QA
Services trade sign off/QA
GN inspection
Details checked
Any CANs
Starters and cover checked
Clean formwork and ready to pour
Structural Eng inspection report received and close-out
Pour sequence mark-up
Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Post pour
Checks
Finish
Levels
Starters
Pour QA received including dockets

## 2.b. Slabs on Grade
Pre-start
Services sign-off
Electrical
Hydraulic
Comms and Fibre
Subgrade sign-off/QA received
Backfill and blinding
GL and datum provided
Clean work area
Pre-Pour
Service trades sign-off/QA
Waterproofing sign-off/QA
DPM including tapes and laps
Formwork signoff/QA
Entrance set-downs
Reo sign off/QA
GN inspection
Details checked
Any CANs
Starters, cover and thickenings checked
Clean formwork and ready to pour
Structural Eng inspection report received and close-out
Pour sequence mark-up
Access/safety/protection
Clear access for trucks/pump
Safe access to all areas of pour
Exposed reo capped
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Post pour
Finish
Levels – surveyor checks
Curing agent
Saw cuts within 24h of pour and slurry removed
Pour QA received

## 2.c. Suspended Slabs
Pre-start
Ea and portal installed
QA/ signoff
Edge protection in place
Access provided
GL and datum provided
Clean work area
Pre-pour
Comfloor sign-off/QA received
Stud testing completed
Propping sign-off/QA received
Services marked out and double mesh
Reo sign-off/QA received
GN inspection
Details checked
Stair opening checked
Starters, cover, Trimmer installed, Nib Reo location
Clean and ready to pour
f. Structural Eng inspection report received and close-out
Access/Safety
Clear access for trucks/pump
Safe access to all areas of pour
Wash up organized
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Screed to falls in balcony
Post pour
Finish
Levels
Curing agent
Pour QA received

## 2.d. Blockwall
Pre-start
Foundation QA
GL and Datum provided
Upload relevant drawings
Check starters
Clean work area
Confirm control joins
During Works
Check reo details
Control joins correct position and construct
Bottom clean-outs for inspection
Check set-out
Pointing of joints quality
Pre-pour (blocks infill)
Reo sign-off/QA
GN Inspection
Details checked
Any CAN's
Starters lengh and cover checked
Clean-outs free of debris and ready to inspect/pour
Structural Eng inspection report received and closed-out
Formwork and clean-out covers in place
Pour sequence mark-up
Documentation reviewed and accepted during Monthly Council Audit
Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
Post-pour
GN Inspection
Finish quality
Correct levels
Correct starters
Block and pour QA received

## 2.e. Retaining walls and waterp
PRE-START
Foudation QA
GL and Datum Provided
Check starters
Clean work area
DURING WORKS
Check reo details
Control joints
Wash-outs
Back of wall flat joints for waterproofing
PRE-POUR
Eng. Inspection report received and closed-out
GN Inspection
Details checked – including minimum laps and starters for upper slabs
Any CANs
Clean wash-outs
Exposed reo capped
POST-POUR
QA and concrete dockets received
Works reviewed and closed-out during Council Monthly Audit
WATERPROOFING
Pre-start
Corners fillets completed
Mortar joints cleaned
Hydraulic pipes protruding wall min 50mm from the bottom and 100mm past wall
Safe access to area
During works
Waterproofing completed
Works protected with Corflute and XPS
Correct lap with DPM at foundation level
Post-works
QA received
Works reviewed and closed-out during Council Monthly Audit

## 2.f. Structure Steel
Pre-start
GL and datum reference provided
Clean work area
Hold Down Bolt As Builts received where necessary
Concrete Founding levels checked
Access/safety/protection
Clear access for crane/installation
Lifting Area Isolated
Hot Works Permit used as required
Installation
Fixings used are as specified on drawings
All bolted/welded connections inspected and are as per drawings
All necessary works are completed to allow grouting of baseplates/fixing tabs
HOLD POINT: Steelwork checked for plumb, level and alignment
Drypacking/Grouting of base plates and fixing tabs complete
Touch up painting is complete WHERE REQUIRED
Post installation
All associated CANs/Inspection Reports are actioned and closed out
Subcontractor QA attached
Mill Certificates
Weld Testing
Paint Testing

## 2.g. Structure Carpentry
MIDFLOOR FRAMING
PRE-START
GL and datum reference provided
Clean work area
Structural Steel & Blockwork Handed Over
ACCESS/SAFETY/PROTECTION
GF Slab cleared for midfloor framing installation
Edge protection in place for Midfloor Ply Install
INSTALLATION
Fixings used are as specified on drawings
Midfloor Joists installed at 400mm max centres and coordinated with services
Setout/handing of stair void correct
Height check completed
Bolt heads recessed through stair void
Joist Hangers installed
Nailon plates / strapping installed to Double Joist Chord as per drawings
Blocking installed
Ply installed and fixing pattern correct
POST-INSTALLATION
All associated CANs/Inspection Reports are actioned and closed out
Subcontractor QA received
ROOF FRAMING
PRE-START
GL and datum reference provided
Clean work area
Structural Steel & Blockwork Handed Over
ACCESS/SAFETY/PROTECTION
Scaffold/Mobile scaffold suitable for roof framing to commence
INSTALLATION
fixings used are as specified on drawings
Ribbon plates installed and height check completed
Roof rafters installed at correct centres
Joist hangers & Blocking installed
HOLD POINT – Ribbon Plate Fixings in place prior to scaffold drop
Double Rafter installed at roof edges
150mm offset rafter installed for barge fixing
Bracing Straps & Roof Space Braces Installed
POST-INSTALLATION
All associated CANs/Inspection Reports are actioned and closed out
Subcontractor QA received

## 3f. Facade Carpentry
EXTERNAL FRAMING AND RAB
PRE-START
GL and datum reference provided
Clean work area
Structural Steel Handed Over
ACCES/SAFETY/PROTECTION
Scaffold/alternative access & Edge Protection adequate
INSTALLATION
Fixings used are as specified on drawings
Frame positioning Correct
Stud centres & nogging heights as per drawings
Window & Door Openings constructed to window trim sizes
Lintel Bracing Straps installed
HOLD POINT; Insulation Installed, Council framing inspection
Weatherline installed, fixing centres correct
Midfloor expansion joint and Laps to Slab correct
Weatherline Flashing Tape installed to screw fixings & Sheet joints.
HOLD POINT; Council Inspection – Initial Cavity Inspection
Weatherline Jamb, Head and Sill tape & WS Tape installed to openings
POST INSTALLATION
All associated CANs/Inspection Reports are actioned and closed out
Subcontractor QA received
CARPENTRY CLADDING
PRE-START
GL and datum reference provided
Clean work area
Weatherline & Taping completed
Window Surround Flashings & Rainscreen Angles Completed
ACCESS/SAFETY/PROTECTION
Scaffold/alternative access & Edge Protection adequate
INSTALLATION
HOLD POINT: Council Cavity Inspection Passed
Timber Weatherboards
Fixings used are as specified on drawings
Castellated cavity battens installed at 480mm centres
Horizontal cavity closer installed at bottom of cladding
Any Joins located over batten, Z Flashing installed & cavity end sealed with Sikaflex 11FC
Mouldings and Flashings installed
Two coats of Stain applied & Top of Cavity Sealed
Eterpan Fibre Cement
Wall Cladding and Soffit Framing Handed Over
Services installed and located as per RCP
HOLD POINT – Council Soffit Framing Inspection Passed
Aluminium Perimeter angle installed as per drawings
Fixings used are as specified on drawings
Fixing layout correct - Nails at 200 centres, edge of soffit 12mm, corners 50mm
Perimeter seal installed as per drawings
Joint Stopping & Sanding complete
Exotec Cladding
Aluminium Perimeter angle installed as per drawings
Fixings used are as specified on drawings
Fixing layout correct - Nails at 200 centres, edge of soffit 12mm, corners 50mm
Perimeter seal installed as per drawings
Joint Stopping & Sanding complete
POST INSTALLATION
All associated CANs/Inspection Reports are actioned and closed out
Subcontractor QA received

## 4. Internal services and wall l
PRE-START
GL and datum reference provided
Clean work area
INTERNAL FRAMING
Ceiling framing installed as per drawing
Wall Setout as per drawings
Studs & Nogs installed at correct centres
DPC installed as required
Stairs Installed as per drawings
Services and Fixture nogs installed as required
Glass Screen Nogging installed to ceiling
GIB Handibrackets installed at correct locations
GIBfix angles installed to tiled areas
Subcontractor Preline Sign Off received
SERVICES FIRST FIX
Hydraulic Services
Underslung drainage and floor wastes installed as per drawings
Waterfeeds Setout & Installed as per drawings
Hydraulic vent installed to above roof
Subcontractor Preline Sign Off received
Mechanical Services
Ducting Installed as per drawings
Flexi’s installed to correct location as per RCP
Roof cowl and connection installed
Subcontractor Preline Sign Off received
Electrical Services
Cabling, outlets & Switches installed as per specs & drawings
Lights located as per Arch RCP
Subcontractor Preline Sign Off received
Ceiling Grid
Perimeter angles installed
Furring channels installed at correct centres
Subcontractor Preline Sign Off received
Pre-line photos
HOLD POINT Council Pre-line Inspection Passed
Plasterboard
Plasterboard fixings as per requirements (aqualine x standard)
Braceline Wall fixings as per requirements
HOLD POINT Council Post Line Inspection Passed
Set/Sand/Paint
Stopping completed
Painting completed as per drawings