## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-013-STR-Pile Cap Construction | itp |  |  |  |  | ITP-013-STR-Pile Cap Construction Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-013-STR-Pile Cap Construction
note | ITP Description: Pile Cap Construction
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): STR
note | Revision Number: 0
note | Revision Date: 01/12/22
note | ITP created by: Victor Mira
note | ITP approved for use by: Victor Mira
note | 1.1 Non Dependent
note | Reference: VicRoads Section 602 October 2007
note | 1.2 Non Dependent
note | Reference: VicRoads Section 610 February 2020
note | 1.3 Non Dependent
note | Reference: VicRoads Section 611 November 2018
note | 1.4 Non Dependent
note | Reference: VicRoads Section 614 June 2017
note | 1.5 Non Dependent
note | Reference: AS3810.1 2018
section | Preliminaries - Materials
checkpoint | 2.1 Concrete Mix
note | REFERENCE:
note | 610.07
note | Table 610.071
note | IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete Mix is Registered with VicRoads.
note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 ACRS Certification (for Reinforcement)
note | REFERENCE: 611.05 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Current ACRS certification for materials and for bar processing.
note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once for each supplier, 14 days of award of contract
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Bar Chairs/Aspros Certification
note | REFERENCE: 610.26 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Evaporative Retardant
note | REFERENCE: 610.17 (f)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.5 Curing Compound
note | REFERENCE: 610.23 (d)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
note | REFERENCE: 610.18 (a) (i)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.2 Concrete Sampling and Testing Procedure
note | REFERENCE: 610.18 (a) (v)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
note | REFERENCE: 610.18 (a) (iv)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
note | • Minutes of this meeting to be submitted to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
note | REFERENCE: 610.17 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, 2 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
note | REFERENCE: 610.23 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Curing methodology/procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.7 Concrete Drilling Procedure
note | REFERENCE: 610.46
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
note | • The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, once, 2 days prior to drilling
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.8 Temprature difference measuring-Calibration
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Calibration records are valid and up to date.
note | Attach: Calibration certificate
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
textbox | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to starting Works and at regular intervals
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: All
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.2 Survey Set-out
note | REFERENCE:
note | IFC Drawings
note | 610.47 (a)
note | Table 610.472
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Piles
note | REFERENCE: IFC Drawing
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Related piling Lots are closed.
note | – Pile design strength is achieved.
note | – Integrity and Dynamic tests performed and interpreted.
note | – Pile is broken back to the design level.
note | – As-Built Survey performed.
note | – Related piling NCMs are closed.
textbox | Enter: piling Lot numbers:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Doument Check
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Piling Lots
textbox | Date Completed:
checkpoint | 4.3 Excavation support
note | REFERENCE: 602.02
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: WP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
checkpoint | 4.4 Excavation Inspection
note | REFERENCE: 602.03
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, prior to placing blinding concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Construction Activities
checkpoint | 5.1 Formwork Design and Construction
note | REFERENCE:
note | IFC Drawings
note | 614.04
note | 614.05
note | 614.06
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Designed and constructed in such a manner so it can be removed without damage to the concrete.
note | • Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
note | • Formwork shall not be placed where steel & fixtures cannot be inspected.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review, Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each type of element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
note | REFERENCE: 614.08
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
note | • Pile caps with heights greater than 2.0 metres
note | • Any member for which self-compacting concrete is proposed.
note | Attach: Attachment A
note | Attach: Attachment B
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review, Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element (where greater than 2m)
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
note | REFERENCE: 614.08
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
note | • Pile caps with heights less than 2.0 metres
note | Attach: Attachment C
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review, Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element (where 2m or less)
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.4 Pre-pour Survey
note | REFERENCE:
note | 610.47 (a)
note | Table 610.472
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • A pre-pour survey carried out by a surveyor.
note | • Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.5 Reinforcement Placement
note | REFERENCE:
note | IFC Drawings
note | 611.06
note | 611.09
note | 611.10
note | 611.11
note | 611.12
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
note | • Projecting reinforcement is the correct length and location.
note | • Splice lengths achieve the minimum length and are in contact for this length.
note | • The reinforcement surface condition is free from dirt, debris and damage.
note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
note | • Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.7 Cast-in Items
note | REFERENCE:
note | IFC Drawings
note | 610.47 (a)
note | Table 610.472
note | AS3810.1 Table 3.3.6.2
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
note | ii. Running dimensions of a group of the above = ±6mm
note | iii. Ducts and conduit location = ±12mm
note | iv. Diameter of ducts and conduits = ±3mm
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.8 Thermal Differential Monitoring
note | REFERENCE: 610.22
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Thermal differential monitoring thermocouples installed.
note | • Only applicable if the element has:
note | i. the smallest sectional dimension exceeding 500mm
note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.9 Pre-pour Inspection
note | REFERENCE:
note | IFC Drawings
note | 610.18 (a) (ii) & (iii)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
note | • All foreign material has been completely removed from the forms.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.10 Weather Conditions & Evaporation Limits
note | REFERENCE:
note | Hot and/or Cold Weather Concreting Procedure
note | 610.17
note | 610.17 (a) & (e)
note | Table 610.171
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
textbox | Date Completed:
checkpoint | 5.11 Concrete Testing - Sampling Frequency
note | REFERENCE:
note | Site Sampling & Testing Procedure
note | 610.16 (b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
note | ○ 0m3 to 10m3 = 1 sample
note | ○ 10m3 to 25m3 = 2 samples
note | ○ 25m3 to 50m3 = 3 samples
note | ○ 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
note | • For each additional 50m3 and additional sample shall be taken.
note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
note | • Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
textbox | Date Completed:
checkpoint | 5.12 Concrete Testing - Slump
note | REFERENCE: 610.16 (c)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Slump testing tolerances =
note | <60mm = ±10mm
note | ≥60mm to ≤80mm = ±15mm
note | >80mm to ≤110mm = ±20mm
note | >110mm to ≤150mm = ±30mm
note | >150mm = ±40mm
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
textbox | Date Completed:
checkpoint | 5.13 Concrete Testing - Spread, Passability & Viscosity
note | REFERENCE: 610.13 (b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Spread range = 550mm to 750mm
note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
note | • Passability = ≤10mm (aggregate height differential)
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each sample of Self-compacting Concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
textbox | Date Completed:
checkpoint | 5.14 Concrete Testing - Compressive Strength Cylinders
note | REFERENCE: Site Sampling & Testing Procedure
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Correct quantity of cylinders manufactured per sample.
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each sample
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.15 Supply & Discharge Rates
note | REFERENCE: 610.13 (a) & (f)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete is supplied at an adequate rate to ensure no cold joints are formed.
note | • No water is to be added once discharge commences.
note | • Maximum time between batching trucks is 25 minutes.
note | • Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
note | • Concrete that stiffens or is showing signs of stiffening shall not be used.
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each load
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
textbox | Date Completed:
checkpoint | 5.16 Placement & Compaction
note | REFERENCE:
note | Placement & Compaction Work Procedure
note | 610.18 (a) & (b)
note | 610.18 (d) (i)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All concrete batches are traceable.
note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
note | • Concrete is not dropped freely from a height exceeding 2m.
note | • Concrete is not moved horizontally by use of vibrators.
note | • Adequate compaction is ensured
note | • Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
note | • Concrete layers are not more than 350mm
note | • Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
note | Record: Required information on the Concrete Pour Record.
note | Attach: Concrete Pour Record
note | Attach: Concrete Dockets
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each load
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: SP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
textbox | Date Completed:
checkpoint | 5.17 Surface Finishes
note | REFERENCE:
note | IFC Drawings
note | 610.31
note | 610.20
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Surface finish as per IFC drawings.
note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Curing-Top Surface
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Curing after formwork removal
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Thip ITP
textbox | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Thermal Differential Monitoring
note | REFERENCE: 610.22
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Maximum thermal differential between the core and exposed surface not to exceed 20°C.
note | • Only applicable if the element has:
note | i. the smallest sectional dimension exceeding 500mm
note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
note | Attach: Thermal Monitoring Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.3 Early Age Compressive Strength Test Results - Removal of Formwork
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.4 Surface Inspection - Cracks
note | REFERENCE: 610.24
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • No cracks greater than 0.2mm (exposure classification B1)
note | • If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.5 Surface Inspection - Surface Finish
note | REFERENCE:
note | IFC Drawings
note | 610.31 (a) - (n)
note | 610.32
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Comply with the IFC drawings and specifications.
note | • Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.6 Measurement of Concrete Cover
note | REFERENCE: 610.34
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete covermeter check one 3m2 test area for every 25m2 exterior surface area.
note | • Minimum 10 no. measurements recorded in each area.
note | • Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
note | Attach: Covermeter Check Record
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.7 Early Age Compressive Strength Results - Placement of Fill Against Concrete
note | REFERENCE:
note | Early Loading and Trafficking of Decks and Approach Slab Procedure
note | 610.35
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Fill is not placed against concrete within 14 days of pour.
note | • Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
note | Attach: Concrete Test Results or Maturity Test Results
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each substructure element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: SP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.9 Compressive Strength Test Results
note | REFERENCE:
note | IFC Drawings
note | Table 610.05.051
note | 610.16 (g)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
note | Attach: Compressive Strength Test Results
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each cylinder
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.10 As-built Survey
note | REFERENCE:
note | IFC Drawings
note | 610.47
note | Table 610.472
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
note | Attach: Survey As-builts / Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.11 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP