## Project breakdown
William Sanders (CF King)
Brick works
B05
Façade
North Elevation
[5 empty] | Ground Floor | Prepopulate | FC - S - Brick Works
[5 empty] | Level 1 | Prepopulate | FC - S - Brick Works
South Elevation
[5 empty] | Ground Floor | Prepopulate | FC - S - Brick Works
[5 empty] | Level 1 | Prepopulate | FC - S - Brick Works
East Elevation
[5 empty] | Ground Floor | Prepopulate | FC - S - Brick Works
[5 empty] | Level 1 | Prepopulate | FC - S - Brick Works
West Elevation
[5 empty] | Ground Floor | Prepopulate | FC - S - Brick Works
[5 empty] | Level 1 | Prepopulate | FC - S - Brick Works
|  |  | Completion Documents |  |  | Prepopulate | CST - S - Completion Documents
Block works
B05
Pre-Commencment Checks
Quality Management Plan Completed, Agreed & Attached
Inspection & Test Plan Completed, Agreed & Attached
Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
Conqa Setup & Project Team Trained & Given Access
Review Access Granted to Main Contractor & Relevant Parties
Matrix/insights Setup (if required)
Building B05 - On Site QA
Ground Level
[5 empty] | Blockwork-Grid Line A-C and 1-3 | Pre-populate | Blockwork
[5 empty] | Blockwork-Grid Line A-E and 3-5 | Pre-populate | Blockwork
Level 1
[5 empty] | Blockwork-Grid Line A-C and 1-3 | Pre-populate | Blockwork
[5 empty] | Blockwork-Grid Line A-E and 3-5 | Pre-populate | Blockwork
|  |  | Completion documents |  |  | Pre-populate | Completion documents

## Checklist
Type | Name | Value
checklist | FC - S - Brick Works
section | Preinstall checks
checkpoint | Area accessible, substrate acceptable & approval to start works - Consider services, cavity & waterproofing requirements prior to install
checkpoint | Ground clearance correct to specification
checkpoint | Grids/Wall marked for reference. RL reference/TOW confirmed. Base/Concrete/footing clean, tidy and level ready for first coarse.
section | Brick installation
checkpoint | Base of wall starting correct location - Brick base overhang within tolerances (no more than 20mm)
checkpoint | Control joints installed correctly
checkpoint | Weep holes installed correctly - Consider setout & size
checkpoint | Mortar Joints installed within tolerances (7-13mm)
checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc)
checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checkpoint | All relevant flashings and waterproofing/taping completed as required - If Applicable
checkpoint | Caulking completed (correct colour) and satisfactory finish achieved
checkpoint | Brick cavity is correctly formed and free of obstructions
checkpoint | Brickwork completed to required specification. All brickwork washed/clean & area left clean & tidy - Wall built within tolerance - straight, level and to the correct height and colour
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | ST - S - Blockwork
checkpoint | Grids available for reference and base of wall marked accurately, RL reference/top of wall (TOW) confirmed
checkpoint | Base of wall in correct location
checkpoint | Horizontal reinforcing installed correctly (centres/ size / splicing etc)
checkpoint | Ties / Control joints installed as required
checkpoint | Vertical reinforcing installed as required with appropriate splice
checkpoint | Openings checked and correct - location, height and width
checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
checkpoint | Concrete specifications checked and correct
checkpoint | All blocks filled to correct height
checkpoint | Starter bars in centre of block if applicable
checkpoint | Blockwork wall(s) complete to required specification
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Checklist | Completion documents
checkpoint | Product Warranty Attached
checkpoint | Thickness Test Conducted, passed and results attached
checkpoint | PS3 Attached