## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [8 empty] | Document # FHC-ITP-004
[12 empty] | Revision : 3 | Date : 20/04/2022
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Type A Fill Placement |  | Name: Martin Syawish |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  |  |  | Specifications: VicRoads Specification Sections 173, 204
|  |  |  | Structure / Component: Pavement |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Tarneit Railway Station |  | Date : 20/04/2022 |  | Date : 20/04/2022 |  |  | Date : 20/04/2022
Lot No: |  |  | Lot Details: | [6 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Scale | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | A or B | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | The current revision drawings/documents are being used including subcontractors copy. |  | Prior to commencing | Current revision drawing/documents are being used including the subcontractors copy. | Drawings and drawing registers | Visual Inspection | This ITP Signed Off | HP* |  | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Placement/ Each Lot | All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | Visual Inspection | This ITP Signed Off | HP* |  | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Verify Material |  | Prior to Placement | Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive. Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075. PI between 6 and 25. Permeability of less than 5X10^-9 for capping and verge material | VicRoads Spec. Cl. 204.04(b) Cl. 204.06(c) Table 204.041 Table 3020.052 | Site Inspection | Test Record (If silt is observed) | HP |  | Site Engineer & Superintendent |  |  | N/A
1.4 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* |  | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Survey set-out |  | Prior to Commencing Excavation | Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used | Latest IFC Drawings | Site Inspection | Survey records & pegs on the ground | SCP |  | Site Engineer/ Surveyor | N/A |  | N/A
2.2 | Inspection of fill area |  | Each lot | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent. | 204.10 (b) | Visual Inspection | This ITP Signed Off | HP |  | Site Engineer / Superintendent |  |  | N/A
2.3 | Layer Thickness |  | During Excavation | Layers placed and spread in uniform compacted layers not thicker than 200mm. | VicRoads Spec. Cl. 204.10(d)(ii) | Visual Inspection | This ITP Signed Off | IP |  | Site Engineer | N/A |  | N/A
2.4 | Maximum Lot Size |  | During Excavation | Lot size for testing is to be one day's production or 5,000m2, whichever is lesser. | VicRoads Spec. Table 204.142 | Visual Inspection | This ITP Signed Off | IP |  | Site Engineer | N/A |  | N/A
2.5 | Type A Placement |  | Prior to Placement/ Each Lot | • Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas • Any rocky material present must be uniform throughout the layer • Each layer shall be kept generally parallel to the surface of subgrade | 204.10 (d) (i). 204.10 (d) (ii). Table 3020.052 | Visual Inspection | This ITP Signed Off | IP |  | Site Engineer / Site Foreman | N/A |  | N/A
2.6 | Proof Roll |  | Each lot | Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification | 173.03 204.12) 204.10 (b) | Visual Inspection | This ITP Signed Off | WP |  | Site Foreman/ Superintendent |  |  | N/A
3 | Testing
3.1 | Reduced Test Frequency |  | Each lot | Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails. | VicRoads Spec. Table 204.131 | Test Record | Test Records | AP |  | Project Engineer | N/A |  | N/A
3.2 | Compaction Testing |  | Each Lot | Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B). | VicRoads Spec. Table 204.131 | Verify | Compaction Test Records | TP |  | Site Engineer | N/A |  | N/A
3.3 | Maximum Particle Size |  | Each lot, unless reduced frequency has been approved | Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075 | VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141 Table 204.041 | Verify | Maximum Particle Size Test Records | TP |  | Site Engineer | N/A |  | N/A
3.4 | CBR/Swell |  | First lot then every Second thereafter | CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%). | VicRoads Spec. Cl. 204.14(a)(i) Table 204.141 Table 204.041 | Verify | CBR/Swell Test Records | TP |  | Site Engineer | N/A |  | N/A
3.5 | Atterberg Limit Tests |  | Each lot, unless reduced frequency has been approved | PI between 6 and 25, PI x % passing through 0.425 to be less than 1000 | VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141 Table 204.041 | Verify | PI Test Records | TP |  | Site Engineer | N/A |  | N/A
3.6 | Permeability |  | Each lot, unless reduced frequency has been approved | Permeability of less than 5X10^-9 for capping and verge material | VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141 Table 204.041 | Verify | Permeability Test Records | TP |  | Site Engineer | N/A |  | N/A
3.7 | Material Property Testing (Scale B) |  | Each lot, unless reduced frequency has been approved | Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04. | Cl 204.04 Cl204.14 | Verify | NATA test report | TP |  | Site Engineer | N/A |  | N/A
3.8 | Survey Conformance |  | Each lot | The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031 Scale B: Range x = +5,-25 Max S = 15mm 40 measurements per lot | 204.03 | Survey conformance point | Survey report Lot Register | WP SCP |  | Site Engineer & Surveyor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on L16: Rodrigo Anchico: Write "N/A" to disable the cell.

## Sheet1
Cost Code | Cost Code Description | Unit | Original Quantity | Quantity At Completion | Budget Rate | Original Budget Total | Quantity To Date | To Date Rate | Actual To Date (ACWP) | Quantity To Complete | To Complete Rate | Estimate To Complete | Budgeted Quantity | Estimate At Completion Rate | Estimate At Completion (EAC) | Delta EAC | Delta VAC
01.* | Supervision & Management |  | 0 | 0 | 0 | 1240420 | 0 | 0 | 61416 | 0 | 0 | 1190700 | 0 | 0 | 1252116 | -71743 | 71743
1.01 | SUP - Project Manager | Month | 17 | 17 | 12911.353 | 219493 | 1 | 16000 | 16000 | 8 | 16000 | 128000 | 9 | 16000 | 144000 | -32000 | 31999
1.02 | SUP - Project Engineer | Month | 17 | 17 | 20827.529 | 354068 | 1 | 14000 | 14000 | 16 | 13000 | 208000 | 17 | 13058.824 | 222000 | -52000 | 52000
1.03 | SUP - Site Engineer | Month | 14 | 14 | 21430.143 | 300022 | 0 | 0 | 2224 | 16 | 8000 | 128000 | 16 | 8139 | 130224 | -32000 | 32000
1.04 | SUP - Foreman | Month | 18 | 18 | 17172.944 | 309113 | 0 | 0 | 0 | 7 | 20571.429 | 144000 | 7 | 20571.429 | 144000 | -16000 | 16000
1.05 | SUP - Leading/Hand/Site Management | Month | 1 | 1 | 0 | 0 | 2 | 12460.5 | 24921 | 6 | 13000 | 78000 | 8 | 12865.125 | 102921 | 7321 | -7321
1.06 | SUP - HSEQ Officer | Item | 1 | 1 | 36870 | 36870 | 0 | 0 | 0 | 8 | 12000 | 96000 | 8 | 12000 | 96000 | 16000 | -16000
1.07 | SUP - Staff Expenses | Item | 1 | 1 | 20854 | 20854 | 0 | 0 | 4271 | 1 | 408700 | 408700 | 1 | 412971 | 412971 | 36936 | -36936
02.* | Site Facilities |  | 0 | 0 | 0 | 502046 | 0 | 0 | 98585 | 0 | 0 | 171398 | 0 | 0 | 269983 | 33868 | -33869
2.01 | SITE FAC - Compound/Site Demob | Weeks | 52 | 52 | 200 | 10400 | 0 | 0 | 0 | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 0 | 0
2.02 | SITE FAC - Building Hire | Weeks | 52 | 52 | 2071.385 | 107712 | 18 | 615.611 | 11081 | 38 | 678.947 | 25800 | 56 | 658.589 | 36881 | 11081 | -11081
2.03 | SITE FAC - Services - water, electricity, sewer | Weeks | 52 | 52 | 2474.692 | 128684 | 0 | 0 | 15215 | 1 | 5000 | 5000 | 1 | 20215 | 20215 | 0 | 0
2.04 | SITE FAC - Toilet Pumpouts | Weeks | 52 | 52 | 500 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.05 | SITE FAC - Test & Tag | Weeks | 52 | 52 | 146.654 | 7626 | 18 | 204.111 | 3674 | 38 | 173.105 | 6578 | 56 | 183.071 | 10252 | 2141 | -2141
2.06 | SITE FAC - Waste Bins | Weeks | 52 | 52 | 335 | 17420 | 13 | 471.538 | 6130 | 38 | 458.421 | 17420 | 51 | 461.765 | 23550 | 6130 | -6130
2.07 | SITE FAC - Site Running Costs | Weeks | 52 | 52 | 1846.904 | 96039 | 18 | 1863.278 | 33539 | 38 | 1857.895 | 70600 | 56 | 1859.625 | 104139 | 9969 | -9970
2.08 | SITE FAC - Site Fencing | lm | 500 | 500 | 20.23 | 10115 | 0 | 0 | 4855 | 900 | 4.444 | 4000 | 900 | 9.839 | 8855 | 4277 | -4277
2.09 | SITE FAC - Compound Setup | Item | 1 | 1 | 65091 | 65091 | 1 | 24091 | 24091 | 0 | 0 | 0 | 1 | 24091 | 24091 | 270 | -270
2.1 | SITE FAC - Compound Demob | Item | 1 | 1 | 32959 | 32959 | 0 | 0 | 0 | 1 | 17000 | 17000 | 1 | 17000 | 17000 | 0 | 0
03.* | Site Costs |  | 0 | 0 | 0 | 531388 | 0 | 0 | 235763 | 0 | 0 | 367282 | 0 | 0 | 603045 | 161485 | -161486
3.01 | SITE COST - Cleaner | mhrs | 2813 | 2813 | 50 | 140650 | 31 | 253.677 | 7864 | 117 | 220 | 25740 | 148 | 227.054 | 33604 | -660 | 660
3.02 | SITE COST - Small Tools | Item | 1 | 1 | 59599 | 59599 | 18 | 2197.444 | 39554 | 38 | 913.737 | 34722 | 56 | 1326.357 | 74276 | 15596 | -15596
3.03 | SITE COST - Temporary Lighting | Shift | 420 | 420 | 140 | 58800 | 0.4 | 61465 | 24586 | 0.6 | 60666.667 | 36400 | 1 | 60986 | 60986 | 1166 | -1166
3.04 | SITE COST - Street Sweeper | Hrs | 873 | 873 | 105 | 91665 | 13 | 759.615 | 9875 | 38 | 505.263 | 19200 | 51 | 570.098 | 29075 | 8180 | -8180
3.05 | SITE COST - Plant Mob Small | EaWay | 52 | 52 | 300 | 15600 | 0 | 0 | 2400 | 50 | 312 | 15600 | 50 | 360 | 18000 | 0 | 0
3.06 | SITE COST - Plant Mob Large | EaWay | 40 | 40 | 700 | 28000 | 0 | 0 | 800 | 65 | 430.769 | 28000 | 65 | 443.077 | 28800 | 0 | 0
3.07 | SITE COST - Site Maintenance | Item | 1 | 1 | 85597 | 85597 | 18 | 2001.389 | 36025 | 38 | 2000 | 76000 | 56 | 2000.446 | 112025 | -1456 | 1456
3.08 | SITE COST - Plant Hire Costs | Weeks | 59 | 59 | 872.492 | 51477 | 0 | 0 | 110553 | 0 | 0 | 131620 | 0 | 0 | 242173 | 134553 | -134553
3.09 | SITE COST - Wet Weather |  | 0 | 0 | 0 | 0 | 0 | 0 | 4106 | 0 | 0 | 0 | 0 | 0 | 4106 | 4106 | -4106
04.* | Survey |  | 0 | 0 | 0 | 256413 | 0 | 0 | 47493 | 0 | 0 | 113300 | 0 | 0 | 160793 | 8787 | -8787
4.01 | SURV - 1 Man Survey Crew | Hours | 2000 | 2000 | 102.85 | 205700 | 473 | 100.408 | 47493 | 0 | 0 | 108300 | 473 | 329.372 | 155793 | 8787 | -8787
4.02 | SURV - Base Station | Month | 12 | 12 | 2667.75 | 32013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.03 | SURV - Survey Consumables | Weeks | 37 | 37 | 505.405 | 18700 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0
05.* | Environmental |  | 0 | 0 | 0 | 292045 | 0 | 0 | 89000 | 0 | 0 | 51168 | 0 | 0 | 140168 | 5809 | -5809
5.01 | ENV - Environmental | Item | 1 | 1 | 292045 | 292045 | 13 | 6846.154 | 89000 | 43 | 1189.953 | 51168 | 56 | 2503 | 140168 | 5809 | -5809
06.* | Design Costs |  | 0 | 0 | 0 | 1190246 | 0 | 0 | 955675 | 0 | 0 | 205512 | 0 | 0 | 1161187 | -249 | 249
6.01 | DESIGN - SMEC Subcontract | Item | 1 | 1 | 834817 | 834817 | 0 | 0 | 805736 | 1 | 63545 | 63545 | 1 | 869281 | 869281 | 0 | 0
6.02 | DESIGN - SMEC Construction Phase | Item | 1 | 1 | 64267 | 64267 | 0 | 0 | 0 | 0 | 0 | 64267 | 0 | 0 | 64267 | 0 | 0
6.03 | DESIGN - Cox Architecture | Item | 1 | 1 | 60000 | 60000 | 0 | 0 | 42990 | 0 | 0 | 17000 | 0 | 0 | 59990 | 0 | 0
6.04 | DESIGN - Proof Eng | Item | 1 | 1 | 60000 | 60000 | 0 | 0 | 69412 | 0 | 0 | 20000 | 0 | 0 | 89412 | 0 | 0
6.05 | DESIGN - Powerplant (Street Lighting) | Item | 1 | 1 | 105518 | 105518 | 0 | 0 | 15785 | 0 | 0 | 10000 | 0 | 0 | 25785 | 0 | 0
6.06 | DESIGN - Capire (Stakeholder Consultant) | Item | 1 | 1 | 62404 | 62404 | 0 | 0 | 20512 | 0 | 0 | 28000 | 0 | 0 | 48512 | -989 | 989
6.07 | DESIGN - Temporary Works | Item | 1 | 1 | 3240 | 3240 | 0 | 0 | 1240 | 0 | 0 | 2700 | 0 | 0 | 3940 | 740 | -740
07.* | Tender Costs |  | 0 | 0 | 0 | 171600 | 0 | 0 | 177324 | 0 | 0 | 0 | 0 | 0 | 177324 | 0 | 0
7.01 | TENDER - Tender Costs eg SMEC, Cox, printing, CGE, Power Plant | Item | 1 | 1 | 171600 | 171600 | 0 | 0 | 177324 | 0 | 0 | 0 | 0 | 0 | 177324 | 0 | 0
08.* | Management System Audits |  | 0 | 0 | 0 | 31200 | 0 | 0 | 6979 | 0 | 0 | 25400 | 0 | 0 | 32379 | 0 | 0
8.01 | SQE - Audits | Item | 1 | 1 | 31200 | 31200 | 0 | 0 | 6979 | 0 | 0 | 25400 | 0 | 0 | 32379 | 0 | 0
10.* | Project Manager's Contingency |  | 0 | 0 | 0 | 93808 | 0 | 0 | 0 | 0 | 0 | 786400 | 0 | 0 | 786400 | -528627 | 528627
10.01 | PM - Contingency | Item | 1 | 1 | 93808 | 93808 | 0 | 0 | 0 | 0 | 0 | 786400 | 0 | 0 | 786400 | -528627 | 528627
22.* | Traffic Management - Barrier Hire |  | 0 | 0 | 0 | 212888 | 0 | 0 | 68533 | 0 | 0 | 120000 | 0 | 0 | 188533 | 1971 | -1971
22.01 | TRAF - Barrier Installation/Removal - Cranes, Trucking, Labour | Item | 1 | 1 | 212888 | 212888 | 0 | 0 | 48128 | 0 | 0 | 120000 | 0 | 0 | 168128 | 451 | -451
22.02 | TRAF - Barriers - Installation Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 20405 | 0 | 0 | 0 | 0 | 0 | 20405 | 1520 | -1520
23.* | Traffic Management - Personnel |  | 0 | 0 | 0 | 395800 | 0 | 0 | 102821 | 0 | 0 | 240210 | 0 | 0 | 343031 | 62483 | -62483
23.01 | TRAF - Traffic Crews | Item | 1 | 1 | 395800 | 395800 | 3 | 34273.667 | 102821 | 8 | 30026.25 | 240210 | 11 | 31184.636 | 343031 | 62483 | -62483
24.* | Bridge Closure Traffic Management |  | 0 | 0 | 0 | 172670 | 0 | 0 | 0 | 0 | 0 | 132590 | 0 | 0 | 132590 | 0 | 0
24.01 | TRAF - Bridge Closures | Item | 1 | 1 | 172670 | 172670 | 0 | 0 | 0 | 0 | 0 | 132590 | 0 | 0 | 132590 | 0 | 0
25.* | Traffic Management Consultants |  | 0 | 0 | 0 | 86900 | 0 | 0 | 45910 | 0 | 0 | 30780 | 0 | 0 | 76690 | -560 | 560
25.01 | TRAF -Trafficworks | Item | 1 | 1 | 64000 | 64000 | 0 | 0 | 42550 | 0 | 0 | 20000 | 0 | 0 | 62550 | 0 | 0
25.02 | TRAF - Road Safety Audits | Item | 1 | 1 | 22900 | 22900 | 0 | 0 | 3360 | 0 | 0 | 10780 | 0 | 0 | 14140 | -560 | 560
27.* | Traffic Management - Temporary Linemarking & Signage |  | 0 | 0 | 0 | 72080 | 0 | 0 | 43464 | 0 | 0 | 32959 | 0 | 0 | 76423 | 0 | 0
27.01 | TRAF - Temporary Signs | Item | 1 | 1 | 0 | 0 | 0 | 0 | 38478 | 0 | 0 | 0 | 0 | 0 | 38478 | 0 | 0
27.02 | TRAF - Temporary Lines | Item | 1 | 1 | 72080 | 72080 | 0 | 0 | 4986 | 0 | 0 | 32959 | 0 | 0 | 37945 | 0 | 0
28.* | Temporary Pavement |  | 0 | 0 | 0 | 52365 | 0 | 0 | 15197 | 0 | 0 | 40000 | 0 | 0 | 55197 | 2574 | -2574
28.01 | Temp Road Pavement | sm | 200 | 200 | 18.08 | 3616 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 16410 | -16410
28.02 | Temp Footpaths during Construction (Concrete pavement) - 150mm Thick 32 MPa broom finish F82 with 40mm cover | sm | 1070 | 1070 | 45.56 | 48749 | 0 | 0 | 11039 | 0 | 0 | 20000 | 0 | 0 | 31039 | -13836 | 13836
28.03 | Temp Footpaths during Construction (Concrete pavement) - Crushed Rock Pad - Park | sm | 1 | 1 | 0 | 0 | 0 | 0 | 4158 | 0 | 0 | 0 | 0 | 0 | 4158 | 0 | 0
30.* | Job ready startup costs |  | 0 | 0 | 0 | 35472 | 0 | 0 | 5836 | 0 | 0 | 10591 | 0 | 0 | 16427 | 0 | 0
30.01 | Job ready startup costs - Inductions, medicals, | Item | 1 | 1 | 10045 | 10045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.02 | Job ready startup costs - Labour costs | mhr | 132 | 132 | 73.379 | 9686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.03 | Job ready startup costs - PPE | Week | 72 | 72 | 218.625 | 15741 | 0 | 0 | 5836 | 0 | 0 | 10591 | 0 | 0 | 16427 | 0 | 0
31.* | Defects Maintenance Allowances |  | 0 | 0 | 0 | 101922 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0
31.01 | Defects Maintenance Allowances | Item | 1 | 1 | 101922 | 101922 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0
40.* | SHARED USE PATH BRIDGE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41.* | Earthworks to Bridge Approach |  | 0 | 0 | 0 | 89013 | 0 | 0 | 52166 | 0 | 0 | 47660 | 0 | 0 | 99826 | 15673 | -15673
41.01 | SUP - Bridge Approaches - supply and place Fill | ccm | 2713 | 2713 | 32.81 | 89013 | 0 | 0 | 52166 | 0 | 0 | 47660 | 0 | 0 | 99826 | 15673 | -15673
42.* | Structural Element Excavations & Backfill |  | 0 | 0 | 0 | 49942 | 0 | 0 | 0 | 0 | 0 | 49942 | 0 | 0 | 49942 | 0 | 1
42.01 | SUP - Excavate & backfill - River Span Pier Pilecaps | M3 | 298 | 298 | 82.779 | 24668 | 0 | 0 | 0 | 0 | 0 | 24668 | 0 | 0 | 24668 | 0 | 0
42.02 | SUP - Beaching - East Abutment | M2 | 132 | 132 | 118.538 | 15647 | 0 | 0 | 0 | 0 | 0 | 15647 | 0 | 0 | 15647 | 0 | 0
42.03 | SUP - Contamination - off site disposal | bcm | 47 | 47 | 204.83 | 9627 | 0 | 0 | 0 | 0 | 0 | 9627 | 0 | 0 | 9627 | 0 | 0
43.* | Piling |  | 0 | 0 | 0 | 395489 | 0 | 0 | 1175 | 0 | 0 | 334208 | 0 | 0 | 335383 | 0 | -1
43.01 | SUP - Piling Subbie | cm | 120 | 120 | 2844.008 | 341281 | 0 | 0 | 1175 | 0 | 0 | 300000 | 0 | 0 | 301175 | 0 | 0
43.02 | SUP - Piling - FH Costs | cm | 120 | 120 | 184.808 | 22177 | 0 | 0 | 0 | 0 | 0 | 22177 | 0 | 0 | 22177 | 0 | 0
43.03 | SUP - Piling - Extra Over ASS | LS | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43.04 | SUP - Rock Anchors For Cantilever Crosshead | Ea | 2 | 2 | 10000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43.05 | SUP - Piling - contaminated spoil disposal | bcm | 121 | 121 | 99.43 | 12031 | 0 | 0 | 0 | 0 | 0 | 12031 | 0 | 0 | 12031 | 0 | 0
44.* | Structural Steelwork |  | 0 | 0 | 0 | 1324253 | 0 | 0 | 428085 | 0 | 0 | 1553217 | 0 | 0 | 1981302 | 55000 | -55000
44.01 | SUP - Structural Girder Bridge - supply, paint, & deliver | Tonne | 226 | 226 | 4703.699 | 1063036 | 0 | 0 | 428085 | 0 | 0 | 1292000 | 0 | 0 | 1720085 | 55000 | -55000
44.02 | SUP - Structural Girder Bridge - Assemble & Install | Tonne | 226.6 | 226.6 | 1152.767 | 261217 | 0 | 0 | 0 | 1 | 261217 | 261217 | 1 | 261217 | 261217 | 0 | 0
45.* | Precast Concrete |  | 0 | 0 | 0 | 397089 | 0 | 0 | 22294 | 0 | 0 | 420360 | 0 | 0 | 442654 | 0 | -1
45.01 | SUP - Precast Floor Panels - supply & deliver | sm | 760 | 760 | 278.817 | 211901 | 0 | 0 | 10000 | 0 | 0 | 255000 | 0 | 0 | 265000 | 0 | 1
45.02 | SUP - Precast Floor Panels - installation | sm | 760 | 760 | 63.289 | 48100 | 0 | 0 | 0 | 0 | 0 | 48100 | 0 | 0 | 48100 | 0 | 0
45.03 | SUP - Permastruct Decking | Ea | 4 | 4 | 31000 | 124000 | 0 | 0 | 12294 | 0 | 0 | 117260 | 0 | 0 | 129554 | 0 | 0
45.04 | SUP - Super T Beams - install | Ea | 4 | 4 | 3272 | 13088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46.* | Insitu Concrete Works |  | 0 | 0 | 0 | 448395 | 0 | 0 | 0 | 0 | 0 | 398707 | 0 | 0 | 398707 | -45222 | 45221
46.01 | SUP - In Situ Conc Subbie | cm | 560.3 | 560.3 | 501.315 | 280887 | 0 | 0 | 0 | 0 | 0 | 260000 | 0 | 0 | 260000 | -20887 | 20887
46.02 | SUP - Concrete F15 & F20 - supply only | cm | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2144 | 0 | 0 | 2144 | 0 | 0
46.03 | SUP - Concrete VR 32 MPa - supply only | cm | 21 | 21 | 135.286 | 2841 | 0 | 0 | 0 | 0 | 0 | 2841 | 0 | 0 | 2841 | 0 | 0
46.04 | SUP - Concrete VR 40 MPa - supply only | cm | 275 | 241 | 165.203 | 39814 | 0 | 0 | 0 | 241 | 147.332 | 35507 | 241 | 147.332 | 35507 | 0 | 0
46.05 | SUP - Concrete - testing | cm | 296 | 241 | 24.494 | 5903 | 0 | 0 | 0 | 241 | 14.938 | 3600 | 241 | 14.938 | 3600 | 0 | 0
46.06 | SUP - Reinforcement - supply & deliver | Tonne | 46.4 | 46.4 | 1272.737 | 59055 | 0 | 0 | 0 | 0 | 0 | 59055 | 0 | 0 | 59055 | 0 | 0
46.07 | SUP - Bearings - Supply & deliver | Ea | 16 | 16 | 2054.5 | 32872 | 0 | 0 | 0 | 8 | 4445 | 35560 | 8 | 4445 | 35560 | 2688 | -2688
46.08 | SUP - Bearings - install only | Ea | 16 | 16 | 1688.938 | 27023 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | -27023 | 27023
47.* | Miscellaneous Elements (metalwork, ballustrading, conduits, & line markings) |  | 0 | 0 | 0 | 157750 | 0 | 0 | 6783 | 0 | 0 | 176470 | 0 | 0 | 183253 | 506 | -505
47.01 | SUP - Metalwork - Joint Between Precast Floor Panels | lm | 250 | 250 | 21.548 | 5387 | 0 | 0 | 0 | 290 | 18.576 | 5387 | 290 | 18.576 | 5387 | 0 | 0
47.02 | SUP - Metalwork (Expansion Joints) to both the Steel & Super Tee spans | lm | 19.2 | 19.2 | 1000 | 19200 | 0 | 0 | 0 | 9 | 2133.333 | 19200 | 9 | 2133.333 | 19200 | 0 | 0
47.03 | SUP - Gutter, Kickplate Install | lm | 310 | 310 | 213.913 | 66313 | 0 | 0 | 6783 | 310 | 140.106 | 43433 | 310 | 161.987 | 50216 | 506 | -506
47.04 | SUP - SS Handrail | lm | 84 | 84 | 700 | 58800 | 0 | 0 | 0 | 310 | 189.677 | 58800 | 310 | 189.677 | 58800 | 0 | 0
47.05 | SUP - Line Marking | Item | 1 | 1 | 1500 | 1500 | 0 | 0 | 0 | 1 | 1500 | 1500 | 1 | 1500 | 1500 | 0 | 0
47.06 | SUP - Conduits - supply & install | lm | 310 | 310 | 21.129 | 6550 | 0 | 0 | 0 | 620 | 15.565 | 9650 | 620 | 15.565 | 9650 | 0 | 0
47.07 | SUP - Off Structure Fencing | lm | 0 | 192.5 | 0 | 0 | 0 | 0 | 0 | 192.5 | 200 | 38500 | 192.5 | 200 | 38500 | 0 | 0
48.01 | SUP - Painting | sm | 476 | 200 | 41.615 | 8323 | 0 | 0 | 0 | 200 | 25 | 5000 | 200 | 25 | 5000 | 0 | 0
50* | ROADWORKS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51.* | RW - Demolition, Clearing & Grubbing |  | 0 | 0 | 0 | 170771 | 0 | 0 | 34278 | 0 | 0 | 119986 | 0 | 0 | 154265 | 9274 | -9274
51.01 | RW - Demolition - clear trees, relocate palm trees | Item | 1 | 1 | 59596 | 59596 | 0 | 0 | 20773 | 0 | 0 | 5000 | 0 | 0 | 25773 | 9273 | -9273
51.02 | RW -Demolition - Concrete Kerbs | m | 3894 | 2400 | 33.912 | 81389 | 300 | 27.033 | 8110 | 1800 | 25.667 | 46200 | 2100 | 25.862 | 54310 | 0 | 0
51.03 | RW -Demolition - asphalt pavements | sm | 1800 | 1800 | 12.127 | 21829 | 0 | 0 | 0 | 0 | 0 | 21829 | 0 | 0 | 21829 | 0 | 0
51.04 | RW - Demolition - remove bluestones | sm | 187 | 187 | 31.941 | 5973 | 90 | 59.944 | 5395 | 0 | 0 | 5973 | 90 | 126.322 | 11369 | 1 | -1
51.05 | RW -Demolition - remove Signs | Each | 2 | 2 | 992 | 1984 | 0 | 0 | 0 | 2 | 992 | 1984 | 2 | 992 | 1984 | 0 | 0
51.06 | RW - Remove Existing Concrete Slabs | m2 | 1839 | 1300 | 0 | 0 | 0 | 0 | 0 | 1300 | 30 | 39000 | 1300 | 30 | 39000 | 0 | 0
52.* | RW -Cart & Dispose Contaminated Soil |  | 0 | 0 | 0 | 412925 | 0 | 0 | 126214 | 0 | 0 | 299520 | 0 | 0 | 425734 | -5315 | 5315
52.01 | RW - Contaminated soils - cart & dispose | Tonne | 6640 | 6640 | 96.505 | 640796 | 1158 | 108.993 | 126214 | 3000 | 99.84 | 299520 | 4158 | 102.389 | 425734 | -5315 | 5315
52.02 | RW - Contaminated soils - Reuse In Ped Bridge Approach | ccm | -1000 | -1000 | 227.871 | -227871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53.* | RW - Cart & Dispose Clean Material |  | 0 | 0 | 0 | 0 | 0 | 0 | 8707 | 0 | 0 | 12000 | 0 | 0 | 20707 | 707 | -707
53.01 | RW - Pavements - Cart & Dispose Clean Material |  | 0 | 0 | 0 | 0 | 0 | 0 | 8097 | 2000 | 6 | 12000 | 2000 | 10.049 | 20097 | 97 | -97
53.02 | RW -Pavements - Clean material - Cart for Re Use On Site |  | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 0 | 0 | 610 | 610 | -610
54* | RW - Excavation for Pavements |  | 0 | 0 | 0 | 137372 | 0 | 0 | 64946 | 0 | 0 | 82223 | 0 | 0 | 147169 | 1689 | -1689
54.01 | RW - Excavation for Pavements incl beneath kerbs | bcm | 4459 | 4459 | 27.703 | 123526 | 0 | 0 | 54821 | 3900 | 19.288 | 75223 | 3900 | 33.345 | 130044 | 16 | -16
54.02 | RW - Subgrade Preparation - both Cut & Fill locations | sm | 7994 | 7994 | 1.732 | 13846 | 0 | 0 | 10125 | 0 | 0 | 7000 | 0 | 0 | 17125 | 1673 | -1673
55.* | RW - Fill - supply & placePlacement |  | 0 | 0 | 0 | 19008 | 0 | 0 | 0 | 0 | 0 | 19008 | 0 | 0 | 19008 | 0 | 1
55.01 | RW - Fill - import supply & deliver | ccm | 300 | 300 | 23.66 | 7098 | 0 | 0 | 0 | 0 | 0 | 7098 | 0 | 0 | 7098 | 0 | 0
55.02 | RW - Fill - place only | ccm | 531 | 531 | 22.429 | 11910 | 0 | 0 | 0 | 0 | 0 | 11910 | 0 | 0 | 11910 | 0 | 0
56.* | RW - Topsoil - strip & replace |  | 0 | 0 | 0 | 25187 | 0 | 0 | 0 | 0 | 0 | 25187 | 0 | 0 | 25187 | 0 | 0
56.01 | RW - Topsoil - load from on-site stockpile & place only | sm | 144 | 144 | 44.924 | 6469 | 0 | 0 | 0 | 0 | 0 | 6469 | 0 | 0 | 6469 | 0 | 0
56.02 | RW - Topsoil - strip | sm | 2532 | 2532 | 7.393 | 18718 | 0 | 0 | 0 | 1000 | 18.718 | 18718 | 1000 | 18.718 | 18718 | 0 | 0
57.* | RW - Subsoil drainage - Sand Backfill |  | 0 | 0 | 0 | 201127 | 0 | 0 | 5464 | 0 | 0 | 79912 | 0 | 0 | 85376 | -1985 | 1984
57.01 | RW - Material Supply - Fabric, Pipe, & backfill materials | lm | 3725 | 1494 | 14.454 | 21595 | 1494 | 3.657 | 5464 | 0 | 0 | 0 | 1494 | 3.657 | 5464 | -1985 | 1985
57.02 | RW - Excavate, lay pipe, install quarry, & install pipe & pits etc | lm | 3725 | 1494 | 28.631 | 42774 | 0 | 0 | 0 | 1494 | 19 | 28386 | 1494 | 19 | 28386 | 0 | 0
57.03 | RW - Quarry - supply & deliver | lm | 2734 | 816 | 46.315 | 37793 | 0 | 0 | 0 | 816 | 4.534 | 3700 | 816 | 4.534 | 3700 | 0 | 0
57.04 | RW - Concrete - supply & deliver | lm | 991 | 678 | 31.186 | 21144 | 0 | 0 | 0 | 678 | 13.608 | 9226 | 678 | 13.608 | 9226 | 0 | 0
57.05 | RW - Contamination | Tonne | 806 | 400 | 194.553 | 77821 | 0 | 0 | 0 | 1494 | 25.837 | 38600 | 1494 | 25.837 | 38600 | 0 | 0
58.* | RW - Subsoil drainage - Pits & Flushouts |  | 0 | 0 | 0 | 1352 | 0 | 0 | 1387 | 0 | 0 | 9076 | 0 | 0 | 10463 | -2137 | 2137
58.01 | RW - Pits & flushouts - supply & install | Each | 14 | 20 | 67.6 | 1352 | 0 | 0 | 1387 | 22 | 412.545 | 9076 | 22 | 475.591 | 10463 | -2137 | 2137
59* | RW - Stormwater Drainage (RCPs only) |  | 0 | 0 | 0 | 167324 | 0 | 0 | 26130 | 0 | 0 | 162782 | 0 | 0 | 188912 | 25204 | -25203
59.01 | RW - Pipe - supply & deliver only (all sizes) | lm | 296 | 258 | 99.783 | 25744 | 0 | 0 | 1892 | 258 | 114.911 | 29647 | 258 | 122.244 | 31539 | -1090 | 1090
59.02 | RW - Pipes - quarry supply only | lm | 296 | 258 | 108.267 | 27933 | 0 | 0 | 556 | 258 | 108.267 | 27933 | 258 | 110.422 | 28489 | 556 | -556
59.03 | RW - Pipes - excavate, lay pies, & backfill (install components only) | lm | 296 | 258 | 187.213 | 48301 | 70 | 207.971 | 14558 | 188 | 212 | 39856 | 258 | 210.907 | 54414 | 16614 | -16614
59.04 | RW - Contamination - Cat "C" |  | 0 | 0 | 0 | 65346 | 70 | 130.343 | 9124 | 188 | 347.585 | 65346 | 258 | 288.643 | 74470 | 9124 | -9124
60.* | RW - Stormwater Drainage (Box culverts only) |  | 0 | 0 | 0 | 206461 | 0 | 0 | 198407 | 0 | 0 | 177682 | 0 | 0 | 376089 | 93720 | -93720
60.01 | RW - Box culverts - supply & deliver only (all sizes) | lm | 307.8 | 541 | 204.298 | 110525 | 315 | 342.949 | 108029 | 251.5 | 221.976 | 55827 | 566.5 | 289.243 | 163856 | 71647 | -71648
60.02 | RW - Box culverts - quarry supply only | lm | 307.8 | 541 | 13.771 | 7450 | 315 | 38.086 | 11997 | 251 | 29.681 | 7450 | 566 | 34.359 | 19447 | 3184 | -3184
60.03 | RW - Box culverts - excavate, lay pies, & backfill (install components only) | lm | 307.8 | 541 | 99.277 | 53709 | 315 | 217.651 | 68560 | 251 | 250 | 62750 | 566 | 231.996 | 131310 | 17100 | -17100
60.04 | RW - Contamination (Cat "C") |  | 0 | 0 | 0 | 34777 | 315 | 31.178 | 9821 | 251 | 205.797 | 51655 | 566 | 108.615 | 61476 | 1789 | -1789
61.* | RW - Stormwater Drainage (Pits) |  | 0 | 0 | 0 | 81121 | 0 | 0 | 26550 | 0 | 0 | 155064 | 0 | 0 | 181614 | 1985 | -1986
61.01 | RW - SW Drain - Pits - Construct New | Each | 27 | 47 | 1010.17 | 47478 | 0 | 0 | 26550 | 41 | 2853.659 | 117000 | 41 | 3501.22 | 143550 | 1985 | -1985
61.02 | RW - SW Drain - Pits - Modify | Each | 27 | 10 | 1557.9 | 15579 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0
61.03 | RW - Contamination | Tonne | 71 | 71 | 97.056 | 6891 | 0 | 0 | 0 | 71 | 97.056 | 6891 | 71 | 97.056 | 6891 | 0 | 0
61.04 | RW - Connections to existing | Item | 1 | 1 | 11173 | 11173 | 0 | 0 | 0 | 0 | 0 | 11173 | 0 | 0 | 11173 | 0 | 0
62.* | RW - Stormwater drainage - Miscellaneous |  | 0 | 0 | 0 | 2517 | 0 | 0 | 720 | 0 | 0 | 14900 | 0 | 0 | 15620 | 720 | -720
62.01 | RW - Drainage (existing) - demolish | Item | 1 | 1 | 2517 | 2517 | 0 | 0 | 720 | 0 | 0 | 14900 | 0 | 0 | 15620 | 720 | -720
63.* | RW - Pavements Ex Apshalt |  | 0 | 0 | 0 | 180456 | 0 | 0 | 12071 | 0 | 0 | 86655 | 0 | 0 | 98726 | 15033 | -15032
63.01 | RW - Pavements CTCR Supply | sm | 3615 | 1355 | 38.755 | 52513 | 0 | 0 | 720 | 1355 | 8.806 | 11932 | 1355 | 9.337 | 12652 | 720 | -720
63.02 | RW - Pavements Crushed Rock Supply | sm | 6064 | 5557 | 10.265 | 57041 | 595 | 11.313 | 6731 | 4962 | 6.6 | 32749 | 5557 | 7.105 | 39480 | 9693 | -9692
63.03 | RW - Pavements CTCR Place | sm | 3616 | 1355 | 33.677 | 45632 | 0 | 0 | 0 | 1355 | 6.777 | 9183 | 1355 | 6.777 | 9183 | 0 | 0
63.04 | RW - Pavements Crushed Rock Place | sm | 6064 | 5557 | 4.547 | 25270 | 1140 | 4.053 | 4620 | 4417 | 7.424 | 32791 | 5557 | 6.732 | 37411 | 4620 | -4620
64.* | RW - Concrete Infills, concrete driveways, bluestone driveways |  | 0 | 0 | 0 | 140853 | 0 | 0 | 0 | 0 | 0 | 104946 | 0 | 0 | 104946 | 0 | 1
64.01 | RW - Conc Infills - Crushed Rock - Supply Only | sm | 1503 | 899 | 16.768 | 15074 | 0 | 0 | 0 | 899 | 5.204 | 4678 | 899 | 5.204 | 4678 | 0 | 0
64.02 | RW - Conc Infills- Crushed Rock - Place Only | sm | 1503 | 899 | 25.284 | 22730 | 0 | 0 | 0 | 899 | 9 | 8091 | 899 | 9 | 8091 | 0 | 0
64.03 | RW - Conc Infills - Concrete - Supply Only | sm | 1503 | 899 | 40.929 | 36795 | 0 | 0 | 0 | 899 | 20.79 | 18690 | 899 | 20.79 | 18690 | 0 | 0
64.04 | RW - Conc Infills - Concrete - Place Only | sm | 1503 | 899 | 64.103 | 57629 | 0 | 0 | 0 | 899 | 25 | 22475 | 899 | 25 | 22475 | 0 | 0
64.05 | RW - Conc Infill - Reo Supply | sm | 0 | 899 | 0 | 0 | 0 | 0 | 0 | 899 | 5.069 | 4557 | 899 | 5.069 | 4557 | 0 | 0
64.06 | RW - Driveways - Crushed Rock - Supply Only | sm | 75 | 617 | 0 | 0 | 0 | 0 | 0 | 616 | 3.047 | 1877 | 616 | 3.047 | 1877 | 0 | 0
64.07 | RW - Driveway - Crushed Rock - Place Only | sm | 75 | 616 | 14.002 | 8625 | 0 | 0 | 0 | 616 | 9 | 5544 | 616 | 9 | 5544 | 0 | 0
64.08 | RW - Driveways - Concrete - Supply Only | sm | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 616 | 26.399 | 16262 | 616 | 26.399 | 16262 | 0 | 0
64.09 | RW - Driveways - Concrete - Place Only | sm | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 616 | 30 | 18480 | 616 | 30 | 18480 | 0 | 0
64.1 | RW - Driveways - Reo Supply | sm | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 616 | 6.968 | 4292 | 616 | 6.968 | 4292 | 0 | 0
65.* | Kerb & Channel |  | 0 | 0 | 0 | 177832 | 0 | 0 | 6898 | 0 | 0 | 158470 | 0 | 0 | 165367 | 15261 | -15261
65.01 | RW - Kerb & Channel - Concrete Supply | lm | 2542 | 2788 | 18.314 | 51059 | 0 | 0 | 1584 | 2788 | 19.473 | 54292 | 2788 | 20.042 | 55876 | 1584 | -1584
65.02 | RW - Kerb & Channel - Lay - Include Kerb Bed | lm | 2542 | 2788 | 45.471 | 126773 | 0 | 0 | 5314 | 2788 | 37.367 | 104178 | 2788 | 39.272 | 109491 | 13677 | -13677
66.* | Asphalt |  | 0 | 0 | 0 | 1437851 | 0 | 0 | 0 | 0 | 0 | 1461586 | 0 | 0 | 1461586 | 0 | -1
66.01 | RW - ASPH - Pavement Type 1 (Inc TJ to Rego & Existing) | sm | 10502 | 1355 | 246.165 | 333553 | 0 | 0 | 0 | 1355 | 246.165 | 333553 | 1355 | 246.165 | 333553 | 0 | 0
66.02 | RW - ASPH - Pavement Type 2 (Inc TJ to Rego,Existing) | sm | 27823 | 4357 | 160.388 | 698811 | 0 | 0 | 0 | 4357 | 160.388 | 698811 | 4357 | 160.388 | 698811 | 0 | 0
66.03 | RW - ASPH - Pavement Type 3 (Inc TJ to Rego,Existing) | sm | 4501 | 883 | 115.571 | 102049 | 0 | 0 | 0 | 883 | 115.571 | 102049 | 883 | 115.571 | 102049 | 0 | 0
66.04 | RW - ASPH - Pavement Type 4 (Inc TJ to Rego,) | sm | 189 | 317 | 13.372 | 4239 | 0 | 0 | 0 | 317 | 88.246 | 27974 | 317 | 88.246 | 27974 | 0 | 0
66.05 | RW - ASPH - Pavement Type Rego and Overlay | sm | 13181 | 13181 | 14.683 | 193543 | 0 | 0 | 0 | 13181 | 14.683 | 193543 | 13181 | 14.683 | 193543 | 0 | 0
66.06 | RW - ASPH - Pavement Type Shepherd Bridge | sm | 3333 | 3333 | 14.683 | 48940 | 0 | 0 | 0 | 3333 | 14.683 | 48940 | 3333 | 14.683 | 48940 | 0 | 0
66.07 | RW - ASPH - Pavement - Profiling | cm | 886 | 886 | 64.014 | 56716 | 0 | 0 | 0 | 886 | 64.014 | 56716 | 886 | 64.014 | 56716 | 0 | 0
66.08 | RW - ASPH - Pavement - Kerb Patching | lm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67.* | Signs & Linemarking |  | 0 | 0 | 0 | 78695 | 0 | 0 | 0 | 0 | 0 | 78695 | 0 | 0 | 78695 | 0 | 0
67.01 | RW - LINEMARK - Pavement Markings – Final | Item | 1 | 1 | 32370 | 32370 | 0 | 0 | 0 | 1 | 32370 | 32370 | 1 | 32370 | 32370 | 0 | 0
67.02 | RW - SIGN - Existing Sign Relocations | Each | 18 | 18 | 510.944 | 9197 | 0 | 0 | 0 | 1 | 9197 | 9197 | 1 | 9197 | 9197 | 0 | 0
67.03 | RW - SIGN New Signs - Supply & Install | Item | 1 | 1 | 37128 | 37128 | 0 | 0 | 0 | 1 | 37128 | 37128 | 1 | 37128 | 37128 | 0 | 0
68.* | Shotcrete Wall North East Abutment |  | 0 | 0 | 0 | 102455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.01 | RW - WALL - Shotcrete Supply | sm | 150 | 150 | 23.807 | 3571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.02 | RW - WALL - Shotcrete Spray | sm | 150 | 150 | 193.307 | 28996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.03 | RW - WALL - Supply & Install Soil Nails | Ea | 84 | 84 | 629.286 | 52860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.04 | RW - WALL - Miscellaneous | sm | 150 | 150 | 113.52 | 17028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.* | Off Structure Barriers |  | 0 | 0 | 0 | 744299 | 0 | 0 | 17650 | 0 | 0 | 485490 | 0 | 0 | 503140 | 3390 | -3390
69.01 | RW - OSB - Supply of Medium Containment Barriers inc Transition + Shop Drawings | lm | 172 | 154 | 1076.494 | 165780 | 0 | 0 | 17650 | 154 | 1004.026 | 154620 | 154 | 1118.636 | 172270 | -9610 | 9610
69.02 | RW - OSB - Supply of Regular Containment Barriers | lm | 122 | 72 | 1579.111 | 113696 | 0 | 0 | 0 | 1 | 68520 | 68520 | 1 | 68520 | 68520 | 0 | 0
69.03 | RW - OSB - Install Medium Containment | lm | 172 | 154 | 151.429 | 23320 | 0 | 0 | 0 | 154 | 151.429 | 23320 | 154 | 151.429 | 23320 | 0 | 0
69.04 | RW - OSB - Install Regular Containment | lm | 122 | 72 | 237.514 | 17101 | 0 | 0 | 0 | 72 | 237.514 | 17101 | 72 | 237.514 | 17101 | 0 | 0
69.06 | RW - OSB - Strip Footing Conc Supply | cm | 264 | 264 | 173.125 | 45705 | 0 | 0 | 0 | 220 | 192.777 | 42411 | 220 | 192.777 | 42411 | 0 | 0
69.07 | RW - OSB - Strip Footing Reo Supply | Tonne | 42 | 42 | 1269.643 | 53325 | 0 | 0 | 0 | 26.44 | 1200 | 31728 | 26.44 | 1200 | 31728 | 0 | 0
69.08 | RW- OSB - Strip Footing Concrete Subbie | cm | 264 | 264 | 449.962 | 118790 | 0 | 0 | 0 | 0 | 0 | 118790 | 0 | 0 | 118790 | 0 | 0
69.1 | RW - OSB - Supply and Install Medium Containment Railing | lm | 172 | 172 | 651.453 | 112050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.11 | RW - OSB - Supply and Install Regular Containment Railing | lm | 122 | 122 | 446.984 | 54532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.12 | RW - OSB - End Posts | Ea | 4 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.13 | RW - OSB - Crash Cushion | Ea | 2 | 2 | 10000 | 20000 | 0 | 0 | 0 | 2 | 14500 | 29000 | 2 | 14500 | 29000 | 13000 | -13000
70.* | Sign Gantry |  | 0 | 0 | 0 | 72666 | 0 | 0 | 0 | 0 | 0 | 98009 | 0 | 0 | 98009 | 0 | 0
70.01 | RW - GANT - Manufacture & Deliv Gantry | Tonne | 13.5 | 13.5 | 4680.963 | 63193 | 0 | 0 | 0 | 0 | 0 | 83536 | 0 | 0 | 83536 | 0 | 0
70.02 | RW - GANT - Install Gantry | Tonne | 13.5 | 13.5 | 534.222 | 7212 | 0 | 0 | 0 | 0 | 0 | 7212 | 0 | 0 | 7212 | 0 | 0
70.03 | RW - GANT - Bridge Connections | Each | 4 | 4 | 565.25 | 2261 | 0 | 0 | 0 | 0 | 0 | 7261 | 0 | 0 | 7261 | 0 | 0
71.* | Traffic Signals |  | 0 | 0 | 0 | 472297 | 0 | 0 | 0 | 0 | 0 | 472297 | 0 | 0 | 472297 | 0 | -1
71.01 | RW - SIG - Traffic Signal Conduits - Supply | lm | 1441 | 1441 | 14.478 | 20863 | 0 | 0 | 0 | 0 | 0 | 20863 | 0 | 0 | 20863 | 0 | 0
71.02 | RW - SIG - Traffic Signal Pits - Supply |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71.03 | RW - SIGN - Crushed Rock Supply | lm | 946 | 946 | 2.504 | 2369 | 0 | 0 | 0 | 0 | 0 | 2369 | 0 | 0 | 2369 | 0 | 0
71.04 | RW - SIG - Excavate, Lay, Backfill | lm | 946 | 946 | 29.841 | 28230 | 0 | 0 | 0 | 0 | 0 | 28230 | 0 | 0 | 28230 | 0 | 0
71.05 | RW - SIG - UG Boring | lm | 495 | 495 | 157.903 | 78162 | 0 | 0 | 0 | 0 | 0 | 78162 | 0 | 0 | 78162 | 0 | 0
71.06 | RW - SIG - UG Boring Evap Pond | Item | 1 | 1 | 4973 | 4973 | 0 | 0 | 0 | 0 | 0 | 4973 | 0 | 0 | 4973 | 0 | 0
71.07 | RW - SIG - Traffic Signalling Subcontract | Item | 1 | 1 | 273000 | 273000 | 0 | 0 | 0 | 0 | 0 | 273000 | 0 | 0 | 273000 | 0 | 0
71.08 | RW - SIG - Dispose of Contam to Tip | Tonne | 670 | 670 | 96.567 | 64700 | 0 | 0 | 0 | 0 | 0 | 64700 | 0 | 0 | 64700 | 0 | 0
72.* | Landscaping |  | 0 | 0 | 0 | 11153 | 0 | 0 | 1295 | 0 | 0 | 41472 | 0 | 0 | 42767 | 0 | 0
72.01 | RW - LAND - Topsoil Seeding | sm | 1153 | 1153 | 1 | 1153 | 0 | 0 | 0 | 0 | 0 | 11472 | 0 | 0 | 11472 | 0 | 0
72.02 | RW - LAND - Landscaping Subbie | Item | 1 | 1 | 10000 | 10000 | 0 | 0 | 1295 | 0 | 0 | 30000 | 0 | 0 | 31295 | 0 | 0
73.* | Overheight Detection System |  | 0 | 0 | 0 | 38556 | 0 | 0 | 0 | 0 | 0 | 38556 | 0 | 0 | 38556 | 0 | 0
73.01 | RW - OHD - Relocate existing pole, convert existing VMS to STREAMS and install new control cabinet:, install new POS or extend power from existing supply; supply and install new sensors:; | Item | 1 | 1 | 28024 | 28024 | 0 | 0 | 0 | 0 | 0 | 28024 | 0 | 0 | 28024 | 0 | 0
73.02 | RW - OHD - Civils e.g. cabinet foundation, pole foundation, & minor conduiting | Item | 1 | 1 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 9000 | 0 | 0
73.03 | RW - OHD - Contamination - disposal of "Cat" C material | Tonne | 15.75 | 15.75 | 97.27 | 1532 | 0 | 0 | 0 | 0 | 0 | 1532 | 0 | 0 | 1532 | 0 | 0
74.* | Street Lighting |  | 0 | 0 | 0 | 369845 | 0 | 0 | 0 | 0 | 0 | 418661 | 0 | 0 | 418661 | 0 | 0
74.01 | RW - LIGHT - Street Lighting (Conduits) - supply & deliver | lm | 855 | 855 | 18.255 | 15608 | 0 | 0 | 0 | 0 | 0 | 15608 | 0 | 0 | 15608 | 0 | 0
74.02 | RW - LIGHT - Street Lighting (Pits) - supply & deliver |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74.03 | RW - LIGHT Street Lighting (quarry products) - supply & deliver | lm | 520 | 520 | 4.95 | 2574 | 0 | 0 | 0 | 0 | 0 | 2574 | 0 | 0 | 2574 | 0 | 0
74.04 | RW - LIGHT - Street Lighting (open cut civils) - excavate, lay conduits, backfill | lm | 520 | 520 | 60.581 | 31502 | 0 | 0 | 0 | 0 | 0 | 31502 | 0 | 0 | 31502 | 0 | 0
74.05 | RW - LIGHT - Street Lighting (boring) - thrust pits, bore, install conduits, & grout annulus (if required) | lm | 335 | 335 | 90.991 | 30482 | 0 | 0 | 0 | 0 | 0 | 30482 | 0 | 0 | 30482 | 0 | 0
74.06 | RW - LIGHT - Street Lighting - poles, lanterns, cabling, terminations, Point of Supply connections etc | Item | 1 | 1 | 258000 | 258000 | 0 | 0 | 0 | 0 | 0 | 306816 | 0 | 0 | 306816 | 0 | 0
74.07 | RW - LIGHT Contamination - cart & dispose to tip | Tonne | 328 | 328 | 96.582 | 31679 | 0 | 0 | 0 | 0 | 0 | 31679 | 0 | 0 | 31679 | 0 | 0
75.* | ITS Counter |  | 0 | 0 | 0 | 50080 | 0 | 0 | 0 | 0 | 0 | 10080 | 0 | 0 | 10080 | 0 | 0
75.01 | RW - ITS - ITS Counter (CamLex Electrical Signalling & Lighting price to relocate) including relocation of traffic loops, pit, & control cabinet | Item | 1 | 1 | 50080 | 50080 | 0 | 0 | 0 | 0 | 0 | 10080 | 0 | 0 | 10080 | 0 | 0
76.* | Footpaths |  | 0 | 0 | 0 | 175769 | 0 | 0 | 0 | 0 | 0 | 89791 | 0 | 0 | 89791 | 0 | 0
76.01 | RW - FOOTPATH - Footpaths (crushed rock) - supply & deliver | sm | 1929 | 1274 | 12.601 | 16054 | 0 | 0 | 0 | 1274 | 6.381 | 8130 | 1274 | 6.381 | 8130 | 0 | 0
76.02 | RW - FOOTPATH - Footpaths (crushed rock) - place | sm | 1929 | 1274 | 20.142 | 25661 | 0 | 0 | 0 | 1274 | 9 | 11466 | 1274 | 9 | 11466 | 0 | 0
76.03 | RW - FOOTPATH - Footpaths (concrete) - supply & deliver | sm | 1929 | 1274 | 33.223 | 42326 | 0 | 0 | 0 | 1274 | 24.957 | 31795 | 1274 | 24.957 | 31795 | 0 | 0
76.04 | RW - FOOTPATH - Footpaths (concrete) - place concrete, edge forms etc | sm | 1929 | 1274 | 61.401 | 78225 | 0 | 0 | 0 | 1274 | 25 | 31850 | 1274 | 25 | 31850 | 0 | 0
76.05 | RW - FOOTPATH - Reinforcement - supply only | sm | 1929 | 1274 | 10.599 | 13503 | 0 | 0 | 0 | 1274 | 5.141 | 6550 | 1274 | 5.141 | 6550 | 0 | 0
7B25P4 | AusNet Gas -TP Relocation | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.* | SHEPHERD BRIDGE STRUCTURE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81.* | SB - Access Provisions |  | 0 | 0 | 0 | 378185 | 0 | 0 | 60797 | 0 | 0 | 240638 | 0 | 0 | 301435 | 363 | -362
81.01 | SB - ACCESS - Temp Services | Item | 1 | 1 | 26650 | 26650 | 0 | 0 | 665 | 1 | 26650 | 26650 | 1 | 27315 | 27315 | 0 | 0
81.02 | SB - ACCESS - Extra Access Costs/Deck Repairs | Item | 1 | 1 | 65291 | 65291 | 0.1 | 38930 | 3893 | 0.9 | 33333.333 | 30000 | 1 | 33893 | 33893 | 0 | 0
81.03 | SB - ACCESS CIG - Widening/Transverse | Item | 1 | 1 | 286244 | 286244 | 0.233 | 241369.099 | 56239 | 0.793 | 232015.132 | 183988 | 1.026 | 234139.376 | 240227 | 363 | -362
82.* | Marine Traffic Management |  | 0 | 0 | 0 | 176156 | 0 | 0 | 15941 | 0 | 0 | 176156 | 0 | 0 | 192097 | 3044 | -3044
82.01 | SB - MARINE - Marine Traffic Management | Item | 1 | 1 | 176156 | 176156 | 0 | 0 | 15941 | 0 | 0 | 176156 | 0 | 0 | 192097 | 3044 | -3044
83.* | Hinge Joint Modifications - Demolition |  | 0 | 0 | 0 | 114186 | 0 | 0 | 0 | 0 | 0 | 114186 | 0 | 0 | 114186 | 0 | 1
83.01 | SB - HINGE - Demolition - Concrete Deck & bend back the existing reinforcement bars | cm | 13 | 13 | 7701.923 | 100125 | 0 | 0 | 0 | 0 | 0 | 100125 | 0 | 0 | 100125 | 0 | 0
83.02 | SB - HINGE - Existing steel girders - prepare girder & bend back the existing reinforcement bars | Item | 1 | 1 | 14061 | 14061 | 0 | 0 | 0 | 0 | 0 | 14061 | 0 | 0 | 14061 | 0 | 0
84.* | Hinge Joint Modifications - Steelwork |  | 0 | 0 | 0 | 138771 | 0 | 0 | 0 | 0 | 0 | 93087 | 0 | 0 | 93087 | 0 | 1
84.01 | SB - HINGE - Steel plate (new) - supply, protective coat, & deliver | Tonne | 2.14 | 2.14 | 3129.907 | 6698 | 0 | 0 | 0 | 0 | 0 | 6698 | 0 | 0 | 6698 | 0 | 0
84.02 | SB - HINGE - Structural Bolts - supply & deliver | Each | 855 | 855 | 5.325 | 4553 | 0 | 0 | 0 | 0 | 0 | 4553 | 0 | 0 | 4553 | 0 | 0
84.03 | SB - HINGE - Steel Road Plates (temporary) - supply and install | sm | 101 | 101 | 452.317 | 45684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84.04 | SB - HINGE - Steel plate (new) - install only | Each | 135 | 135 | 606.193 | 81836 | 0 | 0 | 0 | 0 | 0 | 81836 | 0 | 0 | 81836 | 0 | 0
85.* | Hinge Joint Modifications - Concrete Works |  | 0 | 0 | 0 | 68078 | 0 | 0 | 0 | 0 | 0 | 91517 | 0 | 0 | 91517 | 23439 | -23438
85.01 | SB - HINGE - Concrete - supply, deliver, & test | cm | 12.8 | 12.8 | 179.453 | 2297 | 0 | 0 | 0 | 0 | 0 | 2297 | 0 | 0 | 2297 | 0 | 0
85.02 | SB - HINGE - Reinforcement - supply & fix | Tonne | 4.2 | 4.2 | 2266.429 | 9519 | 0 | 0 | 0 | 0 | 0 | 9519 | 0 | 0 | 9519 | 0 | 0
85.03 | SB - HINGE - Formwork - supply & install | cm | 12.8 | 12.8 | 2764.766 | 35389 | 0 | 0 | 0 | 0 | 0 | 58828 | 0 | 0 | 58828 | 23439 | -23439
85.04 | SB - HINGE - Plant Openings | Shift | 2 | 2 | 3198 | 6396 | 0 | 0 | 0 | 0 | 0 | 6396 | 0 | 0 | 6396 | 0 | 0
85.05 | SB - HINGE - Place Concrete | cm | 12.8 | 12.8 | 393.828 | 5041 | 0 | 0 | 0 | 0 | 0 | 5041 | 0 | 0 | 5041 | 0 | 0
85.06 | SB - HINGE - Waterproof Membrane | sm | 90.3 | 90.3 | 104.496 | 9436 | 0 | 0 | 0 | 0 | 0 | 9436 | 0 | 0 | 9436 | 0 | 0
86.* | Strengthening Works |  | 0 | 0 | 0 | 493423 | 0 | 0 | 3600 | 0 | 0 | 666796 | 0 | 0 | 670396 | 1373 | -1373
86.01 | SB - PIER - CT Stress Bars to River Piers | Each | 16 | 16 | 1933.875 | 30942 | 0 | 0 | 0 | 1 | 72315 | 72315 | 1 | 72315 | 72315 | 1373 | -1373
86.02 | SB - CARBON - Carbon Fibre Strengthening | Item | 1 | 1 | 425728 | 425728 | 0 | 0 | 3600 | 1 | 557728 | 557728 | 1 | 561328 | 561328 | 0 | 0
86.03 | SB - ANCHORAGE - Steel Anchorage Strengthening | Item | 1 | 1 | 36753 | 36753 | 0 | 0 | 0 | 1 | 36753 | 36753 | 1 | 36753 | 36753 | 0 | 0
87.* | Rigid Frame Strengthening |  | 0 | 0 | 0 | 113797 | 0 | 0 | 0 | 0 | 0 | 113797 | 0 | 0 | 113797 | 0 | 0
87.01 | SB - RIGID FRAME - Rigid Frame Strengthening (demolition, coring, water proofing, reinforcement supply & place, & concrete supply & place) | Item | 1 | 1 | 113797 | 113797 | 0 | 0 | 0 | 1 | 113797 | 113797 | 1 | 113797 | 113797 | 0 | 0
88.* | Waterproofing to Abutments |  | 0 | 0 | 0 | 10070 | 0 | 0 | 0 | 0 | 0 | 10070 | 0 | 0 | 10070 | 0 | 0
88.01 | SB - ABUT - Abutment Waterproofing | Item | 1 | 1 | 10070 | 10070 | 0 | 0 | 0 | 1 | 10070 | 10070 | 1 | 10070 | 10070 | 0 | 0
89.* | Bridge Widening - Demolition |  | 0 | 0 | 0 | 592346 | 0 | 0 | 260308 | 0 | 0 | 431867 | 0 | 0 | 692175 | 234171 | -234171
89.01 | SB - WIDEN - Demolition - Internal Concrete Nibs | cm | 542 | 800 | 691.11 | 552888 | 160 | 239.838 | 38374 | 640 | 150 | 96000 | 800 | 167.968 | 134374 | 800 | -800
89.02 | SB - WIDEN - Demolition - Precast Slab/Bitumen/Stab Sand | sm | 1120 | 1120 | 6.659 | 7458 | 430 | 25.309 | 10883 | 550 | 18.182 | 10000 | 980 | 21.309 | 20883 | 3278 | -3278
89.03 | SB - WIDEN - Demolition - Remove Steel Railing | lm | 320 | 320 | 100 | 32000 | 160 | 32.95 | 5272 | 160 | 51.594 | 8255 | 320 | 42.272 | 13527 | 480 | -480
89.04 | SB - WIDEN - Demolition Concrete Edge Beam | LM | 320 | 320 | 0 | 0 | 0 | 0 | 69212 | 320 | 375 | 120000 | 320 | 591.288 | 189212 | 134737 | -134737
89.05 | SB - WIDEN - Demolition - Remove Curtain Wall | m | 148 | 0 | 0 | 0 | 0.5 | 32272 | 16136 | 0.5 | 29240 | 14620 | 1 | 30756 | 30756 | 1988 | -1988
89.06 | SB - WIDEN - Demolition - Waterblasting | M3 | 26 | 26 | 0 | 0 | 0 | 0 | 107507 | 26 | 4807.692 | 125000 | 26 | 8942.577 | 232507 | 90652 | -90652
89.07 | SB - WIDEN - Demolition - Drill and Supply Epoxy Starter Bars | EA | 2140 | 2140 | 0 | 0 | 0 | 0 | 12924 | 2140 | 27.099 | 57992 | 2140 | 33.138 | 70916 | 2236 | -2236
90.* | Bridge Widening - In Situ Concrete Works |  | 0 | 0 | 0 | 298764 | 0 | 0 | 192070 | 0 | 0 | 280076 | 0 | 0 | 472146 | 108371 | -108371
90.01 | SB - WIDEN - Bridge Widening (In Situ Concrete Works) - formwork (supply & place), concrete (place only), scabbling | sm | 480 | 480 | 545.219 | 261705 | 0 | 0 | 182604 | 0 | 0 | 218006 | 0 | 0 | 400610 | 98905 | -98905
90.02 | SB - WIDEN - Bridge Widening (In Situ Concrete Works) - Reinforcement & Bolts - Supply | Tonne | 480 | 29.3 | 861.843 | 25252 | 3.67 | 1953.134 | 7168 | 22.33 | 1708.912 | 38160 | 26 | 1743.385 | 45328 | 7168 | -7168
90.03 | SB - WIDEN - Bridge Widening (In Situ Concrete Works) - Concrete Supply & test | m3 | 480 | 90 | 131.189 | 11807 | 7.6 | 302.368 | 2298 | -7.6 | -3146.053 | 23910 | 0 | 0 | 26208 | 2298 | -2298
92.* | Bridge Widening - Parapets |  | 0 | 0 | 0 | 373412 | 0 | 0 | 126540 | 0 | 0 | 203766 | 0 | 0 | 330306 | 5041 | -5041
92.01 | SB - WIDEN - Parapets - supply & deliver | lm | 320 | 320 | 784.363 | 250996 | 0.577 | 219306.759 | 126540 | 0.423 | 219260.047 | 92747 | 1 | 219287 | 219287 | 5041 | -5041
92.02 | SB - WIDEN - Parapets - install | lm | 320 | 320 | 189.022 | 60487 | 0 | 0 | 0 | 320 | 189.022 | 60487 | 320 | 189.022 | 60487 | 0 | 0
92.03 | SB - WIDEN - Stich Pour - concrete supply | lm | 320 | 320 | 10.209 | 3267 | 0 | 0 | 0 | 0 | 0 | 4691 | 0 | 0 | 4691 | 0 | 0
92.04 | SB - WIDEN - Stich Pour - reinforcement - supply & fix | lm | 320 | 320 | 8.394 | 2686 | 0 | 0 | 0 | 0 | 0 | 2458 | 0 | 0 | 2458 | 0 | 0
92.05 | SB - WIDEN - Stich Pour - place concrete | lm | 320 | 320 | 135.572 | 43383 | 0 | 0 | 0 | 0 | 0 | 43383 | 0 | 0 | 43383 | 0 | 0
92.06 | SB - WIDEN - Painting | lm | 320 | 320 | 39.353 | 12593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93.* | Bridge Widening - Steel Railing |  | 0 | 0 | 0 | 208446 | 0 | 0 | 0 | 0 | 0 | 255000 | 0 | 0 | 255000 | 0 | 0
93.01 | SB - WIDEN - Bridge Widening - Steel Railing - Supply & Install | lm | 320 | 320 | 651.394 | 208446 | 0 | 0 | 0 | 0 | 0 | 255000 | 0 | 0 | 255000 | 0 | 0
94.* | Bridge Widening - Expansion Joint |  | 0 | 0 | 0 | 326287 | 0 | 0 | 0 | 0 | 0 | 281385 | 0 | 0 | 281385 | -44902 | 44902
94.01 | SB -EJ - Bridge Widening - Expansion Joint (Existing) - Demolition | Item | 1 | 1 | 44902 | 44902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44902 | 44902
94.02 | SB - EJ - Bridge Widening - Expansion Joint (New) - supply & install | lm | 204 | 204 | 1379.338 | 281385 | 0 | 0 | 0 | 0 | 0 | 281385 | 0 | 0 | 281385 | 0 | 0
95.* | Schedule 3A - Shepherds Bridge over-height detection system |  | 0 | 0 | 0 | 152328 | 0 | 0 | 0 | 0 | 0 | 99380 | 0 | 0 | 99380 | 0 | 1
95.01 | RW - OHD - New VMS sign including cabling, terminations etc | Item | 1 | 1 | 87894 | 87894 | 0 | 0 | 0 | 0 | 0 | 87894 | 0 | 0 | 87894 | 0 | 0
95.02 | RW - OHD - Cantilever pole - supply & install | Item | 1 | 1 | 52948 | 52948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95.03 | RW - OHD - Civils eg cabinet foundation, pole foundation, & minor conduiting | Item | 1 | 1 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 7000 | 0 | 0
95.04 | RW - OHD - Contamination - disposal of Cat "C" | Tonne | 677 | 677 | 6.626 | 4486 | 0 | 0 | 0 | 0 | 0 | 4486 | 0 | 0 | 4486 | 0 | 0
P1 | Provisional - Daywork | Item | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P3 | Provisional - Testing of Earthwork & Pavement Materials | Item | 1 | 1 | 0 | 0 | 0 | 0 | 3119 | 0 | 0 | 0 | 0 | 0 | 3119 | 3119 | -3119
P4 | Utilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P4.01 | Provisional - Utlities | Item | 1 | 1 | 81870 | 81870 | 0.791 | 584006.321 | 461949 | 0.21 | 1458028.571 | 306186 | 1.001 | 767367.632 | 768135 | 0 | 0
P4.02 | Provisional - Utilities - Water Main Footpath |  | 1 | 1 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 44089 | 0 | 0 | 44889 | 0 | 0
P4.03 | Provisional Utilities - FH HV Works | LS | 0 | 0 | 0 | 0 | 0 | 0 | 14328 | 0 | 0 | 0 | 0 | 0 | 14328 | 1016 | -1016
P5 | Provisional - Concrete Crack Repair | Item | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P6 | Provisional - Asphalt Pavement Repair | sm | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P7 | Provisional - Asphalt Regulation | Tonne | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
{_Misallocation} | Misallocations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ungrouped |  |  | 0 | 0 | 0 | 17313604 | 0 | 0 | 4134668 | 0 | 0 | 14633894 | 0 | 0 | 18768562 | 194338 | -194337