## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-001 - Clearing and Grubbing | [5 empty] | FHC-ITP-001 - Clearing and Grubbing
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Flora & Fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
label | REFERENCE DOCUMENTS: EMP, ECP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.4 Permit to distrurb flora & fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | REFERENCE DOCUMENTS: EMP, ECP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
section | Clear & Grub
checkpoint | 2.1 Define work area
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | REFERENCE DOCUMENTS: 201.03
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
textbox | Date Completed:
checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
label | REFERENCE DOCUMENTS: Drawings 201.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Identify No-go Zones
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
label | • Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
label | • Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP. Any works required inside TPZ shall be completed under the supervision of an Arborist
label | REFERENCE DOCUMENTS: Drawings 201.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Clear felling distances of trees are adequate.
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
label | REFERENCE DOCUMENTS: 201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Clear and grub trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
label | • Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
label | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.6 Backfill holes
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
label | REFERENCE DOCUMENTS: 201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.7 Dispose of Trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works. Noxious weeds shall not be mulched.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: