## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-004 - Type A Fill Placement Rev3 | [5 empty] | FHC-ITP-004 - Type A Fill Placement Rev3
section | Preliminary Works
checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Placement/ Each Lot
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Verify Material
label | FREQUENCY: Prior to Placement
label | ACCEPTANCE CRITERIA: Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive.
label | • Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075. PI between 6 and 25. Permeability of less than 5X10^-9 for capping and verge material
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b), Cl. 204.06(c), Table 204.041, Table 3020.052
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Record (If silt is observed)
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
label | • Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Survey set-out
label | FREQUENCY: Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | 2.2 Inspection of fill area
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: 204.10 (b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Layer Thickness
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Maximum Lot Size
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.5 Type A Placement
label | FREQUENCY: Prior to Placement/ Each Lot
label | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas
label | • Any rocky material present must be uniform throughout the layer
label | • Each layer shall be kept generally parallel to the surface of subgrade
label | REFERENCE DOCUMENTS: 204.10 (d) (i)., 204.10 (d) (ii)., Table 3020.052
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.6 Proof Roll
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Site Foreman/ Superintendent
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Reduced Test Frequency
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
label | INSPECTION/TEST METHOD: Test Record
label | RECORD OF CONFORMITY: Test Records
label | AP
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
checkpoint | 3.2 Compaction Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Compaction Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.3 Maximum Particle Size
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii), Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Maximum Particle Size Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.4 CBR/Swell
label | FREQUENCY: First lot then every Second thereafter
label | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(i), Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: CBR/Swell Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.5 Atterberg Limit Tests
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii), Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: PI Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.6 Permeability
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii), Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Permeability Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.7 Material Property Testing (Scale B)
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
label | REFERENCE DOCUMENTS: Cl 204.04, Cl204.14
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: NATA test report
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.8 Survey Conformance
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
label | • Scale B:
label | ○ Range x = +5,-25
label | ○ Max S = 15mm
label | ○ 40 measurements per lot
label | REFERENCE DOCUMENTS: 204.03
label | INSPECTION/TEST METHOD: Survey conformance point
label | RECORD OF CONFORMITY: Survey report, Lot Register
label | WP / SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: