## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-014 - Subsurface Drainage Rev2 | [5 empty] | FHC-ITP-014 - Subsurface Drainage Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Placement of no fines concrete
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
label | REFERENCE DOCUMENTS: 702.09(g)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 Material Classification
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes:
label | ○ 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | • Granular filter material for bedding and backfill:
label | ○ Trench backfilled and bedded with specified material on drawings
label | • Geotextiles:
label | ○ Shall comply with Cl 702.06.
label | • Subsurface drain pits:
label | ○ All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | • Pit Lids:
label | ○ Type M3 circular lid (as per SD 1051) for Type S1 pit
label | • Flushout risers:
label | ○ Constructed to the detail of SD 1631
label | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 1.5 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | • Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.6 Excavation of Trench
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
label | REFERENCE DOCUMENTS: 702.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 Placement of bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | REFERENCE DOCUMENTS: 702.09 (c)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.8 Placing pipes and geofabric (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | • If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | REFERENCE DOCUMENTS: 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.9 Placement of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
label | REFERENCE DOCUMENTS: 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.0 Install Pits and Flushouts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: 702.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.1 Flushing Test
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | REFERENCE DOCUMENTS: 702.09(i), 702.09(h)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
textbox | Date Completed:
checkpoint | 2.2 CCTV
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
label | REFERENCE DOCUMENTS: 702.09(i)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: