## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Ventilation - First fix |  |  |  |  | Yes | Ventilation - First fix | 76c7a1d9-847e-4928-9dee-b66c3b78ef5c
checkpoint-group |  |  | section | Fan
checkpoint-status |  |  | checkpoint | Suspended in accessible location
checkpoint-status |  |  | checkpoint | Sitting level
checkpoint-status |  |  | checkpoint | Power Supply brought up to surface mount powerpoint
checkpoint-status |  |  | checkpoint | Power supply run to switch as shown on plan.
checkpoint-status |  |  | checkpoint | Filter
checkpoint-status |  |  | checkpoint | Filter box installed in accessible location
checkpoint-status |  |  | checkpoint | Filter inside filter box
checkpoint-group |  |  | section | Ducting
checkpoint-status |  |  | checkpoint | Ducting run to locations shown on plan
checkpoint-status |  |  | checkpoint | Air inlet is brought out in correct location
checkpoint-status |  |  | checkpoint | Air inlet has tradeseal
checkpoint-status |  |  | checkpoint | All joins are taped
checkpoint-status |  |  | checkpoint | Grille locations marked on plan
checklist-sectioned |  |  | checklist | Ventilation - Second fix |  |  |  |  | Yes | Ventilation - Second fix | 0e51ad6e-2044-40da-ae10-56e5e940c6ed
checkpoint-group |  |  | section | Grilles
checkpoint-status |  |  | checkpoint | All internal grilles are fitted off
checkpoint-status |  |  | checkpoint | Air inlet is fitted off and sealed
checkpoint-group |  |  | section | Testing/Commissioning
checkpoint-status |  |  | checkpoint | Fan switch is fitted off
checkpoint-status |  |  | checkpoint | Fan switch is labelled
checkpoint-status |  |  | checkpoint | Fan works on switch (switch is up the right way)
checkpoint-status |  |  | checkpoint | Air flow felt through all supply grilles.
checklist-sectioned |  |  | checklist | Ducted Prepipe |  |  |  |  | Yes | Ducted Prepipe | 7427c985-f347-4f2b-941f-88d771d26952
checkpoint-group |  |  | section | Indoor Unit
checkpoint-status |  |  | checkpoint | Hung level (all axis)
checkpoint-status |  |  | checkpoint | Threaded rod/nuts tight and secure
checkpoint-status |  |  | checkpoint | Supply plenum installed
checkpoint-status |  |  | checkpoint | Top plate stiffener
checkpoint-status |  |  | checkpoint | Indoor unit model and serial number
checkpoint-group |  |  | section | Pair coil pipe run
checkpoint-status |  |  | checkpoint | Pipes run straight down wall
checkpoint-status |  |  | checkpoint | Pipes supports through roof cavity to indoor unit
checkpoint-status |  |  | checkpoint | Pipes supported down wall to exterior
checkpoint-status |  |  | checkpoint | Pipes brought out exterior in protective pipe with tradeseal
checkpoint-status |  |  | checkpoint | Pipes brought up to indoor, connected and insulated
checkpoint-group |  |  | section | Drain
checkpoint-status |  |  | checkpoint | Drain trap is installed
checkpoint-status |  |  | checkpoint | Drain has fall the length of run
checkpoint-status |  |  | checkpoint | Drain exits exterior wall with tradeseal
checkpoint-group |  |  | section | Power supply/cabling
checkpoint-status |  |  | checkpoint | Interconnect is supported by pipes and/or pin clips
checkpoint-status |  |  | checkpoint | Indoor feed at switchboard
checkpoint-status |  |  | checkpoint | Outdoor feed at switchboard
checkpoint-status |  |  | checkpoint | Indoor isolator
checkpoint-status |  |  | checkpoint | Indoor electrical connections
checkpoint-status |  |  | checkpoint | Outdoor feed at switchboard
checkpoint-status |  |  | checkpoint | Outdoor isolator loop with tradeseal
checkpoint-status |  |  | checkpoint | Controller cable run and brought out through flushbox
checkpoint-group |  |  | section | Return grille(s)
checkpoint-status |  |  | checkpoint | Framed in on 2 sides
checkpoint-status |  |  | checkpoint | Framing is above gib line
checkpoint-status |  |  | checkpoint | Neck adapter installed
checkpoint-group |  |  | section | Ducting
checkpoint-status |  |  | checkpoint | Supply ducting installed
checkpoint-status |  |  | checkpoint | Return ducting installed
checkpoint-status |  |  | checkpoint | Grille locations marked on plan
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Highwall Fitoff |  |  |  |  | Yes | Highwall Fitoff | 17165294-e75e-40c6-9106-0ad64d115207
checkpoint-group |  |  | section | Indoor unit
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-status |  |  | checkpoint | Drain fitted and secured
checkpoint-status |  |  | checkpoint | Pipes insulated
checkpoint-status |  |  | checkpoint | Wiring correct
checkpoint-group |  |  | section | Outdoor unit
checkpoint-status |  |  | checkpoint | Unit is level
checkpoint-status |  |  | checkpoint | Unit is on feet
checkpoint-status |  |  | checkpoint | Isolator installed with correct terminations
checkpoint-status |  |  | checkpoint | Wall penetration is sealed
checkpoint-status |  |  | checkpoint | Wall cap installed
checkpoint-status |  |  | checkpoint | Pipe connections correct
checkpoint-status |  |  | checkpoint | Electrical connections are correct
checkpoint-group |  |  | section | Drain
checkpoint-status |  |  | checkpoint | Securely fitted off
checkpoint-group |  |  | section | Unit details
checkpoint-status |  |  | checkpoint | Indoor unit
checkpoint-status |  |  | checkpoint | Outdoor unit
checkpoint-group |  |  | section | Power Supply
checkpoint-status |  |  | checkpoint | MCB fitted off
checkpoint-status |  |  | checkpoint | Switchboard labelled
checkpoint-status |  |  | checkpoint | Test results
checkpoint-status |  |  | checkpoint | COC completed
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Commissioning sheet
checkpoint-status |  |  | checkpoint | Remote and instruction book left on site
checkpoint-status |  |  | checkpoint | Ampt sticker on outdoor unit
checkpoint-status |  |  | checkpoint | photos
checklist-flat |  |  | checklist | Walkthrough |  |  |  |  | Yes | Walkthrough Checklist | 5bced69f-bc4f-4810-970f-037b8a570886
checkpoint-status |  |  | checkpoint | Power outlet locations confirmed and marked
checkpoint-status |  |  | checkpoint | Light switch locations confirmed and marked
checkpoint-status |  |  | checkpoint | Switchboard locations confirmed and marked
checkpoint-status |  |  | checkpoint | Bathroom outlet locations confirmed and marked
checkpoint-status |  |  | checkpoint | Bathroom outlets vertical or horizontal
checkpoint-status |  |  | checkpoint | Towel rail locations confirmed and marked
checkpoint-status |  |  | checkpoint | Interior light locations confirmed
checkpoint-status |  |  | checkpoint | Exterior light locations confirmed and marked
checkpoint-status |  |  | checkpoint | Exterior fan grills soffit mount or wall mount
checkpoint-status |  |  | checkpoint | CCTV locations confirmed
checkpoint-status |  |  | checkpoint | CCTV soffit mount or wall mount
checkpoint-status |  |  | checkpoint | Aerial locations confirmed
checkpoint-status |  |  | checkpoint | Aerial cabling location confirmed and marked
checkpoint-status |  |  | checkpoint | Plans updated with changes
checklist-sectioned |  |  | checklist | Ducted fit off |  |  |  |  | Yes | Ducted fit off | eb99a3ad-d3b3-46f5-89bc-81312eb5ad99
checkpoint-group |  |  | section | Outdoor unit
checkpoint-status |  |  | checkpoint | Sitting on feet
checkpoint-status |  |  | checkpoint | Sitting level
checkpoint-status |  |  | checkpoint | Isolator installed
checkpoint-status |  |  | checkpoint | Sealed penetration
checkpoint-status |  |  | checkpoint | Wall cap installed
checkpoint-status |  |  | checkpoint | Pipe connections complete
checkpoint-status |  |  | checkpoint | Electrical connections complete
checkpoint-status |  |  | checkpoint | Ampt sticker on unit
checkpoint-status |  |  | checkpoint | Drain
checkpoint-status |  |  | checkpoint | Fitted off appropriately with a cobra clamp (using screws)
checkpoint-group |  |  | section | Return grille(s)
checkpoint-status |  |  | checkpoint | Fitted into neck adapters
checkpoint-status |  |  | checkpoint | No gaps evident around flange
checkpoint-group |  |  | section | Supply grilles
checkpoint-status |  |  | checkpoint | All installed
checkpoint-status |  |  | checkpoint | Clean
checkpoint-group |  |  | section | Power Supply
checkpoint-status |  |  | checkpoint | Fitted off at MCB
checkpoint-status |  |  | checkpoint | Labelled in switchboard
checkpoint-status |  |  | checkpoint | Testing complete
checkpoint-status |  |  | checkpoint | COC filled in
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Commisioning sheet completed
checkpoint-status |  |  | checkpoint | Air coming from all grilles
checkpoint-status |  |  | checkpoint | Instruction manual left on site
checkpoint-status |  |  | checkpoint | Outdoor unit model and serial number
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Highwall Prepipe |  |  |  |  | Yes | Highwall Prepipe | e39aefad-7aaf-456b-af60-de7828632f33
checkpoint-group |  |  | section | Top Plate
checkpoint-status |  |  | checkpoint | Top plate stiffeners x2
checkpoint-group |  |  | section | Pair coil pipe run
checkpoint-status |  |  | checkpoint | Pipes run straight down wall
checkpoint-status |  |  | checkpoint | Pipes secured at indoor unit and bent at right heigh
checkpoint-status |  |  | checkpoint | Supports are in place on pipework
checkpoint-status |  |  | checkpoint | Interconnect fixed at 300 centres/taped to pipework
checkpoint-group |  |  | section | Exterior pipework
checkpoint-status |  |  | checkpoint | Pipe protection installed
checkpoint-status |  |  | checkpoint | Tradeseal affixed
checkpoint-group |  |  | section | Drain installation
checkpoint-status |  |  | checkpoint | Indoor taped to bottom of pipes
checkpoint-status |  |  | checkpoint | Exterior brought through building paper with protection pipe and tradeseal
checkpoint-group |  |  | section | Powersupply
checkpoint-status |  |  | checkpoint | Feed located at switchboard
checkpoint-status |  |  | checkpoint | Isolator loop with tradeseal
checkpoint-status |  |  | checkpoint | Tail brought out with pipework
checkpoint-status |  |  | checkpoint | Photos