## Proj Resources
type | name | values | prefix | postfix | Template Name | Template Id
checklist | Pre start stage
section | Drawings
checkpoint | Drawings saved in job
checkpoint | Unit/plant selections labelled on drawings
checkpoint | AC pipe sizes shown on drawings
checkpoint | Ducting sizes shown on drawings
checkpoint | Penetrations to wall and roof are shown(with sizes)
checkpoint | Condensate connection points marked on drawings
Checkpoint | Photos
section | Purchasing
checkpoint | All plant has been ordered for first fix
checkpoint | All plant has been ordered for second fix (check Programme)
Checkpoint | Photos
section | Health and Safety
checkpoint | SSSP has been produced
checkpoint | SSSP has been dropped to site office
checklist | First Fix
section | Penetrations
checkpoint | Penetrations are marked out on roof and walls
checkpoint | penetrations being done by builder. Builder has been infomed of our requirements
checkpoint | Photos
section | AC Preppies and prewire
checkpoint | AC Units ( Ducted or Cassette ) Units have been hung and siesmically restrained
checkpoint | AC Units refrigeration pipe and interconnect cable runs between indoor and outdoor. Connected at indoor if cassete or ducted
checkpoint | AC Units Condensate drains have been run to agreed connection point by plumber or outside.
checkpoint | AC Units Power feed to indoor and out door run
checkpoint | AC units Pipe work put under pressure 500 PSI and leak checked. Label added to pipework at outdoor location.
checkpoint | AC Units ( Ducted ) solid and flexible ducting has been run and restrained
checkpoint | Photos
checkpoint | Drawing marked up for as builts.
section | Toilet Extract Systems first fix
checkpoint | Toilet extract fans installed
checkpoint | Toilet extract cowl supplied to builder
checkpoint | Solid nude extract duct installed
checkpoint | Toilet extract cowl installed
checkpoint | Flexible ducting installed and connected
checkpoint | Extract grill boots installed
checkpoint | Fan is pre wired and connected
checkpoint | Builder advised of hatch location and size
checkpoint | Builder advised of undercuts to doors required
checkpoint | Builder advised of door grill location and size for penetration to the door
checkpoint | Drawing marked up for as built
checkpoint | Photos
section | Fresh Air Systems first fix
checkpoint | Fresh air iline fan installed ( if applicable )
checkpoint | Fresh air roof mount fan installed ( if applicable )
checkpoint | Fresh air in take cowl or lourve installed ( if applicable )
checkpoint | Fresh air filter box and filter installed or filter in roof mount fan dropper( if applicable)
checkpoint | Fan / heaterbank is pre wired and connected
checkpoint | Builder advised of hatch locations and sizse
checkpoint | Grill boots installed
checkpoint | Grill Locations mark on plan
checkpoint | Flexible ducting installed and connected to grill boot
checkpoint | Drawings marked up for as builts
checkpoint | Photos