## Proj Resources
type | name | values | prefix | postfix | Template Name | Template Id
checklist | Pre start stage
checklist | Second Fix
section | Outdoor AC units
checkpoint | AC Units Pipes connected, pipe run and capping.
checkpoint | AC Units Pressure tested to 500psi 24 hrs
checkpoint | AC Units vaced to,100mirons and precharge with extra charge
checkpoint | Units wired and ready for Commissioning
checkpoint | Units fixed with stainless fixings
checkpoint | Photos
section | Indoor AC units
checkpoint | AC Units Higwall Pipes, drain and cabling is connected
checkpoint | AC Units are level
checkpoint | Units are left clean and any marks on walls are removed
checkpoint | Remote controls are mounted to wall in agreed locations or handed to client
checkpoint | Units fixed with stainless fixings
checkpoint | Photos
section | Fit Off Grills
checkpoint | AC Ducted unit grills fitted
checkpoint | AC Unit covers fitted
checkpoint | Toilet extract grills fitted
checkpoint | Fresh air grills fitted
checkpoint | Photos
checklist | Commissioning
section | Commission AC units
checkpoint | AC Units , Power on, units vacced and crackecd
checkpoint | Units operated in heating and cooling
checkpoint | Airflows balance for AC Ducted - Design airflow obtained +10%
checkpoint | Commissioning sheet filled out
checkpoint | AC Units model and serial numbers recorded and photographed
section | Commissioning Ventilation Systems
checkpoint | Fresh air systems, airflows commissioned +10% of design airflow
checkpoint | Extract systems, airflows commissioned +10% of design airflow
checkpoint | Ventilation commissioning sheet filled out
checklist | Project Completion
section | Compliance Information
checkpoint | Airflow test results submitted
checkpoint | Warranty completed and submitted
checkpoint | Producer statements completed and submitted
checkpoint | COC submitted
checkpoint | As builts updated and submitted
checkpoint | Photos uploaded
section | Manuals
checkpoint | Manual info compiled
checkpoint | Manual Structure and descriptions completed in word document
checkpoint | Word document converted to PDF snd relevant info added to each section
checkpoint | Manual submittied to client
checklist | After Project
section | Customer Follow up
checkpoint | Follow up with customer on installation and training with in 2 weeks of occupation
checkpoint | Set up maintenance agreement and submit for approval.