## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | SSSP Information Checklist |  |  |  |  | Yes | SSSP Information Checklist | 1b1ad530-337e-4116-8e1e-75a36985df29
checkpoint-group |  |  | section | SSSP Documentation
checkpoint-status |  |  | checkpoint | Upload SSSP Agreement
checkpoint-status |  |  | checkpoint | Upload Site Safe Copies
checkpoint-status |  |  | checkpoint | Upload Drug & Alcohol Test Copies
checkpoint-status |  |  | checkpoint | Upload Training and Certificate Copies
checkpoint-status |  |  | checkpoint | Upload TA & Register Sign On
checkpoint-group |  |  | section | TA Documentation
checkpoint-status |  |  | checkpoint | Upload Current TA
checkpoint-status |  |  | checkpoint | Upload Updated TA
checkpoint-group |  |  | section | Site Inspection Documents
checkpoint-status |  |  | checkpoint | Initial Inspection
checkpoint-status |  |  | checkpoint | On going Inspections
checklist-flat |  |  | checklist | Handover Checklist |  |  |  |  | Yes | Handover Checklist | 366c6e3a-3c2b-4dbc-b044-1556abce3fc9
checkpoint-status |  |  | checkpoint | QA Complete, area left clean and tidy
checkpoint-status |  |  | checkpoint | Work completed as per drawing's and specifications
checkpoint-status |  |  | checkpoint | Accepted and approved for concrete by MC (attach photos)
checklist-flat |  |  | checklist | Foundation Panel Reinforcing QA Checklist |  |  |  |  | Yes | Foundation Panel Reinforcing QA Checklist | 48fb2cb6-95de-4b7f-aaef-d79a852ceb8b
checkpoint-status |  |  | checkpoint | PC Panel type checked as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Specified covers checked as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Stirrup centres as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Stirrups spacings as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Link centres as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Link spacings as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Column bars and amount's as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Column Lap's and locations as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | IBMS/Reid/Ancon fittings as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | All reinforcement tied, secured and rigid (attach photos)
checklist-flat |  |  | checklist | Prestart Checklist |  |  |  |  | Yes | Prestart Checklist | 5a6643f2-c904-4de3-a4ab-3039d9b1adb2
checkpoint-status |  |  | checkpoint | Have all workers on site reviewed, Understood and signed onto the SSSP and confirmed all their details are correct
checkpoint-status |  |  | checkpoint | All workers are wearing required PPE
checkpoint-status |  |  | checkpoint | Weather conditions acceptable? (Add comments)
checkpoint-status |  |  | checkpoint | Select relevant work areas for the day
boolean | 16a095aa-573f-5d5c-b6a8-9741809f1aa2 |  | tickbox | Zone 1 Prefab
boolean | 5d91cb5e-7918-56aa-a713-13ae41c26e79 |  | tickbox | Zone 1 Insitu
boolean | a70644ad-fd80-5740-aea6-d39962fc4f3a |  | tickbox | Zone 2 Prefab
boolean | 0bdd271f-d61d-511c-ad5a-d173fad756e7 |  | tickbox | Zone 2 Insitu
boolean | 3f074e05-17e4-50a7-9cb8-578815f07b08 |  | tickbox | Zone 3 Prefab
boolean | 3162ec0f-ef20-5388-b241-e3b3a37cd034 |  | tickbox | Zone 3 Insitu
boolean | 91f40272-68af-5bfc-89ff-0f6d04c7694c |  | tickbox | Zone 4 Prefab
boolean | 6689ce24-0ec2-5ddf-be5a-780c688bfb5e |  | tickbox | Zone 4 Insitu
boolean | 37517aae-14c9-51fd-903d-7005774daba1 |  | tickbox | Level 1
boolean | d27f5e72-0f5b-5211-b99c-cd4324def179 |  | tickbox | Civil Sitework Level 1
boolean | 93cc6c5a-262d-5a5a-9c7c-92853d09f32e |  | tickbox | Level 2
boolean | 06c09ce5-7807-5d69-863a-c5f86622ab64 |  | tickbox | Level 3
select | d68d0947-7dc2-56ea-adea-9e64a2413ad2 |  | dropdown | Select potential hazards & control methods | Services strike - issue new safety permits, Service locating, Manual handling, Working at heights - PPE required / Ensure harnesses delivered
checkpoint-status |  |  | checkpoint | Are there any issues from the previous day not resolved
checkpoint-status |  |  | checkpoint | Work permits or isolations required for today's activities
checkpoint-status |  |  | checkpoint | All site team to sign on (attach signature)
checklist-flat |  |  | checklist | Beam Reinforcing QA Checklist |  |  |  |  | Yes | Beam Reinforcing QA Checklist | 65bfea5c-7e9f-43fa-a516-ad244670ea15
checkpoint-status |  |  | checkpoint | Beam type checked as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Specified covers checked as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Stirrup centres as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Link centres as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Beam bars and amount's as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Beam Lap's and locations as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | IBMS/Reid/Ancon fittings as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | All reinforcement tied, secured and rigid (attach photos)
checklist-flat |  |  | checklist | Workplace Diary Checklist |  |  |  |  | Yes | Workplace Diary Checklist | 7aab9566-ac8a-49e6-a470-6209a17becbb
checkpoint-status |  |  | checkpoint | Safe and suitable access provided by MC at workplace (Attach photos)
checkpoint-status |  |  | checkpoint | Scaffold tagged, Stairs and safety railing inspected, no openings through floors or perimeter of the scaffolding
checkpoint-status |  |  | checkpoint | Cranage arranged and reinforcement at workplace
checkpoint-status |  |  | checkpoint | Grid lines set out by MC at workplac and visible
checkpoint-status |  |  | checkpoint | Datums provided by MC at wworkplac and visible
checkpoint-status |  |  | checkpoint | Site concrete poured
checkpoint-status |  |  | checkpoint | Formwork installed
checkpoint-status |  |  | checkpoint | Tanking, Waterproofing complete
checkpoint-status |  |  | checkpoint | All cast in items set out or in place (Hold down bolts, Weld plates
checkpoint-status |  |  | checkpoint | Precast starter bar setout my MC
checkpoint-status |  |  | checkpoint | Couplers, threaded inserts cleaned out and prepared my MC
checkpoint-status |  |  | checkpoint | Is there any uncompleted work by the MC that will hinder the progress of your work
checkpoint-status |  |  | checkpoint | All pre install checks completed and approved - Ready to start work
checklist-flat |  |  | checklist | Toolbox Talk Checklist |  |  |  |  | Yes | Toolbox Talk Checklist | 7c0b9311-1e1f-4ac8-b1e7-ff1f72781fe4
checkpoint-status |  |  | checkpoint | Complete project information below
boolean | 53c450fd-5c65-5851-928d-f498ea5b6177 |  | tickbox | Site-specific meeting
boolean | 03bf37b0-4fe9-540c-9294-fcbea41c26f5 |  | tickbox | In-house meeting
text | ce451f9b-a5cd-536e-aee2-ffebcee889ee |  | textbox | Office location
text | cf0a14c8-f6e6-5c05-82aa-923dacfad373 |  | textbox | Write the name of who is running this meeting.
checkpoint-status |  |  | checkpoint | List agenda items
label | 807853b7-3ca5-5ff4-b1e4-4cfb4e90e430 |  | note | Add in comments theme of the meeting (topic for focus) + agenda items
checkpoint-status |  |  | checkpoint | Complete Health & Safety issues. Add in comments - Issues raised for site safety inspection. List actions taken, by who and when.
label | 1a3d7c8d-3571-556b-b5e3-d77c3541fe4c |  | note | Site activities/safe work practices/incident reports and investigations discussed.
checkpoint-status |  |  | checkpoint | Job plans reviewed. List in comments job/task & action/outcome
label | 0c0c3d3b-76c0-5cfb-87db-52a56914c394 |  | note | Includes permits to work, Task Analysis or other documented work-planning process.
checkpoint-status |  |  | checkpoint | Complete operational issues below. List in comments issue & action
label | 5dc004bd-3f4c-5aaa-b407-7d19131b6d7f |  | note | Day-to-day site management issues/items for discussion.
checkpoint-status |  |  | checkpoint | Other business?
label | 6cc0b491-5967-5ede-b024-1cb2420c8095 |  | note | List item & action
checkpoint-status |  |  | checkpoint | Attendees
label | ce677e70-66c8-56d5-b3fb-3e57e2f89b97 |  | note | Attach signatures of all attendees
checkpoint-status |  |  | checkpoint | Review by management
label | 01a0b80f-93dc-56aa-9132-ef52963f0150 |  | note | Attach signatures of Party 1 & Party 2
checklist-flat |  |  | checklist | Job Details Checklist |  |  |  |  | Yes | Job Details Checklist | 855ed5a0-d59a-445d-97a2-8ba2fe209a70
checkpoint-status |  |  | checkpoint | Details
text | cb531d94-bfdc-5a59-8d32-a050e3c9d327 |  | textbox | Site Location
text | d568f49f-d326-5b4d-8dfa-e121bb3bcf79 |  | textbox | Main Contractor
text | b38f4086-fb14-5ece-be20-b58b2c20c670 |  | textbox | Contact Details
checklist-flat |  |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | Site Inspection Checklist | c632f4fe-8370-44a4-b1b1-cdf2898b8634
checkpoint-status |  |  | checkpoint | Name of inspector
checkpoint-status |  |  | checkpoint | 1. Site Control
boolean | 9caf823e-26c4-5538-8d0b-abf5b86a8a9e |  | tickbox | Hazard board & signage up-to-date
boolean | fe41eb77-bb45-581a-a776-9acffe672e13 |  | tickbox | Environmental plan – issues
boolean | b710abd9-31c8-55e4-9d1f-e0240f7c7fb4 |  | tickbox | Toolbox talk last date
boolean | 3eb85608-3e04-568e-8eaf-0b162beb2bad |  | tickbox | Safety inductions for all on site
boolean | 3eec3fb2-bc85-5dde-9a59-89bd03eae286 |  | tickbox | Safety notice board current
checkpoint-status |  |  | checkpoint | 2. Site Facilities
boolean | 62dbf688-e9a8-51cf-ab15-502ae817a063 |  | tickbox | Offices clean, adequate & good lighting
boolean | 0218c543-df22-55b0-8751-a7e2ef124292 |  | tickbox | Smoko sheds – clean, potable water
boolean | cea79c6b-c0de-56f6-90d5-0e543fa356a9 |  | tickbox | Toilets – clean, washing water
boolean | 708efc7b-576e-584e-87d1-16ebf476f326 |  | tickbox | Tool / equipment sheds adequate
checkpoint-status |  |  | checkpoint | 3. General Site Tidiness & Access Ways
boolean | 879560d6-bfc9-59d4-a83b-a06a2eb89281 |  | tickbox | Clear, safe access to work areas
boolean | da39c0cc-6c6d-510d-9b89-cee70fd3c68a |  | tickbox | Stairways and access ways clear
boolean | edddfe02-4844-526b-b043-33b066621ece |  | tickbox | Hoardings/fence and gates secure
boolean | 5742f20c-67b1-54f0-a742-fa37698fe0ae |  | tickbox | Loose materials secure from wind
checkpoint-status |  |  | checkpoint | 4. Personal Safety Equipment
boolean | 680e2df9-49a7-5d0f-901d-3a8ed753e351 |  | tickbox | Signage displayed and legible
boolean | 64002d93-c557-5d2f-83be-a3432c4671b7 |  | tickbox | Hardhats being worn
boolean | d0336cf6-c09b-5496-af51-e9cc7c9b9a09 |  | tickbox | Correct footwear being worn
boolean | 273d8de9-bf5b-5551-8e46-e0177da00b4a |  | tickbox | Glasses/ ear muffs/ vests/masks used
checkpoint-status |  |  | checkpoint | 5. First Aid / Fire Prevention
boolean | 2ec1a3c7-f07d-58ad-ae39-f966b61add2a |  | tickbox | First aid box available
boolean | 6db13d93-e450-5f94-95d0-080cca6d33ec |  | tickbox | Accident register available
boolean | 3b399646-a09d-5e2f-ab4e-f4f9db1b84ed |  | tickbox | Fire extinguishers available
boolean | b1054876-fb74-5093-bbd7-883347a5eaf3 |  | tickbox | Current (12mth)
boolean | 53883c2f-2b72-5fd0-b60f-b85acd1e315d |  | tickbox | Sufficient number
boolean | 0ee26137-4138-5208-b0c6-fa0388d89910 |  | tickbox | Evacuation procedure current
boolean | 3252fdc0-d543-5b67-aad9-7afa4f135618 |  | tickbox | All emergencies included
checkpoint-status |  |  | checkpoint | 6. Cranes / Hoist / Lifting Equipment
boolean | 0ba4b462-8688-56b8-ae7d-5b87e528ea23 |  | tickbox | Proper lift assessment plan done
boolean | cfd8855b-3b6b-5a48-baa8-e9c5fa24c1ab |  | tickbox | Crane certification current
boolean | c53d9637-8dc0-5b68-8bf8-650fc1170b66 |  | tickbox | Operator procedures in place
boolean | 69752d40-2c1f-5911-809f-cf9d64e839fd |  | tickbox | Slings/ chains certified
boolean | b8899e8d-beed-53fe-b480-0f8de4a45bb3 |  | tickbox | Inpections being done
boolean | 0d37df45-1557-5e42-8b30-365dad6d5128 |  | tickbox | Man cage available
boolean | e9fb6c5a-e72b-5da3-9e68-2a6282e46d89 |  | tickbox | Emergency plan in place
checkpoint-status |  |  | checkpoint | 7. Compressed Air Equipment
boolean | 7b83d767-07ad-530f-b782-8ba1bc2253c7 |  | tickbox | In good condition
boolean | 8815366b-6b25-5978-b1ce-d0d9d6482c83 |  | tickbox | Appropriate guards fitted
boolean | 19ca5d14-ce6b-5317-8171-a554a10b902f |  | tickbox | Trained user
checkpoint-status |  |  | checkpoint | 8. Excavations
boolean | 9a731055-a29b-518d-8bd3-98a9140adcbd |  | tickbox | Correctly shored and secured
checkpoint-status |  |  | checkpoint | 9. Welding / Gas Cutting
boolean | 54c534d8-3faa-5cf5-9737-6f50236b1259 |  | tickbox | Hot work permits being issued
boolean | 1fbbe8ed-0a06-5c9e-896d-a75deb697546 |  | tickbox | Fire extinguishers on hand
boolean | 376eae3f-8121-5861-ac40-17aba3b1294d |  | tickbox | Operators using PPE
checkpoint-status |  |  | checkpoint | 10. Electrical Equipment
boolean | d87b7ad7-b467-5756-9842-3d0fb94fdfa3 |  | tickbox | Main board lockable /weatherproof
boolean | 952cdce0-539a-5113-80df-df2465d1e1dd |  | tickbox | Current tagged and damage-free leads
boolean | 5307b312-4c51-5f1d-8bc3-9d4e5b7bca40 |  | tickbox | Current tagged plant
boolean | 998da61f-20df-59de-aed4-299efefe8b97 |  | tickbox | Current tagged lifeguards
boolean | f2bc952a-718d-5128-a39d-e7a19a858ddb |  | tickbox | Leads safely placed
boolean | 6bd5bcc1-b4de-5e4c-a2db-fcbb441611fd |  | tickbox | Equipment in good condition
boolean | 96dfa418-1d70-5d26-a1d7-475249a6ab7c |  | tickbox | Appropriate guards on equipment
boolean | 59e005ff-7da3-535a-80a1-fbdbe2ae7732 |  | tickbox | Adequate temporary lighting
checkpoint-status |  |  | checkpoint | 11. Chemicals
boolean | 85569f31-3fb5-51c5-a9df-97ed58db90fc |  | tickbox | Correctly stored
boolean | 17a238ba-b717-544a-8642-7a0ee44c2282 |  | tickbox | Safety Data Sheet (SDS) available
boolean | a4ed3d44-323e-52d2-9ec6-aac21167f267 |  | tickbox | Operators using PPE
checkpoint-status |  |  | checkpoint | 12. Tools
boolean | f48e2c3f-31d8-5392-9691-7708cd55745e |  | tickbox | PAT tool WoF current and secure
boolean | 8c2e609a-a3ff-51a0-99a8-2dd0110cce13 |  | tickbox | Staff trained in tool use (SWPS)
boolean | 0d4b9b47-6c8c-5a2c-9a21-0686e0d9387c |  | tickbox | PAT signage on site
checkpoint-status |  |  | checkpoint | 13. Scaffolding
boolean | 317b536b-0e80-518b-a4a6-04dbd461d2c1 |  | tickbox | Notifiable weekly Scaftag / current
boolean | 669fba71-4df2-58a4-b9ae-15d8d1ce28a8 |  | tickbox | Handrails/mid-rails
boolean | 0777069a-03bd-5337-8a20-19051bce6912 |  | tickbox | Toe boards
boolean | c0d7986d-cdbf-5089-96ad-a1fcd4ff596f |  | tickbox | Platforms
boolean | a58e84ef-237e-56bd-8e55-5f778f4021d2 |  | tickbox | Ladders/stairs
boolean | e1148bad-3c0c-5680-a712-9af76b91e9ba |  | tickbox | Base sound
boolean | 23f13160-9fe0-58a8-8b25-15f9aedf8a1f |  | tickbox | Work platforms clear
boolean | 9446f008-8e57-5e21-8bb3-f1be6e69c7b5 |  | tickbox | Platforms trip free
boolean | 04e0cd8d-974b-5363-92d7-b64a069ad944 |  | tickbox | Planks tied down
boolean | b1f51b86-7b8c-5ce2-99b4-6d1e5b5de9c0 |  | tickbox | Headroom clear
boolean | d598c30b-fcc6-5eba-aef4-b798ced978cf |  | tickbox | Ties/ bracing adequate
checkpoint-status |  |  | checkpoint | 14. Ladders
boolean | be4a0abd-958e-5fa2-9e1a-57fc5bd912bc |  | tickbox | Good condition
boolean | 002f7aff-9c5c-5a00-bc94-1fda54a09d48 |  | tickbox | Secured top and bottom
boolean | 94d52a5f-9467-5964-a168-c7d19bc5c028 |  | tickbox | Stays to step ladders
boolean | 9d999d27-0a30-5053-a1b2-cfc856f33e6e |  | tickbox | Working 2 steps down
checkpoint-status |  |  | checkpoint | 15. Fall Hazards
boolean | 3c0dad62-b647-56c5-b871-9d027cb7e5ed |  | tickbox | Floor edges/ openings
boolean | dee6e368-c818-51d9-8f72-08e97f63c1d9 |  | tickbox | Lift shafts/stairs
checkpoint-status |  |  | checkpoint | Remedial action required. In comment please list, item, comments/action description & person to action.
label | 19fe4dc5-74e7-5177-a970-8ea8ef21867c |  | note | PASS when all items complete.
checklist-flat |  |  | checklist | Column Reinforcing QA Checklist |  |  |  |  | Yes | Column Reinforcing QA Checklist | d8d93ad7-b373-4d1a-800c-a1a29e598069
checkpoint-status |  |  | checkpoint | Column type checked as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Specified covers checked as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Stirrup centres as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Stirrups spacings as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Link centres as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Link spacings as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Column bars and amount's as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Column Lap's and locations as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | IBMS/Reid/Ancon fittings as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | All reinforcement tied, secured and rigid (attach photos)
checklist-flat |  |  | checklist | QA Documents |  |  |  |  | Yes | QA Documents | f3cd87e3-ec63-4b3a-9c8d-2babe36453a4
checkpoint-status |  |  | checkpoint | Upload drawings
checkpoint-status |  |  | checkpoint | Upload details sheet