## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0015 Precast Stormwater Drainage Pits | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0015 Precast Stormwater Drainage Pits | 2451c140-96d4-4351-8545-ddea0bf57254
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Design
label | c4c87fb5-dadc-5fe0-8fb1-23433361b853 |  | note | Ref docs - 705.08(a)
label | 6f9eedff-44c6-5b20-b875-f052e88c6b57 |  | note | Acceptance criteria - Design has been provided, including Proof Engineering (by prequalified VicRoads engineer) to confirm that all requirements of AS5100 and additional loading requirements have been met.
label | 8546f544-06ab-5f1e-b7e5-aa40d016a218 |  | note | Freq - Each Lot
label | bb8a192a-bdc9-5f57-b651-90d4fc7121a3 |  | note | Key - R
label | 43e84a19-35f5-56f2-be1a-0ec2cd82b619 |  | note | Resp - SE
label | 3f8d9ad8-413a-52e5-9392-fd19310191b6 |  | note | Remarks/record - Design
label | 0a97706d-d509-5ad5-be28-88e4d7c1abdb |  | note | Remarks/record - Proof Engineer Certificate
date | 8ea5b34d-fca2-5cfd-a4dd-48ec23766f70 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | c8065e8c-5a49-5248-98bc-4377752c814a |  | button | Lot map | Yes,No,N/A
date | 5d0f6f46-c5ea-529e-b913-ff747475163c |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 5532ea74-bd2d-5797-9fe9-37ecc7c3c48f |  | button | Environmental permit | Yes,No,N/A
date | c6da9d80-b82b-58a5-ac41-78f7e87b7790 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Concrete Mix Design
label | 36aaf60a-d80c-555e-acae-8d8cf4db3631 |  | note | Ref docs - 705.04(b)
label | 86532d9c-cdbe-5dba-887b-27195e9c6ac7 |  | note | Acceptance criteria - The concrete mix design used by the pre-cast supplier is approved and current in accordance with the requirements of VR610.
label | 2a72d99d-4d92-59e3-8bb3-bce0e607e23a |  | note | Freq - Each Lot
label | deb4eb81-72bd-54c2-9a6f-37065e07af7c |  | note | Key - R
label | 33b29f07-d8f2-597b-a5c6-56fb2bb2d6db |  | note | Resp - SE
label | 2ec4ab79-6ac9-53e8-ad4b-a52a01aae0ed |  | note | Remarks/record - Concrete mix design
date | 532bcb68-0ff7-570f-bb01-7cd53ca0752d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.3 - Concrete Supply
label | 76fcdcd9-7888-5377-88ab-814568f0bdc1 |  | note | Ref docs - 705.04(a)
label | cc637b2f-5e20-5e4f-84c9-ecf33259bdc0 |  | note | Acceptance criteria - Concrete has been provided in accordance with VR610 and VR705. The minimum grade of concrete is VR450/50.
label | 9e7e34c0-d4aa-51d6-9f49-b69d46419ab0 |  | note | Freq - Each Lot
label | e088742b-cd12-554b-a6c6-0fe70fdf2fd6 |  | note | Key - R
label | f04c4339-cb43-5019-8721-be0755198138 |  | note | Resp - SE
label | 45263553-b465-5297-a99c-c2319419de56 |  | note | Remarks/record - Compliance Certificates or Dockets by Supplier
date | bf0bfad6-e1a2-568b-a90a-ec2cd11a8076 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.4 - Fibres
label | 606cbb8c-8f13-5c33-b361-d495329a1fc8 |  | note | Ref docs - 705.04(f) 705.08(d)
label | 42d05a32-2a33-5e46-aaf1-d53251894381 |  | note | Acceptance criteria - Fibres comply with the requirements of ASTM C1116 and have been supported with documentary evidence confirming their long term resistance to deterioration when in contact with the moisture and alkalis present in cementitious paste or the substances present in chemical admixtures.
label | 3d3d5c4a-36e5-591d-bdb9-8e691d54fc47 |  | note | • Fibres have been tested to the requirements of ASTM C1609 (flexural toughness) and ASTM C1399 (average residual strength of fibre reinforced concrete) and comply with the requirements of AS 5100.
label | 4eb3e1d2-2320-52bb-976a-827e519ce465 |  | note | • Evidence has been provided by the supplier than the minimum fibre content has been achieved.
label | 80fb8845-42cb-5b05-936f-4f8439b2abac |  | note | • The worksheet and/or report for determination of fibre content shall be submitted to review by the Superintendent.
label | b51b0a92-22d4-5ec3-9987-1adb363f02b7 |  | note | Freq - Each Lot
label | 90b8b4d1-4e44-5299-a7ec-e5272288c4b6 |  | note | Key - R
label | 71102c05-8ebf-5180-8d21-95a79aadec81 |  | note | Resp - SE
label | ef7ec0e2-aae8-54f0-9e96-aa8a3792d5d0 |  | note | SI Key - R
label | 0cf4ef8f-0da9-55ae-b271-8c05573d4a14 |  | note | Remarks/record - Compliance Certificates and/or Test Reports
label | fddf9b45-a119-5067-b796-d098b61b2203 |  | note | Remarks/record - Worksheet for determination of fibre content
date | 654dee8d-eecc-5746-a5e3-8dca00593e58 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.5 - Wall thickness
label | 8285db7d-c6cb-549f-b202-2b7a06f08640 |  | note | Ref docs - BTN033
label | 655bfb2d-93aa-5f51-bde9-4b81d36b2e22 |  | note | Acceptance criteria - For concrete drainage pits up to 2 m deep, the minimum wall and base thickness must be 100 mm. For concrete drainage pits more than 2 m deep, the minimum wall and base thickness must be 150 mm or thicker if required.
label | 6389ff46-f1d0-58b3-80cd-2ca65cc94195 |  | note | • Where the depth of the concrete drainage pit exceeds 2 m there may be a need to adopt two different wall thicknesses in the construction of the complete pit. The wall thickness at the bottom will need to be a minimum of 150 mm thick whilst the wall thickness of the riser must be a minimum of 100 mm thick.
label | 7505c325-18a2-5bab-869f-b5b0101dd5c2 |  | note | • The depth of drainage pit must be measured from the bottom of the pit towards the surface. The bottom 2 m must have 150 mm minimum wall thickness.
label | 6c570f0a-d3fc-51af-9439-269e305883aa |  | note | • Where the depth of the drainage pit is over 2 m in height then it is acceptable to construct the complete pit as one section with 150 mm wall thickness.
label | ef4bf2c2-e3cf-5c7e-9d5b-6ca742bb7d36 |  | note | • Where the depth of the drainage pit is greater than 4 m, the wall thickness and reinforcement requirements must be structurally designed and Proof Engineered, but not less what has been specified under Section 5 for unhaunched concrete drainage pits up to 4 m in depth.
label | 6faed019-5117-59a6-aea8-4f9682db958f |  | note | Freq - Each Lot
label | b4872027-28c0-57aa-a47b-93a97fb5aa90 |  | note | Key - R
label | b612ccda-6801-5b9a-ad08-a0c5e8d860e3 |  | note | Resp - SE
date | 5e86f124-3e4e-5656-91d0-4b64a59b1ccd |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.6 - Supply Precast Covers, Grates, Lids
label | 5026090b-8741-57c0-badf-2cfe4e49dd92 |  | note | Ref docs - 705.04(c)
label | 8dc4b6c8-98b9-532e-8b51-e46da0e0dc80 |  | note | Acceptance criteria - Pit covers and grates have been designed in accordance with AS 3996 and table 7 from BTN 033.
label | d80cd302-27b1-5c46-aada-95b91079cfe4 |  | note | Freq - Each Lot
label | 13a9da6c-4ccf-5c6c-9188-d22f2b941c6b |  | note | Key - R
label | fd1d3b95-acdf-50dc-b91f-9d0cb9d36c16 |  | note | Resp - SE
date | ad39a473-2698-5361-b991-a79c64d4b1db |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.7 - Step Irons (pits greater than 1.0m)
label | e21df7ad-b9f9-5131-a2bf-4eff23926249 |  | note | Ref docs - 705.04(d)
label | 8e122a32-a2aa-5678-a2c6-dfe3522cd375 |  | note | Acceptance criteria - Ensure step irons are manufactured from steel AS/NZS 3679.1 grade 250. Step irons are hot dip galvanised as per AS/NZS 4680 or 13 mm steel bar covered with polypropylene shall be approved by design.
label | ab8c49ae-4162-50ca-9c2d-5f73e2be925a |  | note | Freq - Each Lot
label | 13634822-1dde-5801-8b7b-374c374b3e16 |  | note | Key - R
label | f6c38933-927e-5648-8830-76456b1f8ae9 |  | note | Resp - SE
label | d158241f-6bdc-5251-8f46-9b6ea75ffec5 |  | note | Remarks/record - Compliance Certificates Superintendent Approval (for polypropylene step irons)
date | d1cfc2d4-5723-5e24-97ec-d7241b3128f4 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.8 - Weep Holes
label | 2d8e3d98-08ea-5cc1-ad09-9cb13e17e254 |  | note | Ref docs - 705.09(c)
label | fd84f395-1ad4-5706-8523-f6ba786d26f2 |  | note | Acceptance criteria - Weepholes of 50 mm diameter shall be provided in all precast pits and shall be placed between the midpoint and top of the stormwater drain in those walls which have openings for drains.
label | 1fc2162e-0411-581c-8063-0c5b13a96658 |  | note | Freq - Each Lot
label | ad94d417-b8bf-58b7-bdb9-42acb85fa003 |  | note | Key - R
label | 56b2a246-81a2-5bfa-9169-32f044938856 |  | note | Resp - SE
date | 736fe747-dc5c-5ea2-bce2-081bb1f3f8c4 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.9 - Segments
label | 407c67f2-fd65-5076-8dc6-9234b71cb0fe |  | note | Ref docs - 705.09(b)
label | 42a21176-1180-50bc-bc5f-b8cb046d42b0 |  | note | Acceptance criteria - If a precast drainage pit is cast in segments, each section of the drainage pit shall be rebated to ensure correct alignment and to prevent horizontal movement. A minimum rebate of 15 mm shall be used.
label | 59140a36-ff4c-5364-ac16-f9b164153e64 |  | note | Freq - Each Lot
label | f60749d7-6c17-54ba-83d2-f40bf358cb8d |  | note | Key - R
label | 5ec00a63-a4fd-5d7f-8918-d3b3d59d2ed0 |  | note | Resp - SE
date | 2ab53413-cc32-55fe-bc38-55f2cc2d4738 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.10 - Repair to Defective Pits (if applicable)
label | 2e18e2dd-2386-5590-b3fa-1a767a3c4c36 |  | note | Ref docs - VR Clause 689 687
label | fe81a189-2980-5c9b-b031-576ad5328d27 |  | note | Acceptance criteria - Any Pits damaged due to handling onsite post acceptance at delivery of non-defective product are to be repaired as per the approved Cracks and/or Patch repair procedure. A Non-conformance to be raised for the defects identified and issued to the State and IR for information and refer it to the Designer for assessment.
label | 04ae2a45-b271-5af5-9eb0-a19b0e109a6f |  | note | • Prior to any patch repair of concrete, Symal shall assess the damaged pit to determine the influence of spalled, deteriorated, damaged or honeycombed concrete on load bearing capacity, serviceability and durability, and submit the assessment to the Superintendent for review.
label | 78248d72-e392-52af-b0f4-73a3e4617aae |  | note | • The Designer and the Engineering team to agree upon an appropriate repair treatment(s) and materials, consistent with the requirements of VR Spec. Section 687 and 689.
label | bf74d206-c2a4-518c-ab6c-fab6f7ed5189 |  | note | • Complete ITP for either crack repair or patch repair.
label | 75a072d8-d133-556b-a595-1b7aeb9034f9 |  | note | • Measure, document and photograph the dimensions and condition of the defects.
button | 1a858ce3-f08c-5fab-ae55-6b11b9bba182 |  | button | Has all of the above been completed and approved? | Yes,No,N/A
label | 2b1cea1d-f65a-570d-bbbd-52e8888fae39 |  | note | Freq - Prior to start of works. Each Lot
label | 2a8f29cd-8740-5c2c-b36b-c81fdee2f9cb |  | note | Key - H W
label | b5297e82-0e09-5839-82a3-8c28c478bbb0 |  | note | Resp - SE
label | 960a2d8e-0847-5bde-a478-eaabec297737 |  | note | SI Key - H
date | 25ec1ea1-2e19-54b8-88f4-03f4d5146f24 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Excavation
checkpoint-status |  |  | checkpoint | 2.1 - Conformity with Drawings
label | 6ff3e672-dc1e-51d3-839a-57d5c2c49c21 |  | note | Acceptance criteria - Prior to commencement of excavation for the pits the Contractor shall confirm the position of all pits with the Superintendent.
label | 22bd148e-8817-5e83-8022-7fa25806cf24 |  | note | • The location of each pit may be altered to suit site constraints ±1m with both the approval of Survey and the superintendent.
button | 294b791a-8c5d-56d5-b8c7-13e239a1009d |  | button | Approval to proceed? | Yes,No,N/A
label | 546fc7d1-3707-5ac2-b17a-f816c99dafc9 |  | note | Freq - Prior to start of works
label | 12246ffa-3cc2-5084-8c4f-b8e457a66305 |  | note | Key - H
label | 66363737-2869-5605-93a2-a168528211bc |  | note | Resp - SE
label | c0d04504-59dc-5b9c-88b4-c8c287dd27b2 |  | note | SI Key - H
date | 1ac7cae7-13eb-581f-a703-94ed873a91b7 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Excavation for Pits
label | f6c62df3-3e71-50dc-bf6b-485a37755901 |  | note | Ref docs - VR Clause 705.05
label | 8a0b79b2-60b8-5fc8-a1d3-b00bcdb74ec8 |  | note | Acceptance criteria - Excavate to required depth which shall also include excavation necessary to prepare the pit foundation & provide the full specified depth of pit bedding. Maintain excavation width clearance. Excavation for pits shall not be less than 400 mm from external wall to side of excavation.
button | 998a6ba7-fbd6-5bc3-81de-bdba76e2b4b5 |  | button | Has all of the above been completed? | Yes,No,N/A
label | c0b679ad-708d-57df-9b4a-96c8662b80c3 |  | note | Freq - Each Lot
label | afdde096-ed4c-5df4-b3e4-af54084a16c5 |  | note | Key - S
label | 9da36e9b-394c-57bc-b2eb-e40e0e919cee |  | note | Resp - SE
date | 3cb3a2e7-7895-5224-8073-d6df85dcd5d6 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Bedding
checkpoint-status |  |  | checkpoint | 3.1 - Bedding
label | 80dfbdfa-5416-56e5-838a-4d754f9d759b |  | note | Ref docs - VR Clause 705.05 Table 701.091 & 701.092
label | d6e76c0f-aa15-5044-a8dc-b37e5f25aae4 |  | note | Acceptance criteria - Bedding placed and compacted to a thickness not less than 80 mm on clay foundation or 150 mm on rock foundation.
label | 6211ed6b-b214-5a38-9751-e56c5f1f36c8 |  | note | • Bedding needs to conform to Table 701.091 & Table 701.092.
button | e9099129-2c15-5739-b10f-ee7625000ac8 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 54be929e-efc1-5026-9ddc-83036dcdbecf |  | note | Freq - Each Lot
label | 272ce974-a9e7-5e4a-9c98-0388cf857725 |  | note | Key - S
label | f7aad43f-57e8-5d9b-8a8b-3744961ea0f8 |  | note | Resp - SE
button | 712eaff3-cba6-568b-9531-f7f925d3f37e |  | button | Remarks/record - Bedding and Backfill Material Conformance | Yes,No,N/A
date | 9dbaa96f-02c1-5396-870a-c2853bef5ab8 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Installation of Pits
checkpoint-status |  |  | checkpoint | 4.1 - Installation of Pits
label | 4bb3c86c-52b0-59bb-9869-dd77557520c2 |  | note | Ref docs - VR Clause 705.07 705.08 705.09 705.11
label | 2161dce2-efd1-55bf-98b0-1b4d2e32393c |  | note | Acceptance criteria - Precast pits shall be installed at the locations and to the dimensions shown on the drawings.
label | 4f86518d-5044-584f-bdb2-e7a0875ba54f |  | note | • Subsurface Drainage Connections – Holes for subsurface drainage shall be 150 mm diameter (cored not broken), unless specified on the drawings.
label | 86881686-c6a4-52bf-9c0f-222eb4b10dc5 |  | note | • Segments – If a precast pit is cast in segments, each section of the pit shall be rebated to ensure correct alignment and to prevent horizontal movement. A minimum rebate of 15 mm shall be used.
button | 99b38b3a-b8eb-5d35-8eb1-6b9ef8785c45 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 42a50711-2ad9-5055-aecc-ee36e8fac32a |  | note | Freq - Each Lot
label | c157ad8c-09c7-5b9c-9304-e33cf570bfad |  | note | Key - I
label | 1853a7a0-ad4e-5afa-a4d3-3abf33ed543d |  | note | Resp - SE
button | 3100447a-3dfc-5668-8938-f36265c2c12e |  | button | Remarks/record - Test results for fibres and fibre content (if applicable) (Compliance Certificate provided by Supplier) | Yes,No,N/A
date | f083a874-a0e2-57a4-9dea-d2ffa5bdba09 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Pits with Risers
label | e66fab0c-14c8-5306-b989-41ad4db3380e |  | note | Ref docs - BTN033
label | 98b54c3f-3c2f-53bb-9908-5e5884d43802 |  | note | Acceptance criteria - Where a drainage pit is manufactured in multiple sections with different wall thicknesses, the internal wall face must be vertically aligned, and the step in the wall thickness is to be located on the outside face of the pit. Joints must be sealed with cement mortar to provide watertight joints. No bonded anchors to be used for the construction of the drainage pits.
label | 0fd37816-a118-5c18-a672-f530a2160263 |  | note | Freq - Each Lot
label | 1cce5e35-2405-5596-bd78-8e0494f4c8ab |  | note | Key - R
label | 15cdcaed-65a8-554e-9370-61d34d495d2a |  | note | Resp - SE
date | 81d27583-79f0-5289-9180-38f23bbc1417 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Step Iron Fitting
label | 330e83fc-a66f-5e70-a5fa-41c96ed0b54a |  | note | Ref docs - VR Clause 705.12
label | 0db24bcc-25cb-5914-9420-635f6f2f3d10 |  | note | Acceptance criteria - Pits greater than 1.0 meter shall be fitted with step irons. Step irons shall not obstruct openings or be fitted to a wall which has openings.
label | 07046fd7-2e46-557b-a6d2-05a052b108a1 |  | note | • Step Irons shall be installed in accordance with the manufacturer’s instructions and shall be an approved proprietary type.
button | dbcfa8d0-f534-5465-956d-ae7a997c14c6 |  | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
label | 02973095-82e0-513c-880c-192879c20473 |  | note | Freq - Each Lot
label | 8c2130d6-8099-5511-913b-676adf831b21 |  | note | Key - S
label | d048ce73-3db9-5aab-a75e-9bbf3c87d373 |  | note | Resp - SE
button | aea4fe7f-a6a5-5769-a42e-150491ea5ca1 |  | button | Remarks/record - Material Conformance Certificates | Yes,No,N/A
date | 9fda0814-496f-5fd8-a4bf-9bb8d38bff58 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.4 - Shaping the floor
label | 10402814-f54a-5b38-88d3-14e1ce923387 |  | note | Ref docs - VR Clause 705.13
label | 583f9cf1-46dd-549a-bdc9-9f4c0539326b |  | note | Acceptance criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar, to provide a profile that will ensure smooth flow conditions between inlet and outlet pipes and prevent any snagging of debris. The cementitious mortar shall comply with the requirements of clause 610.33
button | 80f67807-0d95-54ef-97fe-58cd2e6ae20a |  | button | Has all of the above been completed? | Yes,No,N/A
label | c00e04a3-b4e9-5b24-976d-cafba102a0ce |  | note | Freq - Each Lot
label | 1516c909-ff92-5d5f-8f2d-8af4c7e73c93 |  | note | Key - S
label | ac8ff956-d6dc-59fe-a3a8-13aa5de72e40 |  | note | Resp - SE
date | f4b65c11-10ac-5bb8-838e-01d47790205e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.5 - Jointing
label | 480e23bd-37f1-58a4-bf7e-9ca797bf7851 |  | note | Ref docs - VR Clause 705.14 705.16 610.33
label | 9fedef23-a59c-52f7-8a7f-2ebe265a178a |  | note | Acceptance criteria - The joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
label | df1cc141-09d0-5302-b62a-72230a37aaad |  | note | • Mortared joints and recesses shall be cured for a period of not less than 48 hours with no backfilling until the curing period is finished.
button | 31d7b099-62e1-5098-b72e-64426e190386 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 3f843ed2-cc9e-5cb0-888a-3a3a4f8d0061 |  | note | Freq - Each Lot
label | 4020d288-9af9-5c7a-8506-987bf9287c21 |  | note | Key - W
label | dd31c1a2-2d50-5232-b03a-21108eba248b |  | note | Resp - SE
date | 117dee00-1258-5585-a34b-6856d089bf4d |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Backfilling
checkpoint-status |  |  | checkpoint | 5.1 - Survey Location Confirmation.
label | 5581731b-f62f-5e81-98f5-037bd6160559 |  | note | Acceptance criteria - The location of each drainage pit shall be verified by a survey certificate prior to backfilling the drainage pit.
label | 925be89f-6b2b-5dfa-8c7a-1937d946edb6 |  | note | • Offset of entry pits required to match lines of kerbs or barriers ±20 mm.
label | 1bfe2c6d-bf7c-553f-9587-f7e99ef4417e |  | note | • Plan location of pits other than offsets to kerb lines or barriers ±100 mm.
label | 0d96c718-ac02-5ba1-b5f5-c6d40aec099d |  | note | Freq - Each Lot
label | bebe0b16-97d4-5109-b92e-21279c9f1890 |  | note | Key - R
label | 018c7694-befe-54fb-ae45-78dbc18fd884 |  | note | Resp - SE SV
button | 43740099-8fc6-5c9c-99a5-0ed666b71d46 |  | button | Remarks/record - Survey Conformance Report | Yes,No
date | e903d022-15bb-5862-9527-6cf9039e2a3c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Backfill Material
label | 49478161-53c6-52e7-bafb-7f6498323610 |  | note | Ref docs - PS3030.07 (a)
label | 25ca2e77-26ec-5e78-a160-e4f55396c5f3 |  | note | Acceptance criteria - Backfill material shall conform to the requirements for type A material.
button | fe6207c7-04ed-57e0-ab61-0fcb0b18be0f |  | button | Has all of the above been completed? | Yes,No,N/A
label | 86445d82-ee5b-5aa0-9a5f-28c2f442a074 |  | note | Freq - Each Lot
label | 22954d0b-4e3d-5c06-a719-ec05000e091c |  | note | Key - R
label | bf48ebc0-7bf1-595e-b35d-9f877c8f954a |  | note | Resp - SE
button | 7e2a4df7-2b06-5dab-a4f9-2fdc1edce1a6 |  | button | Remarks/record - NATA Test Report: Grading/PI | Yes,No
date | 1f162f4e-5489-522e-b9ab-2aa16cc0c964 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Backfill Pits
label | 13df0a99-e537-5da3-8f8f-3ad46de7d60f |  | note | Ref docs - VR Clause 705.18 PS3030.07 (b. iv)
label | 244b7901-1650-593e-8218-aaa65e43aff8 |  | note | Acceptance criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment.
label | 49dbc2f5-c993-58fd-b649-99ff149453b2 |  | note | • Superintendent must inspect before backfilling as indicated in PS3030.07 (b. iv).
button | 8eb1e5a4-cd31-5e5a-832d-a45dafcc5bed |  | button | Has all of the above been completed? | Yes,No,N/A
label | 97cea43f-d210-5a58-93f1-fe826212d3b1 |  | note | Freq - Each Lot
label | 8295f170-8edf-583e-ba53-cac56f7b30c8 |  | note | Key - S
label | 16762890-e62f-5718-9336-04e21716cf9a |  | note | Resp - SE
label | bbb02d9a-8879-5c96-bacd-8a9b2db3aeb3 |  | note | SI Key - H
date | 7822d4cb-4902-53d7-9683-6dbb828b8a91 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.0 Completion
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | c51a6fb7-0841-59af-be76-fc11b90861c6 |  | note | Ref docs - VR Clause 705.19 610.46
label | dd9f64e4-1955-59e8-b0ad-506fd0e1bcb2 |  | note | Acceptance criteria - Survey complies with specified requirements.
label | fee2296c-6f68-516b-9619-a319c59948fc |  | note | • The level at every point of the pit covers perimeter shall be within 10 mm of the design level. The line of the cover shall be within 10mm of the design kerb line
label | a9438fa6-30d0-5027-9635-4eb5a4f0627d |  | note | • Offset of entry pits required to match lines of kerbs or barriers ±20 mm.
label | fa1137a2-3e5f-5d61-b510-8ee5d08baa37 |  | note | • Plan location of pits other than offsets to kerb lines or barriers ±100 mm.
label | 12bb5b9f-0886-5a57-9021-4ec9e9a821e9 |  | note | • The tolerance listed in Clause 610.46 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
button | 83d35d06-d9e4-508b-852e-ed6f8d1fe9b2 |  | button | Has all of the above been proven and meets requirements? | Yes,No,N/A
label | 70eec5f7-ae7f-59ca-8208-12c2a2ba7550 |  | note | Freq - Each Lot
label | 94a02cc0-a402-5bc5-bad6-4c1b5f470c19 |  | note | Key - R
label | 503a9e0a-9e8f-51cc-82d4-286ec078c5a5 |  | note | Resp - SE
button | d7c0d839-d107-5fa7-8a3e-62405d9ffa37 |  | button | Remarks/record - Survey Conformance Certificate | Yes,No
date | 8addc9b6-2dff-5b0f-8cfa-5127286a87c4 |  | date | Inspection Date:
checkpoint-group |  |  | section | 7.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 7.1 - Test Reports
label | b73bb617-abc9-5251-a087-1b07f5cd8489 |  | note | Ref docs - DoT Specs
label | 6da64a56-f07b-5238-b82c-873b9b3bcfaa |  | note | Acceptance criteria - All Test reports received and Reviewed
label | a5914969-4062-5b29-a66e-ccab8c952025 |  | note | Freq - Each Lot
label | d633c025-2c29-545a-a57f-442376e1610f |  | note | Key - R
label | 24dae65c-83ac-5c80-a63e-f2c9edf0be16 |  | note | Resp - SE
button | bdbdf54f-cca3-501f-9e95-087a8a60cc7f |  | button | Remarks/record - NATA Endorsed Test Reports | Yes,No
date | 2f061b42-8426-50e4-85c3-19fefa8b40ae |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.2 - Product Non-Conformance
label | f83d11a8-0eae-5c7f-a49c-fb9635bc9768 |  | note | Ref docs - CQMP
label | 868968b4-1562-5541-b80e-735c72c16428 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 6a01f8dc-f357-5976-99b4-dd093f586ce2 |  | note | Freq - Each Lot
label | 0fd9aa62-7902-5ad2-b1df-b6dc4f0e97dd |  | note | Key - R
label | ecc3daa5-6dde-534c-a03f-f899df71ff9c |  | note | Resp - SE
button | b8bff080-8173-5851-bbfe-2bf8e1d3d213 |  | button | Remarks/record - NCR reports | Yes,No,N/A
date | 69eb6a38-3564-567b-9bcf-eb39acf86704 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
label | 7ef4b7c4-c025-572b-830f-102ffa85c31e |  | note | Ref docs - CQMP Lot Records
label | 0c0e7dab-9134-532b-982a-d409a27da34e |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 06315200-038d-5202-a000-479298df02a7 |  | note | Freq - Each Lot
label | 77ceacb6-1c6d-5f49-b1d6-3098866afe22 |  | note | Key - R
label | 75c028a4-83dc-5f2f-b65d-3ecf09549573 |  | note | Resp - SE
label | cf15468c-f60c-5001-b8fc-aa7cdcdef22c |  | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
date | 4aa91d87-ae8c-5368-8dfb-687547642f32 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B | 3111f2df-fd4d-4607-ba81-ecbd85e8df1e
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Work Lot
label | f8fa8744-13b2-595c-98cc-5859150f61f7 |  | note | Ref docs - 173.02 204.03 (h) Table 204.142
label | d1ea8105-ee7f-591a-8a11-cf1e60ef4236 |  | note | • Quality Management Plan
label | 39a8c9d4-027d-5918-a9d9-4f96876e37ba |  | note | • Lot Diagram
label | f7650654-fefc-5b5e-bfb4-1486c27d2111 |  | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works.
label | 6c69807b-c950-5009-b94a-9b772664fe74 |  | note | • Lot diagram to be provided clearly marking up extents of lot area.
label | 1ef85644-cc9d-512f-a208-6d9367fc4fea |  | note | • Work Lot open on TeamBinder.
label | a27b5b57-cf0a-5840-a13e-ec109c455015 |  | note | • Lot size with no more than one day’s production or a maximum of 10000m² for Type B Material.
label | e043f336-5a94-5ae2-a395-e00c15916d1f |  | note | • In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
button | 4aa1afbb-375c-5a7e-ac1a-5fda953d13ee |  | button | Has all of the above been completed and approved? | Yes, No
label | 51e77f8a-25a9-54bc-8d9c-b1377033a817 |  | note | Freq - Prior to start of works
label | 02f07382-4226-50c2-9891-8c218a386800 |  | note | Key - R S
label | dd7a00e0-c420-5602-bfe6-856a64eb27da |  | note | Resp - SE
date | e6baac3d-c301-52f2-aad0-0820319eb366 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | a527cbc1-0923-5c2e-ad31-06011b6ba5f7 |  | button | Lot map | Yes,No,N/A
date | ecb63e7b-67b2-5db8-941e-630cb3effe6d |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Set Out
checkpoint-status |  |  | checkpoint | 2.1 - Set Out Survey Completed
label | 118def92-7ae8-52bd-b7c1-ea6f3cef4ac3 |  | note | Ref docs - VR Clause 204.03 (a)
label | 083d1f38-9c86-5175-acba-f078f9465f9c |  | note | • IFC Drawings
label | a87b551f-99f5-5e2e-9c83-fffacbde0053 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
button | df6f0577-1631-5a38-b0c9-16f6c114cbaf |  | button | Has all of the above been completed and approved? | Yes, No
label | 2407d0e7-d52d-5181-b4d3-0a9dfcebc940 |  | note | Freq - Each Lot
label | 81be863e-484c-5078-a26c-f7cc0949fd96 |  | note | Key - R
label | 46a738c1-b9ef-55d1-ad30-b8cea37b6831 |  | note | Resp - SE
date | 8f1df7ae-9e76-5ce3-b3e0-e1d5bce4f776 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 2.1.1 - Surveyor Report Reference
button | d0773029-ab7c-5a97-a6e3-6fee281402ef |  | button | Surveyor report reference | Yes,No,N/A
date | 6c002025-1df5-543b-98a4-3b2386c01680 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Placement of Type B Material
checkpoint-no-status |  |  | checkpoint | 3.0.1 - Incoming Material Docket
button | b966ac30-4021-58e8-9e25-53ac22743838 |  | button | Incoming material docket | Yes,No,N/A
date | ba0c806a-d3c7-541e-84c9-293c5fbc20e7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.1 - Underlying Layer Conformance
label | bd08aef2-18fe-5935-9b33-534f3172ffee |  | note | Ref docs - VR Clause 204.10(b)
label | bed0d4e8-4bf8-5135-9c69-31ce505ae231 |  | note | • Construction Document
label | 7b201fa8-bc5e-5218-a9b7-ff88bbdbd546 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
button | e2e69e54-079b-54e8-bf2a-853bfcdc9f85 |  | button | Approval to proceed granted? | Yes, No
label | 1d76b062-9cf5-56bb-ac26-05353f135e50 |  | note | Freq - Each Lot
label | 7deae25b-6a43-55c8-9c0a-e03d78545609 |  | note | Key - H W
label | fc7d1e8e-a611-5846-ad63-1d9f6fb5cc32 |  | note | Resp - SE
label | efbf72a2-32fa-5bdb-8151-f91635077240 |  | note | SI Key - H
date | 4230b240-da06-57b7-8733-02e0bd3e58a6 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Placing Geotextiles (if applicable)
label | c2034b4b-82fc-5d1f-8cf5-18254a913649 |  | note | Ref docs - VR Clause 210.05 Table PS3020.071
label | b412a3a4-e44c-569c-83cc-e43719c8b8c1 |  | note | • IFC Drawing
label | ac42204d-bfaa-5ef5-92af-13c35b074e8f |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent.
label | a2d77c7f-be3a-53b5-b980-46659f5d2cca |  | note | • Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with
label | f7afb9f1-9e7e-5743-945b-18b0c379a85a |  | note | • imperfections shall not be used.
label | 58de0113-ad2f-5738-b895-9d8385cd944c |  | note | • All joints shall be overlapped or sewn in accordance with the Geotextile Record.
label | d81479cd-00a9-57e4-a8a6-fc50ebd29eea |  | note | • Geotextiles shall be covered by filling within 48 hours of placement.
button | fb6c1e43-1fa9-51aa-9b3f-c6167f221205 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | ddec750e-39c0-59b4-bde8-4e6fadcb24db |  | note | Freq - Each Lot
label | c91a7505-60de-556a-a6ff-be74ce9a57d1 |  | note | Key - H W
label | 3ae27b8b-0063-5e42-ba64-8d61a385df27 |  | note | Resp - SE
label | 82556293-1b7c-5a49-98ef-3d6145622c23 |  | note | SI Key - H
date | 6ced88e4-37e1-5aa5-a003-e159be5bce15 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Placing Subsurface Drainage
label | 7439b7b5-66df-50e3-a649-1a765a24b725 |  | note | Ref docs - 1630-P200-SYM-TPW-RPT-0001 Appendix B – Table 5
label | 28d26d1c-81e3-58b0-bc4d-813f00975d6d |  | note | Acceptance criteria - Subsurface drainage mat to be prepared in accordance with drawings.
label | 3a6b356c-7c7b-51c3-969e-8aa27e959b17 |  | note | • Superintendent to review and approve prior to placement of any fill on top of subsurface drainage mat.
button | d507a032-f181-5036-a2fb-f8af3dd72c5f |  | button | Approval to proceed granted? | Yes, No
label | 381e8f85-d34e-5ad1-9948-f65d4724db91 |  | note | Freq - Each Lot
label | f3d345ed-beab-5838-a56e-0c928bd4059b |  | note | Key - H
label | 1d3d8f53-25e9-51be-9fe7-3d1bf0212b2e |  | note | Resp - SE
label | fb1fd68f-3689-503a-b2a3-30945ae7f1aa |  | note | SI Key - H
date | 29ec73c8-0132-5f84-9ad3-f1bf427e7307 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Placing of Fill
label | 104e13ea-72e4-50b7-9030-c40ac7450b5f |  | note | Ref docs - VR Clause 204.10(d)
label | d2dc909a-758d-540a-b4b6-7ab223f911c2 |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm.
label | e9791f4e-7e59-56c9-ab57-d49d73cfbe7d |  | note | • Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
label | 38f8450d-1e00-59b9-8d76-7e00e071fde9 |  | note | • Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material.
label | 314a6108-2574-5fbc-90da-06ab1b524735 |  | note | • Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
label | b107da41-6929-541f-a597-a3e3252f3b38 |  | note | • Material shall be compacted at minimum moisture ratio of 80%
button | 4a29c030-b1ba-5c93-9e80-70926b846973 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | e6df2306-34ae-55bf-99f5-166ca6cd7ffc |  | note | Freq - Once Each Lot
label | 0ed218b3-9346-596e-a98c-2b61bbed0ba0 |  | note | Key - W
label | 93986a07-6a29-55bc-8bcf-f93982acb552 |  | note | Resp - SE
button | edc14315-1eec-5fa6-a7a2-2359b9b53bdd |  | button | Verification Records: Layer Thickness at least every three layers | Yes, No
button | 4b004435-85b8-5337-b074-7f21a86b6652 |  | button | Material Compliance Certificates & Material Approval Register | Yes, No
button | eed86837-8847-562d-9751-a40ab2653789 |  | button | VicRoads registration of recycled material blend (if applicable) | Yes, No
date | e3ebbdf7-8c9f-5b9f-95f2-ea98d1f981ca |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Keyed Fill Layers
label | 983500ac-6324-5b1f-a3a5-760b49f65ccf |  | note | Ref docs - VR Clause 204.10(c) 204.10(d)
label | 03ab576d-3c63-5c45-8e37-c69b63ee2ebc |  | note | • Construction Document
label | 8ac0100a-3cc4-57a2-827d-242ef2f85a73 |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
label | 8ab6705a-6931-59b9-9435-644477ea4b54 |  | note | • Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | e1633663-4a1e-5a62-a78a-21738e56505f |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 4ac2db4a-8b83-5c58-9a16-585bedd8a7e1 |  | note | Freq - Once Each Lot
label | 217b824b-a26a-5a00-abd7-1baf1c824518 |  | note | Key - W
label | a7733f88-456d-5861-80a7-2e93b24c4b8e |  | note | Resp - SE
date | f64f483a-3116-5b3d-ae5e-aa37eff088d4 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.6 - Test Roll of Type B fill layer
label | a4810167-86c5-5440-a8f4-045b186645db |  | note | Ref docs - VR Clause 204.12 173.03
label | 45a0352e-c31f-5aa6-9eff-0a009224c43d |  | note | • Construction Document (Test roll Procedure in specification 173.03)
label | f96f803d-b391-52ea-b794-8befd62d86a5 |  | note | • 1630-P200-SYM-GEO-DPK-0001 Table 43
label | 67343215-be75-5c27-b8d7-f09ebd168b85 |  | note | Acceptance criteria - Test Roll in accordance with Section 173.
label | dc3ad455-ee27-59f4-af30-018174f27a78 |  | note | • Surface shall withstand test rolling without visible deformation or springing.
label | 2f8c38f9-a9ca-5b46-bf6b-d9ef04f84855 |  | note | • Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass.
label | b19d176e-cc32-57de-a9f2-2e603517c7c4 |  | note | • Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted.
label | bce1ad60-b581-5f0f-ad31-55936a8b5014 |  | note | • The Contractor shall provide for the Superintendent to be present during all test rolling.
button | 9cd85883-6751-561e-8b28-022788358b85 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | fedea765-b8fb-56a5-b2dc-c5f76ffedbc1 |  | note | Freq - Each Lot
label | 6878c82f-f0a0-5809-b49c-55b399d92467 |  | note | Key - H
label | 2ed9baeb-2371-5896-9eec-2cdd98ce380f |  | note | Resp - SE
label | 5827d578-ef52-5212-be3b-e56f06afda64 |  | note | SI Key - H
date | df392e42-8e70-5cb1-8651-38179c5f77a7 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 3.6.1 - Proof roll if applicable
button | 7d20b188-3a8b-5b38-b7c2-48c9ff2d1a8b |  | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
text | 4a6027b9-7852-54f0-b437-47adc79b621e |  | textbox | Chainage
date | d2c1147d-1755-59b8-8563-a1894bdc81c9 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Geotechnical Analysis
checkpoint-status |  |  | checkpoint | 4.1 - CBR/Swell – Initial Testing
label | 91bfb728-5fdd-56b5-9e6b-ac3930a0339c |  | note | Ref docs - VR Clause 204.04(c) PS3020.05 (c)(v)
label | 98ae63c7-d3ea-549d-a559-f013517b318d |  | note | Acceptance criteria - First lot tested to determine assigned CBR and Swell:
label | ac9f9e30-d565-5a74-9fdf-c652b63fbf0f |  | note | • CBR ? 2.5%
label | 40712dda-c500-5516-a3be-ee59d7a2ffb7 |  | note | • Swell < 2.5%
label | c8fd70c5-d39f-5296-8304-b8ba47b10ce4 |  | note | • If swell exceeds 2.5%, material shall be classified as expansive. Raise RFI and request approval from Superintendent to use material.
label | 74cdb9ed-6770-53e7-b2a8-6609f5dccd6f |  | note | Freq - Each Lot
label | 62941524-c285-5027-9c3c-e3c947cef67d |  | note | Key - R
label | 7c85ecca-e400-55e4-9984-6aa85352f368 |  | note | Resp - SE
button | 5af2ccd3-3031-5d0a-b331-4d94cd946b32 |  | button | NATA Test Report: CBR and Swell | Yes, No
date | 1f87eedc-fdb4-512c-a77f-31c1f28b0512 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Compaction Testing / Moisture Testing
label | 7c0ba699-a638-5e26-b8a7-5e1c5d91cb62 |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) Table PS3020.072
label | 365f91d9-d18a-5119-932e-47785f1bf2d3 |  | note | Acceptance criteria - All areas of the job will be considered as scale A.
label | 212572ac-70c5-508f-b9ca-53060fd99d7a |  | note | • Scale A Testing: HWKR Rd, Princes Freeway, All Freeway Interchange Ramps, All other arterial roads.
label | 7ee65017-459d-559c-b479-746fda37da19 |  | note | • Scale B Testing: All other local roads, SUP.
label | 2f174dd1-5828-59a2-b6eb-a3fb2d21dade |  | note | • Type B material placed within 400 mm of top of Type B material: 99% (Scale A)
label | 63df42a2-8de3-5d69-a0f4-cb1441ceb73b |  | note | • Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A)
label | 12c0681f-8950-55a5-af8d-bed53a51f43f |  | note | • Type B material placed within 400 mm of top of Type B material: 98% (Scale B)
label | c17b1b5c-307a-5be3-b77d-618e417bcd29 |  | note | • Type B Material placed more than 400 mm below top of Type B Material: 95% (Scale B)
label | 1c49a7b5-13e6-5104-9d8c-e51023541254 |  | note | • Type B material is to be tested as per table 201.142. And should meet the moisture content requirements as per VR204.
label | 4c4325f5-a2eb-595c-aeb8-4fa5fa196f09 |  | note | • >70% for any material within 150mm of subgrade.
label | 6864dc93-2ff2-597b-be3e-333a8a6e0ea7 |  | note | • >80% for all material below cut floor level.
button | 93d15fb4-c8bf-5773-9678-b2b60d35f8fb |  | button | Have the results been achieved? | Yes, No
label | ba39e6a5-b6fb-5ab4-8cd9-d92b0271b339 |  | note | Freq - Each Lot
label | b654dc38-3ff9-58b6-ba21-8539363b5c51 |  | note | Key - R
label | 9c6d5e95-5e1e-5d3e-a0ff-48acaa61cc9e |  | note | Resp - SE
button | 15761318-036d-54de-a751-fa8d2dd404c5 |  | button | NATA Test Report: Compaction | Yes, No
date | e35b4a03-00b1-558e-a33d-52aa7383c86d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Material Requirements
label | 44b65fdc-6368-5473-9181-924946fa2b1c |  | note | Ref docs - VR Clause Table 204.041
label | 4379448b-b6d0-523c-895a-3a8037cefebd |  | note | Acceptance criteria - Maximum Particle Distribution (MPD) ? 150 mm within 400 mm of Top of Type B. or MPD ? 40mm at depths greater than 400 mm below the top of Type B material.
button | e93b3fa0-8dfe-5d84-97ec-8c2e52a68c6c |  | button | Have the results been achieved? | Yes, No
label | 2114a86e-059c-513d-8ac6-c29e058925f5 |  | note | Freq - Each Lot
label | f1bf0faf-db49-5dfa-aa54-d6a4039fe6f3 |  | note | Key - R
label | c6f2522f-598b-54ce-9292-02bb59549387 |  | note | Resp - SE
date | bf83510c-aecf-5606-ae1d-5cbe088eac04 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.4 - LL and PI Testing
label | d76fb0de-d97d-5ad8-bb27-d9cad57deddc |  | note | Ref docs - VR Clause Table 204.141 Table 204.142 173.04(d)
label | b43e6d06-8615-5fbf-9c35-94e547b16dad |  | note | Acceptance criteria - LL and comparison of PI against LL, (identification of silt) is required for Type B Material. Initial testing is 1 Test per 2 lots.
button | 2d8a3c83-32fb-5e62-945e-811f84c8e672 |  | button | Have the results been achieved? | Yes, No
label | 8a87e1fc-e8f2-5058-b430-c4a92ab6be0a |  | note | Freq - Each Lot
label | a074bc31-e9e7-5db8-9466-23e5ee89dbed |  | note | Key - R
label | a1a2e96e-f8cb-5c9f-8320-4dd0eb3b590d |  | note | Resp - SE
button | 5e59158b-3225-586c-ba9a-0f1a244dfb02 |  | button | NATA Test Report: LL, PI | Yes, No
date | fde104fc-9b01-55a7-9108-bff43d4c61a3 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.5 - Reduced Frequency Post compaction testing of initial lots.
label | c1479262-f6af-5c15-8091-aea0aeeec38f |  | note | Ref docs - VR Clause 204.14 – Table 204.141 PS3020.07 (f)
label | 6ca61033-2d69-5dfe-b061-4ac3da306207 |  | note | Acceptance criteria - Test initial lot for CBR/Swell.
label | 6a5f862d-a29f-5c5d-8c92-8c70cd03c944 |  | note | • Test initial 3 lots for compaction.
label | 3dc0e1e8-ee11-519d-9fd4-64846fc3338b |  | note | • Once material and work have achieved the specified requirements in the first test. And;
label | 8e90521c-245d-5507-83d5-0d8399de7d38 |  | note | • Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
label | c146e570-2dc6-55a0-aa24-a0e65def17fa |  | note | • If Reduced frequency has been granted, the testing can be conducted at the following frequency.
label | 90769965-a46f-5dcf-b97c-69c6347f2a09 |  | note | • 1 test per every 8 lots for CBR/Swell
label | 85d87464-9a88-5dac-968c-3ab7b678f556 |  | note | • 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing.
label | 6d34f96d-4895-5b35-bb0b-e076b5114d76 |  | note | • 1 test per 4 lots of LL and comparison of PI against LL.
button | 98404032-c260-52f1-b2c1-d684e7b4d057 |  | button | Has the criteria been achieved? | Yes, No
label | 62c7bb6b-86dc-5ec1-8058-f1017a9a105a |  | note | Freq - Each Lot
label | 6f56bbda-c8a8-5593-bcd7-98839f3d65c7 |  | note | Key - R
label | 6610f325-093b-5730-a0b6-f5990129546b |  | note | Resp - SE
label | 2ad28cee-3061-52a9-ac78-8535637aa9a9 |  | note | SI Key - R
date | 208ca7a8-167e-584d-a47c-f7f0b6b799f3 |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
label | d1345fae-145b-5b0d-af14-74c5227c0a94 |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | e7ab7d81-c896-592e-a99b-d0cc763d63c6 |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements.
label | af2cb4d9-359c-50dd-a958-2d376315462b |  | note | Scale A: 80 measurements per lot
label | e697266b-9e3a-583d-a9ca-703f6478ac6e |  | note | Mean +5 / -15 mm Max Std Dev. 12 mm
button | 57eed39e-620e-516e-b12b-e8601eb7111f |  | button | Does the final product conform to the above criterial? | Yes, No
label | 7e3734b0-d44c-5430-8d10-c4df18b361a7 |  | note | Freq - Each Lot
label | ffd92195-084d-576a-8f26-dcf60131aafc |  | note | Key - R
label | 5ef8ba29-032e-54b5-8b18-6f3446dd71a6 |  | note | Resp - SE
date | a234cb9e-7b87-58d2-8d45-8074d4c05cd1 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 02eb49a0-3f89-5637-8bf6-d42b2315dec8 |  | note | Ref docs - VR Clause 204.15
label | 6a9e98f9-e1dd-5121-9cbe-fa3007557e1c |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
label | a5e66414-f1c3-501d-b611-fd5fb5a245dd |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | acd96646-20c0-58e3-a7d7-c8045e83f782 |  | button | Does the final product conform to the above criterial? | Yes, No
label | b8d92a8d-0ee1-5320-a7f5-11f9adcbe01a |  | note | Freq - Each Lot
label | 23697983-92a5-572a-bc45-af87969c195b |  | note | Key - R
label | b58f0636-5780-500d-b5bf-0f358a1ecf94 |  | note | Resp - SE
date | 21888d3c-e248-521b-90f5-42b79710c920 |  | date | Inspection Date:
checkpoint-group |  |  | section | 6.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 6.1 - Test Reports
label | 1c5e28cd-b7a9-5172-831f-e6eeb8f870fb |  | note | Ref docs - DoT Specs
label | 9825c7b4-8b07-5800-a59a-a24f61edc366 |  | note | Acceptance criteria - All Test reports received and reviewed
label | e650331a-449c-5697-a402-dd04edaeca4b |  | note | Freq - Each Lot
label | 0a39f398-8347-5ff8-91c6-4028ececdb48 |  | note | Key - R
label | a835032b-54f1-5e3d-9bc4-434f31806b21 |  | note | Resp - SE
label | 301e79f9-cc24-5399-b011-84686b184546 |  | note | NATA Endorsed Test Reports
date | 14434944-eedb-5e51-8bfd-22f0a0aea0b3 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.2 - Product Non-Conformance
label | 7e067f12-75f7-5cb1-998c-30bec7510d73 |  | note | Ref docs - QMP
label | 87a3287c-1139-5a79-9f05-8820e0e93eb5 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 4fb2e3d3-112c-5769-a2e0-0987651e0f94 |  | note | Freq - Each Lot
label | a4f426b2-0b77-53c9-b298-95adbd8fcf6a |  | note | Key - R
label | 5948400e-70e1-5ca6-a1ff-bc0bb4eed080 |  | note | Resp - PE
label | 922db5e6-793c-5502-a517-9305dd6a331e |  | note | NCR reports
date | 3393f966-3760-542d-8d15-4d556b915d5d |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0019 Lower Subbase Layers | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0019 Lower Subbase Layers | 3526fc3e-f635-4689-99f3-f7af02eba99f
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Check Survey Set-out and TCM’s
label | b99e4d74-7856-5dad-92c3-a78c2d07213e |  | note | Acceptance criteria - Record existing TCM’s on TCM offset sheet. Survey set out including frame, benchmark, and recovery points in place.
label | 07a641cc-9de2-56c7-9ca8-56b7d62939b7 |  | note | Freq - Prior to start of Works
label | 559f184a-50bf-53b4-beb1-69c10045e48c |  | note | Key - H
label | 8c5c8bae-02b5-5f26-b6a3-941d751d9508 |  | note | Resp - SE
date | 08f94f57-66a8-5f53-9636-9a38334992f5 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 8dea6dc8-3b70-5aa9-99cf-2aa6bd2e4ade |  | button | Lot map | Yes,No,N/A
date | e44a8763-d941-5791-8aaf-5d3077a4f6e8 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 4afa04ca-c2e4-59ef-a235-195718fc4045 |  | button | Environmental permit | Yes,No,N/A
date | 9c3c6d19-5007-530b-8724-bf3b7b11e5d0 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Subgrade preparation
label | 928bef34-6dca-5390-a922-9a93985a9a88 |  | note | Ref docs - DoT Clause 304.04
label | cab27010-71b9-537a-9368-671d59f969e2 |  | note | Acceptance criteria - The subgrade should conform to the requirements (compaction and levels) of Section 204 before the lower subbase can be placed.
label | e8cc7b87-f06c-5e63-9a72-be11c7190e01 |  | note | Freq - Prior to start of works
label | 00c3ac6a-e1ca-5844-a922-53a0dca990aa |  | note | Key - H
label | 00022e9d-9e78-538c-bed2-7bb830bcfb84 |  | note | Resp - SE
label | 8b7a02af-e1dc-5457-82cc-52b736a5d4a2 |  | note | SI Key - R
label | 9a377d97-e484-53da-aa1a-31b72e481c77 |  | note | Remarks/record -
button | 8f80b867-9d91-5510-a6a9-24cfb671b338 |  | button | • Survey Conformance Certificate | Yes,No
button | 38e04c9a-2cbf-5631-b6de-7a49f382b886 |  | button | • Test Reports | Yes,No
date | d504a524-a2b9-540e-830a-aa5da356ef91 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.3 - Material procurement for construction
label | 9deb86ac-fb0c-5781-9781-3320e40094d2 |  | note | Ref docs - DoT Clause 304.03, 812, 204.04
label | 4e5f9488-d476-5ee3-aa4c-c467a5653eba |  | note | Acceptance criteria - HP: All crushed rock proposed for use on VicRoads funded works shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
label | 7c52698a-13d9-55e5-bbbc-cc50129794c6 |  | note | • The Contractor shall be responsible for the procurement of sufficient specified material to complete the work. The Contractor shall supply details demonstrating compliance of the materials with Section 801.
label | 1d9d6343-5e7f-5bf7-a71e-74aa089cd861 |  | note | • Water added to the pavement will be clean and suitable for construction and substantially free from detrimental impurities such as oils, salts, acids, alkalis, and vegetable substances, and have no more 1000 mg/L of suspended solids.
label | 417b795c-37c4-54f7-a938-e03a753dc5d4 |  | note | Freq - Prior to start of works
label | 87da74e8-cacd-5dc0-be33-9c206a372fbd |  | note | Key - H W I
label | 7d5b9f60-dd4d-556a-82fe-9ec8094604a5 |  | note | Resp - SE
label | 1d5843bf-6eba-5ddd-82ae-ffaa17b2e224 |  | note | SI Key - H
label | a9ea14e3-28c8-5904-b211-63335f7a7efa |  | note | Remarks/record -
button | 8c3c9034-6854-57c7-978e-0d902ed35612 |  | button | • Crushed Rock Mix Registration | Yes,No
button | af01d87f-f1c7-512c-9c69-95c3bde76f9b |  | button | • Delivery docket and material compliance checklist | Yes,No
button | 6123e4f5-b36c-549c-8b90-c59b0c1849b7 |  | button | • VicRoads Materials conformance | Yes,No
date | 7e25a1ed-2bf8-5ce4-beeb-81d185b0e21d |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Installation of Lower Subbase Layer
checkpoint-status |  |  | checkpoint | 2.1 - Construction - Jointing
label | 78900972-6ba4-5a01-9e32-4f0d48f26b49 |  | note | Ref docs - DoT Clause 304.07
label | 30130d8c-00aa-5acc-bd93-8bbb7fda5992 |  | note | Acceptance criteria - Transverse - Offset by not less than 2 m to any underlying pavement layers.
label | 275f9e27-36bc-59bd-9eec-1d17a862e22f |  | note | • Longitudinal - Offset by not less than 150 mm to any underlying pavement layers. Located within 300 mm of the traffic lane lines or within 300 mm of the centre of a traffic lane.
label | 6fd2b3f9-492c-5746-aa9d-cf65798f7c9e |  | note | • The exposed end of each lot and the exposed edges of any part width construction shall be kept moist until spreading and compaction has been completed over the entire layer.
label | 46f30bdc-e10b-5e7a-b334-c58a7366880f |  | note | Freq - Each Lot
label | 01861c8a-ecb8-56eb-ad70-e0ec498427bb |  | note | Key - S I
label | 7979ffe7-3c84-5086-885e-05c397e0787d |  | note | Resp - SE
date | 120ca43d-a406-5553-9564-94d520000ac2 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - Placement of Material & Testing Compaction
label | dd955adb-2c72-59e7-a6f1-5cc6f08bef5b |  | note | Ref docs - DoT Clause
label | 4b5ffe9e-476b-543e-aea3-73c14b7bc1a6 |  | note | • 304.06
label | 1313efe3-2520-5c18-9229-ac055b53c2cf |  | note | • 304.06 (b)
label | f04cfa67-6402-5be0-8f76-50c83db28258 |  | note | • 304.06 (c)(i)
label | 36174cc9-6fc6-5790-9fcc-37e1ee05a164 |  | note | • 304.06 (d)
label | d966b78d-1fd5-595b-b7e4-2c8baef071c7 |  | note | • 304.08(a)
label | 29b69ee5-667c-586d-83d7-9887b7f27bd5 |  | note | • IFC Drawings
label | bc55cd16-16a6-55b5-bb4f-9e721c480c34 |  | note | • Construction Work Pack
label | 577642c7-4777-592e-9a9b-b875bd2a32c1 |  | note | Acceptance criteria - Place and compact layers so that the surface finish is smooth and uniform.
label | 2f9311a1-87a4-5ffc-bc4b-41e2220fcb71 |  | note | • HP: Any material that has been compacted and then trimmed from the compacted surface to conform to the correct level or thickness as shown on the drawings shall not be re-used in the pavement construction without the approval of the Superintendent.
label | 3eea983c-2e2a-52ad-b5f4-d25a9f5f79c1 |  | note | • The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | f911cf37-83db-54b0-bbfb-3a49cb17f311 |  | note | • The subbase course shall be not less than the specified thickness by more than 15 mm.
label | 7b62a0fa-f09c-5207-8c08-a57c2cba6cad |  | note | • No point > 8 mm below a 3 m straight edge in any direction
label | d90793b4-dac7-58c6-940f-dabd6177673f |  | note | • No point >10 mm below a 6 m straight edge in any direction
label | 397849d2-1ea5-5efd-8d6c-b0d1ea9ce12b |  | note | • No Ponding of Water.
label | 775f7d64-d09b-56f8-8305-0db9c4303561 |  | note | ○ For material of nominal size > 40mm:
label | 5fc00657-ac1d-59db-bfab-cf9111c25fbd |  | note | • The first lot shall be placed as a trial section. Following acceptance of the trial section, the Contractor shall then confirm the moisture control and compaction procedure and submit the procedure to the Superintendent for review and record.
label | bc0dfdac-b01b-52cb-bddc-4f1f4ae62d85 |  | note | ○ For material of nominal size < 40mm:
label | a76dbbda-b70a-5385-b531-7b8a630f426f |  | note | • No trial sections needed.
label | 3f3c5324-02db-551f-b88a-a12295b4efc2 |  | note | Freq - Each Lot
label | 84135121-b28b-55ae-9347-aec9e1906f36 |  | note | Key - H I W
label | e9085903-830d-5e25-886a-1371b6ccab4c |  | note | Resp - SE
label | cea73a5c-2786-5329-8742-b473915284a7 |  | note | SI Key - H R
label | 356b02ec-d241-52ea-8a3d-17c9f1755373 |  | note | Remarks/record -
button | 49898788-ff7b-515d-ad99-c1936bf76db1 |  | button | • NATA Test for Compaction | Yes,No
button | 1eb745d5-492c-5234-933b-3fa78db037be |  | button | • NATA Test Report for Material | Yes,No
date | 7e922665-6479-5865-afb4-0ba1f3de488e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.3 - Testing – Stability (Proof Roll)
label | abb749de-297e-59f1-98fc-f85ab0add235 |  | note | Ref docs - DoT Clause 304.08(b)
label | 431e7726-69f8-54df-a8b5-36ace7c613b8 |  | note | Acceptance criteria - Test rolling of the subbase layer, irrespective of material size, shall be in accordance with the test rolling procedure that was submitted to, and approved by, the Superintendent.
label | 61537bf4-3a01-5296-a5bb-3834e8c8155c |  | note | • Area shall withstand test rolling without visible deformation or springing.
label | f94f5eb7-bbf5-59b1-a2ba-be419b06461d |  | note | Freq - Each Lot
label | d8721f56-2e85-57af-a2a9-502fac353ff2 |  | note | Key - H W
label | 955d2626-a43c-5aec-8d69-809d0d48a486 |  | note | Resp - SE
label | 330383b7-ef04-5e51-a201-d7533ec92b4c |  | note | SI Key - H
date | ae119e49-c3e1-59a1-9cc8-f218a7c81669 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Protection of compacted layer
label | 6fc04e0b-e0a8-5b18-922d-64b0a3bfe29a |  | note | Ref docs - DoT Clause 304.09 Construction Work Pack
label | e0ffd55a-75b3-5e20-b623-30deea323680 |  | note | Acceptance criteria - Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
label | b97285c4-9630-57c7-9159-0a69ee6ec003 |  | note | Freq - Each Lot
label | 2527abfe-8635-519f-af47-0a0870756ba4 |  | note | Key - I
label | 1289f08d-81c4-5df6-8926-0c6f95aea369 |  | note | Resp - SE
date | 522e4f7b-b10c-550f-beb8-ae0eb3769a5e |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Testing
checkpoint-status |  |  | checkpoint | 3.1 - Testing – Compaction
label | 71cb93ea-2e8b-54fd-a021-dbab1f515a21 |  | note | Ref docs - DoT Clause 304.08(b) 304.10 304.11 Table 304.111
label | 72a2548b-4971-5497-8e34-042c6c3d26fc |  | note | Acceptance criteria - Characteristic Density Ratio % (six tests): Not less than 98.0% Modified
label | b0565aab-5cba-51ff-8cdc-9157f61b6080 |  | note | Freq - As required by section 3.2
label | 61b8cf09-5efe-5338-86fd-b0af3fab6256 |  | note | Key - R
label | 83d894a2-eb50-59dd-8ef6-6d54da2f126d |  | note | Resp - SE
label | 439c9d50-31be-5b83-ae88-9e3c963087a6 |  | note | SI Key - R
label | 2441d932-081f-5ef9-88e4-61bb85a16893 |  | note | Remarks/record -
button | b253cbe6-a430-5884-85e7-6fb8599f03d0 |  | button | • NATA Test Report | Yes,No
date | d450ac2c-11ab-5032-9595-e2a81369cf42 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Scale A Requirements for Post Compaction Grading and PI Testing
label | 693f8002-ac4b-5e7f-a407-435743e14913 |  | note | Ref docs - DoT Clause 304.11 (c) (i)
label | 2a32281a-aa94-569c-a690-bb64d40e8bed |  | note | Acceptance criteria - Where testing is specified in Clause 304.10(c) or (d) and Clause 304.12 requires it to be Scale A, all pavement layers shall be tested for post-compaction grading and PI at the frequency specified in Table 304.111.
label | a182f3d5-906a-5843-86ea-07187fe59d5d |  | note | • The first lot of each pavement layer shall be tested for post-compaction grading and PI.
label | 95d30c17-b67e-5835-8845-9f81066cca73 |  | note | • The Contractor shall immediately notify the Superintendent of any lot that does not meet the specified requirements and any subsequent lot shall be tested as if it were the initial lot.
label | 609053d8-25a1-52f5-a77b-a5b74777e9fe |  | note | • If any lot meets the specified requirements but is reworked to comply with the specified compaction requirements, it shall be retested for compliance with specified requirements.
label | d69dda11-2519-50ef-8f43-de6fc8c8fe80 |  | note | Freq - Each Lot
label | 5a8cbc8a-98aa-5f7c-8bdf-18fc7a659e5b |  | note | Key - H
label | cdb4da61-392c-5ad3-9481-a3665913cc93 |  | note | Resp - SE
label | e6a2e5a7-7dd4-5932-ac2d-d8bfa5b42e4d |  | note | SI Key - H
label | cd4e7bfa-2c0b-5fe8-bb3e-62e6dc95ff93 |  | note | Remarks/record -
button | 96d78990-e3dc-5a92-a363-94c77effcd30 |  | button | • NATA Test Report | Yes,No
date | 1988579a-915e-5bac-a444-0ae957ff9408 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Post Compaction Grading (Nominal Size = 20mm)
label | d81a2dcf-fd84-5e48-9803-e1fd1cfe315a |  | note | Ref docs - VR Clause 304.10 (a)
label | 9f7e93fe-1ead-5b14-84b7-c5bc16076892 |  | note | Acceptance criteria - Sieve 26.5 mm – 100% passing by mass,
label | 7d1c6e73-a3f8-5f74-94e5-6b23760797cd |  | note | • Sieve 19.0 mm – 95 - 100% passing by mass,
label | c0a6ed53-61c7-5850-9575-f0076ebe9230 |  | note | • Sieve 13.2 mm – 75 – 95% passing by mass,
label | d90bb3c0-20d7-5a0b-935b-216022449248 |  | note | • Sieve 9.5 mm – 60 - 90% passing by mass,
label | 4c9370d0-767a-59c1-95b6-5ed9e069ccaa |  | note | • Sieve 4.75 mm – 42 - 76% passing by mass,
label | e8bc41ce-8be3-583c-8516-1b7757f9a4ee |  | note | • Sieve 2.36 mm – 28 - 61% passing by mass,
label | fd7ed6b8-9c1b-59e9-9d1e-1e8ce341f89f |  | note | • Sieve 0.425 mm – 14 - 29% passing by mass,
label | 63424bb2-38ea-55bd-98b9-a693efd5131d |  | note | • Sieve 0.075 mm – 6 - 14% passing by mass.
label | c8a065b2-563c-5198-b89a-39005e641ce2 |  | note | • Initial testing frequency: 1 test for each lot tested for compaction until 3 consecutive lots achieve specified requirements.
label | f462c67b-c35d-5ce1-9be5-738abe842228 |  | note | Freq - Each Lot
label | 45d43ea0-2286-5d53-8211-86ec27e5b648 |  | note | Key - R
label | dbc9bc92-fcc0-5b01-a683-7eaa35c7a1d7 |  | note | Resp - SE
label | a6110f33-7dc5-552d-b9a7-40f723681180 |  | note | Remarks/record -
button | 09d54dcc-ed10-5489-92e7-2281d4c7c170 |  | button | • NATA Test Report: Grading | Yes,No
button | 54bb9329-97ea-5c2b-965f-f09d6d98d093 |  | button | • Visual Inspections for Maximum Particle Dimension | Yes,No
date | b0b46c81-4ebb-564c-a3f7-4370f8d011ce |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.4 - Plasticity Index
label | 8d702aa9-4981-5cbc-bf80-1000612986b3 |  | note | Ref docs - VR Clause 304.10 (b)
label | 7371eb74-9e9f-51a1-a727-54deabb4c3f0 |  | note | Acceptance criteria - PI: 0 – 10%, Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
label | d62d3c2b-743c-5e61-8e3b-0b511a041645 |  | note | Freq - Each Lot
label | 662eb067-bc98-56c4-bb7e-6123fd230b47 |  | note | Key - R
label | 84d5c91f-b1a5-5975-99ba-cb27c33d1eae |  | note | Resp - SE
label | 4be01b32-5af9-5016-a3b1-e882b9da6962 |  | note | Remarks/record -
button | 8f643088-d301-5e90-a5fe-a8f01dd34c6c |  | button | NATA Test Report: Atterberg Limits | Yes,No
date | ac6c3bbe-bfd5-5ae2-87e3-4884f08b2e86 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Testing – Reduced Frequency
label | faa7e5a7-8e06-5a69-b1c3-f1801d20b31a |  | note | Ref docs - DoT Clause 304.11 Table 304.111 Table PS3040.061
label | e2cb4b68-a4a4-5cc2-b329-3eee0bcc0f20 |  | note | Acceptance criteria - Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
label | a8f6f1d1-785a-5f38-aad3-45618a18b75a |  | note | • Testing may then be completed at the minimum frequency outlined in Table 304.111 and Table PS3040.061.
label | d9c93473-3917-5321-89bd-da8c995ec3e3 |  | note | • For Subbase, one Characteristic Density Ratio % (six tests) will be completed for every second lot.
label | 4624fb76-e2ca-5538-b0e2-0f01a149d614 |  | note | • Testing will be completed at the minimum frequency until such time as a lot fails to achieve the specified requirements. After a failed result, all subsequent lots will be tested until three consecutive lots of like material and work have achieved the specified standard, at which time the frequency of testing may revert to the minimum frequency.
label | a0e1a91b-769c-5958-b068-fb0956002c78 |  | note | Freq - Each lot
label | f00ae2e2-23e4-5c50-bb41-2b16f914abe1 |  | note | Key - R
label | 32f87c21-d203-503e-a1d6-ce7fe23ca9a7 |  | note | Resp - SE
label | 0819bcf7-26b3-5ddf-8d44-2414e7be275e |  | note | SI Key - R
label | 3f1c9a48-4c12-5a33-b4df-c14227c6d08c |  | note | Remarks/record -
text | 5cc30595-ce03-5d8a-aa26-f196568b35ab |  | textbox | • If using reduced frequency, provide lot number of previous lot tested:
date | e33a088d-909f-5ad7-86a4-a6ba94c04d7e |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Completion
checkpoint-status |  |  | checkpoint | 4.1 - Survey as built
label | 40516cd4-e82b-52ee-bb5f-87b36832c897 |  | note | Ref docs - DoT Clause 304.06 Table 304.061 Table 304.062
label | 3b3f18dc-0d20-51dd-80e5-5a05105c855b |  | note | Acceptance criteria - Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
label | cb35fb57-7ea7-5800-9b8b-229cd131e105 |  | note | ○ Surface level checked for compliance with 304.06:
label | da2a24c8-fdd0-5d4a-a918-a7c8ee6982a7 |  | note | • Mean +6 mm to -10 mm with a max std deviation of 10 mm (Scale A)
label | c8e79556-b99c-572b-8895-dda6329e153f |  | note | • Min 80 measurements per lot (Scale A)
label | 782e2166-1ee6-5fe9-9e3a-89db758ee1c0 |  | note | ○ Number of survey points to be at random locations in accordance with VicRoads test method with minimum number in accordance with Table 304.061.
label | 898c2fad-d45c-57d1-ab32-4cf4b871ce77 |  | note | Freq - Each Lot
label | ad21d2e1-0c08-56f1-87a9-621e26e86b4d |  | note | Key - R I
label | b0293030-f8ad-5795-b2a6-62c48a1347af |  | note | Resp - SE
label | d873418c-2963-5853-95f4-78c29e97d23f |  | note | Remarks/record -
button | c24bd7d2-b4b7-503d-b52f-b50af1f89832 |  | button | Survey Conformance Certificate | Yes,No
date | 06c0ee22-c56c-515c-b9a4-23fc42d8af1a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Thickness of Pavement Layers
label | 00592ccf-6db4-546c-a304-c75cd20b9464 |  | note | Ref docs - VR Clause 304.06 (c)
label | 76421ecd-4a40-5dcc-b7b9-fbcf0a16e21b |  | note | Acceptance criteria - The following tolerances shall apply to the thickness of any pavement layer:
label | 9562c98d-2635-5a0f-aebf-a37e1f1eb6f6 |  | note | • The subbase course shall be not less than the specified thickness by more than 15 mm;
label | dfa5820d-c96d-5d8f-9074-6398428e7638 |  | note | • The base course shall be not less than the specified thickness by more than 10 mm and the average thickness of base over every 100 m section, over the full carriageway width, shall be not less than the specified thickness;
label | 1257b284-6902-590f-9edc-2ab8079c0296 |  | note | • The combined thickness of subbase and base courses shall be not less than the specified thickness by more than 15 mm.
label | 6110d383-d99f-59dd-8d1d-fecc83618153 |  | note | Freq - Each Lot
label | 0f929b1e-ec48-5c0d-8f77-716d125a532e |  | note | Key - R I
label | 42e02618-d257-53ac-9c80-2952bdd09af8 |  | note | Resp - SE
label | 9c71bc51-4efb-5ee2-a601-0834151af502 |  | note | Remarks/record -
button | cda87787-52b3-5a62-94f7-580fdfa240c3 |  | button | • Survey Conformance Certificate | Yes,No
date | df4cb55d-220d-57cc-a967-ce1295de10fe |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 5.1 - Test Reports
label | f380ea94-538c-527f-a9c2-b95eb7c802a6 |  | note | Ref docs - VIC Roads Specifications
label | db73627c-167c-5a50-8786-624d6225b4c5 |  | note | Acceptance criteria - All Test reports received and Reviewed.
label | 37927a82-e42a-5284-8b8b-25559fafaf03 |  | note | Freq - Each Lot
label | 868846d0-3248-593d-a394-4a92d13bff4b |  | note | Key - R
label | e6ce1c12-3a38-5b60-b495-a457c75bb730 |  | note | Resp - SE
label | 73c0e856-8f89-5766-aca4-b1c24e6a6089 |  | note | Remarks/record -
button | a2ada059-7c23-5066-9db6-51d2e5bfc4dd |  | button | • NATA Endorsed Test Reports | Yes,No
date | 5f1d1d54-fa46-5623-9f1c-a04e6287143a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Product Non-Conformance
label | 22c854ba-0ff1-575e-a995-e2f17a09a5f4 |  | note | Ref docs - CQMP
label | dfea45df-ecbe-5148-bf0f-f6c0ab0a3deb |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | d41d9b3e-0402-54d1-af1e-ccc41844b23f |  | note | Freq - Each Lot
label | e982308e-7ad0-594f-8195-33ec793f9694 |  | note | Key - R
label | fde1d45d-f03d-5655-8e77-f8da714d2910 |  | note | Resp - SE
label | b9505a46-1304-5c69-bea9-8e83ba3b2bc7 |  | note | Remarks/record -
button | f980fd33-2799-502e-90fa-9655afa1ffc4 |  | button | • NCR reports | Yes,No
date | ec1564b1-e241-541d-99c7-23986263cbc8 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
label | 1381efa3-d1e5-5822-bcd4-1ddd02867e82 |  | note | Ref docs - CQMP Lot Records
label | 73ed2239-6812-58c6-954c-4c966a71f679 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 23b243a8-ae1d-5f11-aaa0-ed5a4abee708 |  | note | Freq - Each Lot
label | cc3d85e0-fad7-5b6f-ad13-0e71b4a82841 |  | note | Key - R
label | c1bbf8a5-77f5-571d-8de0-5467b0cd9723 |  | note | Resp - SE
label | 75ae5bea-294a-5cf9-9bbb-7ce6f6458267 |  | note | Remarks/record -
button | 7aa62367-e24e-5204-b89b-07dcd9631157 |  | button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No
date | c7e58678-9875-5a3d-9d7f-3603c6084688 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0049 Fill Earthworks Type C | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0049 Fill Earthworks Type C | 3af0804c-9944-481b-97b3-f90f1a23c33d
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Work Lot
label | 9ea0de6d-4329-5898-bef1-3cb608f5a825 |  | note | Ref docs - 173.02 204.03 (h) Table 204.142 Lot Diagram
label | 5e71ebe4-a0e1-507e-ad19-c8d5276603ef |  | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type C Construction works.
label | 2608235d-67ce-51f4-82be-9c352636ba8c |  | note | • Lot diagram to be provided clearly marking up extents of lot area.
label | 99890e8a-9e2f-5899-8e2a-7a77ac73668a |  | note | • Work Lot open on TeamBinder.
label | b95a3501-0e24-5ffa-9987-8dc0b59ddfb8 |  | note | • Lot size with no more than one day’s production
label | 97047556-7670-5eb9-9871-e5ef0c4dff30 |  | note | Freq - Prior to start of works
label | 890ed55e-dd6b-570e-b472-a7675f2ce41e |  | note | Key - R
label | 23016b80-c867-5a91-9ef7-1e5f7cc8bc3b |  | note | Resp - SE
date | d39ab405-c7e9-51e5-aea9-72b9d1701615 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | e76c933a-14e7-5cad-89fa-2e8c42aab422 |  | button | Lot map | Yes,No,N/A
date | 161f33d0-d921-5f4c-8364-e2004960580b |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | cbe8de43-c9fc-57f3-a518-7fb17cb7b5d1 |  | button | Environmental permit | Yes,No,N/A
date | 069dd909-e654-5889-a4bc-147802ef693c |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Set Out
checkpoint-status |  |  | checkpoint | 2.1 - Set Out Survey Completed
label | 599dfdff-bb73-5d2b-be42-a6bd057e3c9e |  | note | Ref docs - VR Clause 204.03 (a) IFC Drawings
label | b09c2e59-5a1f-513e-b3be-ad10ad9795e8 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
label | 0f5e11f3-0a7c-58f3-95b1-b916251c9eec |  | note | Freq - Each Lot
label | 7c7c87fa-edaa-542f-880b-3ca1e926fdb5 |  | note | Key - R
label | e8946709-143d-5bd4-9a89-559eadcde98e |  | note | Resp - SE
date | 691b5323-4497-5638-8756-c6fe889fb152 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Placement of Type C Material
checkpoint-status |  |  | checkpoint | 3.1 - Underlying Layer Conformance
label | 370562c2-4067-578a-bcd1-f0ae2f5801f5 |  | note | Ref docs - VR Clause 204.10(b) Construction Document
label | 758b07ba-001d-5125-99c5-8183d9dc458b |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
button | 9859684b-8e5c-5730-aa71-127675da9b3c |  | button | Approval to proceed granted? | Yes,No
label | d7e777ce-a2d5-540c-8c08-99532aa17511 |  | note | Freq - Each Lot
label | 199714c2-6e04-592b-87be-1333aa7e6957 |  | note | Key - H W
label | 39a17aa7-db57-5c6e-aed6-5011a9203feb |  | note | Resp - SE
label | 09346a5c-a712-56c6-89ff-9c7dcfa56d8e |  | note | SI Key - H
date | fe2f799e-60e2-5d16-9262-0586bbbbed5b |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Placing of Fill
label | 4e9e6798-528d-5ac5-8aac-5035662b4a8d |  | note | Ref docs - VR Clause 204.10(d)
label | af04d73a-c485-5a40-a3e3-f486868d3a48 |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 300 mm.
label | 5cd428f3-42ae-55b1-803a-ea72afbdeaf8 |  | note | • Where Type C material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 300 mm thick layer, the loose thickness of each layer may equal the maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
label | 31326611-5d09-5b27-ad0b-a297c7a76ac9 |  | note | • Rocks with a maximum particle dimension of less than 800 mm may be placed in Type C material zones as specified, with sufficient spacing between larger rocks to enable full compaction of the Type C material.
label | a88bf83c-0310-50e4-82b6-f17cd7d88388 |  | note | • The material shall be placed and compacted such that voids are completely filled with fine material.
label | 4f0f774e-e762-5ad1-9948-1c20747e52c0 |  | note | • Material shall be compacted at minimum moisture ratio of 80%
label | 6cbdfc03-7a42-52b9-bc95-1812e4ccee84 |  | note | Freq - Once Each Lot
label | db30b875-bce9-5e9b-ba7b-89e6808990da |  | note | Key - W
label | c9fcb384-2738-562c-8e14-268cfc10ec25 |  | note | Resp - SE
label | d33065bc-aa54-5e92-b592-9c529d595b53 |  | note | Remarks/record -
button | 775b0939-a4d1-58ab-9c29-f6ea8b5b614b |  | button | • Verification Records: | Yes,No
button | 4fd115d7-7692-5dd3-8661-7ac7df7900bf |  | button | • Material Compliance Certificates & Material Approval Register | Yes,No
button | 07232ce7-20c3-5749-a8d1-a813f4df4169 |  | button | • VicRoads registration of recycled material blend (if applicable) | Yes,No
date | c6b64e7a-af36-5b6f-a82f-e5a836c40510 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Keyed Fill Layers
label | 88bb3b40-fcf3-5d9a-a3bd-935348e21d39 |  | note | Ref docs - VR Clause 204.10(c) 204.10(d) Construction Document
label | 72f6b21f-4ae9-5766-8761-2e6a0552959e |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
label | a7509ddf-f963-59d0-bcdf-f1d962db6a09 |  | note | • Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill.
label | f152b137-533d-546a-b215-7086d192969f |  | note | • The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
label | f91298c2-8b3c-52b0-9c4b-80388a4f10a6 |  | note | Freq - Once Each Lot
label | b7244457-a102-54c2-9a13-231df961e46d |  | note | Key - W
label | 03d265ae-5919-5ffb-a6bf-27ed08b97208 |  | note | Resp - SE
date | 211d0220-f9ac-5ec1-b16b-313d6e83aa6f |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Geotechnical Analysis
checkpoint-status |  |  | checkpoint | 4.1 - Compaction Testing / Moisture Testing
label | e215b2b0-60c4-565e-8156-074fb18b33e3 |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) Table PS3020.072
label | 74495c2c-25c0-5627-8bf3-77ec81944ee7 |  | note | Acceptance criteria - All areas of the job will be considered as scale A.
label | ec0fccae-401d-5881-8952-467395fb3527 |  | note | ○ Scale A Testing: HWKR Rd, Princes Freeway, All Freeway Interchange Ramps, All other arterial roads.
label | 03df5a87-37ae-5d8b-9c31-7daa48844e1e |  | note | ○ Scale B Testing: All other local roads, SUP.
label | 8c1c3a68-91ff-5600-b691-0d933394bb79 |  | note | ○ Type C Material should meet the following compaction:
label | ed432d75-a0ef-5746-89cc-5122e4cac911 |  | note | • 95% for Scale A
label | 7af71f92-5c09-5043-bb3d-972c661610ee |  | note | • 93% for Scale B
label | 5981b486-c823-5c20-85b8-12d7e872616c |  | note | • 92% for Scale C
label | 44722f09-42b1-5456-a444-8427abfb6f47 |  | note | ○ Type C material is to be tested as per table 201.141 and table 201.142. And should meet the moisture content requirements as per VR204.
label | ae24813c-afed-52b3-aec5-ee61fa3fa532 |  | note | ○ >70% for any material within 150mm of subgrade.
label | d992b7ea-404e-59e3-bebf-ae9850107d43 |  | note | ○ >80% for all material below cut floor level.
button | a0a7497a-7485-5066-8e9d-50818ccb1dcd |  | button | Have the results been achieved? | Yes,No
label | 53d35691-a1d9-5f4f-abca-56068c70050b |  | note | Freq - Each Lot
label | 9cf3d127-9c90-5da4-8c3a-a1cce9c98b11 |  | note | Key - R
label | f10d9286-6bcd-5bfb-937a-845edb0c16fa |  | note | Resp - SE
label | 617b9cf2-df5c-5c18-9b60-97e9304bb552 |  | note | Remarks/record -
button | 8d22e582-601e-539e-819d-65c6a2298ef8 |  | button | • NATA Test Report: Compaction | Yes,No
date | 838fe65f-2163-59ef-afa9-585b8af5b32e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Material Requirements
label | ba4d7880-adb4-5ff9-9624-6578515c8e3b |  | note | Ref docs - VR Clause Table 204.041
label | 81a350fd-63be-5fc4-9c13-c8a2e34ba7f6 |  | note | Acceptance criteria - Type C material shall be capable of being spread in layers of not more than 500 mm and compacted as specified to achieve a stable condition.
button | f85dae6a-8cc3-5fd1-9530-6cec444b31d8 |  | button | Have the results been achieved? | Yes,No
label | 04dda004-2c4a-50cd-a1b1-d56b37b20550 |  | note | Freq - Each Lot
label | 82ff42af-1ba6-565d-a9fd-922fada03c00 |  | note | Key - R
label | 91cba9c0-88bb-532f-81ae-b90eeb357f1d |  | note | Resp - SE
date | 86895e5e-b873-52a1-92a9-05834d36b44f |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Reduced Frequency Post compaction testing of initial lots.
label | 2e8fe6f2-ca02-5827-afda-d4a8906adab4 |  | note | Ref docs - VR Clause 204.14 Table 204.142 PS3020.07 (f)
label | eb9680f6-9fa0-5562-bd79-28d2310036d2 |  | note | Acceptance criteria - Testing of compaction for each lot as per Table 204.142
label | 139adbdc-45b6-5395-93da-48835d6b0fb3 |  | note | • If Reduced frequency has been granted, the testing can be conducted at the following frequency:
label | 106c2e65-07ac-580b-a0c3-87d00d3d6ae7 |  | note | • Compaction will only be required for every 6th lot.
button | 59dfce6b-76ef-590d-9543-477ad6f279f1 |  | button | Has the criteria been achieved? | Yes,No
label | 961e43eb-5a14-5144-8970-5cbba5e279e0 |  | note | Freq - Each Lot
label | f29511d9-1eba-567e-9d95-ee90791184a1 |  | note | Key - R
label | 7f127af3-6d8a-55e6-b3b1-cae23168d49d |  | note | Resp - SE
label | 62d0c62e-7e2a-5587-bb04-47f25058a140 |  | note | SI Key - R
date | a002b335-771b-587a-aff7-4f79a7700a94 |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
label | 04885355-8de2-506a-83aa-f0965214fcaa |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | aaba57cd-c283-5d98-a8f0-0c116e5cc6eb |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings.
button | 96f5daa6-d08e-52d3-8422-4c9f46dbde67 |  | button | Does the final product conform to the above criterial? | Yes,No
label | 2bac1c75-7281-5237-84b8-1f7a1187f87b |  | note | Freq - Each Lot
label | 80078f6a-110d-58e8-9417-670e55dd1db6 |  | note | Key - R
label | 0329ad64-bdfe-5b4a-b28c-7e079a9991bf |  | note | Resp - SE
date | 3861828f-659c-5e3c-8738-3537b842e4f0 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 16ea9dae-b1c3-595d-829c-8fdc9660e620 |  | note | Ref docs - VR Clause 204.15
label | 46ef3385-d75e-568a-9e51-f0481fa74144 |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
label | 36631b3d-ed40-5508-9f54-3c33843f4949 |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | e4ec87d4-f0fd-5ed1-9060-3842a929f734 |  | button | Does the final product conform to the above criterial? | Yes,No
label | 45231f03-a2ca-5c20-b6fd-f633775f13d7 |  | note | Freq - Each Lot
label | 13f59b89-5767-5fdd-9d23-dcf1896a0ab5 |  | note | Key - R
label | 6c9bf42f-0e91-5a2a-ad4b-975025fca5b6 |  | note | Resp - SE
date | 3f1d190d-2597-51af-819c-5fa5f64d4048 |  | date | Inspection Date:
checkpoint-group |  |  | section | 6.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 6.1 - Test Reports
label | c577dc1a-546f-5b7f-9c32-6456e799eb1c |  | note | Ref docs - DoT Specs
label | c489df70-a3ba-5d05-b01d-3db2179f67a5 |  | note | Acceptance criteria - All Test reports received and reviewed
label | 6ae75d0a-9b33-5f2e-b656-333f613d39d6 |  | note | Freq - Each Lot
label | 4b045265-05e8-5a60-a370-b848c0cb837d |  | note | Key - R
label | db706eef-ad12-5897-a4dc-d7293f46384c |  | note | Resp - SE
label | 82de72b2-7d51-55e6-ac97-416cbd0b1600 |  | note | Remarks/record - NATA Endorsed Test Reports
date | 2eeaab85-e6aa-5df9-a598-20ca5b9124e9 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.2 - Product Non-Conformance
label | 5dfba075-1951-5a7b-8871-a9f0b59a2b9b |  | note | Ref docs - QMP
label | a4e7c1f1-49a9-5a97-bd19-9b7b42b48ba1 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | a6df7b39-b31a-50cd-a410-bf9568f014ee |  | note | Freq - Each Lot
label | 790fc848-a2ca-516d-bbf8-bed916593076 |  | note | Key - R
label | 47134d44-f6d8-541a-9213-080d64db2aff |  | note | Resp - SE
label | f195881f-a884-5d6d-8e41-1e6ba7ebe697 |  | note | Remarks/record - NCR reports
date | aa296e1a-5e1d-5598-9ef8-33339649f8b8 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0026 Bored Piling | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0026 Bored Piling | 4920c700-883f-4f62-91a4-b194949556c6
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Preliminary Approval
label | 1c4f985c-b6ab-5126-aa2b-af3892eb328b |  | note | Ref docs - VR606.03
label | b4ce3d8c-8380-5a39-b0e0-bdc99ffeee19 |  | note | Acceptance criteria - The Contractor shall submit for review by the Superintendent a quality procedure for the construction of the piles not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent.
label | b99507c0-d6ed-55b9-8d49-45ba26172ab7 |  | note | Freq - Prior to start of works
label | 7aa2f610-923a-5540-9678-6cc13ede8464 |  | note | Key - H
label | 1b8a0113-3a0c-548e-b065-8c3552f6c0b1 |  | note | Resp - SE
label | 09c92efb-18d6-5357-a552-afe3cd86435c |  | note | SI Key - H
label | 4acf20c6-3de6-5f0b-bdc9-7e510e47b161 |  | note | Remarks/record - ACRS certificate from Manufacturers, Suppliers and Processors of Steel Quality Procedure
label | c8d8a544-a2dd-543e-9877-ab2f9f1ae03a |  | note | ○ Quality Procedure and checklist
label | 108fb0bb-ae6a-52e1-9ada-317021e76775 |  | note | ○ VicRoads pre- qualification certificate of pile testing consultant
date | a5c4aeb3-e2b2-5f2d-817e-ca1569466fd3 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | caaad263-7507-5b66-bbcf-c60615773df4 |  | button | Lot map | Yes,No,N/A
date | d290b3d8-159a-5e36-ac75-de7aac5e34d4 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 6e73988f-cf5d-5256-b998-56b8cb26fac2 |  | button | Environmental permit | Yes,No,N/A
date | 61d80640-59c2-532a-b59d-1d0be7f52e99 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Installation of Temporary Casing
label | ba0c318d-6d79-545d-88a5-0772b565f52b |  | note | Ref docs - VR606.03
label | fe19af0e-5e7e-571c-be89-163d95e80019 |  | note | Acceptance criteria -
button | 9f284f1b-3412-51a2-a7ed-6fbc734155bb |  | button | Type and thickness of casing has been proof engineered by a Proof-Engineer who is prequalified in accordance with the VicRoads scheme for prequalification. | Yes,N/A
label | 7bc74e10-9945-5480-8989-7dcada18d4fc |  | note | Freq - Prior to start of works
label | fd81e653-745a-5740-8f7b-5b33ae5c001f |  | note | Key - I
label | efdcc689-7a71-516a-9c6b-9b0b6730d5c3 |  | note | Resp - SE
label | 483bc0f4-809d-5956-bfaa-50eec972e3ce |  | note | Remarks/record - Proof engineering certificate (or written advice)
date | ba4b73ff-ada9-5c7f-ae72-d7dcab8fc574 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.3 - Concrete Mix Design
label | c2186916-c075-596a-ae1c-6f456d33319d |  | note | Ref docs - VR610.07, VR610.13, VR610.18
label | c52354ee-1b97-5567-ae6c-5e6ad5adf2aa |  | note | Acceptance criteria - Concrete mix design is a registered mix and approved by the Superintendent.
label | b7f16bc8-90e1-55e9-9b28-4e6852c1fdc9 |  | note | ○ Concrete placed under water is self-compacting concrete (SCC) & Concrete placed in the dry is either self-compacting concrete (SCC) or highly workable concrete in accordance with the requirements of clause 610.07, clause 610.13 and clause 610.18(c).
label | babe9d3e-e43d-5c56-9ca2-f00e50b7b198 |  | note | Freq - Prior to start of works
label | 396fc65e-5f91-57ae-84fd-468b1b8234bf |  | note | Key - H
label | f76b4e90-0c4a-5381-bba1-9d755e5ab147 |  | note | Resp - SE
label | 3df53faf-c5d1-58cf-9cc5-6b581e5d4a76 |  | note | SI Key - H
date | 0f9639a4-3962-5f46-b6a9-3be2f5547741 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Reinforcement cages
label | 45518c19-36fc-570c-a771-61b88a433ffe |  | note | Ref docs - IFC drawings
label | 8823e86a-4aed-589b-96b5-1427a19c3095 |  | note | Acceptance criteria - Reinforcement details to be as per IFC drawings and shop drawings.
label | a3ef24eb-d55f-5a7c-868b-5be041cd2850 |  | note | Freq - Prior to start of works
label | ac20f855-be85-5bc3-ac1c-54c6ec47c7e2 |  | note | Key - R
label | 7698c451-0ed4-5522-a510-eea94b606295 |  | note | Resp - SE
label | 03a19063-b8ac-52ef-80a8-a099744981f4 |  | note | Remarks/record - Steel Schedule
date | 2b6ec3ed-ca72-5a4b-9f28-f55388564508 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.5 - Site Toolbox Talks
label | b687eaa8-8338-53aa-ad6c-6daf75aeb72b |  | note | Ref docs - VR610.18
label | cf9d63dd-d8fa-5010-a32d-3733a6daa5de |  | note | Acceptance criteria - The Contractor has submitted documented evidence of conducting tool box meetings of all concrete construction personnel on all aspects of the WMS, the ITPs, quality control checklist(s) and all specification requirements prior to the placement of concrete
label | 93bf5d60-d0a6-5022-90f7-e6e01a1905d2 |  | note | Freq - Prior to start of works
label | 61b97a32-0e70-576e-af48-12d725e21ca8 |  | note | Key - H
label | eedb8f10-85e8-511f-abe1-5dc514fa14dc |  | note | Resp - SE
label | f7aa796a-b9f8-5944-91b2-3d627cde1510 |  | note | SI Key - R
date | 020a6e6a-5dbe-5f89-b04a-96064acbf990 |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Installation of Bored Cast-In-Place Piles
checkpoint-status |  |  | checkpoint | 2.1 - Survey set out and drilling setup
label | bc888702-a0b4-5f7b-a210-4f1ae44b8478 |  | note | Ref docs - IFC Drawings
label | a68799eb-2f8d-5d22-9e01-3ca64ce2218d |  | note | Acceptance criteria - Surveyor to set out centre of pile prior to excavation. Minimum of 2 survey offset marks to maintain the centre of the pile during excavation.
label | 2ffd4793-dd00-5b9c-b212-eb09c13a84bb |  | note | Freq - Prior to drilling, Each pile
label | 249663fc-c9bc-53b2-9d4f-32877893e6e7 |  | note | Key - I
label | 626e9125-3afd-57dd-a296-79d69ceb08b2 |  | note | Resp - SE
date | 86a52eb6-c038-514a-97d4-e3fd428eef91 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - Adjacent Piles – Check Adjacent Pile Strength
label | c7098946-72d7-5332-a9c3-e39a23c9611c |  | note | Ref docs - VR606.04
label | 4ae28157-1b75-5ef8-a1db-00af8bb69be7 |  | note | Acceptance criteria - No pile construction to commence within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
button | e7994974-3fd9-5aeb-b296-ad8c36f1abd4 |  | button | Installation of piles resulting in significant vibration was not carried out within 2.5m to 9m until concrete strength has reached 15MPa. | Yes,No,N/A
label | 3dff69dc-d98a-58b5-8a6e-7c731ed8d71f |  | note | Freq - Each Pile
label | 930811a0-563d-5763-9fb8-3cbf55443908 |  | note | Key - W
label | c6a069f6-52f0-51a5-8f35-0b9f4a27e01c |  | note | Resp - SE
date | f66f3fa0-a378-5c01-ab87-4816f743a01c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.3 - Pile Excavation
label | d8c3f9dc-2258-5810-a724-8d63f2218cb6 |  | note | Ref docs - VR606.03 VR606.05 IFC Drawings
label | 8a2d2794-adb9-5379-b8b1-a3eb4c54336b |  | note | Acceptance criteria - Boring to correct size, position and level as shown on the drawings. Auger diameter to be no larger than 25mm of the specified pile diameter.
label | 3b0b394b-530b-5040-a35b-c93abe755982 |  | note | ○ If the final level of bored pile is above natural ground level, the pile must be formed to the correct level by using temporary liner.
label | 92922eac-1de6-5e36-8b5b-dae14d99bc61 |  | note | Freq - Each pile
label | b9d12493-5b27-5e44-8683-4d4f28bb210f |  | note | Key - I
label | 60c60f1c-0cc2-5427-a044-7966650dae76 |  | note | Resp - SE
label | dfde81a9-30e2-5778-847a-6e64ed7a3681 |  | note | SI Key - H
date | 4ea6ad9c-d19c-56b3-8076-181f40f971a1 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Installation of Temporary Casing
label | 5279811f-026b-5b25-bf75-7285869b6897 |  | note | Ref docs - VR606.03 VR606.06
label | eb13f1e9-961f-5c60-a702-a2e00ced59f2 |  | note | Acceptance criteria - Temporary pile casings have used unless the Contractor can demonstrate to the satisfaction of the Superintendent that an alternative construction method without casings will meet the required tolerances, cover, and durability.
label | 0e428917-1837-501d-8172-c11a59e75117 |  | note | ○ Type and thickness of casing has been proof engineered by a Proof-Engineer who is prequalified in accordance with the VicRoads scheme for prequalification.
label | e5c76916-ec0d-5b9f-b983-73c9c266eecd |  | note | ○ Unless otherwise approved by the Superintendent, temporary casings have been used to prevent the collapse of piles during excavation.
button | 99b87bff-7446-5eaf-8473-8cf74759c295 |  | button | ○ Temporary casing toes have been driven into solid rock or suitable material as required to seal pile and prevent water and soil from entering from outside the casing. | Yes,N/A
label | c873e4ab-3f48-591f-b31d-b5e516098066 |  | note | Key - I
label | 79d85fc8-e616-5b77-a7a8-6b393df3e6a4 |  | note | Resp - SE
label | bfb05158-27ff-559b-82da-66e9cde9137c |  | note | SI Key - R
date | 7d2bd1ca-e594-54bf-b25f-0e855139c5f9 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.5 - Inspection of Pile Excavation
label | 0b04d162-d0af-55a5-9547-53f869fcfc9b |  | note | Ref docs - VR606.05
label | b3078971-dee5-52d1-948b-6302be0b959b |  | note | Acceptance criteria - Pile hole to be dewatered and cleaned as per the approved methodology prior to inspection by the Superintendent. The dewatered pile walls and base excavation should be inspected and confirmed satisfactory by the Superintendent.
label | c8dfa6d1-c3c2-5f50-a34b-72d9ba7c7d9a |  | note | ○ Any temporary casing installed was not removed, and reinforcement and concrete was not placed until such inspection above has taken place, and satisfaction of design assumptions by a geotechnical engineer has been received.
label | 4a8f4bbb-6ea5-5043-90fa-49be027ecdd2 |  | note | ○ Contractor to Ensure pile toe level has been measured and recorded. Inspection of hole to select either approved dry hole or approved underwater concrete mix.
label | 1a971b63-f32e-517b-82b3-e713f3ac1f5a |  | note | ○ Method of pile cleaning & inspection in the event the pile was unable to be dewatered has been reviewed by the Geotechnical Consultant and MRPV.
label | 26865d87-6ae9-50ff-a1ca-7c818a4ca561 |  | note | Freq - Each Pile
label | 2dcf58e3-abe0-563a-ac2f-568cdaaede85 |  | note | Key - H
label | a752e697-48fd-5162-8e88-4cfea291d2c8 |  | note | Resp - SE
label | 7657dc90-b9bb-5010-9031-1a4a0a7b6e63 |  | note | SI Key - H
date | 539c2a1b-7f91-5dac-b22a-eeaaf2e5200c |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pile Verticality
label | ec23c852-a408-5b73-8074-a89c3369c460 |  | note | Ref docs - VR606.08
label | f18daf62-f1d4-50b7-b13c-a71c9755213c |  | note | Acceptance criteria - Once excavation operations are complete, visually inspect the excavation and confirm verticality using a plumb bob, spirit level against mast, piling rig data or other suitable method.
label | d5061391-8f42-52e6-9eda-a68ad2edfd9b |  | note | Tolerances as follows:
label | 4b5aed8d-9510-5a51-920a-dd22560ace84 |  | note | – Variation from the vertical or the specified batter/rake is not more than 1 in 100
label | 7da85f31-46c9-59fc-8a77-db6c814d669b |  | note | – Where piling excavation has developed a curve or out of verticality, the offset from the theoretical straight pile line does not exceed 150 mm over a length of 15 metres or proportionally for greater or shorter lengths.
label | 22e1ce92-0b9d-5644-8d0c-615ab9bd9264 |  | note | Freq - Each pile
label | 5cf2a02f-76ad-54b0-b66d-06749359614c |  | note | Key - I
label | d933088f-a18d-54f1-9bf9-f71383450a65 |  | note | Resp - SE
date | 6e6c74a2-84f7-548d-844b-d1738bddcbd3 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.7 - Pile Excavation Cleaning
label | fd71a7ef-fe61-51b7-b330-fdda28d261bb |  | note | Ref docs - VR606.06, 610.18
label | 5a169b95-5e0a-5b9b-a10d-51a9b634035c |  | note | Acceptance criteria - Piles have been concreted within 24 hours of completion of Pile excavation.
label | 9eaa4072-034d-5f0b-8a06-bf5214a580f3 |  | note | ○ For delays greater than 24 hours, ream the walls and the base of the pile to remove not less than 25 mm thickness of material, or any other foundation material which has softened in that time.
label | 14d97b17-bbba-58c1-a704-3d9d2a673560 |  | note | ○ If water is present in the pile, water is to be cleaned out by means of NDD prior to pour.
label | 67a50c1c-a4b8-5583-9adf-d69bcf2702be |  | note | ○ All foreign materials have been removed from the pile bore.
label | fb125530-ba4d-588e-aa2d-6359a0f7ebbc |  | note | Freq - Each Pile
label | 471fd455-e949-59f6-98c4-bdd5bf0d2b61 |  | note | Key - H
label | 59c24598-b926-54d9-a69b-058774b0390d |  | note | Resp - SE
label | 939e4a45-72fb-529b-8e2b-31a6cdb7c53e |  | note | SI Key - H
date | 2f988419-3afa-5e8b-93da-1149f040cf83 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Spacers and Bar Feet
label | 45295de3-3c5e-5f66-88a5-0739c23d2ff4 |  | note | Ref docs - VR606.06
label | d20c454b-e243-5fcb-8ee8-4db686e2c3aa |  | note | Acceptance criteria - Spacers and supports for bored pile steel reinforcement to be placed at intervals of no more than 2 meters along the full length of the steel reinforcement cage.
button | b1ed10f8-c700-5b4d-bc27-fc2da4e4c0c6 |  | button | ○ Ensure that spacers are also placed across the diameter of the cage such that even cover is achieved across the diameter of the pile. 75mm spacers must be used to achieve deign cover. | Yes,No,N/A
label | 290f3227-6087-58aa-b66a-eac74054fdca |  | note | Freq - Each pile
label | ad54dad6-e7c9-5352-831c-a44505b27262 |  | note | Key - H
label | 32637826-ad11-59fd-bfad-9c573481b193 |  | note | Resp - SE
date | f15eb1eb-330f-5357-a33a-3778f25b916c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.9 - Installation of Reinforcement Cage
label | 113b89ca-19db-5bf1-a287-a1d3283e4e9e |  | note | Ref docs - VR606.06, 611.09, 611.10
label | d6e8ec1a-2e83-5ab4-a051-ca71af5abb2b |  | note | Acceptance criteria - Ensure cage is vertical and sufficient cover to Reinforcement as per design drawings.
label | ced8d7c2-8b2d-563c-ad91-106c7c8c5ae8 |  | note | ○ Ensure that the orientation of the cage is as per the design.
label | ac7188e8-35cd-537d-bc4d-a28f14d4b0a8 |  | note | ○ Steel reinforcement is not be fixed to temporary casing.
label | 79e7fbc6-e4fe-5c8a-aab2-fee64f473834 |  | note | ○ Ensure that starter bar alignment is compatible with the reinforcement and hold down bolt details for the pile cap to avoid clashes with the pile cap reinforcement.
label | 627a4a40-934b-5826-8267-5d9d76f15d38 |  | note | Freq - Each pile
label | 84b40321-b491-5411-821b-e96beda5cffb |  | note | Key - R
label | cf8e07a3-2bc4-56d7-af44-39d98c1223e0 |  | note | Resp - SE
date | 619d4792-dcab-5a2e-ab05-97bcdcbdc906 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.10 - On-Site Tack Welding (if required)
label | b11b0a7a-0c0f-5796-b896-b4201f160ac1 |  | note | Ref docs - VR611.13(a, VR611.14(b)
label | a2eebfce-ca66-5b1a-9ce8-2b7e454b0605 |  | note | Acceptance criteria - Tack welding of steel reinforcement will be permitted for Grade 250N and Grade 500N carbon steel reinforcement bars provided welding is not within 50 mm of the tangent point of a bend in the steel.
label | f3232156-94ce-5dba-893d-5236fbb05646 |  | note | ○ Welders have appropriate training in accordance to AS 1554.3.
button | ee7f2b68-baa5-51a9-b0b2-9912f18e0bfc |  | button | ○ Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding procedure has been qualified and reviewed by the Superintendent. | Yes,No,N/A
label | 73009ce2-92e9-59b3-aef2-c3732a280dfd |  | note | Freq - Each Pile
label | 31c237f4-75c1-5199-8911-d32f92f245c2 |  | note | Key - H
label | 065e95a8-9a75-513d-b919-d1768ebb7704 |  | note | Resp - SE
label | 9a12c28d-dbec-5ee1-841e-9da3e950cb8c |  | note | SI Key - H
date | 96513929-5e60-5a1b-8715-a5eb9cd4d21f |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Concrete Delivery
label | ed391d43-29ff-5a39-8af4-3c62dbcb0e5e |  | note | Ref docs - VR610.13, 610.16
label | 8d74290f-6485-51e6-8f84-968f69d36440 |  | note | Acceptance criteria - Concrete to achieve required uniformity and discharge time in accordance with 610.13.
label | 6edc749c-7908-5b0c-b100-3764fc0c12be |  | note | ○ (60 minutes unless mix design is approved by Proof Engineer and Superintendent to be extended)
label | b6923f8a-cd67-546e-a563-efc8020866d9 |  | note | ○ Time between discharge ending and restarting is to be less than 45mins for a continuous pour.
label | 0c5dbddc-31ed-5c89-bc16-e0f262e76915 |  | note | ○ Concrete docket has been verified to confirm mix, slump and moisture content of aggregates is as per design.
label | 2c22214b-e5ea-53af-b2f3-1fb3c2517ae2 |  | note | ○ Records of actual amounts of water added into the agitator drum at the slump stand is available for review by the Superintendent.
label | d1cb2299-bdd1-5af4-9e31-b6cc73bd0315 |  | note | Freq - Each pile
label | 08e1ae40-eb1f-5b16-bef6-810b848e454e |  | note | Key - R
label | bf8503a8-dcd0-57dc-b5f7-38e35f4cbdda |  | note | Resp - SE
label | 91bdf35c-37d1-540a-aebe-0ca424b2fc1e |  | note | SI Key - H
label | fe7bc973-db02-5a34-a357-adf99f9574a0 |  | note | Remarks/record - Concrete dockets Pour record
date | afa08696-2340-55d6-bc5f-066241350f56 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.12 - Concrete Placement
label | 33774a70-7d55-5cc7-b0cd-6ef400aa0a4e |  | note | Ref docs - VR606.06, 610.17, 610.18
label | 2df9e52f-d165-532a-810f-9c972dcf9e82 |  | note | Acceptance criteria - Piles have been concreted within 24 hours of completion of the pile excavation.
label | ec491bca-1942-50ef-87bc-c93dbd41be06 |  | note | ○ Concrete has been placed through a tremie tube and was not dropped from a height greater than 2m through air.
label | 0fe7539c-b80a-596b-bf02-80af9617ec8f |  | note | ○ Concrete was not mixed when the air temperature is out of the range of 5-35 degrees.
label | 7445f143-d83c-5ee4-b603-99897798c554 |  | note | ○ Discharge time to be 60 minutes unless an otherwise approved by the Superintendent.
label | 1f424a73-c5f8-54f3-be4d-f8a35a1e7c02 |  | note | ○ If water is required to be added, it can be done so if no more than 60 minutes has elapsed. Concrete samples including slump test to be taken after adding water.
label | 6b7ddd59-f5a9-586f-97eb-020153ef68ae |  | note | ○ Any repairs have been carried out using a method and materials as approved by superintendent.
label | 08a58eeb-1541-5710-96dc-891c82952796 |  | note | ○ Concrete to be placed in dry bores is either (I) Self Compacting Concrete (SCC) with no vibration or (ii) Highly workable concrete which is to be vibrated by using immersion type, high frequency vibrators.
label | 2445586e-ca74-57bf-975c-cc903c1781d7 |  | note | ○ Where a temporary casing is used, the free surface of the concrete are at least 1.5m above the bottom of the casing.
label | eba423d6-1e30-57d6-ac4a-69d3562f5981 |  | note | ○ Piles placed in the dry have been constructed to a minimum of 300 mm above pile cut-off level to allow breaking back of contaminated concrete at the top of the pile. Unless otherwise approved.
label | 06c0ca06-7f99-52a8-8f54-f81be1ffc9a1 |  | note | Freq - Each pile
label | bdb16cb9-29b7-587b-972a-78a70ee33c83 |  | note | Key - R
label | 2b279863-852e-5255-bbf2-c57b9a8d4066 |  | note | Resp - SE
date | 72928fda-aa56-5336-b228-6c6ab409aded |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.13 - Concrete Placement – Under Water
label | c3faf146-eb6f-5286-9c3b-e9bbb5c79687 |  | note | Ref docs - VR606.06
label | fff15f9f-8e72-5cfe-b2ec-4a5bffbed565 |  | note | Acceptance criteria - Concreting using tremie methods is not commenced until the pile hole is filled with such head of water as to equalise the external water pressure from the surrounding ground.
label | 6fbdee69-d5d4-57b6-9a6b-8a0eb357ec7e |  | note | ○ 2m head of concrete has been maintained above the tremie tube while placing underwater to avoid contamination and mixing.
button | 18e7bbef-7f3d-5cca-8c97-090c373ede71 |  | button | ○ The rate of withdrawal of the tremie pipe or pump discharge hose versus the volume of concrete placed has been recorded by the Contractor and the records has been submitted to the Superintendent for review. | Yes,N/A
label | 20fcf508-7e6b-54b4-a078-6c7d629ec76e |  | note | Key - W
label | 73ad22bb-d8d8-545d-9a03-8bc0a45849a8 |  | note | Resp - SE
label | dfeec85f-b8c3-534e-a12d-da3ebd5a15cd |  | note | SI Key - R
label | 54f32548-1ea5-57ce-88ce-2e28bd570212 |  | note | Remarks/record - Tremie withdrawal record
date | a1830260-0d71-52b6-976c-21bb55d4bf38 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.14 - Concrete Sampling
label | 89d1ff70-45de-5485-957e-35d22b14e1a4 |  | note | Ref docs - VR610.16, Table 610.131
label | 96d7cb81-1944-5bbf-8214-b93c9d234aaa |  | note | Acceptance criteria - Slump test in accordance with clause 610.16 (c).
label | d968f6d2-fd6f-51b3-99d4-9b1fb4ffbeb1 |  | note | The specified slump ranges are:
label | 9d4b5067-7d5e-50d9-b26b-2c2fbec125d4 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 44d8efb7-0b3e-58b8-914a-2e8bf12a895a |  | note | Specified Slump, mm ¦¦ Tolerance, mm
label | 831a86c1-732b-5d95-952d-c7992d522e21 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 7c9030af-76e1-55aa-8430-d362b208885d |  | note | <60 ¦¦ ±10
label | 3900986c-592f-514d-bd78-9529ef03895e |  | note | ≥60 ≤80 ¦¦ ±15
label | 4235a8cd-b2b0-597f-8260-05fe5ab57a14 |  | note | >80 ≤110 ¦¦ ±20
label | bfe83c9b-6ea2-54bc-bf56-5dfa70ec6c40 |  | note | >110 ≤150 ¦¦ ±30
label | 40007054-cdc4-5b3d-8909-c261c863bbff |  | note | >150 ¦¦ ±40
label | 71505750-5de4-551b-8192-e45b1f650bd9 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | b0a5d430-4023-56e3-aeca-c669f5cb0c3c |  | note | ○ The consistency of the concrete to be measured by a slump test after the water has been added.
label | a126c236-a206-5fbf-b3b5-113cf0ec8be8 |  | note | ○ Tests are to be conducted for volumes cast in one operation as per:
label | b44eb271-996f-5a68-a2ba-6cc6c8bd7f7d |  | note | 0 to 10m3 – 1 test
label | 8de0aed0-31b2-5c25-a967-0f87056f0da0 |  | note | 10 to 25m3 – 2 tests
label | 1643353e-46f3-5fac-be86-7dbf762429c6 |  | note | 25 to 50m3 – 3 tests
label | d61a627c-0e83-5711-9b18-c6bbf1f019af |  | note | 50 to 100m3 – 4 tests
label | e95e23c8-ed90-572b-8fe9-2f030acba222 |  | note | ○ One extra test sample has been taken for each additional 50m3.
label | 521503cf-2ff8-5d15-910a-4a073eeb35bf |  | note | ○ The compressive strength of the concrete has been tested with a minimum of 1 sample being tested at 7 days and 2 samples being tested at 28 days.
label | 31f0d67c-f938-54bd-b4c0-db617ee98cc8 |  | note | ○ If SCC is used, it meets the requirements as stated per VR 610.16 (c) and (n).
label | 6a35ae0e-4b33-5774-85bf-1621133dc597 |  | note | Freq - Each pile
label | dcc01d02-5b0e-5fa1-9d13-3df39de682c7 |  | note | Key - W
label | 25c4e145-fbd9-5a57-ba33-19106ad1bdb9 |  | note | Resp - SE
date | 4b928572-c3f5-5668-92e3-e26e5a928f12 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Pile Testing
checkpoint-status |  |  | checkpoint | 3.1 - Integrity testing
label | 9a8903f0-a1c6-5725-af45-fb5bfba757a8 |  | note | Ref docs - VR606.07(a) VR606.07(b) AS2159 PS3050.07 (a) (iii)
label | 8184fd0f-d315-5fd2-9d13-f44db29cc2a7 |  | note | Acceptance criteria - Integrity Testing has been carried out in accordance with integrity test methods specified in A2159. Pile testing consultant is independent of the piling contractor and pre-qualified. Details of the pile testing consultant has been submitted for review by the Superintendent at least 2 weeks prior to testing.
label | f697ed29-a8ad-52d5-94e7-b032f5e71a2a |  | note | ○ The measured cross-sectional area of each test pile is not to be less than 5% of the required area. Integrity testing was not carried out until the concrete has achieved a compressive strength of at least 25 MPa and not before 7 days after casting of the pile.
label | fff9fcc9-8798-5841-ba25-47680a0022d5 |  | note | ○ The frequency of testing to be as per specification and the submission of raw integrity testing data to be available to the Superintendent within 48 hours.
label | 07baebb8-e7be-506c-bc13-df5064927820 |  | note | ○ Testing has been carried out on the first 6 piles constructed, and subject to acceptable integrity test results being obtained, 1 in 3 remaining piles have been tested. If any pile fails to meet the acceptance criteria, all piles must be tested. Reduced frequency is to be approved from the Superintendent.
label | b8211bdc-d6b8-533c-a674-512ae35475f0 |  | note | ○ Raw data of pile integrity testing has been provided to the Superintendent within 48 hours of request of the Superintendent.
label | 50fb3201-44ea-5ca2-ad97-26c5b42e5198 |  | note | Freq - Each Pile
label | ef68ad58-3b1e-58b5-98ea-2d91f40789ac |  | note | Key - H
label | dede5fca-081d-5179-9cde-0dbf944396f9 |  | note | Resp - SE
label | 14c5f34b-7bbc-5cef-824b-0a479b825201 |  | note | SI Key - H
date | 19b51547-b29e-5eeb-871f-38291da43627 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Static Load Testing
label | b40feac3-f81d-56c0-bee3-4e2cc0e1e02e |  | note | Ref docs - VR606.07(b)
button | 23d0a83f-bbeb-53b0-ac42-a60888076742 |  | button | Acceptance criteria - Static Load Testing – compression, static and lateral load test in accordance with AS 2159 and as specified in drawings and once concrete has achieved 28-day compressive strength. | Yes,N/A
label | b53f5ea7-422e-5656-9b9d-508b48c31374 |  | note | Freq - Each Pile
label | e9b2ab65-704e-5053-9bfa-1c967b125b7b |  | note | Key - R
label | 1dc061bf-4e3b-5491-b57e-47a61649d9a1 |  | note | Resp - SE
date | 7b93ff9c-2d0f-5a26-9358-3afdd2bc4f0b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Details of the Dynamic Testing Pile Driving Analyser (PDA)
label | 2a45517b-4bd4-5cca-bcab-c0af748804e6 |  | note | Ref docs - VR606.07(c)
button | 689ff2fc-1245-5d8d-951c-27eb5fca59ef |  | button | Acceptance criteria - The details of the proposed pile driving rig, hammer size and drop heights have been provided to the Superintendent for review prior to undertaking the testing. | Yes,N/A
label | 401ed7ed-dd3c-56fa-9d5e-82bb26395e30 |  | note | Freq - Each Pile
label | 595be2d4-538c-5242-b62b-9df31e7f56d7 |  | note | Key - R
label | 1b38237e-5ed5-5c1e-8a93-a238203f3395 |  | note | Resp - SE
label | 7319b2f4-f6df-5854-bd5e-b8917eb2dddb |  | note | SI Key - R
date | b46977d1-e7fc-5e37-a792-c8e9ee8a19bb |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.4 - Dynamic Testing
label | ce7f9eed-46ab-515a-ac66-cc8c3e99d27e |  | note | Ref docs - VR606.07c) VR606.07 (d)
label | c411ac5e-0a88-57b4-827e-82ed734a1249 |  | note | Acceptance criteria - At least one (1) load test every 10 piles or, one load test per pile cap or bridge abutment which ever gives the greatest number of piles tested.
label | fca452cd-8559-595f-a3c1-4deda14f2543 |  | note | ○ Dynamic testing has also been carried out on piles of which the pile toe levels vary by more than 2 metres from the test pile.
button | 6ed15d1a-b5c0-5033-909f-996cf40aed15 |  | button | ○ The test procedure and test reports to conform with the requirements of AS 2159. | Yes,N/A
label | 75771e5b-2f83-5672-9e87-dbf69be373cd |  | note | Freq - 1 in every 10 piles, Piles with varying toe levels > 2 m
label | dd517411-0e1a-54f6-8adb-644e1ccfc90e |  | note | Key - R
label | 10f5a8e7-9de2-5414-9d79-d4d5fb94af18 |  | note | Resp - SE
date | b6cf346a-f5c5-5b4f-8d0e-eca2c5b370b3 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Reporting & Acceptance of Test Results
label | 8e9af600-a96b-5230-906e-f0168907073d |  | note | Ref docs - VR606.07 (d) & (e)
label | c8fbe907-afba-5421-955e-bc29b024e844 |  | note | Acceptance criteria - Two copies of the test report to be provided for the Superintendent.
label | 2a4e3f16-2ea9-5664-ac08-b22429c607c1 |  | note | ○ The test results to demonstrate acceptance criteria as shown on the Drawings with ultimate capacity equal to or greater than the pile test load.
label | 9e97fcb4-e267-5602-905f-0c1f6f81094c |  | note | ○ Where confirmation of pile capacity using dynamic pile testing is obtained by re strike, the report includes the results of the initial drive and all subsequent re-strike.
label | 27936b39-b9e6-546d-b2c2-fecbc17dcec7 |  | note | Freq - Each Pile
label | b1caed84-090b-591a-b704-0e4f75ec2d78 |  | note | Key - R
label | ca55b33f-40a6-5900-af0c-19a84b944012 |  | note | Resp - SE
label | 1a15711a-33e8-5d18-a2e3-0f16f87de304 |  | note | SI Key - R
label | 84952121-c49b-55f9-a058-ccb91c5515b7 |  | note | Remarks/record - Test Results/Reports
date | 5e7eba3f-b183-5003-9759-1e09f5c2c2c2 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Pile Completion
checkpoint-status |  |  | checkpoint | 4.1 - Tolerance for Pile heads
label | 0a07ce17-54c9-5475-8c4f-abcd619287ba |  | note | Ref docs - VR606.08
label | 3000e452-63a1-56ba-9b4e-7a60f8c992a4 |  | note | Acceptance criteria - Pile heads have been cut back to design level no sooner than 24 hours after concrete has been placed.
label | 5f693c6f-1e70-5d0b-bffb-f7b0a908721b |  | note | ○ Pile head finishes within 75 mm of the specified plan position.
label | bbc674fd-e627-5d79-b451-d94e329b7829 |  | note | ○ Pile head reduced level finishes within 25mm of design.
label | f47b9327-e63e-52c8-80cb-49544fa3c028 |  | note | Freq - Each pile
label | 7af846c2-5310-5c98-90a1-a0307f618b54 |  | note | Key - R
label | 5662bb04-65d8-5f63-8670-a5d70b7df1c5 |  | note | Resp - SE
label | f6ef6cfa-4d27-5cd7-a8f7-a8901ed5e9b2 |  | note | Remarks/record - Survey Report
date | 6e31fcf8-c197-58bb-9620-4bc41517fc01 |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 5.1 - Test Reports
label | 00b565be-1a46-5cda-8847-eafddd92d5e7 |  | note | Ref docs - VicRoads Specifications
label | 175fdcc2-5e65-578f-b66b-a5de0322a45b |  | note | Acceptance criteria - All Test reports received and reviewed.
button | f19e1137-93b1-5d2f-931e-556815e6c8fb |  | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
label | 278826cc-89bc-5d40-860c-b0a7e280e31e |  | note | Freq - Each lot
label | e411eb4d-ac9e-5ece-afd2-418cc49deb76 |  | note | Key - R
label | 605a6985-a82c-5045-b952-8f6c7bbda946 |  | note | Resp - SE
label | c6ba00f4-03c4-5470-acb9-a35e5f960d35 |  | note | Remarks/record - Pile Test Report, Compressive Strength Test Report
date | e5b84bb6-95ec-594b-a179-f80c93e9ead7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Product Non-Conformance
label | c05eb953-c862-5790-a1c1-42b0514ba4c6 |  | note | Ref docs - CQMP
label | 968815e4-4825-50f0-837e-d3c50f4b0822 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
button | 758b2cd5-a8ae-567f-8775-45df3728d994 |  | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
label | 712a7f6b-409e-5175-92f4-4f3becaf6453 |  | note | Freq - Each lot
label | ca44221b-f948-5cde-b810-326a916d8c18 |  | note | Key - R
label | 0811f4b4-303f-5abf-ae8b-ee1008605367 |  | note | Resp - SE
text | 59a25ebe-a0a7-5194-8d1e-df066171241f |  | textbox | Remarks/record - NCR No:
label | 33447675-a65d-5e50-aa5f-534b5ad29792 |  | note | ○ NCR reports
date | b8cc87fe-bbda-59c4-b39d-e973bea62173 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
label | d7e7eddd-cba7-5255-a1ee-1ba6bb63dfe8 |  | note | Ref docs - CQMP, Lot Records
label | 339b5d3f-f59a-5d56-9ebc-ab580b6b4be7 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
button | 4b21e5f1-34a6-5b73-b631-a9dbd253b78c |  | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
label | a6e76e2b-6265-5de4-a06b-6180b1b7e170 |  | note | Freq - Each lot
label | b99bf73b-57f5-5ab7-bce3-24775bccdc8e |  | note | Key - R
label | a68d4acf-3406-5aef-a5d7-f4fdb43332a6 |  | note | Resp - SE
label | e07eb8e7-7635-5cf8-8ddc-2c93ceb7cbad |  | note | Remarks/record - Reports and other compliance records attached.
date | 65e6bc12-06d0-500e-95ab-11536307c279 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0021 Conduit and Pit Installation REV1 | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0021 Conduit and Pit Installation REV1 | 5c965879-5d7d-41ee-992c-fdf141116985
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Boring under Carriageways
label | 2f713103-617a-5c3d-923a-76d8a5b2c458 |  | note | Ref docs - VR Clause 733.05
label | 5df04e79-e95d-542f-8120-eaf9662a1649 |  | note | Acceptance criteria - Boring by water jet not permitted.
label | 968fd953-5c07-5212-8f51-8c53f5312bc5 |  | note | • Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work.
button | 823fffd2-d9ca-5314-8286-2b3c64901d98 |  | button | Approval to proceed? | Yes,No,N/A
label | a2b1f52f-d66a-5863-8bf8-bfeab56d79bb |  | note | Freq - Prior to start of works
label | 24c6c6e4-c0b6-50d1-9f36-5244ef021436 |  | note | Key - H
label | 07acf559-c7fd-5147-bdb0-09532e014864 |  | note | Resp - SE/SS
label | 49022b87-db93-5abc-a082-7db45fec5ca8 |  | note | SI Key - H
date | 61b05b19-3ac9-531e-bffc-e2ddd9684d91 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 735f5e70-348d-511f-b99a-24bc661a8479 |  | button | Lot map | Yes,No,N/A
date | 2c978f00-3ea4-5db2-8060-7de1be4a6858 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 15c1828e-c21a-50a5-8209-76b6c7e4154e |  | button | Environmental permit | Yes,No,N/A
date | 29c0a3ab-7864-594a-b359-9e891d5fe45e |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Conduit Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance – Conduits and bends
label | 6f482625-6055-5a3f-85bd-02694d3fe93f |  | note | Ref docs - VR Clause 733.02 Table 733.041
label | 82befed0-7a06-5d20-9dce-7be674937cc7 |  | note | Acceptance criteria - Conduits are correct type, class & diameter and comply with AS1477, AS2053, AS4130 (as relevant), unless noted otherwise.
label | 2195aa03-fda0-5a4f-82dc-865f1e49f57f |  | note | • Electrical – Heavy Duty Grade, Rigid orange UPVC conduit to AS/NZS 2053.2.
label | 434942a8-0ab1-56f0-b815-6be9e47308bd |  | note | • Communications – Heavy Duty Grade, Rigid White UPVC communication conduit to AS/NZS 2053.2.
button | 4bf95e97-b172-5c45-ba17-46abc9680b7e |  | button | Have all the above materials been approved? | Yes,No
label | ca44bde3-19fa-5fa6-93f2-8723d3c4e57f |  | note | Freq - Each Lot & Each possession
label | 768b5955-c3a6-5e67-b80a-a99af822e350 |  | note | Key - R
label | 3819045d-b995-5514-8891-325d836a9627 |  | note | Resp - SE/SS
label | 1bba3948-2a89-50cf-9dd4-51b9f6fcfab8 |  | note | Remarks/record -
button | 4bb8c6c7-a41d-5a2a-a6cc-cd63491482a8 |  | button | • Supplier Compliance Certificate | Yes,No
date | 5f17cb15-5b65-527d-8d72-01eb2fe50ebc |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Conduit Cover
checkpoint-status |  |  | checkpoint | 3.1 - Excavation and Cover Requirements
label | 2b3f3f1b-5688-5904-b4fb-e35ffc194d77 |  | note | Ref docs - VR Clause 733.05 Table 733.051
label | 401cf1a4-6a5d-58d5-9944-2b977048a598 |  | note | Acceptance criteria - Cover requirements for both electrical and communications conduits shall be:
label | 57fb2218-48d5-50f8-baee-855cb4bbb832 |  | note | • Pavement surface to top of conduit minimum 1200 mm.
label | 782c7cdd-3bea-5a85-8d79-f4874116c1a6 |  | note | • Invert of open drain to top of conduit minimum 750 mm.
label | 858789b2-6966-512f-bbbd-2f05fbdf066f |  | note | • Unpaved areas to top of conduit minimum 600 mm.
label | ea9eac26-a75f-5931-ad30-39d78d030569 |  | note | ○ Or else as specified on design drawings.
button | 4d627fe2-353b-561d-92d9-e05a21b100d1 |  | button | Has all the above been completed and approved? | Yes,No
label | 985aec8d-fa47-5ca7-ace0-c93e62539bc9 |  | note | Freq - Each Lot & Each possession
label | f9b1dfe5-33e6-5878-90ab-de3918c91cdd |  | note | Key - S
label | 1566fb7d-8743-52ec-8a26-d7374ecd9d83 |  | note | Resp - SE/SS
date | 67750df8-cf3e-58b9-9790-16c9ba3fe4da |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Installation of Conduits
checkpoint-status |  |  | checkpoint | 4.1 - General
label | 224f2f7a-982b-58ba-8bd9-399530206724 |  | note | Ref docs - VR Clause 733.06 Table 733.061 AS/NZS 3000 AS/ACIF S009
label | 899e6132-aa2e-5d86-ad57-6d29fa4bf041 |  | note | Acceptance criteria - All conduits shall be installed as shown on the VicRoads Standard Drawings and Contract specific drawings, or as otherwise specified.
label | 10d1fd33-3d1e-530a-b575-6a3f1a2c6c64 |  | note | All conduits for electrical and communications cabling shall be installed to conform to the relevant requirements of controlling legislation, regulations, industry codes and standards, including:
label | 39a65921-46fc-5e64-8709-74e62bf8ac2b |  | note | • AS/NZS 3000 Electrical installations (Australian/New Zealand Wiring Rules)
label | 39768788-d8dc-5650-ae33-0086e59ec620 |  | note | • AS/ACIF S009 Installation requirements for customer cabling (Wiring Rules), and any other relevant requirements of the Australian Communications and Media Authority (ACMA) for connections to telecommunication carriers’ network.
label | 26f7637c-60b1-513d-94b5-610214e4aad3 |  | note | ○ Installation of conduits shall be carried out in accordance with the following:
label | 86c111c9-d771-5bd3-8faa-1d691ade537d |  | note | • HD UPVC Plain to be Thrust bore or Open Trench.
label | 7437cead-c0d9-5d3a-a0ad-26824570bf92 |  | note | • HDPE continuous (must have ID not less than that of 100 mm HD UPVC for electrical and 90 mm HD UPVC for communications) to be Directional Bore.
label | 1b4f90fd-7da9-52e2-b629-ccec66191ed6 |  | note | Freq - Each Lot
label | f2245e67-04bb-540f-b4b0-f96263914c39 |  | note | Key - I
label | fbe0ffeb-a64a-50a4-8992-c098c7087148 |  | note | Resp - SE/SS
date | 196db6e5-6ecb-55b3-a2d9-eb8b753982e7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Bedding Material/Placement
label | c1ac7761-6b01-5775-8def-36d010f5af25 |  | note | Ref docs - VR Clause 733.08
label | d8c55378-7fa5-597c-ae88-05367fe8ff89 |  | note | Acceptance criteria - Bedding material does comply with the requirements of Table 733.081.
label | 0d7decc0-4971-571f-8fd5-69ec9c7cdeb3 |  | note | • Minimum 80 mm bedding below conduits on earth foundation.
label | 3941b85e-975b-52f7-9961-11e15a79d1d0 |  | note | • Minimum 200 mm bedding below conduits on rock foundation.
label | ce1114d5-ad70-5f92-a514-295c4c4511c3 |  | note | • Bedding placed to full width of trench, and between conduits as shown on trench details on latest revision IFC drawings.
label | 7ed90e44-b4df-5d34-906e-df537400f4c2 |  | note | • Shaped sufficiently to maintain the conduit in line as the sections are placed.
button | d6d441e5-48f6-5b19-bcd2-db3c398d4a7a |  | button | Has all the above been completed? | Yes,No
label | 4f362462-c847-5998-909c-0c49929eca72 |  | note | Freq - Each Lot
label | 830dedc3-a290-54e1-9dd2-8bc83713cb4e |  | note | Key - I
label | 957ed6b2-7270-53e5-9148-8f91abf0f349 |  | note | Resp - SE/SS
label | 7317d926-629d-542b-840f-0bea1aad3b50 |  | note | Remarks/record -
button | 859ec677-aea2-5121-b3d3-cbd93bbdbbe3 |  | button | • Material Compliance for Bedding/NATA Test Report | Yes,No
date | 03a67da6-924d-5c85-96fe-a314e54716fa |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Bedding Material/Placement
label | f1a34b93-19bb-5928-8967-102d621bca7f |  | note | Ref docs - VR Clause 733.08
label | 703e10b8-20c4-5114-8446-d74194366010 |  | note | Acceptance criteria - Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by Superintendent.
button | b96e271a-aca6-5ac4-b920-f6c1bf92a749 |  | button | Approval to proceed? | Yes,No
label | d1259096-4fda-5cea-9b41-bc6eb1274294 |  | note | Freq - Each Lot
label | a03018af-fd3f-5c1c-a188-1cc14cc36815 |  | note | Key - H I
label | 8363fd9f-70fc-51e4-87e8-fb4264db6ffa |  | note | Resp - SE/SS
label | 105f9681-b754-5991-9434-ab791088b820 |  | note | SI Key - H
date | f0df05f1-931c-508b-896e-2899809af279 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Bedding Material/Placement
label | 07ce8da0-e9ed-541f-a13d-8492246e2952 |  | note | Ref docs - VR Clause 733.08
label | 937b6d75-4b34-5bcd-b53e-50717a357535 |  | note | Acceptance criteria - When conduit sections are in position, additional layers of bedding material shall be placed and compacted to a height 150 mm above the bedding previously placed.
label | 873ef3cf-ed73-5db6-9793-d2133def20e9 |  | note | • Bedding material must not be the same material excavated for the trench, it shall be clearly identifiable as introduced material.
button | 72996614-1a6b-5ca5-acce-a56654cf11ea |  | button | Has all the above been completed? | Yes,No
label | 93e078b0-bf1e-59ea-b6d0-b224b5e12fd7 |  | note | Freq - Each Lot
label | 06672ae7-7068-5bb5-8395-55a15b5a5d36 |  | note | Key - I
label | c7d28aa2-a848-5621-82ee-8e4f874061f7 |  | note | Resp - SE/SS
date | 4b9cbb57-cfd2-5782-af08-ed627f4d03ee |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.5 - Conduits for Traffic Signals/ITS/Public Lighting
label | 388b87c4-6d74-56db-84e1-29a39deab04b |  | note | Ref docs - VR Clause 733.06
label | 73d62461-e454-5c10-b666-a1cd6b3d027b |  | note | Acceptance criteria - a) All conduits shall terminate in a pit in accordance with VicRoads Standard Drawing TC 1207, TC-1230 and TC-2200 – TC223.
label | 5a41ff75-4722-545a-9b4f-310b0dbe5c55 |  | note | b) Only one size conduit shall be used for a complete run between pits; unequal size conduits shall not be joined in the ground.
label | 8e11b10e-4c14-5525-bfdf-2ae6dfe71a5e |  | note | c) All conduits shall be temporarily sealed prior to cabling to avoid blockage.
label | e550a327-0aab-547f-810f-e2a9a0fb9476 |  | note | d) Changes in conduit direction or depth shall be made by natural set or in the case of bottom entry, by means of a swept bend; elbows or tees shall not be used.
label | bc87a144-c825-5154-8dfc-0fb5037d5dae |  | note | e) All conduit joints shall be correctly prepared and sealed with approved solvent cement.
label | aa1f51e9-4251-52c2-960c-61f815135099 |  | note | f) Conduits for detector cables shall be installed as shown in VicRoads Standard Drawings TC 1207 and TC 1320; and
label | f4874ab0-1eee-5e93-8482-623b7f1691a5 |  | note | • A 50 mm electrical (orange) conduit shall be used to convey the detector feeder cable from the detector pit to the cable pit, as shown in VicRoads Standard Drawing TC 1207.
button | 01a5b2ae-6a44-5415-b4b6-ff6dd618915e |  | button | Has all the above been completed correctly and to a high standard? | Yes,No
label | 1235b95a-73f1-5654-89f4-e8793eec6a24 |  | note | Freq - Each Lot
label | f5584f9a-94c1-519d-a017-68eeb10c692a |  | note | Key - S I
label | 8c2ae869-ad5c-5cd1-a863-2813d83c02e1 |  | note | Resp - SE/SS
label | 8d437bf9-fedc-5235-9cf9-1c94e8dc13eb |  | note | Remarks/record -
button | ab181abc-38d7-5b92-a8b3-b97937dd96d3 |  | button | • Installation Records from Subcontractor | Yes,No
date | 5965c3f8-8790-55aa-8813-52c5509708bd |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.6 - Draw Cords
label | 5d56464f-d09a-5559-9e36-69493c271704 |  | note | Ref docs - VR Clause 733.07
label | 46fd5b54-ccc7-5b32-8fa5-40c25aa2bd65 |  | note | Acceptance criteria - Draw Cords to be 3 mm diameter and with a minimum breaking strain of 1.6 kN.
label | 9c8d12de-4f10-5abd-b89b-5a354e7f267d |  | note | ○ Where the conduit terminates in a pit
label | 40a6f279-c26d-55f2-a1ed-f5de365d19d7 |  | note | • Have no less than 500 mm of the draw cord tied to a marker peg 25 mm x 25 mm, no less than 300 mm long, left coiled in the pit for future use.
label | 930bb6d8-7d31-51a3-8cf6-f2f005bfbcf7 |  | note | ○ Where conduits do not terminate into a pit.
label | 64c70085-b87e-55dd-9d48-9d798be3afd2 |  | note | • Be tied to a marker peg 100 mm x 100 mm, not less than 400 mm long, driven firmly into the ground with the top 50 mm projecting above finished surface and painted yellow.
button | 798b14ae-b056-50b6-8896-501c534e6c08 |  | button | Has all the above been completed correctly and to VicRoads standard? | Yes,No,N/A
label | d303d998-09b6-5960-8828-5142e1aa78d8 |  | note | Freq - Each Lot
label | 23e9751a-3aa7-5cae-86e7-09fbb5a1529d |  | note | Key - I
label | 1d728f65-1bd3-5ecf-a0eb-390e472d08ec |  | note | Resp - SE/SS
label | 00fa2c9f-b196-54a2-830a-1dd0d937f1f0 |  | note | Remarks/record -
button | ea61a4f7-5e60-51f8-8498-780d073ed458 |  | button | • Installation Records from Subcontractor | Yes,No
button | e514a86e-41f9-509d-ab39-83ab76c919f1 |  | button | • Material Conformance Certificate | Yes,No
date | 28ed96d4-c6f1-59cc-ab6d-dedae42b1585 |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Backfill
checkpoint-status |  |  | checkpoint | 5.1 - Bore access excavation
label | e7a840ef-d2fd-59b4-8e70-168a4b0fd721 |  | note | Ref docs - VR Clause 733.05
label | 685a3020-6e57-5f0a-9073-f58d1b1381c1 |  | note | Acceptance criteria - Before backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative.
button | cfd40866-ad28-5b4e-b4a0-6d3cb957c7e8 |  | button | Has all the above been completed? | Yes,No
label | 8272c4c4-1cb1-56bf-a37d-8d4182000de4 |  | note | Freq - Each Lot
label | 3edb9183-2ed4-530a-b6bf-7a67150d019e |  | note | Key - H
label | f4ceb1fe-fc78-5d0b-8cbe-1d0a53446243 |  | note | Resp - SE/SS
label | 51554504-036f-595a-80ae-079f456f5068 |  | note | SI Key - H
date | 2947ce2d-776e-5e9f-a7f6-493ea4766e46 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material Properties
label | 4d248082-5992-5684-b184-e42777dcc0ad |  | note | Ref docs - VR Clause Table 733.081
label | ce7c2973-1e9e-570b-9e52-cfbc02ca1420 |  | note | Acceptance criteria - Backfill material properties to be as per Table 733.081.
label | 361b1edc-788a-5b0e-a3b7-a92edfb21e8d |  | note | Freq - Each Lot
label | c80e1313-b6f2-5e3a-a85d-18c2a7bdd4c5 |  | note | Key - R
label | 564e566b-227f-5aa6-80fe-27a1d22d3814 |  | note | Resp - SE/SS
label | 4101b591-eafa-544c-9bb4-65a64be25fc9 |  | note | Remarks/record -
button | fd3f3dc2-ee3b-5adc-8190-7bf349b6d5a9 |  | button | • NATA Test Report (if applicable) | Yes,No
date | 4f84725b-42b5-536a-8153-c0c7e7fd7872 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Filling
label | 66f317ea-85b2-5cbf-81be-107d2e540c27 |  | note | Ref docs - VR Clause 733.08
label | c24cc143-5f84-5697-ace4-41a03cd633f1 |  | note | Acceptance criteria - Unless otherwise specified or shown on the drawings, selected and common backfill shall be placed and compacted as follows under, around, and above the conduit after the sections are bedded:
label | d23ee5c4-902e-5999-b4cc-2ff3499900e7 |  | note | • Place and compact selected backfill 400 mm above bedding (in non-trafficable areas) remaining fill to be common backfill.
label | c2cdd5d7-6fb6-51cc-93c4-264f8ff434ac |  | note | • Place and compact selected backfill to subgrade level (in area’s to be paved)
label | 9afa6fd6-22c8-58ba-bba4-6347ad46752c |  | note | Freq - Each Lot
label | 85b01c3e-5140-5adf-b8a5-f6beb3d51c6d |  | note | Key - R
label | bce7daac-dbe9-51fa-bae7-824c504d3f02 |  | note | Resp - SE/SS
date | a4bc9b21-d1ba-5e45-8a6a-dfb665859bec |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.4 - Compaction - Areas not to be paved and below pavement
label | 4a17bec3-51fa-5391-8bf2-a9cbf3a91b82 |  | note | Ref docs - VR Clause 733.08
label | 3d20e959-f46f-5a3d-88fb-b1655eedad24 |  | note | Acceptance criteria - All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
label | 36dd9f44-bf4d-549f-808c-485fe3b0fce2 |  | note | • Compacted to refusal using handheld mechanical equipment.
button | b0e8e5ea-982a-57f0-80ec-ab3c74ba4fd4 |  | button | Has all the above been completed? | Yes,No
label | c6c67d7e-471c-5a8b-a884-2b766286855f |  | note | Freq - Each Lot
label | 8c6c121e-6a69-575b-b4ae-ec5ad4d62b7c |  | note | Key - R
label | e4b41784-aac1-51f6-adcc-9ecb5fc1d6b4 |  | note | Resp - SE/SS
date | 2d7c7cab-761c-54c1-9dea-ab28355cc0f1 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.5 - Compaction – Area’s pavement layer
label | 66070f80-1df2-562e-aaa3-bb2f1d881c71 |  | note | Ref docs - VR Clause 733.08
label | 78ec6b14-bc49-5d69-a773-568a52c6f827 |  | note | Acceptance criteria - Where specified, pavement material shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three.
label | 74b05730-ab29-5dd6-a87a-67199c0d18e2 |  | note | • All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
label | 351b23e0-be36-502d-976d-fceb7acf273e |  | note | • All pavement layers shall be placed and compacted in layers to a density ratio of not less than 98%. The calculation of density ratio shall be based on Modified compactive effort.
label | 5d10baef-d2da-5f6b-9b53-4e8048fc86f6 |  | note | • Compacted to refusal using handheld mechanical equipment.
label | 648591fd-fe0f-5345-98f0-bb42f639845e |  | note | Freq - Each Lot
label | 879f0825-2347-51d7-af7d-9c4a7ac788ff |  | note | Key - R
label | 9d043d10-a87b-5999-a3da-5b6eb6dde889 |  | note | Resp - SE/SS
label | ebd61d4a-25ee-5749-8e74-8e6ddab7b4c8 |  | note | Remarks/record -
button | ad7e2341-e96a-5471-964c-0be4f94bf4ef |  | button | • NATA Test Report (if applicable) | Yes,No
date | afa74d2b-c245-5002-8eb4-65eb5b867571 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.6 - Warning Tape
label | a7038d60-b0dc-59fd-b974-c31ea879910c |  | note | Ref docs - AS/NZS2648.1
label | ef84ea1f-ee9c-5faa-883b-23a637c99d76 |  | note | Acceptance criteria - Where marker tapes overlap electrical tape to overlay communications tape:
label | b5bef862-2b9c-5a2a-9850-3ac38dbb00c0 |  | note | • Marker tape 100 mm wide complying with AS/NZS2648.1 coloured orange with black lettering “DANGER BURIED ELECTRIC CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits in all trenches where electrical conduits are provided.
label | e94e3b9e-3ca0-5ed4-a4b7-6effc0b505b6 |  | note | • Marker tape 100 mm wide with two stainless steel tracer wires coloured white with black lettering “DANGER BURIED COMMUNICATION CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits. In all trenches where communication conduits are provided at least two meters of each tracer wire shall be anchored to and neatly coiled in each communication pit.
label | 3e2b0365-b9a7-554a-8c8d-1470844d0061 |  | note | • Where both electrical and communication conduits are provided in a trench two marker tapes shall be provided one for electrical and the other for communication conduits.
button | e07e1649-8060-590a-a66d-1fb530477299 |  | button | Has all of the above been completed? | Yes,No
label | 6c8ecb60-44db-5ed8-96cc-e0c6c74a107f |  | note | Freq - Each Lot
label | 57a3c365-b0b7-55d8-914f-7a95501cccf2 |  | note | Key - S
label | f3c198d7-e6de-5e16-b882-8c3613d173aa |  | note | Resp - SE/SS
date | 8de034b7-d82e-5669-9577-66c3ca9413eb |  | date | Inspection Date:
checkpoint-group |  |  | section | 6.0 Installation of Pits, Lids and Cables
checkpoint-status |  |  | checkpoint | 6.1 - Location of Pits
label | ccc76270-d86c-59ca-926b-76970fb6cd2a |  | note | Ref docs - VR Clause 733.09
label | 899262eb-8b2a-5433-9c0c-4aecad00cbb7 |  | note | Acceptance criteria - Pits shall be located in accessible locations for maintenance activities.
label | 3a2107c1-6f82-5cad-8888-f69c94d6a682 |  | note | • Pits to have a maximum spacing between cable pits of 100m.
label | 3e399717-f832-51ab-8abe-47f8eb5f1bcc |  | note | Freq - Each Pit
label | f653ec13-8fa0-546e-b70a-08c150f2f2e3 |  | note | Key - R
label | 5d47d084-838a-543f-8d52-c1aaebde2963 |  | note | Resp - SE/SS
label | b5c82cd1-20bc-5dce-b94d-9a0e99ab5010 |  | note | SI Key - H I
date | 859c00fe-5062-5215-a524-114805f9c42c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.2 - Cable Pits & Pit Lids
label | ce1260f2-aa78-5567-8649-5e7881ef7c58 |  | note | Ref docs - VR Clause 733.09 TC2200 TC2201 TC2202 TC2203
label | ef81f1be-81fa-5fc3-9d53-7184b94ad329 |  | note | Acceptance criteria - Before the pit lid surround or pre-formed collar is cemented into position an inspection by VicRoads Superintendent or representative must be carried out.
label | 911cbbe4-3b46-5110-a90e-eeabb6fe7c7d |  | note | • Install cable pits in accordance with the design drawings and VicRoads Standard Drawings TC-1210, TC-1220 and TC-1230, TC2200-TC2232.
label | 881beee6-726b-56a3-b13f-9e7ae39efcf2 |  | note | • Top of pit lid matches the surrounding finished surface level fits neatly without movement.
label | 76a1e091-2f43-5581-948a-4385fe9e7fca |  | note | • Pits watertight and suitably drained.
label | 92504c3a-18dd-5760-a40b-46e74f1624fd |  | note | • All conduit connections to cable pits shall be neatly made and the ends of the conduits trimmed off and fitted with a conduit bush. The area between the conduit bush and pit wall shall be stopped with a suitable sealant that bonds to the pit wall and the conduit.
label | 146d0d41-c457-5b2f-b0a8-159d0af4501e |  | note | • Heavy Duty Pit lids provided for pits in the road pavement.
label | 1aecb02a-53c8-5306-a9d7-da80ffa6ed6b |  | note | • Entry conduits to be installed at: 80mm +/- 20mm into pit (VicRoads)
button | 1d6a01f5-2c75-58fd-9d93-54b5a0ffa748 |  | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
label | b34f2ca1-2bf6-5090-bbbc-0b1d58f557ef |  | note | Freq - Each Pit & Each possession
label | cb5b6d0f-3b13-5556-a109-a9626a0c0394 |  | note | Key - S
label | a70e830b-e48a-501e-9ee7-a57eec86242f |  | note | Resp - SE/SS
label | 993ab9d8-906f-5bf7-a298-ca0d4701f310 |  | note | SI Key - H
date | f26ab98b-4c46-57d0-8957-40425b82e8dc |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Detector Pits for Traffic Signals
label | 8ea70052-7249-5998-a8df-70d8ca632ceb |  | note | Ref docs - VR Clause 733.10
label | 6f54bb4c-9e34-50e7-a3fb-b3e63a542ce9 |  | note | Acceptance criteria - Install detector pits in accordance with the design drawings and VicRoads Standard Drawings TC-1310 and TC-1320.
label | e6409f5d-ebcc-5a1c-8f4d-abafdcecd6c5 |  | note | • Fix pit cover securely using the fixing device supplied.
button | 2eeda5fe-4366-5d95-afa6-a7b96b27d6c9 |  | button | Has all the above been completed correctly and to a high standard? | Yes,No,N/A
label | eae4ad79-4b89-5b91-91e9-689d04f49ee0 |  | note | Freq - Each Lot
label | 48ba33b4-e6e0-50dd-a4f7-7b797e4d1363 |  | note | Key - S
label | 0d51973b-349f-56c6-a07d-f658a849bea1 |  | note | Resp - SE/SS
date | 1afd445e-adbe-5cab-a69c-d264b35d1b40 |  | date | Inspection Date:
checkpoint-group |  |  | section | 7.0 Foundation
checkpoint-status |  |  | checkpoint | 7.1 - Location of Foundation
label | 4f936f2a-2e03-542b-b566-aab18d8b3bcb |  | note | Acceptance criteria - Foundations shall be located in accordance with the drawings and approved at the pre-installation meeting.
label | 7e3a2a9f-8c1b-56d6-b149-3dabc97aa3ed |  | note | Freq - Each Lot
label | 937c4b94-392a-50fb-8141-5bb6d311c528 |  | note | Key - R
label | 3bce82db-d1c4-5540-9dce-c4a5997863d2 |  | note | Resp - SE/SSSE/SS
date | 95b5487c-3d7c-5eb4-b6a0-dc813f03e881 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.2 - Foundation Type
label | e8047862-1d5a-5f04-88e6-07fde8cdaabd |  | note | Ref docs - VR730 Table 730.111
label | 850bc5bb-6cff-53f4-a8df-724eba219f1f |  | note | Acceptance criteria - Foundations and footings shall be as specified in the VicRoads Standard Drawings for the specific item of equipment they are to support, as listed in Table 730.111
label | 52d0e9a1-1f93-57c9-b9ea-6b8597a89737 |  | note | • Where alternative foundations are proposed, they shall be approved by the Superintendent prior to the Contractor installing the foundations.
label | 0b1ff44a-6194-5234-8c58-2a6a4d2e5f58 |  | note | Freq - Each Lot
label | 54e6da90-0fe6-557e-be29-abdd0f36d3da |  | note | Key - H
label | d5fc99e3-6929-5e35-88f4-dab2f7b59829 |  | note | Resp - SE/SS
label | 787124c5-32fc-5dbe-86c6-217ce80f360b |  | note | SI Key - H
date | 5eff9fea-2c8a-5488-96ce-2e1017f2c0ad |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Inspection of Foundation
label | 7e546606-e1b6-53de-b535-52e9fdfcb7df |  | note | Ref docs - VR730.11
label | f817a353-693e-52f7-b003-6f4352904a62 |  | note | Acceptance criteria - All foundation works shall be inspected by the Superintendent prior to the Contractor covering the works.
label | a2d9a895-2a79-52ba-a824-1f3006dcb223 |  | note | Freq - Each Lot
label | bab276ac-dc36-5a2c-9d61-5f0545ba5ddc |  | note | Key - H
label | 15b148c8-b338-5aa2-a3c4-9fb509dffcb2 |  | note | Resp - SE/SS
label | d16ab6ea-ac3d-5943-a7d5-fde70ac5c193 |  | note | SI Key - H
date | d9af6795-9bb2-555c-ac3e-7a2fc6ae8290 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 - Concrete
label | 8ffa414b-272e-5426-ab14-0dbbf7879131 |  | note | Ref docs - VR610 Table 610.161
label | 4a74daf2-46e7-5a2d-ba3d-f4db53f4e541 |  | note | Acceptance criteria - Concrete is to be vibrated, and not dropped from a height greater than 2m.
label | fcd57aab-bacf-59e7-b7fb-8eda0084b58e |  | note | • Concrete is to be tested as per VR610 and should be a minimum concrete grade of VR330/32.
label | 8ee04247-5fd5-53a4-8683-46987ffbdfff |  | note | Freq - Each Lot
label | 9371e84f-7749-59f7-9236-99baf3eb4dbf |  | note | Key - R
label | b71ff581-76ea-56f5-aa05-7bfbf45620bc |  | note | Resp - SE/SS
date | 1fad6096-5f7c-51e0-89c7-6bb309fd836e |  | date | Inspection Date:
checkpoint-group |  |  | section | 8.0 Completion
checkpoint-status |  |  | checkpoint | 8.1 - As-built Information
label | 2eac14ce-462c-5233-b133-171e51cf6eb0 |  | note | Ref docs - VR Clause 733.12
label | 4f93723b-0448-576b-8797-59a15a166b01 |  | note | Acceptance criteria - Identification and recording as follows:
label | 6ed198c5-ca75-5426-93b9-82a7d62767e2 |  | note | • All conduit locations not identified by pits immediately installed at the ends shall be marked with pegs 75 x 38 mm stakes projecting 0.4 m above the ground, with the top 150 mm painted yellow, or as otherwise agreed by the Superintendent.
label | ce602c01-e0bf-5262-96ad-f92d6dfd3120 |  | note | • Conduits under road pavement shall be marked with stakes clear of the road pavement.
label | 33b59de8-047b-5ff1-964c-6d9018fb4520 |  | note | • Conduits not under road pavement shall be marked with stakes at the ends, at changes of direction, and at intervals of not more than 30 m.
label | a515282b-d63d-55a2-932d-70b39a219280 |  | note | • The actual installed location and depth of conduits on the as-built drawings.
button | ca9e87a6-834e-51d4-b9ea-e2700deff95a |  | button | Has all the above been completed correctly and to a high standard? | Yes,No,N/A
label | fa619d9d-bc93-591f-9617-ab695457c1b6 |  | note | Freq - Each Lot
label | b4b096af-2b9e-5932-af8d-375c19cbcd81 |  | note | Key - R
label | a95c7a24-cf16-5574-9d81-cc155bfe0637 |  | note | Resp - SE/SS
label | 53d1085f-6b2c-5d9b-92ce-e5b113a208d3 |  | note | Remarks/record -
button | 6fb7b682-61ea-50b7-8979-7b1e085ec6c2 |  | button | • Survey Conformance Report | Yes,No
date | d112c83a-1345-5e07-83d5-445c44bfb5d8 |  | date | Inspection Date:
checkpoint-group |  |  | section | 9.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 9.1 - Test Reports
label | 2f63ae36-3a7e-52d8-a64f-9fc86f755ffd |  | note | Ref docs - VIC Roads Specifications
label | d61770dc-e5fc-537c-89c8-2fe138406851 |  | note | Acceptance criteria - All Test reports received and reviewed.
button | 52999ed0-8d5a-52e2-963e-b6e05f6e6be1 |  | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | 5b8df7d9-d746-5eab-b172-8da582617a59 |  | note | Freq - Each Lot
label | e9e3ebdb-d4cc-5d07-bffb-40f737d1c066 |  | note | Key - R I
label | 5bed81a5-e033-575c-94ea-dc79ed46c725 |  | note | Resp - SE/SS
label | e3de8ea0-994c-59d0-97f9-87306a594c3b |  | note | Remarks/record -
button | 794073a3-3075-59ef-a40f-423b57688b80 |  | button | • NATA Endorsed Test Reports | Yes,No
date | afbee064-28db-5f71-8d26-94d28f28ec5f |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 9.2 - Product Non-Conformance
label | b1f7814c-18f0-5f3f-821d-e9515bcc0ca6 |  | note | Ref docs - CQMP
label | 8c80acb9-33cf-5aee-b013-266c57cd482d |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
button | 188bd4d9-a2b2-5df3-8f2b-80bff7211938 |  | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | bd39739c-0b56-5ee1-8761-0162d81dc2e4 |  | note | Freq - Each Lot
label | ad5ea24e-de9c-529a-8c40-7595472059cc |  | note | Key - R
label | ec85e8e9-72c0-5202-a800-700099f3bd0a |  | note | Resp - SE/SS
label | b4a17a18-65b4-54bb-8018-c8a3b634dd7c |  | note | Remarks/record -
button | 981e043a-b02d-536a-833c-c3e2601c43ae |  | button | • NCR reports | Yes,No
date | d7ba65c1-d7a8-5880-8e56-c2e3cb07c1ed |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0025 Driven Piling | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0025 Driven Piling | 706fdeca-8299-46f8-b652-6d6496bae618
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Driving System
label | 763c0f24-f36c-538d-b61a-b80bd073e398 |  | note | Ref docs - VR 605.03
label | 9dd4da99-1285-5351-ba2a-5635ad45a65b |  | note | Acceptance criteria - Details of the driving system have been provided to the Superintendent including the make, model and rated energy of the hammer, the mass of the helmet, and the proposed cap block and cushion materials. The driving system ensures that the hammer has a height of fall less than 2m.
label | 7040a1f5-e39e-5856-9dab-c7f8445a9c7f |  | note | ○ The methodology used in determining the pile capacity below the ultimate retention height of the test pile has been provided to the Superintendent for review prior to commencement of pile driving.
label | 944222d4-ac42-5ae6-bcda-e2e0a59b5cd3 |  | note | ○ These details, including calculations which demonstrate that the proposed driving system has sufficient energy to achieve the specified pile test load, have been submitted to the Superintendent for review not less than 14 days prior to the commencement of pile driving.
label | bac354c2-d48c-511b-9eaf-c041445326d5 |  | note | ○ All pile corners are have 25x25mm chamfers except chamfers on the top longitudinal corners.
label | 60ab7240-1bd9-5474-953a-87097a0251d2 |  | note | Freq - Prior to start of works
label | d6bb8ec3-58ce-5113-9a7f-47897991a3ef |  | note | Key - H
label | 3888110c-6c98-5d0c-9d4a-9a053ac4bbac |  | note | Resp - SE
label | 817caacc-fa6d-554c-8034-519ca2dbd58f |  | note | SI Key - R
date | dda028b5-514d-55d2-98b0-3cf2785a49db |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 1a11f781-c5aa-58f9-b317-368c06f26cd1 |  | button | Lot map | Yes,No,N/A
date | 8220e517-cca2-562f-97e2-df5d0e360564 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 09f6706e-4eed-51d2-b20f-05d7e8fa84ed |  | button | Environmental permit | Yes,No,N/A
date | 7bbe170a-d0dd-5ae4-854a-666dd013e587 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Concrete Pile approval
label | f5f4e39f-5855-567f-bdf0-c6f73fb3f1ae |  | note | Ref docs - VR 605.08 AS 5100.3 (6.4.2.1) VR620.03 VR 605.09, Table 1 BTN 023
label | 512033a1-d389-59b9-9e82-cd860f3f3c22 |  | note | Acceptance criteria - The date of casting is clearly marked on each pile along with 500mm intervals starting from the pile toe clearly marked.
label | 2caaa049-b27f-542a-8254-5493e7e405c6 |  | note | Precast square piles chamfers comply with requirements of clause 6.4.2.1 of AS 5100.3. Chamfers are only required on 2 out of the 4 corners.
label | 3ee18d38-9d4e-543b-8e73-7a8db89cea66 |  | note | – The cross-sectional area is not less than 90,000 mm2
label | c43ec065-36c4-51f5-80b5-75564fafe16e |  | note | – The head of the reinforced concrete pile is reinforced with a minimum of 6 mm thick and 75 mm wide steel strap
label | bc11f925-3204-5e2c-ad32-252af8bee4a6 |  | note | – Longitudinal reinforcement consists of not less than four bars and spaced uniformly around the perimeter of the pile are provided for the full length of the pile.
label | 757de847-9373-5494-a4d2-9c4c9240a5fa |  | note | The full length of longitudinal reinforcement is enclosed with stirrups or helical reinforcement of not less than 5 mm diameter, and the volume of the stirrups or the helical reinforcement is not less than 0.2% of the gross volume of the pile.
label | 4eb52d10-cbb8-5ffa-8eee-df2116c9d807 |  | note | – Mechanical joints (if applicable) are only used with the approval of the relevant authority, are not less than 3 m and not more than 20 m long.
label | a8c8a65c-6e00-5edc-89f6-c50b5ed363d0 |  | note | – Driving shoes are either iron casting or made up from welded steel plate with no less than 10 mm thickness. Welding is GP in accordance with AS 1554.1. for hard driving, the driving shoe may incorporate a rock point.
label | a30a3380-c91c-533c-b50a-4b1899f72615 |  | note | Piles are free from damage, cracks or distortion. shall be inspected by the Contractor in conjunction with the Superintendent.
label | bfd305f6-fa56-525e-91bf-f90df0751abc |  | note | Where required, a rectification proposal of any defects has been submitted and agreed by the Superintendent and rectification works have been completed to this proposal.
label | a45dc7ea-284a-5946-a091-87e900345c13 |  | note | All piles are confirmed to have the below minimum age before driving:
label | 0382232f-e4a3-5456-96eb-066fab6cbd36 |  | note | ○ Steam cured = 7 days after the date of casting
label | 75a2b0d6-7c80-5dde-885b-d729ff8e3694 |  | note | ○ Moist cured = 14 days after the date of casting
label | 36efaf44-9f82-5998-8837-f762170abf9f |  | note | Precast [piles must achieve the below strength prior to lifting them up at the precast yard
label | 00f2b625-74ea-5869-be3d-772d3e8460f6 |  | note | i) 10 MPa for piles ≤ 5 tonnes
label | 68620343-83ca-5857-8c15-be4ffb1c34c2 |  | note | ii) 20 MPa for piles > 5 tonnes
label | 94e9dac3-2bab-59cf-a90c-63b2b78c9a6d |  | note | Concrete strength & cover of piles are not less than the value given in Table 1 of Bridge Technical Note BTN 023 for the relevant exposure classification.
label | 78154368-1d22-53e4-ae7f-ed8f6f24a09e |  | note | Freq - Prior to start of works
label | 381b1437-1d74-5189-a0d8-db5c79a411e4 |  | note | Key - H
label | e53c9009-bfad-5f2e-8140-585e94d7b7c5 |  | note | Resp - SE
label | f196d888-1fc8-5bd8-a77b-635a5794e80e |  | note | SI Key - R
date | 6b406779-4ff3-5a49-ac3e-1f444a5ccd78 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.3 - Pile Steel
label | c57a0895-fbb4-5534-a75a-50caa8961676 |  | note | Ref docs - VR605.09 BTN 023 (clause 4.3)
label | 6f2aa573-48a1-5e9d-b684-631bd90b3620 |  | note | Acceptance criteria - Equivalent reinforcement is approved by MRPV (When anchor bars on mechanical joints interfere with longitudinal reinforcement).
label | d97badf8-f2e7-5c58-b155-67fea14c6da1 |  | note | ○ Pile driving rings or head bands are fabricated using full penetration butt welds and backing plates.
label | c4901908-5b09-58f4-94ab-677fed32bd1e |  | note | ○ Pile protection fittings are made ‘integral with the pile’ by using anchor bars welded to these fittings.
label | b8c4c61f-7f16-545b-b958-bf9c8adb407b |  | note | Freq - Prior to start of works
label | c60a5049-8dd8-5991-a4f8-fcb920efb070 |  | note | Key - H
label | df726d30-b4f9-595b-9d93-8e6394e2888b |  | note | Resp - SE
label | af081b8c-e969-5c36-b66b-98c3d7dada60 |  | note | SI Key - R
date | 1f1aa00e-b470-5600-bcc3-d31fed3c400c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.4 - Prequalified testing consultant
label | 1436959f-cfbb-59a9-9334-c64be7e22392 |  | note | Ref docs - VR 605.07(b)
label | c18e082e-67d7-5b86-ba2b-731f460dad54 |  | note | Acceptance criteria - The consultant undertaking high strain dynamic testing is independent of the piling contractor and advised to the Superintendent at least 2 weeks prior to testing. The Tester needs to be DTP prequalified.
label | 6b962954-a65f-5e1f-bc54-7ebcdcfa64b0 |  | note | Freq - Prior to start of works
label | 2b71cbc3-24af-5bae-9ec4-42fc7c1a60b7 |  | note | Key - H
label | f256c09c-3ed1-52c9-af6c-64482ceceba7 |  | note | Resp - SE
label | bac1d8ca-dc2c-5218-9334-809a07cfa95d |  | note | SI Key - R
date | a07917d2-505b-5dbe-868d-af04fd84b954 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.5 - Temporary Works of Piling Pad Design
label | f55b02a7-7a51-5907-8ea6-9549d3747c29 |  | note | Ref docs - General Specification 1170.04
label | 6143664f-c158-5b0b-b32b-ce51371bb393 |  | note | Acceptance criteria - The manufacture, fabrication, erection or construction of any part of the Works of Temporary Works must not commence until the relevant Construction Documents, including the IFC Documents, have been finalised in accordance with the requirements of General Specification 1190.03.
label | 72a05ead-5d43-569f-b343-d1c9212c7982 |  | note | Freq - Prior to start of works
label | c0a4da89-9949-5f80-8f58-d4b701fd25f8 |  | note | Key - H
label | 2826457d-a3c8-54b5-b23b-12ccb7211a77 |  | note | Resp - SE
label | 0027f98b-f097-5461-849c-05443f6b91ab |  | note | SI Key - R
date | 1bc2a33c-447c-55d5-98cc-c826aec6dee2 |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Installation of Driven Piles
checkpoint-status |  |  | checkpoint | 2.1 - Survey set out and drilling setup
label | bdd0f2aa-4c97-5cc2-a116-42c67b7571c8 |  | note | Ref docs - 1630-P200-SYM-SBR-DRG-0102
label | 22d5310d-5a58-53c5-b38b-505e325d8bb3 |  | note | Acceptance criteria - The Surveyor has set out the centre of pile prior to installation. There is a minimum of 2 survey offset marks to maintain the centre of the pile.
label | 3687e20d-6715-59d6-9064-092a34799511 |  | note | Freq - Each pile
label | 083fdf65-9190-5a0f-8be4-4867e31361c6 |  | note | Key - I
label | c4e3bf65-314f-59a6-ac29-e1fa55b886b6 |  | note | Resp - SE
date | fa7ede16-1704-50b7-8693-8cc34e1dd04d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - Isolation Sleeves
label | 34329557-65ae-5300-a281-b01358c679ba |  | note | Ref docs - AMS Activity 6.3
label | 8551d4df-6213-5ecd-a380-09cf50c6310f |  | note | Acceptance criteria - The pile location is bored to the correct depth and a steel sleeve is inserted into the hole to provide isolation for the pre-cast driven pile.
label | c6118da1-3b3d-5853-9973-6b47cd3b2990 |  | note | ○ The voids between the embankment fill material and the outside wall of the sleeves (if any) are grouted using sand grout.
label | 5d8798e9-9022-5523-9221-658c84e84e66 |  | note | Freq - Each Lot
label | 0aa67ee6-645b-57a3-982f-d9637cea773b |  | note | Key - R
label | 22c6c9b5-1916-523f-82de-c0fdbca932aa |  | note | Resp - SE
date | 85135116-0ebb-537b-93ed-b83982f1155c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.3 - Pile driving records
label | 0ab693fd-5709-5d05-9ee7-401707db0679 |  | note | Ref docs - VR 605.06
label | 49359d7f-5ab1-56ee-9368-696343b04a25 |  | note | Acceptance criteria - The following records have been retained for each pile being driven:
label | b46f5c27-bc43-57cf-b7e8-2a848a49aaf8 |  | note | (a) manufacturing lot number and date of casting
label | 80785237-21a3-56f8-a82f-c5d3333a6004 |  | note | (b) location in pile group
label | 2a1176a7-b5e4-51db-96cb-f72824fae68d |  | note | (c) length prior to driving
label | a40ad991-536e-5534-a822-5db0bc6da3c8 |  | note | (d) date of driving
label | 4c985e5b-c8fe-5229-a8df-b794c181ac80 |  | note | (e) toe level
label | 310658b5-1cc2-53a5-be4c-060104bb7e20 |  | note | (f) traces of set measurements showing set and temporary compression
label | 8c49aa90-c966-5d74-b85d-38b1cacfd2c7 |  | note | (g) calculated ultimate pile capacity
label | c2ee7f38-e440-5c09-9a02-91f540284f1b |  | note | (h) measured stresses in the pile.
label | ac45bcbd-65b7-5b72-b2f5-c72a31424414 |  | note | All records shall be provided to the Superintendent within 72 hours of each pile having been driven into position.
label | 0d3b3a0d-1095-59ba-937f-096442ce05b7 |  | note | Freq - Each Lot
label | 2f0e92bd-9caa-57a7-ac2a-322d6c573ef7 |  | note | Key - R
label | 1ee0d219-48b6-5f41-8612-500cdd5e997b |  | note | Resp - SE
label | d4e92b57-0a5c-57a2-98ca-1960299ed5ed |  | note | SI Key - R
date | 88e64ae5-0267-51af-b1e4-6611d3c8c6af |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.4 - Pile driving (1)
label | e930332a-68c2-596a-8a57-28d0f3fa4895 |  | note | Ref docs - AMS Activity 2.06
label | a8df5638-3754-5fab-bc1a-2eb500aee327 |  | note | Acceptance criteria - The starting position of the pile has been checked against offset marks. piling rig and pile segment shall be lined up parallel to each other prior to piling,
label | 22d5bae7-8eba-5c9c-9ff0-23b8087c27b9 |  | note | Freq - Each Lot
label | beb2c2e3-d379-5117-bf55-b38cdb936879 |  | note | Key - I
label | d18820f3-b813-538a-b2d4-eaaf478fefba |  | note | Resp - SE
date | 7b785a6b-3399-53f8-afee-f931b0dfe959 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.4 - Pile driving (2)
label | a1e5760a-f04d-5ebd-a320-c74c72df76a8 |  | note | Ref docs - VR 605.04
label | 88704e0c-2377-56aa-8927-91145617adc2 |  | note | Acceptance criteria - During driving, the tops of the piles are held and guided by a suitable helmet and protected by cushioning material to avoid damage to the pile.
label | e2bff5e5-0082-5e22-a349-88846710d8eb |  | note | ○ Each pile is driven in a continuous operation, if pile needs to be extended, splicing shall be done immediately once section has been completed so driving can re-comment as soon as splice is completed.
label | a094403b-5cf7-5dba-8c82-c7a6b76ad64b |  | note | ○ Pile is driven to the design level
label | 0cfb399f-4d3e-5046-8819-a43a8795018a |  | note | ○ Forced up piles are re-driven to the design level
label | 3c0d938f-0a45-5aee-a747-e9b1c59ee6e7 |  | note | Freq - Each Lot
label | 7fe2d264-03d0-55f8-9c7e-12c800b4b042 |  | note | Key - I
label | 3a900581-2b54-51dc-a9f8-f1162cd59b2e |  | note | Resp - SE
label | 53fc006b-7d20-5c35-b411-753ba83d6ae4 |  | note | SI Key - I
date | 4464bd3a-54c7-55dd-ac7f-4075e1ecf64c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.4 - Pile driving (3)
label | 882a5ab5-33d5-5caf-ba8c-fe5d7e444530 |  | note | Ref docs - AMS Activity 2.06
label | 6f9d5d6a-354d-5ba9-bab8-cf175a75ca75 |  | note | Acceptance criteria - Once the pile has been driven to a level that will allow for a visual inspection, pile driving is to cease so that the piles can be inspected.
label | bfafed45-d958-5ccc-bdda-cd4e69b70454 |  | note | Freq - Each Lot
label | 28a529f2-aa9b-55f3-a6ff-a5ee1066a3c1 |  | note | Key - I
label | 75e9a2a3-64ea-5248-bf03-8e200f996896 |  | note | Resp - SE
date | 67de599c-a510-5a08-86ab-7d9fc00c389b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.4 - Pile driving (4)
label | 7ebe4711-ce81-561d-89a7-9d7b3eb28380 |  | note | Ref docs - VR 605.05
label | d7098d47-6087-57cf-8e84-74a1942a9bc1 |  | note | Acceptance criteria - Pile stress during driving did not exceed the below:
label | 7ff8e90d-cdb2-57d9-b9e4-2db052ec4e72 |  | note | i) For concrete piles stress ≤ 0.8 fc for compression and 1.1√fc for tension
label | ba5c1b7c-401e-54c6-b2da-869e24bc6225 |  | note | ii) For steel piles stress ≤ 0.85Fy
label | dda6a7f0-235b-514f-b2a5-b8c65fd3c4d2 |  | note | iii) For exposure classification B2 or C, concrete pile stress≤ 0.5√fc
label | f736456a-abe3-555f-9d6c-e87683a6c53c |  | note | Freq - Each Lot
label | fdca6fc8-1f6d-53c6-b7d7-070d5313b2ad |  | note | Key - R
label | 13d7473a-9e1b-52cd-8e7e-9e2448b7752d |  | note | Resp - SE
date | a11e82ac-4238-5790-b74c-3dedae2711d4 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.5 - Pile tolerances
label | 09d457a7-76ae-5a12-9dd5-2e40422bbf6c |  | note | Ref docs - VR 605.04
label | c77cbb64-3fe4-553c-bcde-52eeaf6670a9 |  | note | Acceptance criteria - The Contractor shall ensure that piles achieve the specified accuracy of level and position. The following tolerances shall apply to piles after driving:
label | 944261c5-f5ba-5c06-be78-6dda385f927f |  | note | (a) pile alignment
label | 07948336-217c-5429-9b93-d5df4441bd56 |  | note | ○ deviation from the vertical or the specified rake shall not exceed 20 mm per metre length of pile
label | b9155e35-93e2-52ad-8a1a-c1e4e135f66a |  | note | (b) pile straightness
label | 913a0430-e3e4-5d1b-bd93-0a6994d33123 |  | note | ○ deviation from vertical shall not exceed 5 mm per meter length of pile.
label | b0d22b87-c71e-554d-93d3-89ca61eb0d4a |  | note | (c) pile position for piles in pile caps and the underside of crossheads
label | 3be32bab-3eea-52c1-92d4-67d6ed787235 |  | note | ○ pile head center, ± 50 mm of the specified position.
label | e59df1ea-e20d-5100-b895-2e914f3fb92e |  | note | Freq - Each Lot
label | 68470d63-5e18-5740-bdee-8e47a762db71 |  | note | Key - R
label | 013b8458-4d70-5f71-9713-fc34a2899838 |  | note | Resp - SE
date | 940c33aa-0719-5570-b072-7ddf18825640 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.6 - Extensions to piles
label | 2b82950d-2a42-5953-9fd1-505bb47c71b7 |  | note | Ref docs - VR 605.10
label | 28cf7b61-3c00-565e-ab66-dd9f2351241f |  | note | Acceptance criteria - Reinforced concrete piles are extended with either an additional length of precast reinforced concrete pile or with a cast in place reinforced concrete extension subject to the requirements of VR605.09.
label | f3675722-e516-549a-b3fc-3df97748887e |  | note | Freq - Each Lot
label | 40f92aa7-a88e-5103-943f-11daf58afd07 |  | note | Key - R
label | 1a66defb-365a-51d7-859f-c30412bdd5dd |  | note | Resp - SE
date | 3eba372e-b605-5f97-8a0f-473b5151a589 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Pile Testing
checkpoint-status |  |  | checkpoint | 3.1 - Pile Testing (1)
label | 34b71c7c-fdca-5d67-9246-a76d9dd69ce0 |  | note | Ref docs - VR 605.03VR 605.07
label | 15637309-ec30-5577-b85d-2e3e17aa5233 |  | note | Acceptance criteria - Pile testing has been carried out in the presence of the Superintendent.
label | e56466e2-74e1-5ca0-9d56-e30c19459e78 |  | note | ○ The first pile driven in each group is tested (which determined the driving set each pile group) and the ultimate capacity determined in accordance with the formula in clause 605.05(a).
label | 12ff9cbf-4c51-5445-8f6e-76f9956d103d |  | note | Freq - Each Lot
label | 821db45a-0bbe-553e-8f8b-596c12d63313 |  | note | Key - H
label | 5c0d7d41-aecb-5852-a665-108a3dd466e5 |  | note | Resp - SE
label | 75f3fd18-0e7e-5ab8-b821-8cbbc3a02ac8 |  | note | SI Key - H
date | 1a64726f-607b-59d0-99a7-bd97fb332f6d |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 - Pile Testing (2)
label | e13f4520-ca38-5b93-b9d9-8b6f0b3972dc |  | note | Ref docs - VR 605.04
label | 5e136e7b-22c2-5efe-8cbe-4ae99783994b |  | note | Acceptance criteria - Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile.
label | e2c205e8-c7ee-5ea5-92ca-5ea4d71c91e9 |  | note | Freq - Each Lot
label | 8bc4539c-fa00-501c-980c-465ee8c2ad79 |  | note | Key - H
label | 8a00e5d1-9d7a-5b17-922f-946be69f5c56 |  | note | Resp - SE
date | 730f3c3f-eed7-517d-b228-9ac949e12127 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.1 - Pile Testing (3)
label | cb31d067-0102-5610-b827-561cdb4f4a48 |  | note | Ref docs - R 605.07, 605.05(a)
label | 91af5ba2-0c48-5471-9f05-cab676bd217f |  | note | Acceptance criteria - The first pile in each group has been tested and the ultimate capacity determined in accordance with the formula in clause 605.05(a).
label | 4cfa95f7-f042-54ae-a173-a8a9c670a6d2 |  | note | ○ The pile test has determined the driving set for each pile group by correlating the set with the driving system and the designer’s requirements for the pile test loads shown on the drawings. All piles within that group have not been driven to a set exceeding the driving set as determined by the pile test for that group.
label | 53b93579-3311-55ef-98e6-53ea60e9d6c9 |  | note | ○ Nominated testing coefficient will be reviewed by MRPV
label | e151c368-e216-5a2c-8505-fb8721c9926d |  | note | Freq - Each Lot
label | b85f4666-a9af-51f0-be72-a4eede952f40 |  | note | Key - H
label | db391dce-311f-574d-b6f5-4e191d822a11 |  | note | Resp - SE
label | e3ef54ee-e9f1-5349-b2b5-923f31d0bd36 |  | note | SI Key - R
date | 477c2231-e999-5b41-bd6d-db40cd48afc9 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.1 - Pile Testing (4)
label | 082cdbd7-c922-5f11-a8ec-6f7fb706b4d7 |  | note | Ref docs - VR 605.05(b)
label | 08fc687b-9ecf-5d8a-a16a-7c29f9f3ee89 |  | note | Acceptance criteria - In addition to VR 605.05(a), pile capacity should be proven using dynamic analysis (PDA with CAPWAP) as per the drawings:
label | fa38522b-d009-5149-9d42-b8a5add93b6a |  | note | ○ 2 piles at each abutment
label | 02072d29-e317-53f3-bf5b-480a3c727444 |  | note | ○ 3 piles at the pier
label | 58f353b8-c646-5fa9-b922-7e9621945872 |  | note | All high strain dynamic testing has been undertaken by a prequalified consultant and approved by the Superintendent.
label | 6c6e36b9-438c-559e-8c32-7f4b0f6dc86f |  | note | The pile test has determined the driving set for each pile group by correlating the driving system and design pile capacity. All piles within that group have been driven to a set not exceeding the driving set as determined by the PDA test.
label | d539e6c3-c361-59c9-be4a-2f9b65e3528b |  | note | An additional pile test has been conducted where the driving conditions are no longer represented by the initial pile test for that pile group. Additional pile tests are required where:
label | 15551674-6a2b-55b0-9c69-6f096bd2eeeb |  | note | ○ The design pile toe level of individual piles within a pile group is more than 2 metres, or
label | 7a948d5c-4c3b-54bc-bef3-d1d21969df9a |  | note | ○ During pile driving pile toe levels vary by more than 2 metres from the test pile, or
label | d7cdbba4-442b-5b8f-9c94-4d30c83510d4 |  | note | ○ Pile rake differs by more than 8 degrees from the test pile.
label | c1471184-8b32-594c-aa3c-5db1257272c7 |  | note | ○ distance of any pile from the test pile did not exceed 20 metres.
label | 05dcf976-0ecb-5ca2-be1f-03d404a3728f |  | note | Freq - Each Lot
label | 602a6dcb-5791-51dc-a533-d37ac696bcf3 |  | note | Key - H
label | bfc4b75a-184d-50a6-9ac0-72c6010a9e8c |  | note | Resp - SE
date | 471b03e1-4e13-5386-93f9-92ea9342da6d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Restrike Test
label | 48909222-5d60-5bec-a970-90a8e00ec073 |  | note | Ref docs - VR 605.08
label | 7afd0fa6-033f-5994-a29e-6df01a7bfcd1 |  | note | Acceptance criteria - If the ultimate load capacity has not been achieved at the specified level or at refusal, restrike testing has not been conducted less than 24 hours after initial driving.
label | 48151eb2-701b-5b9c-85a7-745df63eaae4 |  | note | ○ If directed by the Superintendent, the pile shall be driven until the specified ultimate load capacity is achieved.
label | 84ca04cb-c7f3-59a8-8080-7ca333fb3c53 |  | note | ○ Driving resistance must be equal to or greater than the pile test load shown on the drawings.
label | 10c9180c-3440-5661-8a9e-b1c30a268038 |  | note | Freq - Each Lot
label | bd3ed88a-1876-57cb-82bb-b720758854a9 |  | note | Key - R
label | 05fbca8f-7dbb-5453-9953-7bd2a0800e76 |  | note | Resp - SE
date | 959417d9-faba-51cf-b73a-2bae34799ee6 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.4 - Defective Piles
label | 2a258c78-27a0-5546-abf6-6d4bbbbdce53 |  | note | Ref docs - VR 605.13
label | 1ca24708-d2c9-51f6-ac65-8f83e5ee8ba9 |  | note | Acceptance criteria - Where a pile exceeds the specified tolerances, is damaged or is otherwise defective, the strength, serviceability and durability of the pile shall be reappraised and where found to be unsatisfactory the pile shall be repaired, downgraded or replaced with one or more supplementary piles subject to the approval of the Superintendent.
label | 89b0efd2-1297-5bd3-a4fc-3e2002a3e140 |  | note | Freq - Each Lot
label | ec782e56-5972-570a-8dc8-9006314ff6db |  | note | Key - R
label | 71f037e7-5148-53bb-9f6e-d1572a406424 |  | note | Resp - SE
date | 19a70481-695e-5487-a8ac-d29fc4582fd6 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Joint location
label | af4d6de3-88f6-524f-afce-25fd6ae7d87d |  | note | Ref docs - Drawing no. 1630-P200-SYM-SBR-DRG-0105
label | 2130d203-7f30-5772-a2f0-9aef756ab1de |  | note | Acceptance criteria - All mechanical joints are a minimum of 5m below natural surface level.
label | fe4ab1ce-6c6e-5e6c-810f-71e592b9960c |  | note | Freq - Each Lot
label | 0025687f-7d75-55f7-b684-3ad2f7faf9d4 |  | note | Key - R
label | 99979d16-4d06-5e5f-a813-7f6dd57cf93f |  | note | Resp - SE
date | 2751218a-7712-5901-8fc7-3a1f5f7f6de9 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Test Reports
label | cab64935-eee6-56ca-a730-d4b9810f6e57 |  | note | Acceptance criteria - All Test reports received and reviewed.
label | 6a620c93-31f9-5477-a752-7eb26c3d49bd |  | note | Freq - Each lot
label | a124be49-47e7-5ed5-b557-13b488b5d944 |  | note | Key - R
label | fee0aa13-df1e-53c3-ab9b-03379a7f3292 |  | note | Resp - SE
date | 6524a50e-f624-5e0a-aa2b-826ac1410b11 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Product Non-Conformance
label | 80222a5e-9cac-5c35-8ee0-86e8396158ba |  | note | Ref docs - CQMP
label | 11d73fb2-53eb-5fc2-a13e-1591779b918e |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | df1ee264-bea8-5b8e-99e9-986cb683b29f |  | note | Freq - Each lot
label | e2be2432-07b7-5589-9d57-e539e1815abd |  | note | Key - R
label | aff42ac9-22d4-5da1-86c3-66de367d8176 |  | note | Resp - SE
text | a59d5633-8077-52a6-8c8c-fc0a16c35298 |  | textbox | Remarks/records - NCR No:
button | fa931800-e978-58ca-a607-0612cd41ad75 |  | button | NCR reports | Yes,No
date | d6915d4d-bd90-5d8b-b6b7-2c8cb7024f67 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Quality Representative to check the above criteria and records to confirm
label | b8b7d8fb-9f49-547c-9724-75024dd1aea2 |  | note | Ref docs - CQMP Lot Records
label | 4d1d171d-ba6e-5760-814a-b401a230f0f1 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 393d8442-97d7-5967-8f69-9bd897b09bc5 |  | note | Freq - Each lot
label | c762b298-2b0e-5649-b99f-90e27d106721 |  | note | Key - R
label | b2c78048-3ff5-5ac6-9e62-beea97685919 |  | note | Resp - SE
label | d271a9df-bc2d-50f6-8bfc-ac1b6fb7359b |  | note | Remarks/records - Reports and other compliance records attached.
date | 49271890-4f83-5c31-8010-8be3f8eaed1c |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0037 Rock Beaching Type 1, 2, 5. REV1 | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0037 Rock Beaching Type 1, 2, 5. REV1 | 75ee6ce0-f337-49ab-a144-852c2b064490
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Conformity and Lot Maps
label | d8827dd7-8cc9-5c09-b0aa-84f05bc2ed9c |  | note | Ref docs - VR713.02 IFC Design
label | f3a01d19-67ef-5e56-aff5-b7f328e9a1fb |  | note | Acceptance criteria - Beaching finished surface shall conform to the levels, lines, and grades shown on the drawings or specified.
label | 8f55e29e-9e07-562c-8eb5-3c760e8cf4c2 |  | note | Freq - Prior to start of works
label | 819b33f3-f089-503a-92d5-79ad6def4897 |  | note | Key - I
label | f22ba963-505f-5473-ac60-288ea3d77b93 |  | note | Resp - SE
date | 6e4da722-d0ec-5b9e-8680-45e462d3a321 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 2d9dbda5-e2c1-5d93-9f93-9736aa0c7a44 |  | button | Lot map | Yes,No,N/A
date | 5d48cfb3-ed15-5dd8-9420-154711c8c470 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | fa809de4-1af3-5831-992e-15a3759df854 |  | button | Environmental permit | Yes,No,N/A
date | 7149b9e8-ad38-5929-945a-2ccaadccc9bb |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Material Approval
label | d495145e-a16f-535c-8aef-fe249e06fb81 |  | note | Ref docs - VR713.03
label | 4a3dc880-81db-5d42-a7f0-6c945977133e |  | note | Acceptance criteria - The contractor shall nominate material source, supply specified test results, and provide a representative sample for approval by the superintendent.
label | 12b28385-f5f8-5fa4-a6ad-4e26ecc60faa |  | note | Freq - Prior to start of works
label | 4c83fa21-a8d1-5ab1-81be-0e8d199b4a8f |  | note | Key - H
label | b2bd0119-17e8-5ceb-89f3-cb15b36c80ba |  | note | Resp - SE
label | e357fa46-33d8-5f83-8d37-5665f8d66a1c |  | note | SI Key - H
date | 82d7eb46-3dae-59cf-afc6-e3eae8714f09 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Beaching Material - Type 1 Ungrouted
label | 9a65ee86-9680-56e2-a8dc-eb8b8d65910d |  | note | Ref docs - VR713.03
label | 77fa900c-8744-511c-9b2d-04f2b3e43b9c |  | note | Acceptance criteria - Type 1 Beaching material shall be:
label | 83a086ae-7c6f-5480-966e-4d1b69e8a6c2 |  | note | • Field or quarry rock >50mm diameter and of mass 20-70kg with at least 60% of Qty greater than 40kg.
label | d1310f17-a342-57ca-a7c4-80473bcbe982 |  | note | • Placed that the length of rock protection >100mm and the total layer thickness is >225mm.
label | 36d92051-1942-5ec9-a8cb-603e57ee916c |  | note | Freq - Prior to start of works
label | 6ce2860c-dc97-5553-9620-6852f01b8960 |  | note | Key - R
label | 0a03d35e-335e-54b7-9f20-325e12fe2ead |  | note | Resp - SE
label | 1271e4da-05ef-5c32-ab81-26752db5c118 |  | note | Remarks/record - Import Docket
date | 209c5761-1af6-54e1-93b4-93a83085c654 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.4 - Beaching Material - Type 2 Grouted
label | 3ad06e16-d7b6-51a3-817f-e73fa3f462c9 |  | note | Ref docs - VR713.03
label | 98703369-2c48-5393-8575-a161d93d2a65 |  | note | Acceptance criteria - Type 2 Beaching material shall be:
label | 1ca21c86-ce12-5e13-9ce4-1322db7dde2c |  | note | • Field or quarry rock >50mm diameter and of mass 10-40kg with at least 60% of Qty greater than 25kg.
label | 24214a73-babf-55a1-9e9e-cec7dbe4f1f6 |  | note | • Placed that the length of rock protection >100mm and the total layer thickness is >150mm.
label | 0c283d85-7933-5719-b099-b51629034a58 |  | note | Freq - Prior to start of works
label | b42fdd54-dccc-5725-a52c-a853e8c95e69 |  | note | Key - R
label | 51b1d970-669b-576b-9737-8d6d9880c704 |  | note | Resp - SE
label | 0f33e219-7de4-5a6d-989b-6ed86299e69c |  | note | Remarks/record - Import Docket
date | ca4b6b72-e181-5554-a26d-29fecf53de87 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.5 - Beaching Material - Type 5
label | 977534b3-6976-5a7e-8816-282b455dc737 |  | note | Ref docs - VR713.03
label | 0054d2ab-6ec6-5aba-8678-11ecb7861928 |  | note | Acceptance criteria - Type 5 Beaching material shall be:
label | c51a63ab-1ca9-561e-b147-ea268256ccde |  | note | • Design accepted by Melbourne Water and record of acceptance provided for superintendent approval.
label | bef9b4ec-941f-5610-956b-ad6e8c989b5d |  | note | • Field or quarry rock >50mm diameter, angular in shape, and 5% mass of rock fines for interlocking.
label | 353fb197-a7c0-51a2-aaf1-9b26443bc9f2 |  | note | • Unless specified, the minimum d50 shall be 300mm rock sizing of depth 2 x d50 (600mm). the minimum d50 shall be 300mm rock sizing of depth 2 x d50 (600mm).
label | d7875e04-3c08-5581-bad6-1e4ece5ad490 |  | note | Freq - Prior to start of works
label | ea58b17a-f9a4-5c03-8eef-9cfad8c63b92 |  | note | Key - H
label | 07190696-a400-51b1-b2b3-776b0de65117 |  | note | Resp - SE
label | e85f50f6-eccb-56a2-a291-55689efdf987 |  | note | SI Key - H
label | 44945042-61c6-588d-9811-558f7b9c28d1 |  | note | Remarks/record - Import Docket
date | 73d0e9d2-7492-59ce-8ea9-9caaf87e2edc |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Construction
checkpoint-status |  |  | checkpoint | 2.1 - Geotextile Placement
label | 821b169f-fc0b-52f2-9f55-ad4727cd845c |  | note | Ref docs - VR210.05(a)
label | b2c06d11-c1a5-50c4-82e6-d42d7bcd89e0 |  | note | Acceptance criteria - Geotextile is not to be placed without written superintendent approval.
label | 1a1fbb23-9190-5dbe-96cd-b6aff43c67b3 |  | note | • Geotextile placed shall be without punctures or tears and rolls with imperfections shall not be used.
label | 4d26693f-e9aa-58f6-b61a-f689ac9415aa |  | note | • Covered with fill material within 48Hr of placement.
label | 98643285-87c0-5d71-9f93-1a60532eea58 |  | note | Freq - Each lot
label | 4dc222fd-d03e-51e8-a718-9752f9dea5ea |  | note | Key - H
label | 4ad173aa-864a-5076-9dc2-e1a1c6cd6a89 |  | note | Resp - SE
label | d626d43a-82f0-575b-ba34-e2a8c40341d2 |  | note | SI Key - H
date | ede85486-41e6-5fb1-a976-f1cee64838fd |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Bedding and Geotextiles - Type 1
label | c87e282d-196e-52e6-805f-1154235e53e1 |  | note | Ref docs - VR713.03(b) VR210
label | f7f97abe-07e4-5200-9775-c06cd8b09e62 |  | note | Acceptance criteria - Type 1 Beaching Material shall be placed on non-woven geotextile >250g/m2, laid with no kinks or folds.
label | 34dba496-ca56-5733-b631-005d89f03433 |  | note | • Geotextile shall be buried 300mm below beaching edges and placed under and around excavation for toe wall and other perimeter walls.
label | 061ddac6-569e-5c7d-aefc-725252c0caa5 |  | note | • Geotextiles are joined with 300-500mm overlap.
label | 3f3639ad-54b1-585a-872e-cfdea05b3395 |  | note | Freq - Each lot
label | 2cca31be-7cc6-5041-85de-b87a5733c3aa |  | note | Key - I
label | 7031e2b3-069b-5e96-be5e-30c92b020bec |  | note | Resp - SE
date | 29db4b7a-fddb-5259-b141-f5f06f560ed7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.3 - Bedding and Geotextiles - Type 2
label | 47148f98-432c-58cf-8a61-5ae80bbfbbc9 |  | note | Ref docs - VR713.03(b)
label | 2e0744a7-3fc4-5adc-992f-b1f7a703091f |  | note | Acceptance criteria - Type 2 Beaching material shall not require bedding unless specified or in design.
label | 74eff602-79e1-5a9d-a0b9-f27f1fea84ca |  | note | Freq - Each Lot
label | 04873f63-bc94-5b3f-a716-c1d26e8fc70d |  | note | Key - I
label | 9427ad39-060f-560a-b7f4-8fee492a9f82 |  | note | Resp - SE
date | c697f3fd-5a44-5083-a612-7901aa2ff64d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.4 - Bedding and Geotextiles - Type 5
label | f3f89a70-6a85-54c3-bd96-5387c5279151 |  | note | Ref docs - VR713.03(b) MWC 7251/08/103
label | cf8f008b-749e-57e8-980c-b1ae069ab2ab |  | note | Acceptance criteria - Type 5 Beaching Bedding shall be:
label | 82d20837-1e8c-5cb7-a037-455a3871079e |  | note | • Developed in conjunction with Melbourne Water.
label | b064ba1b-0022-581d-be37-8bf438637d00 |  | note | • Well graded, and 0-100mm size for granular bedding.
label | 60dc4058-e98a-54cb-bc18-042fa8b869e6 |  | note | • Granular filter thickness >100mm.
label | 1f7c9bb2-5f96-54d4-bc83-74c254f3bb04 |  | note | Freq - Each lot
label | 3d88c641-9885-58e4-9637-adf1585a0a01 |  | note | Key - I
label | 4d4d895b-70bd-55db-9036-7083cbefbc65 |  | note | Resp - SE
date | 0d40a188-550d-58dc-9fb5-615be9abfd6e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.5 - Preparation of underlying surface
label | 6d3d9582-f428-517f-a060-b7abf414b109 |  | note | Ref docs - VR713.04 VR210
label | a4d858a6-ba00-5391-b158-837b3e6cf36b |  | note | Acceptance criteria - Beaching placement surface shall be:
label | 6dfa716d-1f71-54c1-adc1-133b25cef46b |  | note | • Excavated, compacted, and trimmed to provide a FSL of beaching in accordance with IFC design.
label | 23364242-8ee9-50a3-b468-38c2b95b644a |  | note | • Any scours or hollows backfilled with class 4.
label | 184f5bef-15fc-5e57-91bc-0d04acf5128e |  | note | Freq - Each lot
label | ac5d3f17-4d22-516b-a00e-069ae630fc73 |  | note | Key - I
label | e36f08df-3829-5e53-a449-0077c3eed66b |  | note | Resp - SE
date | 63cc2de6-44fe-59d5-b467-56f71a02656a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.6 - Placing Rock Beaching – All Types
label | a76b5294-0f53-56a2-9922-45ced3a70c77 |  | note | Ref docs - VR713.05
label | 3dfbce8d-1fe2-53c6-b164-bd6bd916f280 |  | note | Acceptance criteria - All Beaching shall be placed such that:
label | 51f35258-6a14-54a0-b256-0671c9338d4f |  | note | • There is no beaching protrusion >50mm above surrounding ground levels.
label | 750c4374-a36f-578d-9a06-4e411e1a4a3e |  | note | Freq - Each lot
label | 8a95ce89-2dc5-549e-ace2-b40861dfd6a7 |  | note | Key - I
label | 8f1ffe0d-697e-5be1-afb0-58ce5718c754 |  | note | Resp - SE
date | f7a0932d-f596-5853-9929-17ec3f9ba894 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.7 - Placing Rock Beaching – Type 1
label | 5f91c845-b50a-5815-9ee3-dc38e8609d78 |  | note | Ref docs - VR713.05
label | 3ec9e814-073f-5456-a702-6887828771c6 |  | note | Acceptance criteria - Type 1 Beaching shall be placed such that:
label | 02558cbe-9e18-5553-bd67-52c4aae7a13c |  | note | • A tight ‘interlocking grid’ is formed to retain each rock with gaps <60mm on average.
label | c62d1b7f-3373-5b88-bf6e-4ce7091de04d |  | note | • There is not >100mm height variation along a 3m straight line along the finish surface.
label | d387b37b-2cf9-5a56-99c9-5c73f1db16e8 |  | note | • Voids filled mid-height of rock with topsoil.
label | 0c8a4f71-a1a2-556c-abe0-5b9fb2db8e92 |  | note | Freq - Each lot
label | dbf4eba2-5431-5359-85ee-385ed03eab37 |  | note | Key - I
label | 46921a60-507b-561e-b878-87ca1638d73c |  | note | Resp - SE
date | da47f7d0-968f-5f86-a871-be304575d922 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.8 - Placing Rock Beaching – Type 2
label | df90921d-e018-5878-9946-3cb11b65c500 |  | note | Ref docs - VR713.05 VR13.06
label | 61504b1f-9727-5690-bb0a-170145054b64 |  | note | Acceptance criteria - Type 2 Beaching shall be placed such that:
label | 9f06263a-c12f-5402-9257-3102ae781751 |  | note | • An initial bed of mortar infiltrates the joints VR13.06.
label | 4027ec98-fcb2-54a0-bc8c-e02f573eb95b |  | note | • Width of joints vary are between 10-60mm, and not exceeding 40mm on average.
label | 8c77d6f9-e978-5502-9cfb-93b61c0ab921 |  | note | • There is not >75mm height variation along a 3m straight line along the finish surface.
label | 7f07dbf8-d06b-501a-9ee1-5bae46e0117d |  | note | • Joints are free from debris before grouting.
label | 42a5428a-b11c-5153-aa11-6bf71eca5cbf |  | note | Freq - Each lot
label | 2c8ce4b2-e440-50bb-8faf-09604ce6ec2f |  | note | Key - I
label | d02ab3a3-83cc-5bbb-97f7-fd1aa305fc0c |  | note | Resp - SE
date | 2f7dd1d8-eb5f-5f61-8b48-0db7bd7bc70c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.9 - Placing Rock Beaching – Type 5
label | a0e19b2a-a566-5ffa-8f83-c06fd21bf848 |  | note | Ref docs - VR713.05
label | c3076fe2-5da5-5911-8a48-0fa9b2892ac2 |  | note | Acceptance criteria - Type 5 Beaching shall be placed such that:
label | 01e0fdf3-2481-54b6-88e7-d8c6803cf6d5 |  | note | • There is not >75mm height variation along a 3m straight line along the finish surface.
label | 61db753c-1c3c-5353-a4b8-0df44d6cb7bf |  | note | • Rocks are tightly interlocked, and voids are sealed with smaller rock for stability and sufficient water flow.
label | d7abf4c0-b2e9-5ef1-8ce6-a2e588865c29 |  | note | Freq - Each lot
label | 84973cb3-8140-58dc-ab8a-84af882ff56a |  | note | Key - I
label | b6c22d95-85c1-5421-8de9-87250f5f051c |  | note | Resp - SE
date | 83ace9d6-4beb-5fb3-bcc2-deab354f29ff |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.10 - Grouting – Type 2
label | 83ba6197-09a2-54ad-a674-3de775bbc3c8 |  | note | Ref docs - VR713.06
label | b941d789-500b-54b9-bf62-02e0f982b339 |  | note | Acceptance criteria - Type 2 Beaching grouting shall be:
label | dc7a2054-541e-5864-ac43-85dcf157b396 |  | note | • With mortar one part Portland and 3 parts Sand by volume and thoroughly mixed with water.
label | 952fedf9-fade-5075-a772-c10d953898f3 |  | note | • When air temperature >5°C and kept moist for 3 days.
label | 88131b10-ca86-5a68-920a-9dd8f3b44b2b |  | note | • Such that joints are neatly finished and final mortar shall not be within 10mm of finished rock surface.
label | b3df3d8a-c63d-525d-ae73-012078b3592e |  | note | • Final grouting ensures mortar is firmly tamped into joints to fill the joints 20mm below general top of beaching.
label | c02592fb-888c-5c5a-a164-4f014892e473 |  | note | Freq - Each lot
label | 02e9723b-d01e-5b33-b397-24b3a3c47e14 |  | note | Key - I
label | ab132ac7-e1a9-51cd-8425-592d9628ddf8 |  | note | Resp - SE
label | 9474709c-1b28-5b6f-990c-4951e07ed150 |  | note | Remarks/record - Mortar Mix Product Detail
label | 73b03536-0b22-5906-988b-8967144a02a4 |  | note | • Grout Product Detail
date | 6ce7c686-bf17-576b-8950-18516222e2db |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.11 - Toe Walls – Type 1
label | b2c2887d-ca95-5ab1-bc5d-356f9b8ffeef |  | note | Ref docs - VR713.07 IFC design
label | 43bab7bf-23e0-5368-9bc1-3da81ad8a75e |  | note | Acceptance criteria - Type 1 Beaching Toe Walls shall be:
label | d4cd56f8-660f-58f2-990a-ee51c663ddd4 |  | note | • Constructed where rock beaching slope >1:5 and be 600mm wide x 600mm deep.
label | 09a89515-9172-5744-8654-2c201c141d30 |  | note | • Constructed 300mm wide x 400mm deep at front face and reinforced with L8TM trench mesh top and bottom.
label | b806c852-ed03-58bc-bb3b-a78e291aa0f9 |  | note | • Lined with geotextiles and filled with hand packed rock with larger voids filled with smaller stones.
label | c2557b70-5b43-548d-a729-826e2d4b2e2d |  | note | Freq - Each lot
label | 20b1ce25-be90-5757-aa9b-f2b686e8d9c3 |  | note | Key - I
label | ee2e3e0e-f541-54bd-946f-4d63b005b59e |  | note | Resp - SE
label | a8225b38-3e3c-54f8-8850-b3cb4f80911d |  | note | Remarks/record - Dockets
date | 6779d3ca-46ab-5dc1-9d1f-6aa1ca0b10fa |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.12 - Perimeter Walls – Type 2
label | 86bd5a03-061e-5d8b-bb10-b96b181711a2 |  | note | Ref docs - VR713.07 VR703.11
label | 815e3f12-96f7-5867-9680-07a5d5b35592 |  | note | Acceptance criteria - Type 2 Beaching Concrete Perimeter Walls shall be:
label | 45943265-d13d-5c8c-a013-9c5fbc312152 |  | note | • Constructed around exposed edges of beaching.
label | 54d39f27-e8a4-5811-b4e4-b9c1a1622c58 |  | note | • N20 strength grade.
label | 71ec2964-1a8f-5bfe-a00b-7b01cbc41032 |  | note | Freq - Each lot
label | 0f28ba94-b3ea-5bff-a536-ad05c82b3fd8 |  | note | Key - I
label | 81320b2d-a2fe-506e-96ba-7508edd86338 |  | note | Resp - SE
label | 19244ce7-d9b0-5a39-9965-63a5441dd4ee |  | note | Remarks/record - Dockets
date | 92404713-8a23-5a26-8601-fc0e18f74a75 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.13 - Drainage
label | e5a291ea-12a3-5a9c-be4d-dfc6061c5add |  | note | Ref docs - VR713.08 IFC design
label | dbcdfb22-80d1-5133-9ece-b58b0616cfe3 |  | note | Acceptance criteria - Where specified or shown on the design shall be:
label | 8f4e3b28-e591-592e-b259-a6a52add07df |  | note | • 100mm diameter PVC pipe laid down the batter in a trench beneath the bedding to discharge immediately above the top of the toe wall.
label | 0215c77b-62f0-59d9-b8a1-5b6c995c56ee |  | note | • The pipe securely bedded within the backfilled compacted crushed rock or natural gravel trench.
label | aa9d2854-2c47-59b1-a279-1bfff0babbc7 |  | note | • Weepholes consisting of 75 mm diameter PVC pipes placed through the beaching at 2 m centres immediately above the top of the concrete toe wall and cut off flush with the face of beaching.
label | cf181490-3c83-5f7a-80f1-7cb5c41a9425 |  | note | Freq - Each lot
label | a8dc5346-36a3-5ec5-a71c-39506d9d2a05 |  | note | Key - I
label | 5de7886c-7008-59a3-88e4-30c8670cd13b |  | note | Resp - SE
date | ae542ec1-d621-54cc-901c-615ce2b8585e |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Completion
checkpoint-status |  |  | checkpoint | 3.1 - Cleaning
label | 5acbd415-7417-593e-a89e-f07902512163 |  | note | Ref docs - VR713.09
label | 2bc6d489-692a-5c93-9f7c-675e4ec29a2f |  | note | Acceptance criteria - Post-completion, beaching shall be cleaned, and foreign material and discolouration removed from surface.
label | 2d8980e8-7c3b-5d75-9b10-ec4b8f011973 |  | note | Freq - Each lot
label | 934cbb18-47ae-5320-a290-5d6f4f7cee5a |  | note | Key - I
label | 7357a87d-a9b1-5373-95a2-b099bdddc104 |  | note | Resp - SE
date | 9fd521ee-4843-548b-8f06-3ed6a5870e4d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Conformity with drawings
label | 4ff32819-edf4-50d0-abf0-e9058fb07338 |  | note | Ref docs - VR713.02
label | 47aee2c1-7a6b-5727-8606-0ee5f833025a |  | note | Acceptance criteria - Beaching finished surface conforms to the levels, lines, and grades as shown in IFC design or specified.
label | f4b65a0d-b2f0-5bc6-a221-e7ea16c321d3 |  | note | • As-built survey completed.
label | 38c3f6f6-fbd1-50b6-b8ea-465ac4573bbd |  | note | Freq - Each lot
label | adf29bf0-7cca-56cf-93ab-3d1f8e7e4f7d |  | note | Key - R
label | 70b8a114-ab28-5daa-bcf5-c51227c3b9bf |  | note | Resp - SE
label | 97151bbe-abf6-5f34-99af-966da6c16563 |  | note | Remarks/record - As-built Survey
date | 1419f1bb-a097-5c34-8da7-da6380f6160f |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Work Lot Close out
checkpoint-status |  |  | checkpoint | 4.1 - Product Non-Conformance
label | 24c55196-1d09-5d11-a862-788b48746571 |  | note | Ref docs - CQMP
label | 17118027-966c-598c-b4ba-db1b4ce2e62e |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 87f668f1-9b8e-5175-bce7-b226284b774e |  | note | Freq - Each lot
label | c451ad61-d0c4-59b0-b0b1-20956470f329 |  | note | Key - R
label | 3874b381-66dd-597b-9e76-beb9af4b421d |  | note | Resp - SE
label | b3243a0f-34f7-581b-b9cc-233b4bd0f7bb |  | note | Remarks/record -
text | d7a7aa05-ddb6-5152-a98d-6e1f2447affe |  | textbox | • NCR No
date | b2bfce6f-06d1-58e1-9241-8569c8dde05a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
label | 56ee4264-90d5-5fe3-8e99-e86433058665 |  | note | Ref docs - CQMP Lot Records
label | 5e196f1a-a1a7-53a5-baee-3b42c1d8daba |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 9dc761f7-9253-5076-a5e3-b58313b5f097 |  | note | Freq - Each lot
label | 1eb970ac-c92f-5d6d-a882-ee669d1c6fec |  | note | Key - R
label | e6e3e7c6-eae0-5d39-97a1-30a7515264e7 |  | note | Resp - SE
label | 788e9860-796d-56fe-a6c2-696062e33bc4 |  | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
date | f884d328-3aa1-5ce6-9806-a1fa6caa896e |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A REV01 | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A REV01 | 7c815c14-dd38-4c3e-885f-4d0e050c79e6
checkpoint-group |  |  | section | ITP Details
checkpoint-status |  |  | checkpoint | ITP Details
label | 4899ce53-c870-5fbe-aba0-fbc8647ecbe3 |  | note | ITP No. 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A
label | 74386f2a-0e78-52c9-a725-726f91b15b15 |  | note | Rev No. 01
label | 9f6ba596-8d3d-5477-a677-ce80a731e6d7 |  | note | Date of Issue 01/11/2023
label | b05f62c2-84ba-586c-ab0a-9f5cdd7384b7 |  | note | ITP Type - Revised
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Site excavation and Material classification and supply (Site only)
label | c55496ea-53fd-5c32-90ed-3e941dc6ff68 |  | note | Ref docs - VR Clause 204.06 (c), 204.04 (b)
label | 8d5cd10f-6bc3-55f1-9b56-3b2a58dedf52 |  | note | Acceptance criteria - For site-won material: Prior to commencing excavation in any area and during excavation work, the Surveillance Officer and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
label | 68172d3f-14e1-5015-b5d3-aebf0f8c6921 |  | note | ○ Material classified as silt prior to compaction shall not be used as Type A material without stabilisation to the satisfaction of the Surveillance Officer.
label | 95312752-fd59-5177-97cc-8e2155c957ff |  | note | Freq - Each Lot
label | e66e8784-3ba2-5e89-a187-c4498a844e62 |  | note | Key - H
label | 499f7f2e-ad9a-5a49-871f-d3e324b1f758 |  | note | Resp - SE
label | bd7ac52f-5caf-58ba-ae7c-e32f1ea58bdb |  | note | SI Key - H
label | 7a017d04-486c-5cab-b1b3-60daca10601b |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 8e8dfc60-abed-57f0-940b-39499fca5d30 |  | button | Compliance Certificates/ Test Reports | Yes,No
button | 9976401f-715c-5e10-b5ac-90902b4eccc7 |  | button | NATA Test Reports: CBR, Swell, Permeability, Grading, PI | Yes,No
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Set out
checkpoint-status |  |  | checkpoint | 2.1 - Set out and survey land appropriately for intended works.
label | b453ce4b-5e3f-53af-b716-cfbc1ad5aad5 |  | note | Ref docs - VR Clause 204.03 (a), VR Clause 204.14 Table 204.142
label | 485ecb09-e2f9-5418-9adc-0a5865b956c6 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per design IFC drawings. Lot size to be one day's production or 5,000 m2, whichever is the lesser.
button | a6b1b539-962e-580c-ade7-263e28bb8311 |  | button | Has all of the above been completed per standard? | Yes,N/A
label | e4d25c49-d015-57ab-8a44-9f127d524482 |  | note | Freq - Each lot
label | fbba7f81-4305-5d82-9428-fde4635d7b73 |  | note | Key - R
label | a4135598-bd83-583f-b3d1-c7d959d2709a |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Placement of Type A Material
checkpoint-status |  |  | checkpoint | 3.1 - Underlying Layer Conformance
label | de53b4d7-42b2-5e6b-a835-c495f3eaa7d5 |  | note | Ref docs - VR Clause 204.10(b) 204.06
label | 2e71621e-01d4-5aa0-8736-08e99a87d343 |  | note | Acceptance criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. Any unstable areas detected by test rolling shall be rectified.
label | c958215b-a34f-53ab-ad01-6ff13f3575e3 |  | note | ○ Where ground water or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | 29939a0a-e62b-582f-add8-c783a089a0d8 |  | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | c517dd61-af63-543a-9002-fe5e697a2a84 |  | note | ○ The Contractor shall not commence playing any fill on the prepared areas until the area has been reviewed by the Superintendent.
button | e6ff0a67-45c3-56f7-98d7-ad1befb5574c |  | button | Approval to proceed granted? | Yes,No
label | a7727933-9ffe-5ce3-8386-aeef7a1d459d |  | note | Freq - Each lot
label | 323aa496-0845-5cfa-8dc4-118c81a8a12e |  | note | Key - H
label | fbae6f05-6144-5ebf-b2b6-c6a603eca7f7 |  | note | Resp - SE
label | ee9017cf-507c-5af6-9481-9338b808573f |  | note | SI Key - H
label | e93ff2ea-71db-5c3b-a386-8e37c1cec407 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
text | 7616017a-f552-548c-814b-651ffa78f71d |  | textbox | Ref
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Placing of Geotextiles (If applicable)
label | 517683b8-140c-515b-9dc4-c2eb651618b6 |  | note | Ref docs - VR Clause 210.05 IFC Drawing
label | 6c528777-71db-5fce-9572-166fec6941b0 |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval from the relevant Surveillance Officer.
label | 9026adc5-7043-53c1-b6b0-b6506991f6d4 |  | note | ○ Geotextile shall be placed to the limits as shown on IFC Drawings without punctures or tears. If these occur, they shall be rectified, or the entire roll of geotextile replaced prior to covering.
label | ca6e2599-2c17-501b-a898-03d217a165f6 |  | note | ○ Geotextiles in subsurface drains shall be placed to conform to the approximate shape of the excavation and fully envelop the drainage material.
label | b34f22b9-fb7e-5000-834b-461b8854a4d4 |  | note | ○ All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
label | 9071ce16-e3e9-5c7d-a8be-f4e2b203975d |  | note | Freq - Each lot
label | 860492a3-a25e-546f-8519-8057fa576f41 |  | note | Key - H
label | 8d5ca5ef-72a3-513b-b944-9ad78164baa5 |  | note | Resp - SE
label | 44019ccd-f545-53e7-9f2b-bc49618d7519 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Placing of Fill
label | 491730d0-800b-5504-870b-1da5d5e32186 |  | note | Ref docs - VR Clause 204.10(d)
label | d14d52d0-da24-5e4a-b30f-353b2e4ddadd |  | note | Acceptance criteria - Spread and compact in uniform layers not exceeding a compacted thickness of 200 mm.
label | f9d6b7df-4775-5d8b-9080-297cb7deab3d |  | note | ○ Visual Inspection for maximum particle dimension.
label | 34b5672f-c9d8-5d88-a8cc-f2067f7a2446 |  | note | ○ Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4H:1V, benches shall be progressively cut
label | e879b056-4aa9-5f35-a05b-5370c7cc415c |  | note | Freq - Each lot
label | 573a220e-e621-5d68-a508-1852c38b3344 |  | note | Key - R
label | 97cc3f8d-9844-587e-b1c7-68f7c8993793 |  | note | Resp - SE
label | c306390a-ee5d-5b38-86cd-a4c152f038e0 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 71a6fdcd-cea2-563f-b52e-4d060f7f0029 |  | button | Verification Records: Layer Thickness at least every three layers | Yes,No
checkpoint-status |  |  | checkpoint | 3.4 - Keyed Fill Layers
label | 844cfb8b-0fd3-537c-bfa3-e08ec72b6405 |  | note | Ref docs - VR Clause 204.10(d) Construction Work Pack
label | 624850d0-be2c-54fb-a047-7dccfaa0a41a |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
label | ce5be331-73d3-550b-a5bb-4be0a605bed3 |  | note | Freq - Each lot
label | 28847810-fc67-5410-8113-25b736b308e6 |  | note | Key - R
label | 76c2b7dc-3689-5b8f-80fd-4a2d97ac6d8b |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.5 - Test Roll of Type A fill layer.
label | 5b680f9d-00ec-5e49-89ba-c0c84e67682c |  | note | Ref docs - VR Clause 204.12 173.03 Construction Work Pack (Test roll procedure in specification 173.03)
label | 2a81a371-0149-59be-b302-5e41b0d20cf6 |  | note | Acceptance criteria - Each layer should be test rolled immediately following completion of compaction but if test rolling is carried out at a later time the surface of the layer shall be watered and given a minimum of three passes with the test roller prior to commencement of test rolling.
label | c3c95374-84e0-5591-9202-7edf12b25977 |  | note | ○ Surface shall withstand test rolling without visible deformation or springing.
label | 7d736c5a-6fd1-59f8-9f6d-c0b8833a6ed1 |  | note | Freq - Each lot
label | 91f3743a-5aa2-5a36-85ca-61069548c53d |  | note | Key - H
label | d5024776-0401-586b-81a0-0ddefd057ed7 |  | note | Resp - SE
label | 550d1ab2-2499-5a8c-b0ec-398164519437 |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Fill at Structures (if applicable)
label | 4a15c94e-89d5-5102-8dd4-0eb2c8df9785 |  | note | Ref docs - VR Clause 204.11 (b) Table 204.111 Construction Work Pack
label | f78852ab-8bb0-5afe-9fcb-dc850bbd6249 |  | note | Acceptance criteria - No Fill to be placed within 3 m of structure until the foundation is reviewed by the relevant Surveillance Officer.
label | 7b6c43d6-f0e6-5d85-9ab5-58bac61d2c0b |  | note | ○ Culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
label | bb538ba0-e24b-5fb3-a439-5ecc164f2744 |  | note | Freq - Each Lot
label | 9c84ded7-3dac-5e9f-9478-c07fdac94353 |  | note | Key - H
label | be3a3b5f-eb01-505f-b982-4c9a1f3bbaa9 |  | note | Resp - SE
label | e2f3690f-effc-5c3d-97a4-bd03f683676d |  | note | SI Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Fill within 300 mm of structures
label | 55d9a68c-9377-5729-9f65-ce505be01654 |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | 92b37372-2f5d-58a5-9cc4-f46f0abe7e62 |  | note | Acceptance criteria - Use of geo-composite drainage material or Permeable Fill in accordance with 204.04(f).
label | 52a35d68-0503-5be6-a89e-dd56807c2f77 |  | note | ○ Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111.
label | b7991812-4084-5cf5-bb9d-ad72e5a3e014 |  | note | ○ The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
label | 2005eb48-7c23-53f3-97f3-f62bad10a64e |  | note | Freq - Each Lot
label | 8d5d077c-19a8-563b-a508-596c2627be43 |  | note | Key - R
label | 6a27d4e2-8cf1-542c-aff6-b84704b2598a |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.8 - Fill Material against Concrete Structures
label | fb127a0e-ee1e-5a99-bf4a-66c86797149d |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | b86bb90d-0172-5e7a-90c8-6382aafb469f |  | note | Acceptance criteria - No material shall be placed against concrete within 14 days of casting.
button | 1ea63c1a-a90b-5b30-925f-d818ee966b66 |  | button | Has all of the above been completed per standard? | Yes,N/A
label | ddbaf68f-f205-553b-ab30-8f739d19a8df |  | note | Freq - Each Lot
label | d89df0a5-a2a9-52a6-8b82-491c94b6367b |  | note | Key - R
label | 59c05abb-2e3c-5683-90e7-283cdd44b205 |  | note | Resp - SE
label | a469b20e-3ea3-5546-bf30-ced93e4afed9 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | c9fb92f7-e0e1-50b8-83f5-2503cd3e82fe |  | button | Concrete Pour Recorded | Yes,No
button | 7cf77dd9-5130-5523-b1eb-f7ad6d466f0c |  | button | NATA Compressive Strength | Yes,No
checkpoint-group |  |  | section | 4.0 Geotechnical Testing
checkpoint-status |  |  | checkpoint | 4.1 - CBR / Swell
label | e4e2bb80-bb5b-5839-9927-9d757372f611 |  | note | Ref docs - VR Clause Table 204.041, 204.141 Table PS3020.051
label | 2c6cecff-e831-592d-b071-c3a039666011 |  | note | Acceptance criteria - Unless otherwise specified:
label | 384cf521-0d80-5d30-b217-20fa4948015f |  | note | ○ CBR: ≥ 6%, Swell: ≤ 1.5% (1.0% for Verge Material).
label | 64fb6347-cf20-55f6-a48c-ee1e76e2159b |  | note | ○ Initial testing frequency: 1 Lot test to determine Assigned CBR and swell.
label | 097bc6ab-f57b-5bb2-897f-b7f82051fda3 |  | note | ○ Continued acceptance of the material will be assessed against the Assigned CBR and percentage swell values of a single CBR and single percentage swell test.
label | 5a532c9c-98d6-56d1-885b-20e0e6608e3b |  | note | ○ However, if the material fails single CBR, swell testing then another assigned CBR to be conducted.
button | fdb0b4b2-8f1b-598f-a526-942a4088dcc3 |  | button | Have the ideal results been achieved? | Yes,No
label | d55c4578-9cf9-52bf-81a9-7f386f459d94 |  | note | Freq - Each Lot
label | 0ca1eaff-cba9-5df0-9801-674d53303fc5 |  | note | Key - R
label | f0a79d01-b9fc-5ee6-8c9a-42f334ea1ef4 |  | note | Resp - SE
label | 37b70c7c-d602-56fb-896c-8f38c1ad7d2d |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | bfde03e9-d161-5c20-9b9c-5d98df25dfba |  | button | NATA Test Report: Assigned CBR, Swell | Yes,N/A
button | 9dd004d9-eb2c-59b0-9569-bdf80144e3b9 |  | button | NATA Test Report: Single CBR, Swell | Yes,No
checkpoint-status |  |  | checkpoint | 4.2 - Post Compaction Grading
label | c04d6b9a-291a-569e-b9c0-dde17178aab1 |  | note | Ref docs - VR Clause Table 204.041
label | 6bf075e7-48aa-5650-9b3b-57906bee5db6 |  | note | Acceptance criteria - Sieve 75.0 mm – 100% passing by mass, Sieve 4.75 mm – 40 - 80% passing by mass, Sieve 0.075 mm – 10 - 40% passing by mass.
label | 86ffd096-ffcd-5d57-8511-2c2e1f91377e |  | note | ○ Initial testing frequency: 1 test for each lot tested for compaction until 3 consecutive lots achieve specified requirements.
button | 233e309a-7324-5979-ad22-1f2f97486b10 |  | button | Have the ideal results been achieved? | Yes,No
label | 2edf02e2-f682-5830-9d40-e546c1fe024e |  | note | Freq - Each Lot
label | 0cdb54af-aebf-53e3-a569-cc42d8dfc039 |  | note | Key - R
label | 80c0462d-e94a-57cf-93fa-7aacac5f9aa8 |  | note | Resp - SE
label | 6e36a9c1-0550-5f01-bf74-623432e0d184 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | da81bb8f-b912-5f83-a33f-aba39ccc98e5 |  | button | NATA Test Report: Grading | Yes,No
button | 4f921d43-819a-5adf-b701-fa5a0b308fd9 |  | button | Visual Inspections for Maximum Particle Dimension | Yes,No
checkpoint-status |  |  | checkpoint | 4.3 - Plasticity Index
label | 02a5c7d3-7e98-5822-90e6-2185ae28e484 |  | note | Ref docs - VR Clause Table 204.041
label | cb67eb90-f1c3-5da0-bb27-c9c51dd35947 |  | note | Acceptance criteria - PI: 6 - 25, PI x % Passing 0.425mm: 1000 Max.
label | 6565bd8d-71a6-5b42-9b13-2bf2f5ebfe8b |  | note | ○ Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
button | d6e43935-a479-52ff-a86f-d7bf04fe3ac8 |  | button | Have the ideal results been achieved? | Yes,No
label | dc8abee3-e319-5863-92f0-9b5d640eee60 |  | note | Freq - Each Lot
label | f2eb5c2a-3265-5c75-9654-d8efaf836d95 |  | note | Key - R
label | 6cad01b9-3fd0-5149-a365-6029b0cfddd8 |  | note | Resp - SE
label | b2d67e5b-4bca-5b58-9c11-d9a9eb9a99a4 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 9fc6d8de-851e-5a65-9a92-64e224c3eb5f |  | button | NATA Test Report: Atterberg Limits | Yes,No
checkpoint-status |  |  | checkpoint | 4.4 - Permeability (Capping & Verge Material only)
label | 4361c771-3c87-5971-b017-a4a652362271 |  | note | Ref docs - VR Clause Table 204.041
label | f506c5a9-0c59-5459-8f36-12a177cfae2a |  | note | Acceptance criteria - Permeability: 5E-9 m/s
label | 381402e1-8fa5-548c-a4b7-66e0ba13e56b |  | note | ○ Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
button | 2fb8427f-ef46-51d2-a393-c2c6eb628e98 |  | button | Have the ideal results been achieved? | Yes,No
label | 37b2dc22-1f73-56d2-8edd-793b3d261b69 |  | note | Freq - Each Lot
label | 0b355fba-ab49-5c73-a437-cccba626610a |  | note | Key - R
label | 175826c1-67be-5800-9205-f316537b4f34 |  | note | Resp - SE
label | 4cbd428e-f765-5f1c-a9a7-cda1c5024323 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | bd5abf8d-9e1a-573d-a1e4-17aa3abb461d |  | button | NATA Test Report: Permeability | Yes,No
checkpoint-status |  |  | checkpoint | 4.5 - Compaction Testing
label | 3bb93d5c-4278-55a0-ade5-e34cd4815c1e |  | note | Ref docs - VR Clause Table 204.131, 173.04(d)
label | 4394a7a6-2843-5d6d-867c-b72a35adf1b3 |  | note | Acceptance criteria - Minimum Characteristic Value of Density Ratio: 99% (Scale A), 98% (Scale B).
label | 66367898-9ad9-5ed5-b415-135a9849fdd0 |  | note | ○ For small areas (<500 m2): Mean value of density ratio: 101% (Scale A), 100% (Scale B).
label | ed9a9627-345b-5ac7-911d-e20e7ad3ddf4 |  | note | ○ Initial testing frequency: Each lot until 3 consecutive lots meet compaction requirements.
button | 036fea84-e1bb-5064-a34b-cada55aff1c1 |  | button | Have the ideal results been achieved? | Yes,No
label | 5b1169f9-6c3f-5add-b828-febcbce4bd51 |  | note | Freq - Each Lot
label | 51cc4b1d-6809-5c90-9e96-38e7532d9b7d |  | note | Key - R
label | 2bb7b8f9-6fef-50c4-ae19-b52333a8e265 |  | note | Resp - SE
label | 949dc06a-19a3-501d-93bf-3d0c39594601 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 0517d04e-2b24-511c-897b-aeb529a4f49f |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
checkpoint-status |  |  | checkpoint | 4.6 - Reduced Frequency of Testing
label | 18b16e37-f576-500f-91e5-2bbf125518ae |  | note | Ref docs - VR Clause 204.14 – Table 204.141
label | 30b35df1-b429-557e-8efb-033d1fd5bef9 |  | note | Acceptance criteria - Unless otherwise specified:
label | 75a9f66d-a45d-50dd-a5f3-839975ca4e78 |  | note | ○ Material properties (Scale A): Test at the initial testing frequency, if compliant, seek approval from Surveillance Officer for minimum testing frequency.
label | d2c37334-b878-5436-abf5-411b4b28c727 |  | note | ○ Material Properties (Scale A): CBR/Swell: 1 test every 2 lots. Grading: 1 Test for every 2nd lot PI: 1 test every 4 lots
label | 57587ab3-1fbf-5157-98b9-6e871d7a7c61 |  | note | ○ Permeability: 1 test every 4 lots
label | 3dc7dc17-3997-564a-bd25-1717d74f1053 |  | note | ○ Material properties (Scale B): Test initial lot and no further testing required until changes in physical property/material source are observed.
label | 33ac273f-7fbd-597c-8cc4-ceee6094d8f8 |  | note | ○ Compaction / Moisture Content:
label | 0c6a668f-72eb-5b9b-84b3-3c8c340808a9 |  | note | ○ Reduced frequency: Test every 2nd lot.
button | 54ab2914-e902-5a8e-93b3-073829ebd1f3 |  | button | Have the ideal results been achieved? | Yes,No
label | b484ce44-83b6-5fe2-8a13-cf501fce6726 |  | note | Freq - Each Lot
label | dbc0ad55-5325-5778-8ac1-b44f1aa701be |  | note | Key - R
label | 7f058a0e-e373-5a07-a95d-5927fd68e41b |  | note | Resp - SE
label | 3fe40537-ccc6-5183-b500-431a045e03cf |  | note | SI Key - R
label | 0559c0d8-8056-5f7c-9ad2-34fcc821cfca |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 94ab9934-0e0c-5f5c-9583-03e30d679de3 |  | button | NATA Test Reports: CBR / Swell Grading PI (Atterberg Limits) Permeability Compaction | Yes,No
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - Conformity with Drawings
label | 625cbc8f-1289-5cfb-ac58-a5023f4822ed |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | 2791355a-cc34-5ff3-b9e0-8ca73c1bc53c |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements.
label | bddca4c4-7de7-5378-994c-0e01957c64e5 |  | note | ○ Scale A: mean +5 / -15 mm Max S 12 mm.
label | b4765b0c-7925-5180-a7da-b710a298cba1 |  | note | ○ Scale B: mean +5 / -25 mm Max S 15 mm.
label | 3eb74f90-1dd6-5a22-ae18-f68634536a7b |  | note | ○ Alignment: ±50 mm.
label | 28b307ef-dcf9-5fa6-b27d-35a7e96b0609 |  | note | ○ Scale C - random levelling not required, no point > +10 / - 30 mm.
button | ea8d827a-6e8f-5fbc-b7f3-3955c19156e1 |  | button | Does the final product conform to the above criterial? | Yes,No
label | bb074275-82c8-596a-98f7-bdc8a5cdfda9 |  | note | Freq - Each Lot
label | 5a4ce6ed-fe29-5100-899f-5fef431f7d54 |  | note | Key - R
label | 2342d557-944e-5e6f-8f8a-fdc5cbb21645 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 9573e644-2c84-5796-bb0e-d0ae9f888e40 |  | note | Ref docs - VR Clause 204.15
label | 84c83fc4-3b37-5db4-96cc-3c368767e759 |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
label | acde3ba7-960a-55cb-8260-1b9ebfb50eba |  | note | ○ Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | fbbfb24c-b075-56ec-8f42-80e04337c89d |  | button | Does the final product conform to the above criterial? | Yes,No
label | fa67be75-3bec-522d-bf9f-810942ca5262 |  | note | Freq - Each Lot
label | 57573743-0620-5b0f-a432-e53eec370f66 |  | note | Key - R
label | 3d72a598-6180-50af-825b-d4a4fad49ee7 |  | note | Resp - SE
checkpoint-group |  |  | section | 6.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 6.1 - Test Reports
label | ac51daff-1b14-5c19-9c75-cf30f09f6da2 |  | note | Ref docs - VicRoads Specifications
label | 8400ef24-63dc-5394-9210-0696a7ffb93b |  | note | Acceptance criteria - All Test reports received and Reviewed
label | c03e5b29-c83f-593b-8e62-aa205c44f072 |  | note | Freq - Each Lot
label | bc1e1520-00be-5cfa-ba1d-0b8b2b6425fc |  | note | Key - R
label | 8c1ab3aa-2579-524d-b969-c0500f4e4af8 |  | note | Resp - SE
label | 083af6a6-3b65-5bc0-95c6-21ffe0fa3253 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | d35f31fa-2596-5eb6-8651-db3126ced243 |  | button | NATA Endorsed Test Reports | Yes,No
checkpoint-status |  |  | checkpoint | 6.2 - Product Non-Conformance
label | 8aa81ef9-fb99-53bb-9e4b-6c5655e7ea92 |  | note | Ref docs - CQMP
label | 4e485263-54e8-5db5-b104-bd64e1e7aaa8 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 09e44aec-113e-54e4-a5de-bc16de19f09a |  | note | Freq - Each Lot
label | 43847dff-4992-542c-90e2-70a02fe5d2c0 |  | note | Key - R
label | 1804ba8c-f424-544a-a7ef-c63d6eab25a5 |  | note | Resp - SE
label | e36df632-a082-5914-8a9f-3984d64d2907 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 7ade5e9b-3bf0-531c-a97d-b302a6a3e48b |  | button | NCR reports | Yes,No
checkpoint-status |  |  | checkpoint | 6.3 - Quality Representative to check the above criteria and records to confirm
label | fe374904-5a69-57e2-b370-d4f56b72facc |  | note | Ref docs - CQMP Lot Records
label | c93199b2-2b4b-5eae-af20-bff84ae38688 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 2c557fae-5377-5383-800b-41f3c53699bb |  | note | Freq - Each Lot
label | bb021243-1cee-5860-902c-574fb7c16984 |  | note | Key - R
label | c129bc26-8282-5237-b661-bf96fa0aceb9 |  | note | Resp - SE
label | 189897c5-c529-53a0-91d8-014a5d7ada9c |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0027 Structural Concrete | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0027 Structural Concrete | 95261b41-8ccc-4d88-bd4b-a56a53524af0
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Concrete Grade, Exposure Classification and Cover Requirement
label | a6a748df-23d8-542b-a6f7-02adb87f0d0d |  | note | Ref docs - VR 610.04 AS5100.5
label | 2f08f954-3796-54c1-b5f4-6505d8b5238e |  | note | Acceptance criteria - The concrete grade, exposure classification and cover requirement of the structural element is confirmed and recorded below.
text | 9ab325cc-ca3e-5627-b924-6bc37a1ab362 |  | textbox | Concrete Grade: |  | VR /
text | 179ea50d-3719-5c30-8d1f-8f2e1c4193b9 |  | textbox | Exposure Classification:
text | 0bb31706-7d05-566c-a1e8-9a2415d0af8d |  | textbox | Cover Requirement: |  |  | mm
label | c15492d4-5dc3-5e3f-8add-46b39766759a |  | note | Freq - Prior to start of Works
label | 6007c722-6d4c-52f4-9f6c-a793a462238f |  | note | Key - H
label | a8b30873-5b62-541f-96e8-3bac9ef92aff |  | note | Resp - SE
date | 589e497a-7c27-5673-bfd4-caa62dc1f1a4 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 7bfdf40f-c034-5597-8c29-b6a571fe08d9 |  | button | Lot map | Yes,No,N/A
date | d7a0cd9b-e0fc-5e73-8a9e-ea6ac5eaf16a |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | f33aba10-d067-5bef-bfad-5321f9e3a59f |  | button | Environmental permit | Yes,No,N/A
date | ca99271a-34cd-55b1-844d-bad4d15f1f94 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Concrete mix design approval
label | fbaa2e36-e156-5553-b90c-ef9a74c25796 |  | note | Ref docs - VR 610.07 AS 1379
label | c6d8e10e-c15a-5c4e-b45a-1d9d01dd6159 |  | note | Acceptance criteria - The concrete mix design for the specified grade has been approved by the Superintendent.
label | 5d15dbd8-1811-5d40-bbe1-d0d9457ce32a |  | note | ○ The concrete mix design includes details on the cementitious material used in the Works along with CMRS registration number and test certificates endorsed by a AS ISO/IEC 17025 accredited laboratory.
label | 7a5e68a8-da6c-505c-a410-1952cdff8302 |  | note | Freq - Prior to start of Works
label | 7b12bad8-5f9f-55c2-a8b3-afdccea9ee65 |  | note | Key - H
label | 6eec47c7-98f4-5bf6-a405-9f4dedb8547d |  | note | Resp - SE
label | 5ca49461-b423-572a-aa74-37bb820c189a |  | note | SI Key - H
text | 73dc57e8-5d6c-52f6-8e62-b3a853d53a38 |  | textbox | Remarks/record - TeamBinder Ref No.
date | bc0113b7-9c9a-5498-b6bf-e0a6ec2b0b21 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Approval of procedures
label | 0ed398ed-0d3c-5bdd-9e84-c538ab462a9e |  | note | Ref docs - VR 610.18(a)
label | fa2517e0-fd3b-55ae-b95f-e06a245b0912 |  | note | Acceptance criteria - The WMS, ITP’s and quality control checklists have been reviewed by the Superintendent. These documents shall include:
label | c6adfab9-dacf-51a2-a2fe-503cd24f1e46 |  | note | ○ Conducted toolbox meetings of all concrete construction personnel on all aspects of the WMS, the ITPs, quality control checklist(s) and all specification requirements.
label | 90f3aa7d-a6b8-54f5-b706-92e161daa454 |  | note | ○ A site sampling and testing procedure with minimum frequencies of testing requirements.
label | f23bba4e-aab3-5b6f-9015-df7bb9e72bd5 |  | note | Freq - Prior to start of Works
label | 167c7a52-efe0-5776-b42d-af2186079b13 |  | note | Key - H
label | 0085afc6-9aba-523a-9f4e-737d9b67af7b |  | note | Resp - SE
label | 0000be06-d294-566d-9f54-8fd352a1721e |  | note | SI Key - H
date | c64c1a37-df2a-5a3c-93fc-8d00c817907f |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Curing methodology
label | 8d009214-dc03-5c8b-aea1-10bcdbbd1753 |  | note | Ref docs - VR 610.17(f) VR 610.23
label | 7bdd0838-4a95-5937-a5b0-84f9c980818e |  | note | Acceptance criteria - Full details of the proposed methods of curing, as part of the concrete mix design submission has been reviewed by the Superintendent.
label | 6263ae8d-569a-5c4a-8c8c-8d9c55ef290d |  | note | ○ The curing method also includes any details on evaporative retarding compound and its application procedure including minimum application rates.
label | 81ff78ae-309a-5ff6-924e-fdef189f7b12 |  | note | Freq - Prior to start of works
label | 866e890e-8b40-50fb-9fea-e3e0224ab50d |  | note | Key - H
label | 8771e630-f2e3-5c37-b030-dcda2d49bdea |  | note | Resp - SE
label | e89e36a6-298d-5424-8655-a5861999638a |  | note | SI Key - H
date | 8ceaf6f6-d2cf-5821-a371-c4dc4d937b74 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Setting Out
checkpoint-status |  |  | checkpoint | 2.1 - Setting Out
label | fa506e75-02b4-5745-a860-3c4c720a05e8 |  | note | Ref docs - IFC Drawings
label | ed68cc55-072f-501a-8f24-aa1847f95c78 |  | note | Acceptance criteria - Survey set out as per the IFC drawings.
label | 21a19a19-d6c5-5ff4-bf6f-d92203bd9dd4 |  | note | ○ The concrete will be constructed in accordance with the confirmed line, level, grade and cross-sectional profiles as shown on the drawings.
label | 9b4590d9-3629-5cb0-bcb9-2de8eba838a3 |  | note | ○ The extent of the work has to be clearly pegged and underground servicers have been located.
label | 7dde42da-f52e-526e-a8c3-c5ade90bca95 |  | note | Freq - Each lot
label | 6e9edec1-4fcf-5cda-8764-5b3ce1dd20e1 |  | note | Key - W
label | e512843e-46ed-5c49-9c8f-6abfb6487464 |  | note | Resp - SE
date | 268bb277-c28b-524d-879f-10505c1722b9 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Preliminaries
checkpoint-status |  |  | checkpoint | 3.1 - Substrate preparation
label | 8d3eb8c3-19cb-54c6-adf3-17c5c09ab665 |  | note | Ref docs - VR 610.18(a)
label | 7be534d9-4c94-5041-ba35-7db2d2f028e8 |  | note | Acceptance criteria - Prior to placing concrete any absorbent surfaces including blinding concrete and construction joints shall be thoroughly moistened and excess free water shall be removed.
label | 5eea4970-beef-55b0-b01f-3842aea2e2db |  | note | Freq - Each lot
label | 1daee159-74c4-5527-ac54-34152489a4a5 |  | note | Key - R
label | 729117a5-5010-51c2-907e-5aa862868789 |  | note | Resp - SE
date | 6b04eb49-d743-5f9e-9a8c-d5130fdc48f3 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Construction Joints
label | 1fea6952-334b-50c2-b0fe-4d8866ed3adc |  | note | Ref docs - VR 610.20
label | b8580366-de41-550c-b18f-fb448687efd6 |  | note | Acceptance criteria - Existing concrete, against which new concrete shall be placed, shall be roughened by removing all laitance and sufficient mortar to expose the coarse aggregate to a depth of 3 mm. The roughened surface shall be cleaned of foreign matter, laitance and loose or porous material.
label | e0c88c2e-ba05-54fd-bcbb-40849ffecd2e |  | note | ○ Permission has been gained, through the RFI process, from the Design Engineer to locate construction joints at locations other than shown on the IFC Drawings and approved by the Superintendent.
label | 4d908d2a-d47f-5d03-8f1a-6d361df1d814 |  | note | Freq - Each lot
label | cbc18e5c-e763-51c4-b337-33c53b0ffb66 |  | note | Key - R
label | c28e3a3f-a93a-5e66-85ce-06e18f2b780a |  | note | Resp - SE
date | f69a28d2-c534-592c-bf34-576c863800e2 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Insertions and Greased Joints
label | 47b19435-5554-586f-b1a5-7c5f6ed0f599 |  | note | Ref docs - VR 610.21
label | f8df741f-df30-5eb9-8d01-c8aaff0e224c |  | note | Acceptance criteria - Abutting surfaces of concrete shall be separated by grease or other surface coatings or insertions of bituminous impregnated felt or fibreboard as shown on the drawings, so as to prevent the surfaces from bonding or binding together.
label | 66df9571-370d-50bb-b936-b73ca4d628a4 |  | note | ○ Dowels shall be placed as shown on the drawings and prior to placing the surrounding concrete.
label | 3cc5e870-6946-5646-a39c-eb6bf1a7d6fb |  | note | Freq - Each lot
label | 0c26fe5b-bd78-57bf-a029-1b23deb122fe |  | note | Key - R
label | a37dac44-3146-54d2-a142-fcede1e8e3d4 |  | note | Resp - SE
date | c9e543fc-1a14-5acc-8613-dafeed10a5ae |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.4 - Steel Reinforcement / Embedded Items
label | 0e98feb2-4c25-50d7-82d7-3a1434e7c595 |  | note | Ref docs - VR 611
label | d6a18541-ab03-5485-ba09-8e8f4b8e0f09 |  | note | Acceptance criteria - The evidence that the forms, reinforcement, any stressing materials and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent.
label | b5eb0e4b-088d-5c9b-8a5b-c8f85506521c |  | note | ○ Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel.
label | 5096ebec-b05b-5c5d-827d-81ed69de0e8f |  | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS).
label | 3258fee0-3fd9-51dc-9dbf-341bba3c08c8 |  | note | ○ Evidence of compliance with this clause shall be submitted to the Superintendent within 14 days of award of the Contract.
label | d7fc01a6-8e47-5adc-995e-99918723501a |  | note | Freq - Each lot
label | b06e67e5-755e-5723-935a-6681f98f15c8 |  | note | Key - H
label | 66ee680a-0ebe-593e-83e0-4c2c7525256c |  | note | Resp - SE
label | 0e914781-e422-5e56-9591-32a25fdbae4a |  | note | SI Key - H
date | 701f0abf-d5df-58c9-af3f-d606f6d2eb0a |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Steel reinforcement supports
label | c4145157-5d31-5f46-b853-09f99ee329c8 |  | note | Ref docs - VR 610.26(a)
label | 715c6b38-14cc-5dff-a071-1130c236039a |  | note | Acceptance criteria - Concrete bar chairs and spacers are manufactured from machine mixed concrete and shall have a minimum 28 day concrete compressive strength of 60 MPa when tested in accordance with AS 1012.9. Notwithstanding the requirements of AS/NZS 2425, concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12% when tested in accordance with AS 1012.21.
label | cdfce22b-ac2f-5ed5-b4af-9a7c087fa48f |  | note | ○ A sample consisting of two specimens has been tested for each of compressive strength and VPV, in accordance with the sampling frequency as stated in clause 6.2 of AS/NZS 2425.
label | 0dff63f7-e97b-53df-bca2-027917384524 |  | note | ○ Each concrete bar chair and spacer mix design has been tested for soluble salts (chloride ion and sulphate ion content) in accordance with AS 1012.20.1 on a 12 monthly basis or earlier if the mix design changes to demonstrate compliance with the requirements of clause 610.07(k) for soluble salts.
label | 56f8be12-236c-5ee5-9e67-39fe925eef5c |  | note | Freq - Each lot
label | 6163b323-cd41-59e9-ad1a-238db3725b6b |  | note | Key - H
label | a4311d5b-8002-5312-b4e6-ca77e5bcd07f |  | note | Resp - SE
date | a88b2ac4-1b91-59f2-b625-f5c2efbba696 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Installation of Structural Concrete
checkpoint-status |  |  | checkpoint | 4.1 - Reinforcement Placement
label | cd6e2a4a-4588-5452-9f47-f3d2fba7344b |  | note | Ref docs - VR 610.26(b)
label | 4c3dea55-a434-5355-a5d6-364554a20e0c |  | note | Acceptance criteria - All steel reinforcement is securely held during placing and compacting of the concrete. Steel reinforcement supports comply with AS/NZS 2425. The supports are made of durable materials strong enough to withstand the imposed loads without movement of the steel reinforcement as specified in this section, shall be positively attached to the steel reinforcement, and of such size as to maintain the specified cover.
label | 3a9c1a50-72df-5cf1-b8d2-f3a5dde50d7e |  | note | ○ All steel reinforcement is securely held with the correct tie wire during placing and compacting of the concrete.
label | 169c7760-2ede-561a-be42-f373d7f61eb8 |  | note | ○ The supports shall be positively attached to the steel reinforcement, and of such size as to maintain the specified cover.
label | e4ef248e-29ac-56f0-85c9-54c839b5a15b |  | note | ○ Bar chairs and spacers shall be placed sufficiently close together to ensure that the specified cover is maintained before and during concrete placement, compaction and finishing operations, and to prevent any potential deformation, displacement or crushing of the bar chairs and spacers such that deformation or displacement of the steel reinforcement is also prevented.
label | 97910a03-3816-5d1e-871b-0671bc5fd346 |  | note | Freq - Each Lot
label | 8f90f77d-b31a-5734-9357-e6a6395e8e8f |  | note | Key - H
label | faebe67a-8c62-501d-af03-d16b095f5def |  | note | Resp - SE
date | 3f46d0c9-609b-59b7-90d4-ec7ddc6abee7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Early Age Thermal Cracking / Thermocouplers
label | f1d24801-cfdd-5d08-a9ce-378ca94cf162 |  | note | Ref docs - VR610.22
label | d6f1e085-df9d-5c6d-9bb1-e190831387a9 |  | note | Acceptance criteria - Measures have been taken to control early age thermal cracking of concrete for large and restrained members including but not be limited to crossheads, diaphragms, columns, abutments, footings and pile caps where:
label | 75d4133e-eb27-553b-8dcc-5e9a208422e9 |  | note | (a) the least dimension of a member exceeds 500 mm; or
label | d8c98111-1eb7-57a9-83a9-edc153325857 |  | note | (b) one or more faces of a concrete member is restrained by previously placed hardened concrete or by other external restraints.
label | 14e1a38f-e610-53fe-a4ec-46ad23f91add |  | note | ○ Temperature differential monitoring is installed (unless already undertaken on at least one representative member from each type of large and restrained members, provided that any required control measures to reduce the differential temperature within the specified limits is adopted for the subsequent construction of members of the same type).
label | 7da4bbaf-2471-5c5d-aa95-ff0f810368fb |  | note | Freq - Each Lot
label | c516091a-3b96-5b79-bb70-51adeacb97cf |  | note | Key - H
label | 4d8633b9-9edd-5007-b459-88a9fdad0a10 |  | note | Resp - SE
date | dc104540-6226-5534-8a62-c8d1d1ac30eb |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Pre-pour inspection
label | 8ecb6541-1953-51ce-8832-62b898edbb92 |  | note | Ref docs - VR 610
label | a0758a19-6aed-5601-b8b8-38325c409554 |  | note | Acceptance criteria - Pre pour inspection to be conducted prior to placement of concrete.
label | a6be818e-0b59-5ade-9f4c-52b2eae0fdb0 |  | note | ○ All formworks shall be erected as per specifications and all reinforcements shall be installed as per specifications.
label | 97ee69fb-ac64-5e52-9382-7910be800337 |  | note | ○ The specified minimum concrete cover shall be maintained at tie wire positions. Excess tie wire shall be cut off and the twisted ends of wire ties shall project away from the cover zone.
label | 5567f46d-1fe8-524e-ac1c-2919a9bffa81 |  | note | ○ Contact between carbon steel and galvanised steel reinforcement or carbon steel and stainless-steel reinforcement or other similar metal embedment’s shall not be allowed.
label | 052a8928-a789-50a2-a21d-69d1cc161cd2 |  | note | Freq - Each Lot
label | 35068514-6e66-55a4-a62e-2166127bbb6f |  | note | Key - H
label | e8292509-9871-505d-80ea-0d49e107221f |  | note | Resp - SE
label | 40099d4c-dabb-503f-be16-ecc9e093791a |  | note | SI Key - H
date | 9fa2cfcf-1eca-5247-b0b9-07b7237ed543 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Concrete Batching
label | 37837bd9-9baf-5e35-8cf2-c9f0bb920f8f |  | note | Ref docs - VR 610.14
label | 1c5f7d13-7b8c-565e-a97a-eb794a3e205c |  | note | Acceptance criteria - Alternative supplies of concrete are available from stand by mixing plant(s) capable of being operated immediately in case of breakdown, together with adequate supplies of cementitious material, fine and coarse aggregates for an approved compatible mix(es).
label | 9e0cfdf2-71fe-5060-ab1a-2153a00557f9 |  | note | Freq - Each Lot
label | 6189b705-4e8c-5b4d-ac75-0b848b822151 |  | note | Key - H
label | 1439aaec-d6ae-56eb-a647-bcd1af9ecbfc |  | note | Resp - SE
date | cda01dd3-ea14-584a-94f1-c5bb658e837d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.5 - Placing, compacting and finishing concrete
label | e81fdf59-7e6d-5804-9b9e-1390912c3948 |  | note | Ref docs - VR610.13, VR610.18
label | 672849a7-d435-5f4b-ab8c-02a44c040106 |  | note | Acceptance criteria - Concrete shall not be mixed when the air temperature is lower than 5°C or greater than 35°C.
label | 614db646-dbb5-5b1e-8dac-e87d1d69dc1d |  | note | ○ Discharge Time to be 60 minutes unless mix design is approved by the Superintendent for 90 minutes.
label | 5a8db276-b827-57b5-88c9-b5d2d7eb6dcd |  | note | ○ Concrete shall not be dropped from a height exceeding 2m.
label | 9ec0dbc9-200a-5444-9110-46d9b5d50072 |  | note | ○ In continuous concrete pours, the maximum time lag between truck loads on site shall not exceed 25 minutes.
label | d988a408-118f-5dc3-9a04-5e5e680aec9f |  | note | ○ If water is required to be added, it can be done so no more than if 60 minutes have elapsed from the time of adding cement and before commencing discharge. Concrete samples including slump test to be taken after adding water.
label | d7624502-666a-5ddb-91c1-02d6173768d8 |  | note | ○ Concrete shall be thoroughly compacted by internal vibrators of appropriate size and supplemented by external form vibrators.
label | 80d274ee-0c1a-5485-870d-1496618c9032 |  | note | ○ When the value of the rate of evaporation as determined from Figure 610.171 exceeds 0.50 kg/m² per hour precautions to minimise evaporative moisture losses such as the application of an aliphatic alcohol based evaporative retarding compound or controlled fog spray are taken.
label | 0dc41f06-35fd-5212-8d03-a4c0458504ab |  | note | ○ The evaporative retarding compound, when required, is to be applied immediately after initial screeding. The remaining finishing operations can be carried out after application of the compound.
label | 176671f2-1455-5cbf-bb7b-4f9742d47614 |  | note | ○ An evaporative retarding compound is used for concrete decks and slabs.
label | 2513fac7-1bee-5ee5-832d-4054b6d957b3 |  | note | ○ Records of water added to agitator drum are made available for review by the Superintendent.
label | 72be7faa-3f98-5821-ba5b-75d93ab9720a |  | note | Freq - Each Lot
label | dcabe075-e7cd-52d5-b2b5-b4514700dc85 |  | note | Key - H
label | e7fa6cbd-f26f-5d8f-a64d-fb34777d7755 |  | note | Resp - SE
button | 11370508-8e52-5d7c-9625-d2c2f3a49877 |  | button | Remarks/record - Concrete pour record attached | Yes,No
date | 09438a66-c4a4-5aea-a916-c3a1491c2390 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.6 - Concrete Testing (Compressive Strength, VPV and Slump)
label | c0106ea7-4461-578c-beca-9d0f086b59d2 |  | note | Ref docs - VR 610.16, Table 610.161, Table 610.162, Table 610.131
label | 27e8664f-b88a-57f4-9095-9c5b76d8d550 |  | note | Acceptance criteria - When concrete is being cast into a structural member, it shall be tested with a frequency in accordance with table 610.161.
label | 44ec13ce-f449-582f-8df7-15bfba291f13 |  | note | ○ For volume casts in one continuous operation:
label | 10af66a3-902c-551f-8e98-8d92dcb53ae6 |  | note | 0-10m3 : 1 sample must be tested
label | 74a852ca-beb7-53b6-9b01-d11482ab164e |  | note | 10-25m3: 2 samples must be tested
label | e78e7bff-5877-588a-9c97-ad6d30088517 |  | note | 25-50m3: 3 samples must be tested
label | aa5df1ce-1c5d-5826-b2c7-06d33d9c03f3 |  | note | 50-100m3:4 samples must be tested.
label | 9e3c4fe7-6f46-5298-bc70-b30e9858de1e |  | note | ○ For each additional 50m3, one additional sample must be tested.
label | b3e3ba66-d54a-5f90-94fe-b4c9dbb91fd1 |  | note | ○ The concrete samples shall conform with the testing requirements of VR 610.16. This includes a slump test being conducted to test the consistency of the concrete. With tolerances to be for specified slump of:
label | f71f5d57-7c84-5e99-95fa-8befc797b0e1 |  | note | <60mm: +-10mm
label | 73bf40d7-f004-52da-b2b4-8c31d226084f |  | note | 60-80mm: +-15mm
label | b1bc5257-470a-54b1-b61b-0ba745fc23e0 |  | note | 80-110mm: +-20mm
label | e4089b09-f2e3-58ab-b7c1-c9ba3c038736 |  | note | 110-150mm: +-30mm
label | 73381f98-e646-50f2-823f-0ba157152c69 |  | note | >150mm: +- 40mm
label | ea9342f2-0d35-5b5a-9d6d-0211f9018e29 |  | note | ○ The compressive strength of the concrete shall be tested with a minimum of 1 sample being tested at 7 days and 2 samples being tested at 28 days.
label | a8520321-ee63-55a5-81a3-67162d810f5f |  | note | Freq - Each Lot
label | 6c26f573-cc2d-5789-9a1b-ec60298b40cf |  | note | Key - R
label | e4159907-0d9c-58bb-91de-bf3b10a615d8 |  | note | Resp - SE
date | cb44e012-3410-5d4e-8e6d-578f1f3d8ade |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.7 - Surface Finish
label | be442f5d-ce76-54ee-832d-270175e9e97f |  | note | Ref docs - VR610.31 IFC drawings
label | 0a9e86a5-86e3-5489-a8f6-bba75cc2e96d |  | note | Acceptance criteria - The surface finish shall be as per the drawings and VR610.31.
label | e0306cd2-1814-574f-8594-1280c44861ac |  | note | ○ Where the surfaces finishes are not specified in the drawings, surface finish shall be class 1,2 or 3.
label | 657f7d2e-5a4c-5821-9e83-4814695c8e9d |  | note | ○ Class 1 finish shall be a uniform colour and texture with no defects which structurally affect the concrete. Class 2 finish shall achieve a concrete surface of uniform colour and texture and be free from any major surface defect. A class 3 finish shall achieve a concrete surface of uniform colour and texture and free from surface defects.
label | 63017c3d-a200-568d-845c-89c2b740fa72 |  | note | Freq - Each Lot
label | c2b3ce02-4a91-5746-a0db-e0414a58f1da |  | note | Key - R
label | f2909f9e-1650-534e-963e-5ea7f51df637 |  | note | Resp - SE
date | 71e81ce9-9af4-5b2b-bd9d-ac343d0d9843 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.8 - Curing of Concrete
label | 645e0bed-1e30-59a0-9480-8489a86ca57b |  | note | Ref docs - VR 610.23 AS3799 Table 610.231
label | 1b5b3dcb-c835-5ca1-8448-15feeecabf06 |  | note | Acceptance criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed at any location and shall continue uninterrupted for not less than the periods specified in Table 610.231. Methods of curing appropriate to job include, and are not limited to;
label | 19506d83-47d0-5f59-9b31-71cab85457a5 |  | note | ○ Water Curing
label | 4c37d1ad-92d7-53c2-8792-842f5f4c42a2 |  | note | ○ Curing compound
label | e76d2323-5a68-5c87-a8fb-f82f01d876a3 |  | note | ○ Polyethylene Sheet
label | 8f97471d-3d7e-5b02-a59a-50bb8166a970 |  | note | ○ Maintaining Formwork in Place
label | c380562f-26b1-5f94-b425-bf503a732655 |  | note | ○ Steam or Radiant Heat Curing
label | 63395462-3daf-54c7-931f-6522136fbb7b |  | note | Freq - Each Lot
label | 77fa7443-c144-5229-a232-d15dc3fd8907 |  | note | Key - R
label | ac388574-413a-5c43-a1c2-2c0ea1cbed04 |  | note | Resp - SE
date | ff3b3964-ed50-5f4e-a860-1659fcbbb4cb |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.9 - Formwork Stripping
label | adf32654-b64c-505e-b1ce-933e5751c49c |  | note | Ref docs - VR 610.25 Table 610.251
label | d7b561b3-4787-54a0-b76b-44a3e1deb226 |  | note | Acceptance criteria - Formwork shall be removed as per specified in VR 610.25.
label | da3718e2-ab23-51f4-a335-465f0a11e54c |  | note | Freq - Each Lot
label | 7c8d8508-8beb-5eb3-a902-3b337c3047c1 |  | note | Key - R
label | d9005792-2c74-51bb-8384-27796e836ab6 |  | note | Resp - SE
date | 3ddfa13d-9f4b-5d25-becd-5f9982051052 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.10 - Curing of Concrete (after stripping)
label | dfa3f72f-0bec-551c-9ca9-d68500f8e8e8 |  | note | Ref docs - VR 610.23 Table 610.231
label | 6e4475ff-ef90-5fff-9b73-5c284b016251 |  | note | Acceptance criteria - Immediately after stripping any formwork curing has commenced to the approved procedure and minimum durations.
label | a4ff195f-9e4d-5a5a-a25c-dcf2a49b0f9e |  | note | Freq - Each Lot
label | 1afd6982-2ff9-50a3-87ad-1865653a6c7b |  | note | Key - R
label | b0f8060d-b475-5d07-a918-fcdb4a123dbd |  | note | Resp - SE
date | 6d3f73db-d0ba-59eb-9b61-de2c3bd53c2b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.11 - Coating of concrete (if applicable)
label | 57c189ab-7081-5ca0-bb95-f155280971f1 |  | note | Ref docs - VR 686
label | 0f37df27-ae13-5cfe-9006-ec709d8cb5ae |  | note | Acceptance criteria - The procedures and surface preparation in accordance with clause 686.06 have been reviewed and accepted by the Superintendent.
label | 76fc2379-c42d-51f2-b432-71757cf38434 |  | note | ○ Coating of concrete shall be as per VR 686.
label | af54826b-ac75-5764-a0c6-787eb5be515f |  | note | ○ Coating has not proceeded without trial coating application with outcomes reviewed and approved by the Superintendent.
label | 916bc5df-66f2-52fd-911c-1b25f473c73d |  | note | Freq - Each Possession
label | 01332947-c9ec-5982-8bb5-0ba50a569eb6 |  | note | Key - H
label | 8bb7f3e4-cd9c-538e-a8db-e39dc003c8a6 |  | note | Resp - SE
label | 03a42d21-21ee-557b-a05b-012e496552ac |  | note | SI Key - H
date | cffc37a6-7426-59b1-943f-4e2dbbb4f137 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.12 - Measurement of concrete cover to reinforcement
label | e76df8d5-f18d-56cf-abf4-91e3925acf60 |  | note | Ref docs - VR 610.34
label | a499d9bb-15d6-5b33-a629-509c71603cde |  | note | Acceptance criteria - A concrete cover measurement survey shall be conducted after construction on a representative and randomly selected number of exterior surface areas, using a concrete cover meter in at least 3 m2 test area for every 25m2.
label | b0e8f05d-6378-5de8-8233-07e0d2b27903 |  | note | ○ Records to be available for review by the Superintendent.
label | 4917ac90-0511-5729-bd86-8afd1b8a828c |  | note | Freq - Each Lot
label | 66ae41b7-4f43-56e0-b6fb-4ff60db6df30 |  | note | Key - R
label | fa37cf15-2160-501b-ae61-5cf69064224f |  | note | Resp - SE
date | b978299e-0391-5c24-b0d7-282e91015e9c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.13 - Cracking of Concrete
label | ddb329e4-a868-5a1f-914f-0b6aff2735fb |  | note | Ref docs - VR610.24 Table 610.241
label | 92c2f8d1-fd3d-50f3-90e1-05c8a1957204 |  | note | Acceptance criteria - Cracks may be no wider than 0.1-0.2mm depending on exposure classification in Table 610.241.
label | ceff0895-a2e6-5c8e-8692-e89dee8d736e |  | note | ○ Minor surface imperfections are repaired in accordance with VR 689.
label | 9f46a5d4-20af-5d06-9cca-d1f2b077d61a |  | note | ○ The assessment of cracks has been undertaken by a specialist with at least 5 years’ experience in concrete structures.
label | 8bfe38c8-2352-5d2c-91db-75d7ae097c94 |  | note | Freq - Each Lot
label | db67a5b6-19f1-5202-b7d6-7b404f06b95f |  | note | Key - H
label | 97d6e547-e4c4-526d-97fa-dabf1e58f850 |  | note | Resp - SE
label | fa125d79-b93b-5b4e-b2c0-c5d8fb9a4aa0 |  | note | SI Key - H
date | f68724d9-a09c-56fc-b7ec-02a3055c6f16 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.14 - Backfilling
label | 2687f90e-dfe6-5c81-aa29-3f9441959e64 |  | note | Ref docs - VR 610.35
label | 53675bad-9c18-5a94-aa8c-9df043e72665 |  | note | Acceptance criteria - No fill material is placed against concrete within 14 days of casting in accordance with the requirements of clause 204.11 of Section 204.
label | 5fc8ca5a-d881-58be-87ed-2874a7bff79b |  | note | ○ Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements of clause 610.16(l) or maturity testing requirements of clause 610.16(m).
label | 2ad6e69b-1492-5d73-a179-325df7beee78 |  | note | Freq - Each Lot
label | 739b180e-cafb-572f-9a76-c5fcaaa76293 |  | note | Key - H
label | f3afa181-e372-5f14-8dd6-02c72ef4cf45 |  | note | Resp - SE
date | cce40504-9cb6-5301-8707-518857a36374 |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Completion
checkpoint-status |  |  | checkpoint | 5.1 - As Built Survey
label | a72988bc-07e2-5216-a141-8281fbd8aaa7 |  | note | Ref docs - IFC Drawings Table 610.471, Table 610.472, Table 610.473
label | 8275f40f-2788-5adb-b489-0e5b513f4274 |  | note | Acceptance criteria - Survey as built will consist of:
label | 563a94cc-4b5e-5c29-beb7-e13f310844ae |  | note | ○ All surfaces satisfy lines, levels, thicknesses and cross sections as specified on the drawings within the specified tolerances.
label | 0b1a9fad-55d8-5cef-9adb-dc7dc587b0bf |  | note | ○ The tolerances are as per Tables 610.471 610.472 and 610.473
label | f48eb498-ddeb-5886-976d-935b98a3b5ab |  | note | ○ For placing of reinforcement and post tensioning sheathing, this is +-5mm. For concrete cover, this is 0 to +5mm.
label | dbf3f8bc-48d1-5e39-8ff4-5c5ac194b677 |  | note | ○ Section dimensions shall be as per design drawings
label | 53b609fb-41ef-5f0e-bcd6-73567e47efcd |  | note | Freq - Each Lot
label | 01688166-abc8-5fde-aef6-1095d4827c82 |  | note | Key - R
label | cc359344-8651-5693-b4d1-fb0424faf079 |  | note | Resp - SE
button | 0d568bf8-c74e-5268-9bac-e8cceeb26de1 |  | button | Remarks/record - Survey Conformance Report Attached | Yes,No
date | c219530a-6706-59e6-b13c-ec4701d8d09c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Test Reports
label | dd4132fa-e25a-5197-945b-7e7fb4020c11 |  | note | Ref docs - VR 610
label | 39bf70ce-139c-5bd7-b9e4-593160197aaf |  | note | Acceptance criteria - All Test reports received and Reviewed.
label | 7d4db588-751e-5d15-99bd-a652f9eb12d7 |  | note | Freq - Each lot
label | c2fd7845-472a-5331-b317-b6adf362037a |  | note | Key - R
label | af5e83bb-37e6-5f55-8ece-418fdebf3889 |  | note | Resp - SE
button | 22399c2c-d928-5b86-aecb-0c9ceab52040 |  | button | Remarks/record - NATA Endorsed Test Reports | Yes,No
date | 83b41a74-d9e0-54f6-b5e9-0c10115b900a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Temperature Data
label | 29437fce-40c8-55ed-8ecb-4644cd4924bc |  | note | Ref docs - VR 610.22
label | 50fdc6f6-68cb-5374-b622-faf13abaccf6 |  | note | Acceptance criteria - The maximum internal temperature of all concrete members following concrete placement has not exceeded 75°C.
label | ed42b632-592a-5b8d-bec5-2374a58016e2 |  | note | ○ Except where justified by analysis and testing, the temperature differential across the concrete member being constructed shall not exceed 20°C during the period of curing.
label | 07d74b80-98ff-59a2-a627-01f02b0a197f |  | note | Freq - Each lot
label | ad1a683e-6ac7-54cf-ab4e-46045a6b2dde |  | note | Key - R
label | 8b549100-c474-5c79-9143-56dd0f0945a5 |  | note | Resp - SE
label | 9f42f875-a88b-53b8-a75c-3f7bf3263387 |  | note | Remarks/record - Thermal Data
date | bd2f0ca7-012b-5060-b79e-67a717e7363b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.4 - Product Non-Conformance
label | b979b209-0d1e-5ec3-934e-290595923452 |  | note | Ref docs - CQMP
label | 698ea578-8e27-5dc1-9e57-8dc11c232526 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | f53804d0-11bb-5e45-a1d3-ba88753ce76b |  | note | Freq - Each lot
label | c582c2a4-f7ed-5000-8417-1c01dc6c80d7 |  | note | Key - R
label | a665caac-a2dd-57d5-a28b-b4eca74caeef |  | note | Resp - SE
text | 5409ef02-2475-5aff-ae94-7a1a35c7a00c |  | textbox | Remarks/record - NCR No:
button | 39089835-cc9e-5430-93af-71caca14e3af |  | button | NCR reports | Yes,No
date | 708ccbc2-8784-54b6-900a-cf3f2a24ae39 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.5 - Quality Representative to check the above criteria and records to confirm
label | 91ca28c0-22a9-5ddd-a0fb-8e61b89ffcbd |  | note | Ref docs - CQMP Lot Records
label | c39108bf-ec19-5565-b1aa-d9125a9eae7b |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | 4bb45156-350a-5baf-bee2-c8a9a27e6d32 |  | note | Freq - Each lot
label | acfc631c-0cde-57a5-8a16-87232feddcfb |  | note | Key - R
label | 5b2401ff-8139-5d6a-a336-e9dcce4e573d |  | note | Resp - SE
label | 91d860ab-88bc-5f2d-a982-9ea9eef77a6f |  | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
date | ad08c9c5-0b42-5050-931c-271fcf8a108c |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing | a073e436-6148-4f4e-a1cf-0ac516489764
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Lot
label | 1aeaacd4-4230-5865-95c7-c87b67f2f725 |  | note | Ref docs - 1200.15 (b) (i) (B)
label | 3051c949-737e-5f17-91d2-d04bc948cd17 |  | note | Acceptance criteria - Clearly mark out lot and extents.
label | 25f3fbd6-318a-5d65-a217-61e8af37ca55 |  | note | • All No-Go Zones must be protected by temporary fencing and signage visible.
label | e9c9eb16-22e5-521a-bc5f-0ef130232142 |  | note | • All fencing of No-Go Zones must be:
label | ecddb32e-7a18-5e98-9fa4-a7143532f8b8 |  | note | a. erected a minimum of 1 metre beyond the boundary of the habitat to be protected, at the Tree Protection Zone or as directed by the Superintendent;
label | 99495e62-1c44-50e3-a545-ba563cb4783e |  | note | b. at minimum, constructed of star picket and paraweb with two wire supports. The star pickets must be 1.3m in height, installed to a height of 1m above ground level and the paraweb must be installed to ensure a minimum 30cm gap is available between the bottom of the fence and existing ground to allow for fauna movement;
label | a255df34-f2a2-559a-b045-2a60203e192a |  | note | c. communicated by signage installed on the temporary fencing at intervals no less than 10 metres apart stating ‘Environmental No-Go Zone – no unauthorised access’;
label | ab6a4518-209c-5efe-a7cc-1e738598fe04 |  | note | d. installed prior to commencement of works in the immediate area, in accordance with the relevant approved SEP; and
label | 568faa27-ea5e-5522-bef7-dc75982fd353 |  | note | e. retained in place for the duration of construction activities.
button | a2ec6a87-7d84-5ed9-bab7-5201a648016d |  | button | Has all of the above been completed? | Yes, No, N/A
label | 7f7c9a1b-c030-5997-9f37-8956a46d8830 |  | note | Freq - Prior to start of works
label | 9c7638ba-17e3-58a3-af91-d967e4e51e98 |  | note | Key - R
label | 067a77d9-060a-5143-8e55-8390c0ede22c |  | note | Resp - SE
date | 6ecb996b-d7d5-50ae-833b-4a296f144f2e |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | b489b33a-e894-50f7-8c1c-b138239e478a |  | button | Lot map | Yes,No,N/A
date | 613ac238-8319-5ae0-baa9-1f3b3f5eeabc |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Works required inside a No-Go Zone
label | 688d3eca-247d-5a7a-b7b8-acf90a952cce |  | note | Ref docs - 1200.15 (b) (i) (B)
label | fde1cadf-b659-5684-bfc1-d3340246aa53 |  | note | Acceptance criteria - No works are to occur inside any No-Go Zones, except for where the following process is followed:
label | f732ba0c-e9fd-5929-8e92-7c4091da8c37 |  | note | • Before commencement, where works have potential to impact flora and fauna protected by a No Go Zone, the Superintendent has been provided a report to the requirements of 1200.15 (b) (i) (B) for approval 5 days before the proposed Delivery Activities and it has been approved by the Superintendent.
button | f04de08a-0d34-5f7f-9f75-010c0a684c1a |  | button | Has all of the above been completed? | Yes, No, N/A
label | 28124040-ea02-55df-9758-54259c361318 |  | note | Freq - Prior to start of works
label | 4164726a-ef54-5049-9e7b-ce07d6c2dd95 |  | note | Key - H
label | e12ed4c0-a438-59c1-86cf-80df686a891c |  | note | Resp - SE
date | fe262d40-665f-5cc2-aaec-2754e0e61847 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.3 - MRPV Vegetation Removal Permit
label | 7a32c4b3-012d-5891-8c3f-6e4e4dcc2985 |  | note | Ref docs - Vegetation Removal Permit / PS3020.07 (a) (ii)
label | 8eada7fd-3d79-5a74-9c08-5df5768ef2a7 |  | note | Acceptance criteria - Sign off by the Project and MRPV Environmental Representatives. This is to be reviewed by the Superintendent prior to removal and provided to Environmental team
button | 91c9385b-5359-5c43-a9da-ef3460a5a3a4 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 1e81eec6-8f15-5f5c-96a7-05ff41dfdfab |  | note | Freq - Prior to start of works
label | 134cdc22-d059-503f-95b4-726cd717a2f7 |  | note | Key - H
label | 949dfb55-f788-516a-bea0-33cd437f9916 |  | note | Resp - SE
label | 930838fc-ee73-52da-a4f3-110030ccbd87 |  | note | SI Key - H
date | 49215191-82bf-5cc2-a396-a1097e7b6353 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 1.3.1 - Environmental Permit
button | 367059b9-87d4-5293-8214-cc1b1896b2e4 |  | button | Environmental permit | Yes,No,N/A
date | 7cb6d97e-008a-5996-ae1c-4ac9c740634b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.4 - Design Documents Required
label | ddb00bbb-e7ab-57f2-81b0-8425fbb29e82 |  | note | Ref docs - 1170.11
label | 59a61109-20b6-57de-aeff-cf5e1ccbd714 |  | note | Acceptance criteria - For site clearing and grubbing, the documents needed are:
label | 2b330eb7-feb5-564a-9a12-44a4d86574ad |  | note | (1) marked up drawings that relate to the design Documents and clearly define the scope of the Enabling Works;
label | 81920bc8-2e13-5fb5-9d30-f6bf93d12b48 |  | note | (2) any relevant Construction Specification for the Enabling Works.
label | 491ba839-26c1-582a-abab-fc2dba44b97b |  | note | (3) a drawing showing environmental approval boundaries, activity areas and no-go zones.
label | ce172a45-eb29-594e-a08d-0831f91bdb8b |  | note | (4) evidence that any required design related Approvals have been obtained; and
label | 184d644a-afa8-5878-babb-4a2dfde0aa17 |  | note | (5) a list of all required Approvals.
button | b6acb5f8-f07e-5526-a319-55cdf6a7dae6 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 669666cd-7ee5-5476-942d-038f2b53a010 |  | note | Freq - Prior to start of works
label | f94b0a48-3c1f-59dc-886f-d98f14684e4d |  | note | Key - R
label | c7ab6282-e9f6-5eb6-bc94-0886ca02e57d |  | note | Resp - SE
date | d97e5a42-3ba5-5920-b111-2a0b0f162084 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.5 - Site Environmental Protection Plan
label | 19b113f9-f428-575a-a795-80ceb50f031a |  | note | Acceptance criteria - Site Environmental Protection Plans and Site Erosion Control Plans have been reviewed and approved for works.
button | e6a5fa35-acb7-55af-ac19-2539536068d7 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 49d20439-dafe-5eee-916f-3a2959737bc2 |  | note | Freq - Prior to start of works
label | 74f9980d-823b-549b-bae0-1f0f015353e4 |  | note | Key - R
label | bbf7fb5b-40d0-5ab0-9c52-2712c4822e9e |  | note | Resp - ENV REP
date | c7e89c08-4d17-5bd2-8087-c7015a470469 |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Pre-Clearing activities
checkpoint-status |  |  | checkpoint | 2.1 - Pre-Clearing Identification
label | f66c08f7-26a3-517d-ae71-f8951f49cea7 |  | note | Ref docs - 1200.15 (b)(i)(C)
label | 9c6418f7-b248-5d60-b799-c0428e265a01 |  | note | Acceptance criteria - No less than 7 days prior clearing, an ecologist has certified that all habitat trees are clearly identified and marked with flagging tape or survey, consistent with the Design Documents and permits and approvals.
label | 406073f9-3636-543a-87ce-c92a9517220b |  | note | • Any salvageable timber suitable for reuse to be identified and marked for stockpiling, for it to be reused after clearing.
button | 5caee50c-1dbc-59b4-9134-0420fc38c384 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 304ca1c1-bddc-51d7-8579-614c4c345df5 |  | note | Freq - 7 days prior to proposed clearing
label | 330062aa-d495-5ed1-879e-a331e5e98d40 |  | note | Key - H
label | 5529ab32-761a-5984-9cda-c5b862cf7d98 |  | note | Resp - SE
date | 467af375-8c6b-57cf-ad47-1bd287e4d596 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - On-site inspection
label | cea5e880-ea3b-5e8b-a0cf-4ef27cdbeaca |  | note | Ref docs - 1200.15 (b)(i)(C) (4)
label | 92af811b-f0a9-5f25-80f6-2041775eaec1 |  | note | Acceptance criteria - Prior to removal of vegetation, site inspection to be arranged with the Superintendent and other authorities to confirm the requirements of Sections 1200.15(b)(i)(C)(1) and 1200.15(b)(i)(C)(2) have been achieved.
label | ad722b5e-4838-5ef2-9c69-15b7464a267b |  | note | • All Approvals are in place and the ecologist is always on site, ready to perform further inspections in accordance with Sections 1200.15(b)(i)(C)(3) and 200.15(b)(i)(C)(5).
button | f703935d-b0ce-532b-bf92-62ede504562d |  | button | Has all of the above been completed? | Yes, No, N/A
label | 36b866cc-9670-5900-8449-ff775a11fea8 |  | note | Freq - Prior to clearing
label | 4b0be976-fa55-5a73-bd16-9cb2a8040ce4 |  | note | Key - H
label | a5b589a5-762b-54c6-bece-ffe2e79061d1 |  | note | Resp - SE
label | 0ffbca66-b115-56c7-a6a8-344f4fafb2bd |  | note | SI Key - H
date | 284869ae-1d41-5de2-ae9e-b10f520e701a |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Onsite Clearing and Grubbing
checkpoint-status |  |  | checkpoint | 3.1 - Clearing
label | 8134fbe5-5f9c-51f4-bd1e-2285ba293755 |  | note | Ref docs - VR201.04 1200.15 (b)(i)(C) (5)
label | d1885acc-e2cf-5908-b8a8-3421c18841c4 |  | note | Acceptance criteria - Only non-habitat trees can be removed during the first stage of clearing. Habitat trees can then be removed after approvals have been received and a minimum of 24 hours after the removal of non-habitat trees.
label | 594387f3-cff1-5e29-a205-8c94f69f8f87 |  | note | • Prior to commencing of clearing each day, the ecologist appointed should inspect the area for signs of wildlife.
button | a62414e5-2aa4-57ef-9f46-a24733e6905f |  | button | Has all of the above been completed? | Yes, No, N/A
label | 4aa2dad0-7550-59a2-9b40-919a3fc12b34 |  | note | Freq - Each lot
label | 071f9452-f9ef-53f3-99c2-8969f5ddbef9 |  | note | Key - H
label | ac43cedc-ca20-5277-a6c4-84b94bf60f88 |  | note | Resp - SE
date | 91dbf2b5-9a5d-50f1-8eb0-76ac45015a66 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Grubbing
label | 765705e2-d463-523b-bf79-b23f0f2c2dc1 |  | note | Ref docs - VR201.05
label | 3810f854-6779-5953-ab9d-554d9449e3f9 |  | note | Acceptance criteria - In areas where excavation will be undertaken, all vegetation shall be grubbed as per the requirements of VR 201.05 and early works – subgrade improvement design package
label | dd370420-f1e0-525b-9fb0-3482980c504d |  | note | • Holes resulting from grubbing shall be backfilled with similar material and compacted to same degree as surrounding material.
label | 43af75e3-6205-5bef-b9c0-c92da9f71132 |  | note | Freq - Each Lot
label | a32fc915-ab09-535b-88b4-4d9f9083db34 |  | note | Key - R
label | 942823a9-3770-57c2-8ed8-76b6d4c64c91 |  | note | Resp - SE
date | 9369dfc7-f86c-5902-b865-d9c2e1a85d82 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Clearing at Culvert Sites
label | 17166604-6bf8-5a47-9f4b-549277092086 |  | note | Ref docs - VR201.06
label | 38cd2420-f39d-52ff-880b-d69a58f4dc70 |  | note | Acceptance criteria - Any trees or stumps with 10m of any portion of a proposed culvert having a waterway area greater than 6m^2 shall be cleared and grubbed in accordance with the requirements of VR201.
button | 81f3b80b-3665-5499-8b7d-4b029a1c3143 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b7364ca5-7ef3-5fd9-a367-9c26af473400 |  | note | Freq - Each lot
label | 1c9aa83b-f83f-567a-92a7-7302c41c5b5d |  | note | Key - R
label | b3d7b60a-53ce-548d-9229-0c85a8d738dd |  | note | Resp - SE
date | 3ece8513-7dab-599e-ae32-5aab7ee6679b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.4 - Flora and fauna handling and removal
label | 0c8b1649-bc7c-5328-a8c4-e66f8b8cd5af |  | note | Ref docs - 1200.15 (b)(i)(F)
label | 20c690c6-6455-580f-83a5-255e8110b13d |  | note | Acceptance criteria - The Superintendent must be notified if any significant flora and fauna is found, and an ecologist must identify and provide advice on what to do with the found flora or fauna.
label | 41c59073-a4f0-542b-b774-185ac0f50271 |  | note | • The Superintendent must notify Environmental representative of any flora and fauna found.
button | 6558365f-04f5-5525-b8ca-9e3ada2a8c59 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b015d1ac-2a3a-56ce-a752-5179739c3397 |  | note | Freq - Each lot
label | 6666619e-77af-539b-9be1-17089105176c |  | note | Key - I
label | b4508b45-159e-50f2-807f-3125fb7945ff |  | note | Resp - SE
date | 90f3ce84-c1bd-5525-81ca-d103f46ccb52 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Identified habitat
label | a3eaf210-473b-532b-9b97-c7d2ffb028de |  | note | Ref docs - VR201.10 1200.15
label | db02926b-aa92-5b12-a5c3-e8b948bf7818 |  | note | Acceptance criteria - Trees with hollows can only be removed during initial clearing, if hollow is occupied, the section is to be left and cut after clearance from the ecologist and a minimum of 24 hours after removal of non-habitat trees in the area.
button | 4eaa7fc3-187b-5524-8023-442f29334217 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 50ba95ab-ea75-5cd3-8271-fe53b2ea3dd8 |  | note | Freq - Each lot
label | 0fe09c78-873c-5e1c-b893-7946aa42f93f |  | note | Key - I
label | 9529233f-363e-52e5-a5d0-61fbf76aed4f |  | note | Resp - SE
date | d10bac38-3616-5137-bf68-8ca5bb9cf264 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.6 - Reuse of Material
label | 5ed6226d-b06c-5add-a9fe-05feddd7d5e0 |  | note | Ref docs - 1200.15 (b)(i)(G)
label | 19593e4e-2458-5263-8699-2530c500b7fb |  | note | Acceptance criteria - Seek and adopt where practical reuse opportunities for vegetation felled during the vegetation clearing operations. Reuse may include:
label | 9bb6ebc9-c4d7-59ad-b1e7-68d766c755b3 |  | note | a. retention of sections of a branch/trunk with hollows;
label | 2b188504-37fe-5e54-bc82-0af88263820c |  | note | b. habitat logs on the ground in revegetation sites;
label | 66b7bdcf-916b-57de-a73f-48746ce61f44 |  | note | c. placement as in-stream habitat with the appropriate approval of the relevant Catchment Management Authority; or
label | 63009fc2-485d-513a-97c2-645a99b9c12f |  | note | d. timber for furniture construction
label | d25265f3-e945-5cd5-8707-e2d067632433 |  | note | e. Mulch provided to Council, local schools, or to landscaping facilities
label | e9746773-2157-53de-9d93-5ee8925d70ab |  | note | Update tree removal/retention register
button | c0c4fd5b-50cf-5eee-9858-233bc7904da5 |  | button | Has all of the above been completed? | Yes, No, N/A
label | f25cfa97-395d-5c6a-938e-144f2ff692ce |  | note | Freq - Each lot
label | 51b7f521-36ee-53b7-9930-8dfb665e33b3 |  | note | Key - R
label | c1c1495d-0590-541c-b1c1-16d8fa3d64cc |  | note | Resp - SE
date | 242a1718-aafc-5f0b-a045-0536637fdc39 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.7 - Disposal of Material
label | 22ab1f51-be06-59d3-8723-6a067c3cd4de |  | note | Ref docs - VR201.07 VR177.I2 PS3020.07 (a)
label | 5c8edeb8-5436-5716-b9ad-7eec55c24b3d |  | note | Acceptance criteria - No removal of noxious weeds from the site. Identify and undertake treatment of declared noxious weeds prior to the commencement of any ground disturbing activities.
label | 8ad52fd6-9afe-5a69-8a56-b25741efabe5 |  | note | • The disposal of these materials shall be in accordance with the CEMP and its sub plans
button | 15f8667e-f158-5a0e-b0b5-bb8f79ea6243 |  | button | Has all of the above been completed? | Yes, No, N/A
label | b9bbbd28-46a5-55c2-90e6-b420a0b67e94 |  | note | Freq - Each lot
label | e67357d3-d70a-5557-a6c5-0724d4b43a7b |  | note | Key - R
label | 91f63033-9c44-5f27-99e0-db12236e6a7d |  | note | Resp - SE
date | 7c6b496d-5674-5bf0-b0a5-d20d47a1387c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.8 - Salvage of Vegetation
label | 23549aac-89ad-5bee-b6eb-0969e80f2ae1 |  | note | Ref docs - VR201.11
label | 72147322-28e1-51bc-b978-03f241399063 |  | note | Acceptance criteria - Salvaging any plants as well as collecting cuttings and available seed from areas of native vegetation on site to be completed where applicable
button | e2ce4a55-26c2-5287-aa10-7edb1b48adf0 |  | button | Has all of the above been completed? | Yes, No, N/A
label | ec6acecb-2efe-5060-8553-6bc607710bf8 |  | note | Freq - Each Lot
label | 41cb47bd-0387-50d8-bf7b-8cc6dc6e4fb5 |  | note | Key - R
label | 5e022082-44cf-5f79-8775-0d23395d8ead |  | note | Resp - SE
date | 6863f7ea-39df-5592-a3ef-0a9814484ac5 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Product Non-Conformance
label | 19c26434-6dc1-59af-bc98-36adc0c0cfcc |  | note | Ref docs - CQMP
label | 9518b3f4-350e-5fcf-84bb-20dc7d9bfd0a |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 414be1e4-dd58-514e-9aa9-3aa236908911 |  | note | Freq - Each lot
label | 95c40cbe-2f04-5cfb-9ea7-46afacf4e933 |  | note | Key - R
label | 346b6282-08c5-5e82-b865-5a52190fbf88 |  | note | Resp - SE
text | 1de4e1b9-6e81-5c1e-937e-83f3b62d4ca2 |  | textbox | NCR No:
boolean | 3d042604-f802-5c13-9d3a-f5a67dd771c1 |  | tickbox | NCR reports
date | 379973d5-60a8-5adb-8248-a277533eac6d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
label | ffc76c0f-2b8b-558d-b0d7-dae9d6812bed |  | note | Ref docs - CQMP Lot Records
label | e10d2619-880b-51f6-88de-945be30924e0 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
label | b2e3f48d-5616-5f85-8bbf-b937b6eacd62 |  | note | Freq - Each lot
label | a5c3681d-7870-5675-a7cf-b69ac24a35a6 |  | note | Key - R
label | d049f055-3bb5-56ce-a1ed-2ee1e25ae8ea |  | note | Resp - SE
boolean | 7f5d42cd-6f2a-5cfd-8273-f23af83651c5 |  | tickbox | Completed Checklist (if applicable) and reports and other compliance records attached.
date | 28a22383-1679-51db-93b6-fd88f726cb54 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 16300-P200-SYM-QAC-ITP-0008 Fill Earthworks (Bridge Embankments) | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0008 Fill Earthworks (Bridge Embankments) | b094fd79-7a4e-4ff1-a18e-026a46e28aa8
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Define Work Lot
label | baeeddcf-41a7-5da4-b323-515ea44a97d1 |  | note | Ref docs - 173.02 204.03 (h) Table 204.142 Quality Management Plan Lot Diagram 1630-P200-SYM-GEO-DPK-0001 5.2.1.4 (Table 43a)
label | b3500013-706f-51e8-b9ff-dbed333d62a0 |  | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works. Lot diagram to be provided clearly marking up extents of lot area. Work Lot open on Teambinder. Lot size with no more than one day’s production or a maximum of 10,000m² for Type B Material. Lot size with no more than one days production or a maximum of 5000m2 for Type A1 & A2 Material. In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
button | fb295979-421c-5e90-87e6-50c14546f08f |  | button | Has all of the above been completed and approved? | Yes, No
label | d10c24f3-0daf-5cd5-9f2a-70c4ec4c9bcc |  | note | Freq - Prior to start of works
label | 1bbd20c9-f001-55d2-b354-22bd94d63a3e |  | note | Key - R
label | cafcbf63-9daf-59d0-98cd-260f2ded237d |  | note | Resp - SE
date | e7df7c1f-b67a-50c2-a5ce-5fb1fcc5b988 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 0b566460-90fd-54eb-8493-9e9c9b41c365 |  | button | Lot map | Yes,No,N/A
date | 40027081-9e42-5463-907c-2bdb3d2922b0 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Fill at Structures
label | dc8f5842-0f0f-53f9-bb3b-d473167933dc |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1103 to 1105
label | 73979f6f-8f03-510d-a7c3-ea6a1ee6f340 |  | note | Acceptance criteria - Material type is determined by reviewing the proximity of the fill layer to the future bridge abutment. As per the relevant drawings, fill may be Type B, A1 or A2 materials.
button | b9e1939c-0136-55ac-baa3-262980ecec34 |  | button | Material type determined: | Type B, Type A1, Type A2
label | eee5a9dc-7780-5380-8c99-cba687033fae |  | note | Freq - Each Lot
label | 611f72f9-f7fb-5334-841f-7233bbbc7ec5 |  | note | Key - H
label | 943e6a6d-f1b4-5078-8f27-aae28847a6ea |  | note | Resp - SE
date | f09828e9-d0dc-55b3-99b2-e1f133707d74 |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Set Out
checkpoint-status |  |  | checkpoint | 2.1 - Set Out Survey Completed
label | 85782c57-ed78-52c6-a981-6830a30f2bb7 |  | note | Ref docs - VR Clause 204.03 (a) IFC Drawings
label | 185fad8d-707c-5d61-bd03-1ef38c3a12b5 |  | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
button | c03d677a-d30d-54ce-822f-39f905a76d9d |  | button | Has all of the above been completed and approved? | Yes, No
label | 7aa7fa3d-6444-51d5-ba40-abb020f773c1 |  | note | Freq - Each Lot
label | b8eb5b82-a77b-5511-aeed-48134aa4281e |  | note | Key - R
label | 9f49ba8a-a6cd-5773-a460-6388e7422f0a |  | note | Resp - SE
date | 3a8af651-6667-52fb-9231-f6de886c176e |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 2.1.1 - Surveyor Report Reference
button | 30872b16-bc4b-587d-a099-ce2b4ae2d25e |  | button | Surveyor report reference | Yes,No,N/A
date | be0952d5-9630-5d63-85c3-702255f515b3 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Placement of Type B Material
checkpoint-status |  |  | checkpoint | 3.1 - Initial Testing
label | 037f499f-1e0a-5f82-b085-3fd6ba07f48c |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1004 VR Clause 204.04(c)
label | 4aa87a10-b419-541e-8585-9fe6bec3b6b9 |  | note | Acceptance criteria - Type B: The material is to be meet the following requirements: CBR ≥ 3% Swell < 2.5% Friction Angle ≥ 37° If swell exceeds 2.5%, material shall be classified as expansive. Raise RFI and request approval from Superintendent to use material. Type A structural fill and Type B fill need to be tested to confirm they are able to meet the adopted shear strength parameters.
label | 096c0754-3b46-5492-90ee-1c762cbecbf9 |  | note | Freq - Each Lot
label | 0f9a3470-853c-5e2f-bfc3-e4a3f7308e9d |  | note | Key - R
label | 7fd80c6a-456f-5921-a294-4c8fb827f75c |  | note | Resp - SE
button | 1d440773-bdf0-5e44-8a90-361a259c005b |  | button | Remarks/record - NATA Test Report: CBR and Swell | Yes, No
date | 3613270f-c4db-5c51-ae14-14182d16f1b7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Underlying Layer Conformance
label | fb6a3b0b-1703-5ba8-9741-ccee7516ebd0 |  | note | Ref docs - VR Clause 204.10(b) Construction Document
label | d3c26377-277a-5521-998e-f7dc906de206 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent. Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor, Any unstable areas detected by test rolling shall be rectified. Note for 1st layer: After subgrade cut to the depths (or after in-situ stabilisation) nominated in Drawing Nos. 1630-P200-SYM-GEO-1102 to 1105 in Appendix A, or as required by DoT document Section 204, perform subgrade proof roll to assess stability. Results of proof roll to be provided to the Superintendent for review and approval in accordance with the requirements of DoT Section 204.
button | 59e344ce-49a8-52b2-be28-56f6ad046968 |  | button | Approval to proceed granted? | Yes, No
label | 65bddd2f-798c-5da5-a5c7-8904c6829506 |  | note | Freq - Each Lot
label | 1a8b7091-9e2d-5bb6-a1d6-1e1155004c84 |  | note | Key - H
label | daf4fe1b-9a29-58f3-badb-814d465e620b |  | note | Resp - SE
label | 923d331b-a583-5487-96e6-00cab7f76071 |  | note | SI Key - H
date | f94877ea-f5e8-5ea9-8e5b-3a94f2bfbbf8 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Placing Geotextiles (if applicable)
label | dccbc20a-0b74-5104-adbe-d683e4728622 |  | note | Ref docs - VR Clause 210.05 IFC Drawing
label | 9d3303a0-e76e-5261-939c-89d1a9d81653 |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent. Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with imperfections shall not be used. All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
button | 09fdc6e4-bf00-54bf-b27c-88738cb3f3eb |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 086edbbc-46fc-5c59-bb4d-c6acfd60509c |  | note | Freq - Each Lot
label | 38a2ad61-1109-53f8-bdcf-0693a50afe21 |  | note | Key - H
label | 8b74504f-ac42-591d-99a0-bc82486410d3 |  | note | Resp - SE
label | b7376ac5-18f9-5ec3-90a9-53c56b0738e4 |  | note | SI Key - H
date | b7346628-13c1-5c88-a4a5-8629b0ce7775 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Placing of Fill
label | 68e79fd0-82b2-560b-bd30-cb3289737342 |  | note | Ref docs - VR Clause 204.10(d) 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.4
label | 325aab88-f6c3-5c41-978f-dbd47b06a92c |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm. Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm. Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material. Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones. Placement of fill to full embankment height in lifts of no more than 2.6m per week where monitoring remains within acceptable limits. Hold filling while monitoring settlement and increase in pore pressures. Commence next lift of filling if the measured settlement and excess pore pressures are within acceptable limits.
button | 611c46ff-e0d5-509e-8db4-1a84b8bbccdc |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 8ccda2f4-6be2-5b35-b370-d7fadcfc288b |  | note | Freq - Once, Each Lot
label | 923c9b8c-15cb-5713-be1a-634e77141050 |  | note | Key - W
label | c4a1d893-d7d6-5e16-aa04-a772e631aa34 |  | note | Resp - SE
button | ad8ffc9d-1fa5-5a29-87c1-aa8aa4eb932e |  | button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
date | 0dc98755-a917-5921-93c4-13dfba029346 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Keyed Fill Layers
label | 29f3cc5a-048e-5e9e-9ce7-3274d0389f15 |  | note | Ref docs - VR Clause 204.10(c) 204.10(d)
label | ceded3b1-a0d6-5645-b266-f18ee26373ac |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other. Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | f7514e72-2959-5ea5-8d6f-73caa49265d1 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 53e8f420-453a-50f3-b438-438cfd4764cc |  | note | Freq - Once, Each Lot
label | 4aa30e82-3c78-5310-ac4a-869b0077cec0 |  | note | Key - W
label | bdf063e6-5bb2-535d-95e6-2a3a4f4b85f0 |  | note | Resp - SE
date | 08996005-9398-5568-be80-c5e97fc77390 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.6 - Test Roll of Type B fill layer
label | 08725ee6-7633-5718-b740-cf0acae5c156 |  | note | Ref docs - VR Clause 204.12 173.03 Construction Document (Test roll Procedure in specification 173.03) 1630-P200-SYM-GEO-DPK-0001 Table 43
label | b5729838-e7f3-5c0e-aaee-eccb6e8b4d50 |  | note | Acceptance criteria - Test Roll in accordance with Section 173. Surface shall withstand test rolling without visible deformation or springing. Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass. Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted. The Contractor shall provide for the Superintendent to be present during all test rolling.
button | 0d71b7eb-b99b-5089-8e4b-899d5f98e13e |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 0e9c01f3-8e9c-5970-96cf-d0af81e59ac9 |  | note | Freq - Each Lot
label | 1ce41327-ffbb-5a6d-85f2-244c079a0de1 |  | note | Key - H
label | 8303747e-fe17-5bac-88d9-289a9646466c |  | note | Resp - SE
label | f3577c9b-dd67-54a0-ad51-39aa94cdd8be |  | note | SI Key - H
date | 6acef1c7-5520-56db-a3ff-83e9daf0fc16 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction Testing
label | ea2267a2-316c-5ef4-86ca-9ee183e6aaba |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) 1630-P200-SYM-GEO-DRG-0004 (table 3).
label | 4def999c-126d-5c5c-8300-93661d11c62c |  | note | Acceptance criteria - Type B: Type B material placed within 400 mm of top of Type B material: 99% (Scale A) Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A) All areas of the job will be considered as scale A. Type B material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204. >70% for any material within 150mm of subgrade. >80% for all material below cut floor level.
button | 7c425cac-2e51-5297-8383-7ac61c5f99a2 |  | button | Have the results been achieved? | Yes, No
label | cbb3fc50-3680-5fb4-bc2f-a97b57b97437 |  | note | Freq - Each Lot
label | c6141978-9092-5d98-ba11-9f221fdc2870 |  | note | Key - R
label | 98038a81-f071-580d-b1f6-ffba6ff405de |  | note | Resp - SE
button | faf46499-12d1-50a4-b5aa-adfd9390f599 |  | button | Remarks/record - ATA Test Report: Compaction | Yes, No
date | e05a8d6f-615d-5530-bf53-a05ed121f24d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.8 - Monitoring of Settlement
label | eb5a928e-1bfb-5263-9bec-daa05fe20882 |  | note | Ref docs - 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.10 Table 33 5.4.2.2.10 Table 34b
label | 8c56ba21-d1ff-5432-8e70-54e6366643eb |  | note | Acceptance criteria - The rate of filling lifts and effect on settlement, lateral displacement and excess pore water pressure to be monitored. The ratio of change in maximum lateral movement to change in maximum settlement should be calculate at the competition of each lift. A minimum of two readings are to be taken immediately post installation and immediately prior to the commencement of embankment construction from the settlement plates, extensometers, survey prisms on culverts, inclinometers, and standpipes. During the construction phase measurements are to be taken when the fill height reaches 1.0m and then every 0.5m of fill after (TBC). During the hold period measurements are to be taken twice weekly and monthly until practical completion is reached.
label | 2310cec2-619d-5253-9a52-e7af482ba99c |  | note | Vibrating Wire Piezometers readings are to be taken for at least one week prior to commencement of construction. Continuous readings are to be taken during the construction stages with data sent to the logger on 6 hourly intervals. Survey prisms installed on bridge abutments are to have baseline readings taken immediately post installation. Following that readings are to be taken weekly for two months, two weekly for the following six months and monthly following that until practical completion is reached. Are monitoring results within the allowable limits stipulated in Table 34b (where applicable for this lot)?
button | 5b3138c6-52b2-5095-a2dd-6ca87387607d |  | button | Approval to proceed granted? | Yes, No
label | 8fd94d0b-dee7-5341-92a4-c01dfe9c6fc0 |  | note | Freq - Each Lot
label | fc9ae3c8-47df-50c6-98bd-3f0d67263249 |  | note | Key - R
label | 73916675-a39c-5c46-b5fa-8b586be9905a |  | note | Resp - SE
label | 25fa1044-b75c-5141-aaf0-b89713f2d3a8 |  | note | SI Key - H
button | a300aefa-c3b7-559c-86df-3223448fe3a1 |  | button | Remarks/record - Monitoring Checklist | Yes, No
date | f1d4e071-77f0-548f-a399-011304f87f28 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Placement of Type A material (Type A1 and A2)
checkpoint-no-status |  |  | checkpoint | 4.0.1 - Incoming Material Docket
button | 8042dd2c-0d34-5eaa-b1ab-cb433bc3479a |  | button | Incoming material docket | Yes,No,N/A
date | 65889f87-e196-51b3-b0e2-6642f8b2cd2e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.1 - Initial Testing
label | fbd21e7e-4028-5f79-844e-f1b84bc15e7b |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1004 VR Clause 204.04(c)
label | f2e2113d-1c22-545f-a26a-9f0d028b6261 |  | note | Acceptance criteria - Type A1: The material is to be meet the following requirements: CBR ≥ 6% Swell < 1.5% (1.0% for verge material) Friction Angle ≥ 37° Type A2: The material is to be meet the following requirements: CBR ≥6% Swell < 1.5% (1.0% for verge material) Friction Angle ≥ 32° Drained Cohesion ≥ 6KPA Type A structural fill and Type B fill need to be tested to confirm they are able to meet the adopted shear strength parameters.
label | 779aa915-8b99-574b-8830-72b2d47727eb |  | note | Freq - Each Lot
label | 03917bb0-d9c3-56b2-97ab-8450c6e2dd17 |  | note | Key - R
label | 8f0dbc6d-177c-5594-8b9c-c5220655a0eb |  | note | Resp - SE
button | 0693a0b4-7e53-53ad-a398-2a8072fc8e86 |  | button | Remarks/record - NATA Test Report: CBR and Swell | Yes, No
date | 39554bec-2ab1-5bac-977e-b2e1a4d8bf1d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Underlying Layer Conformance
label | 99a782de-c684-51e0-82de-fb70a3e90de0 |  | note | Ref docs - VR Clause 204.10(b) Construction Work Pack (Placement of fill material)
label | 63a8fe1d-3c60-55b3-a1b6-99c8516dde04 |  | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent. Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor, Any unstable areas detected by test rolling shall be rectified. Note for 1st layer: After subgrade cut to the depths (or after in-situ stabilisation) nominated in Drawing Nos. 1630-P200-SYM-GEO-1102 to 1105 in Appendix A, or as required by DoT document Section 204 dated December 2015, perform subgrade proof roll to assess stability. Results of proof roll to be provided to the Superintendent for review and approval in accordance with the requirements of DoT Section 204.
button | e7e1c75e-f3bd-5b68-a226-0d8ea3ef5d1c |  | button | Approval to proceed granted? | Yes, No
label | 82e1ee0e-1b9b-5289-8a09-708823adf3cc |  | note | Freq - Each lot
label | 0bd8b0ff-7a10-5a43-8a87-aa821d3a1d28 |  | note | Key - H
label | e9d91340-2688-5d1f-a648-80111df275c3 |  | note | Resp - SE
label | d6e6613c-e108-5d27-8243-257236843719 |  | note | SI Key - H
date | deaa99b3-15c6-5cdb-8bd0-48d734f4b6e6 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Placing Subsurface Drainage
label | 8865d1c2-3b8c-53a7-9180-952c6031c1df |  | note | Ref docs - 1630-P200-SYM-GEO-DRG-1102
label | 768a8d68-9454-59cb-b33e-47804b79b1b7 |  | note | Acceptance criteria - Have specified drainage materials been placed at the base of excavation as per drawing 1630-P200-SYM-GEO-1102?
button | 95715c8d-3654-5e9e-ac45-a41b803a05a0 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | c7f137cd-d4a6-5460-919f-67a55374c0c0 |  | note | Freq - Each Lot
label | 54a0baf6-4a39-5afc-a074-0093a4211f3b |  | note | Key - H
label | 5731dcaf-d2ff-5921-b22a-1a324773b184 |  | note | Resp - SE
label | 6f5361bc-7356-5c09-b784-531c857690fc |  | note | SI Key - H
date | 76df183b-c98c-5731-a261-2605b490c5c5 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Placing of Geotextiles (If applicable)
label | 5beb25b3-6dff-5144-a1af-d36b135bfd6c |  | note | Ref docs - VR Clause 210.05 IFC Drawing
label | d922261b-1b13-5972-86e3-7135459d194e |  | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval from the relevant Surveillance Officer. Geotextile shall be placed to the limits as shown on IFC Drawings without punctures or tears. If these occur, they shall be rectified, or the entire roll of geotextile replaced prior to covering. Geotextiles in subsurface drains shall be placed to conform to the approximate shape of the excavation and fully envelop the drainage material. All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
button | a7070955-73a4-5528-99a9-03478af814bc |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 34a82f5d-f281-5fbc-a0d2-94b2458a0239 |  | note | Freq - Each lot
label | 7bbfce29-d517-5044-aa96-d6ca32e9aca5 |  | note | Key - H
label | e25819d6-383c-5e61-b85a-80dc8f93b180 |  | note | Resp - SE
date | df9c7beb-f521-5461-b5d9-5ea553a05917 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 - Placing of Fill
label | 576dad6d-ed75-5e02-ad80-e94abc4c8672 |  | note | Ref docs - VR Clause 204.10(d) 1630-P200-SYM-GEO-RPT-0001 5.2.1.3.1 Table 43
label | ad84aad3-37e5-5d3b-b153-4bee28826990 |  | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm. Visual Inspection for maximum particle dimension Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than H3:1V, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be not less than 1 m. Placement of fill to full embankment height in lifts of no more than 2.6m per week where monitoring remains within acceptable limits. Hold filling while monitoring settlement and increase in pore pressures. Commence next lift of filling if the measured settlement and excess pore pressures are within acceptable limits.
button | d74bbc54-5720-5d09-a2fc-2957ec9ad545 |  | button | Has all the above been completed per standard and approved? | Yes, No
label | 86d9d439-2ae1-52fa-8864-e4f78d53b7e9 |  | note | Freq - Each lot
label | 3a5da9d3-086f-550c-bd6f-a4d0fbe83d4e |  | note | Key - R
label | 56a9f366-2230-5c38-a1dd-80ccfc9c6571 |  | note | Resp - SE
button | 8532109c-e70a-58ff-a180-63e585a15633 |  | button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
date | 2401f632-0b85-5495-b7a4-40a6ecc0ec91 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.7 - Keyed Fill Layers
label | 1b7c88b9-2e90-56d1-9668-32bad8f1e2d1 |  | note | Ref docs - VR Clause 204.10(c) 204.10(d)
label | a62a8e96-7b87-5ab1-b290-0864810f9c6f |  | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other. Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
button | 2896cca6-b5ce-5509-84d0-d929a0bbc259 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 9182a054-3f48-5bf0-ac41-ac010fb90930 |  | note | Freq - Once, Each Lot
label | 08111cc2-16c0-50e6-b0dd-21457dd004e0 |  | note | Key - W
label | 5047887f-45b4-5bb9-832c-88691aed8c05 |  | note | Resp - SE
date | 01d1d298-622e-5099-ba2b-24f4ddc43136 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.8 - Test Roll of Type A fill layer
label | 26cab5da-18ef-5103-b4d2-e65cb7eef4be |  | note | Ref docs - VR Clause 204.12 173.03 Construction Document (Test roll Procedure in specification 173.03) 1630-P200-SYM-GEO-DPK-0001 Table 43
label | fbc3b14d-715a-55e6-9b1f-d8f6ea5a5dba |  | note | Acceptance criteria - Test Roll in accordance with Section 173. Surface shall withstand test rolling without visible deformation or springing. Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass. Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted. The Contractor shall provide for the Superintendent to be present during all test rolling.
button | 57efeebc-e897-52bd-93b6-5f672739a5fb |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 4bd5fb2d-cc78-5583-9312-91cd3adf8150 |  | note | Freq - Each lot
label | e0763b59-94b9-50a0-b6f9-345398b11a47 |  | note | Key - H
label | 4d69a58a-34c3-53fb-8b88-d4ab50ba894f |  | note | Resp - SE
label | 00c4c0c2-e395-5927-8ad7-4e2b638ed17d |  | note | SI Key - H
date | b6fb6af0-5a63-5081-8d61-1d1fcc6e82dc |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 4.8.1 - Proof roll if applicable
button | 11a93d5f-0e31-5a34-81a0-601433075af3 |  | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
text | f35f30c1-c3b2-572b-85c2-b9f453adea2a |  | textbox | Chainage
date | 57a66303-f254-55e7-a0c7-7543903b468a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.9 - Compaction Testing
label | be975b40-af83-5fa2-8e7e-13966a145243 |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) 1630-P200-SYM-GEO-DRG-0004 (table 3).
label | ef950e19-77e9-5b6c-b0ae-d2e0a7126171 |  | note | Acceptance criteria - Type A1: All Type A material: 99% (Scale A) All areas of the job will be considered as scale A Type A1 material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204. Type A2: All Type A material: 99% (Scale A) All areas of the job will be considered as scale A Type A2 material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204.
label | e77b42ab-b468-591a-b449-0809f1fd0742 |  | note | Freq - Each Lot
label | 5031f8e7-0c7e-5262-b8b1-02094c074457 |  | note | Key - R
label | f494d407-dbf9-53a1-ab94-ef67aeaddc15 |  | note | Resp - SE
button | ffc5132c-f7ef-56d5-bc64-264ebe9e67b9 |  | button | Remarks/record - NATA Test Report: Compaction | Yes, No
date | b8324918-b2f1-5d32-a241-4426e37eb72e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.10 - Fill at Structures (if applicable)
label | 6831449e-3d14-5504-8104-22249941fa9d |  | note | Ref docs - VR Clause 204.11 (b) Table 204.111 Construction Work Pack
label | 01662495-eddc-5af6-84b7-f3d8b55b391b |  | note | Acceptance criteria - No Fill to be placed within 3 m of structure until the foundation is reviewed by the relevant Surveillance Officer. Culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality. | Yes, No
button | 1664bd7d-79b0-51f9-87dc-eef8d5d052fa |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 16fffd0c-c5a9-57e7-8c6e-d48850c6c870 |  | note | Freq - Each Lot
label | 9cc0edf5-d5f3-5c86-bc3f-c307379ec5ce |  | note | Key - H
label | 59a3d26d-e5a9-5618-a5b5-05f9b0d2521d |  | note | Resp - SE
label | 7d2e113a-00bb-565a-84d4-746d8ea118fa |  | note | SI Key - H
date | e6226276-073c-5073-9b19-0f7d4f194b79 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.11 - Fill within 300 mm of structures (if applicable)
label | 1fbcc455-8d70-51d9-b875-0fae6a5048a3 |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | 2fdc0347-b9be-52ed-976d-1acf013e4a7e |  | note | Acceptance criteria - Use of geo-composite drainage material or Permeable Fill in accordance with 204.04(f). Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111. The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
button | bfa24cf1-f626-568a-a856-d9edbd35d513 |  | button | Has all of the above been completed per standard and approved? | Yes, No
label | 43377108-b5fc-5708-ac2a-79804ca9076b |  | note | Freq - Each Lot
label | c47b2ec7-1c97-564e-baf0-4c13a29c8a99 |  | note | Key - R
label | 51e47b72-12b6-5987-b224-7fb39c82104e |  | note | Resp - SE
date | 6bb2b794-eabd-5109-bc69-9bf494106e25 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.12 - Fill Material against Concrete Structures (if applicable)
label | 3c0ca7c4-82c7-5d3c-82f1-54091f2cfa64 |  | note | Ref docs - VR Clause 204.11 Construction Work Pack
label | c7e606c0-067d-511a-b5f3-c2928b953a8d |  | note | Acceptance criteria - No material shall be placed against concrete within 14 days of casting.
label | 3a44c6eb-98d0-5af8-862a-ea7033481081 |  | note | Has all of the above been completed per standard?
label | dd3c5264-5e3d-50b3-b166-848fee617c0e |  | note | Freq - Each Lot
label | c5017994-257b-5094-b320-5662a9199c9f |  | note | Key - R
label | 46cbb0ad-8246-50a7-8fdd-877be25878f9 |  | note | Resp - SE
button | 490f3ef5-8204-5e6c-b1af-7a0a6b449ed6 |  | button | Remarks/record - Concrete Pour Recorded | Yes, No
button | e59d747c-3149-5a2e-b1b5-b6d02c01d1e1 |  | button | NATA Test Reports: Compressive Strength | Yes, No
date | 289b9754-d91e-5f96-9471-8d6a880897ad |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | Monitoring of Settlement
label | 629f9a01-f70c-519c-baa7-b685cf28cf27 |  | note | Ref docs - 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.10 Table 33 5.4.2.2.10 Table 34b
label | 32ad9037-9bbe-5160-bc9a-fd25f6fed795 |  | note | Acceptance criteria - The rate of filling lifts and effect on settlement, lateral displacement and excess pore water pressure to be monitored. The ratio of change in maximum lateral movement to change in maximum settlement should be calculate at the competition of each lift. A minimum of two readings are to be taken immediately post installation and immediately prior to the commencement of embankment construction from the settlement plates, extensometers, survey prisms on culverts, inclinometers, and standpipes. During the construction phase measurements are to be taken when the fill height reaches 1.0m and then every 0.5m of fill after (TBC). During the hold period measurements are to be taken twice weekly and monthly until practical completion is reached.
label | b4015614-6468-51f0-be44-601807054371 |  | note | Vibrating Wire Piezometers readings are to be taken for at least one week prior to commencement of construction. Continuous readings are to be taken during the construction stages with data sent to the logger on 6 hourly intervals. Survey prisms installed on bridge abutments are to have baseline readings taken immediately post installation. Following that readings are to be taken weekly for two months, two weekly for the following six months and monthly following that until practical completion is reached. Are monitoring results within the allowable limits stipulated in Table 34b (where applicable for this lot)?
button | bea09a98-752c-5bfb-9959-175460ed24cc |  | button | Approval to proceed granted? | Yes, No
label | 7ad3d2be-c211-5910-affc-7d2b10fc8b5b |  | note | Freq - Each Lot
label | 3ffb358d-02f4-5251-b178-10a3e69a1eb3 |  | note | Key - R
label | 3b775001-0951-5995-b0ad-13df7e431563 |  | note | Resp - SE
label | faff4b79-09d3-5b0d-9d5e-f73aa01be478 |  | note | SI Key - H
button | c6b8c84f-bbf9-5f1d-9d06-5154e952e703 |  | button | Remarks/record - Monitoring Checklist | Yes, No
date | b354d1c1-b15b-5414-b439-40a25a75192d |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.0 Geotechnical Analysis (and Material Testing)
checkpoint-status |  |  | checkpoint | 5.1 - Post Compaction Grading/Maximum Particle Dimension
label | 3c0a14ff-108f-5151-abc8-c4f61d8525d1 |  | note | Ref docs - VR Clause Table 204.041
label | 048abbed-a911-577f-9094-ebada79344f8 |  | note | Acceptance criteria - Type A: Sieve 75.0mm – 100% passing by mass, Sieve 4.75mm – 40 - 80% passing by mass, Sieve 0.075mm – 10 - 40% passing by mass. Type B: Maximum Particle Distribution (MPD) ≤ 150 mm within 400 mm of Top of Type B. or MPD ≤ 400mm at depths greater than 400 mm below the top of Type B material.
button | c879ab91-29f5-52a8-8633-4e35933de44e |  | button | Have the results been achieved? | Yes, No
label | 07061943-5d0d-524f-9bd5-56e0f0c37792 |  | note | Freq - Each Lot
label | d801191e-8de7-5333-a3f3-0d5a863090fa |  | note | Key - R
label | 3d2f15f3-e996-5513-98fc-4638527613de |  | note | Resp - SE
label | 62c497d0-260d-5202-9273-578fbda236f1 |  | note | Remarks/record - NATA Test Report: Grading Visual Inspections for Maximum Particle Dimension
date | 64bebdb3-0995-5306-8395-d4cbd8aeacb0 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - LL and PI Testing
label | a6b76dd0-6a0a-5750-9120-0342ab149f2a |  | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d)
label | 4a32a77e-b144-5c3e-bc70-38c598201db2 |  | note | Acceptance criteria - Type A: PI: 6 - 25, PI x % Passing 0.425mm: 1000 Max. LL and comparison of PI against LL, (identification of silt) is required for Type A2 Material. Type B: LL and comparison of PI against LL, (identification of silt) is required for Type B Material. Initial testing is 1 Test per 2 lots.
button | 6d55f089-e699-5eed-9c3b-f5c64a074e1b |  | button | Have the results been achieved? | Yes, No
label | 91b56f81-c7af-59b7-8514-a0dd616effab |  | note | Freq - Each Lot
label | e264b5cd-c50e-5b45-a1f0-b038fbf1de91 |  | note | Key - R
label | ee0b7b0f-54ec-5c01-a975-3ac88abf4e01 |  | note | Resp - SE
button | fe436c03-06ca-5403-9bb5-d713999dd30b |  | button | Remarks/record - NATA Test Report: LL, PI | Yes, No
date | 4ac5ee9c-6f26-5196-b38b-3bcfa2483174 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Reduced Frequency Post compaction testing of initial lots.
label | 400d6a2f-5679-56f3-836e-c342f63256bf |  | note | Ref docs - VR Clause 204.14 – Table 204.141 RC 500.20
label | 937c3cb2-dea7-5e4a-84bc-af949f28cb74 |  | note | Acceptance criteria - Test initial lot for CBR/Swell. Test initial 3 lots for compaction. Once material and work have achieved the specified requirements in the first test. And; Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142. If Reduced frequency has been granted, the testing can be conducted at the following frequency. 1 test per every 8 lots for CBR/Swell 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing. 1 test per 4 lots of LL and comparison of PI against LL.
button | fe494730-7214-5c10-afcd-23e1f2c2f655 |  | button | Has the criteria been achieved? | Yes, No
label | 531ee94f-379d-5b41-a7f0-b2f1b937988f |  | note | Freq - Each Lot
label | 94d4ce8a-f708-593e-bd6e-f9c3a86d5eff |  | note | Key - R
label | 94e5b8e8-86e7-5975-9b35-7114da3fa858 |  | note | Resp - SE
label | 0b66f1de-b3bb-5099-8d0d-c9d91f67ffa8 |  | note | SI Key - R
date | 5adf570c-9cfc-5dff-8c75-804d1693d0aa |  | date | Inspection Date:
checkpoint-group |  |  | section | 6.0 Completion
checkpoint-status |  |  | checkpoint | 6.1 - Conformity with IFC Drawings and Construction Tolerances
label | 737c0b0d-c5de-571d-9be0-99a46701c6f3 |  | note | Ref docs - VR Clause 204.03 Table 204.031
label | 1f6e8487-94cd-598b-84ec-128216bac7ae |  | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements. Scale A: 80 measurements per lot Mean +5 / -15 mm Max Std Dev. 12 mm
button | a137cb3d-90ff-5000-828d-26f0565dcf54 |  | button | Does the final product conform to the above criteria? | Yes, No
label | c6c8aa5b-44c9-5d5c-827a-5c22ff621c41 |  | note | Freq - Each Lot
label | 33ff35bb-f5d7-5e3b-bd0a-139461b1bada |  | note | Key - R
label | 869f5576-2195-53cf-90e9-278d0349e38e |  | note | Resp - SE
date | 4a005891-8b19-524c-830a-8500778160df |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | 3b197c80-e2da-5e6b-a1fe-87e654aca5b5 |  | note | Ref docs - VR Clause 204.15
label | b228fc07-8c7d-5ebd-af73-04aa4eb7d0dc |  | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | ec249345-1ad8-5cc5-a415-7a95ef9a746c |  | button | Does the final product conform to the above criteria? | Yes, No
label | 3dabf341-8c3d-5eb9-a30a-24adb77cef84 |  | note | Freq - Each Lot
label | 9d8f779c-a933-530e-ab2d-15bff7a5774c |  | note | Key - R
label | c6982f69-adb0-5d50-b124-e874ca3c2077 |  | note | Resp - SE
date | b663b567-252b-5d19-a614-a79855578506 |  | date | Inspection Date:
checkpoint-group |  |  | section | 7.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 7.1 - Test Reports
label | 71d9ea9b-319b-51fc-a33d-afa159828aaf |  | note | Ref docs - DoT Specs
label | 625e9e14-3917-5b1d-905b-0a6e9542d411 |  | note | Acceptance criteria - All Test reports received and reviewed
label | 44e2374e-cda0-5cf1-bd5b-239af1969b3b |  | note | Freq - Each Lot
label | 635d1e25-3f41-56a6-a5e4-cf6196756f76 |  | note | Key - R
label | 28b11944-9860-5341-b674-f06fb0696c01 |  | note | Resp - PE
label | 9df17621-a5ef-545a-9f8d-dcfdbe9a8448 |  | note | Remarks/record - NATA Endorsed Test Reports
date | 6f896df5-ec8e-5d8c-88af-8419ed3241fe |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.2 - Product Non-Conformance
label | 65fb0df3-3755-5975-8723-de50dc8cb571 |  | note | Ref docs - QMP
label | 8e03c6e3-68ba-5630-bc1d-2aa9c5e58523 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 68401126-7f25-5fa6-a8d8-2c6ffec79ddd |  | note | Freq - Each Lot
label | 6662df44-853f-5879-bf61-87123c081173 |  | note | Key - R
label | 37ff0ed3-9f40-525d-9884-64a29a3f51af |  | note | Resp - PE
label | 23aedcba-3e90-5043-a530-8eb9d697ee13 |  | note | Remarks/record - NCR reports
date | 49f53ce0-3244-5e45-aa04-4c3142917314 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0048 Dense Graded Asphalt | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0048 Dense Graded Asphalt | b11c9d8a-2426-40f3-a87a-2d6eba8e2a6c
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Check Survey Set-out
label | bd6d53d1-2395-55c3-bb14-960070c92f38 |  | note | Acceptance criteria - Record survey set out including frame, benchmark, and recovery points in place.
button | 13612449-dd2e-5dfa-8111-fb0f4eb58b7d |  | button | Has all of the above been completed? | Yes,No,N/A
label | b52c00d8-cda4-5fba-8986-1ce41e15b4b9 |  | note | Freq - Prior to start of works
label | 92b1b675-f6e2-58cb-bee5-1feeacb69d33 |  | note | Key - H
label | 6ec9ffe3-0db5-529a-b90b-4403308b62b2 |  | note | Resp - SE
date | 31ffa290-5f52-51fb-b6bf-2adcc76a5280 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 32c93b35-5d60-590a-a25c-30686fe54a00 |  | button | Lot map | Yes,No,N/A
date | 8e8b9814-4b82-595f-8124-31763291bd8b |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 3ca0e2c9-5f46-5839-8ab9-34ddee325c02 |  | button | Environmental permit | Yes,No,N/A
date | f08b3212-0c0a-57e7-9000-fd459910b243 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Asphalt Mix Designs Approval and Compliance
label | 2566c19c-9862-51b2-85dd-45fe4bf82f65 |  | note | Ref docs - VR404.05, VR405.04, VR407.06, VR407.09, PS3040.06 (g)
label | ad546336-bb6c-557c-bd83-6b90d320c7ad |  | note | Acceptance criteria - The mix to be used shall be a VicRoads registered mix and shall comply with the requirements of clause 407.06. The Indirect Tensile Modulus of the mix is not required to be submitted.
label | ab25f019-3203-57c3-883f-24100b088c0c |  | note | • Asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport.
label | f8aa0e4b-bba0-561a-be77-ad1db0976bc0 |  | note | • The registration for all mixes incorporated into the works shall be current at the time of their use.
label | 9c8bf837-e184-5f01-903f-47384a919515 |  | note | • The Contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use.
label | d1da6384-a45c-5fda-9ded-8744b81f24fe |  | note | • The contractor shall ensure to only use asphalt mixes that are registered by the State Road Authority as ‘General’ mixes at the time of placing the asphalt.
label | 553dbe71-f92b-57f1-a5ed-0570b185981a |  | note | • Where the Pavement Design allows the use of asphalt, the asphalt treatments must be applied in accordance with this Section PS3040.06 and the Technical References including section 407 of the VicRoads Standard Specification Sections for Roadworks.
button | ce93419b-4082-5b92-8fd3-5d51f68f7684 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 5def87ae-53ce-5468-88eb-73942d4cdfd2 |  | note | Freq - Each Possession
label | fb62eeea-2e2f-5f40-94cb-2b57953a7a57 |  | note | Key - H
label | 4ab30a43-9016-522d-9946-864529ba78f9 |  | note | Resp - SE
label | b455b445-fca8-52cd-899e-8ffb47cc7cad |  | note | SI Key - H
label | 3fc33e3a-36cd-5e0c-8999-073478edcaf2 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - VicRoads Approval Certificate, Incoming Material testing “sieve analysis”
text | d9cdb6f7-ec82-565a-87ce-4e5e850c5b5d |  | textbox | Team Binder Reference No
date | 3ada6e01-2bbd-57ee-a48c-60d51cea814a |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Asphalt Placement Plan
label | a2b46621-316a-508d-a59e-58f93596fba4 |  | note | Ref docs - VR407.04, VR407.13, VR407.17
label | 19a77850-7e53-54be-865f-6a470e5f620b |  | note | Acceptance criteria - Subcontractor submission of placement and Lot Plan. Review of proposed layers, depths, paver runs, Surface Preparation, Joints and spreading
label | cc8d73db-4580-5093-8e12-2b8965e1c35d |  | note | • In addition to meeting the requirements of Section 160, the Contractor shall provide an asphalt quality plan
label | 39e078bf-71df-55aa-b174-7ddbfb7cb379 |  | note | • The Contractor shall have a detailed Department of Transport approved RAP management plan and inspection and test plan
label | e880b1b7-981d-5cfd-af33-0b967c8625ab |  | note | • No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent
label | 2305f6a4-9f4a-54cf-8191-a03a7fa9a883 |  | note | • Prior to commencing cold weather placement of asphalt, the contractor shall submit a job specific cold weather placement management plan to the Superintendent for review
button | caaee13e-1036-5acb-aff2-971703f6f870 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 27498a2d-f5f3-5463-b241-c80fdb9e8295 |  | note | Freq - Each possession
label | 762978cc-e4d9-5585-9a8d-7ea132a2f7a9 |  | note | Key - H
label | 2c2258d8-279f-52c9-b4b3-8758f286ad54 |  | note | Resp - SE
label | 48b873cd-b268-5729-9941-c8f05bd65bab |  | note | SI Key - H
label | 69c0c1fa-d6ba-5882-b67d-abb6a48e2556 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Check placement adheres to Compliance with IFC drawings
date | ee24e60f-867c-5fc1-a7d1-78bd89fd4df9 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Asphalt Type Wearing and Regulation Courses
label | 13a369b8-08d3-5225-a0aa-844d457982c0 |  | note | Ref docs - Table 407.021 IFC Drawing
label | 2ce92c2c-7f35-5fa2-b098-6445eb3f5f42 |  | note | Acceptance criteria - Dense graded asphalt types L, N, V and H series in accordance with the IFC Drawing
button | 480d74fc-5f42-521a-a577-76171a88255e |  | button | Has all of the above been completed? | Yes,No,N/A
label | fb9b9508-82c9-501d-9b45-96655615b8c8 |  | note | Freq - Each possession
label | 8dcd5e98-0d58-5ace-bb02-d4f0c19cece2 |  | note | Key - R
label | a02bbd39-4f2c-5e20-9a72-7c854e36e962 |  | note | Resp - SE
date | 8482e35e-1e05-59aa-a138-34bcb1777a79 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.5 - Asphalt Type Intermediate Courses
label | 06c8b956-7ab6-5fc8-abaa-81d9f8742ddc |  | note | Ref docs - Table 407.21 IFC Drawing
label | 67cfae1e-6d2e-5882-a9f9-56ba66a4ba24 |  | note | Acceptance criteria - Type SI, SP, SG and SS as per the IFC Drawing
button | c7994cac-ca50-566b-895c-6011fbb9ffd2 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 469b81ee-7fef-58b9-b302-22b57fb0de8e |  | note | Freq - Each possession
label | 9f9b78f4-ee4e-5a6f-ac0d-7940053fbda5 |  | note | Key - R
label | 1cc90350-2db4-543f-abe1-2a4eac0e681b |  | note | Resp - SE
date | ba092bd1-bf21-5932-b132-c860f46ac818 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.6 - Asphalt Type Base Course
label | 463a90f2-964b-577c-a2f5-22fe3106c909 |  | note | Ref docs - Table 407.21 IFC Drawing
label | e0f6a102-aee5-51ee-8034-c64492a67dd7 |  | note | Acceptance criteria - Type SF or SI – as per the IFC Drawing
button | f9a2157a-30a4-5ca5-837f-09834dde4939 |  | button | Has all of the above been completed? | Yes,No,N/A
label | dae3027c-8221-53fc-a694-97ac2457c475 |  | note | Freq - Each possession
label | 54e2d6c5-848b-55b9-b2b3-e292daf231a9 |  | note | Key - R
label | fd4355c0-36f2-5fe6-aee3-d55df8920f97 |  | note | Resp - SE
date | 97e90c82-edc5-5958-9a95-27a275a834b3 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.7 - Conformance of previous layer
label | 2cdc9041-85a2-5fa3-8ab6-7a0a28a4dd4c |  | note | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | 5f2d9e0a-6f34-506f-bafe-e086b1f4e5a4 |  | button | Has all of the above been completed? | Yes,No,N/A
label | eafeb787-9294-562e-8c0e-bf3015639791 |  | note | Freq - Each lot
label | 3db469ef-c561-5512-b7aa-b1f10b78c874 |  | note | Key - H
label | e6088d80-bfe6-5d23-8e53-957ec86a4c21 |  | note | Resp - SE
date | 6bb7b9b2-5b74-5943-8e82-7dafa9d6ff06 |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Hot Mix Asphalt Placement
checkpoint-status |  |  | checkpoint | 2.1 - Profiling (Cold Planning) and preparatory works
label | 5c2aa563-6c38-5f86-b18c-941123a6ccee |  | note | Ref docs - VR402.02, VR402.03
label | 7b191ff4-4727-5fa7-9710-54625671def5 |  | note | Acceptance criteria - Cold planning shall be carried out in a manner as to leave a uniform surface on a plane parallel with the ultimate finished surface of the pavement as shown on the drawings.
label | 9bbcce0c-caa9-564a-99d2-12c7d396a888 |  | note | • The nominal depth and width of pavement to be removed shall be as specified in Clause 402.06. After planning, no point on the planed surface shall lie more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
label | 1cd706bf-94f7-5d73-b79f-bf12dd7019ee |  | note | • In locations where removal and replacement of asphalt or pavement is required on the same day, the rate of cold planning including clean up shall be at a rate consistent with the asphalt replacement process to minimise the pavement area closed to traffic
button | ec1600ed-2886-581e-bba9-b5e104089e2c |  | button | Has all of the above been completed? | Yes,No,N/A
label | dc60fd2b-84df-50a0-bb59-3c90c477da78 |  | note | Freq - Each lot
label | 03d5ec14-9a8e-5b85-be29-2438a2de387f |  | note | Key - R I
label | d1e5fbed-901a-53d1-adc5-9572521faae8 |  | note | Resp - SE
date | 3ae12a4e-a1f1-51ab-8245-02f298206bf5 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - Commencement of Placing
label | 0d6fd0d0-e668-5e35-8f20-c1ab8632c70a |  | note | Ref docs - VR407.23
label | 56a240c5-1914-5dd2-896f-4de207a19969 |  | note | Acceptance criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
button | 63604e1b-a508-5871-b654-f566a6702a0a |  | button | Approval to proceed? | Yes,No,N/A
label | 7736aa5a-8ed8-569f-872c-88ee05ee5378 |  | note | Freq - Each lot
label | dae61109-a233-589c-8379-7dda4acfcebb |  | note | Key - H R I
label | 83cd684f-6590-5fdb-8aff-bcb52c9aaac2 |  | note | Resp - SE
label | 1e05035f-a63d-52c6-bd7a-2eb87076614b |  | note | SI Key - H
date | a4bca026-c176-5245-8ed8-c4af4f9fa6a3 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Ambient conditions for Placing
label | f8f2fb7e-aed0-5582-915f-b96763930042 |  | note | Ref docs - VR407.17
label | 93c7c68e-7fab-5795-8032-f46314cf2494 |  | note | Acceptance criteria - Intermediate and Base Course Asphalt not to be placed with surface temperature < 5˚C.
label | 18c11b12-490b-53d2-a295-005bfd2fd0f5 |  | note | • Asphalt mixes with PMB and Class 600 binder in intermediate or base course layers shall not be placed when the majority of area to be paved has a surface temperature < 10°C.
label | 0d9d2ff0-8b62-5e7a-a520-c96a3af7ff68 |  | note | • Wearing Course Asphalt not to be placed with surface temperature < 10˚C,
label | 442bcb94-1774-5f3c-af75-2f32447602cc |  | note | • Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review if applicable.
button | 931440f0-80a6-5400-9747-80c4fe5023f2 |  | button | Approval to proceed? | Yes,No,N/A
label | fd5c8c83-6202-5c6e-bb46-87866e846eca |  | note | Freq - Each Possession
label | 0cb8bc2e-c291-5643-914d-47a614b31443 |  | note | Key - R I W
label | 00c2225d-f4e6-5ebd-a8ed-fbad36e7d0c0 |  | note | Resp - SE
label | a5224760-7877-53ab-b093-ebf1188ee42a |  | note | SI Key - S
date | 98f2ec31-f1ac-5065-86fb-044445843af7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.4 - Application of Cationic Bitumen Emulsion ‘Tack Coat’
label | 9bb39e3a-701a-5783-b1c8-6debfacb08e1 |  | note | Ref docs - VR407.08, VR407.18, VR407.19, AS1160
label | 6eb06f38-adac-52ad-a6d8-df7ba2f3d0c3 |  | note | Acceptance criteria - Before tack coating and asphalt placement, contractor shall remove dangerous and loose material from site and sweep the area clean.
label | edf913b6-0fb1-5036-8ef1-ce73dfaddbda |  | note | ○ Bitumen emulsion used for tack coating shall be a cationic rapid setting type complying with AS 1160. Emulsion diluted with water shall have a bitumen content of not less than 30%.
label | 90e18975-6e2e-509c-862f-69380ef60390 |  | note | ○ Proprietary grades of bituminous tack may also be used where it can be demonstrated they will provide an equivalent or better bond between pavement layers compared to an emulsion tack and can be applied in a uniform distribution at the residual rates specified in Clause 407.19.
label | d9cd4a51-838e-5798-a1b0-c11c542eab0a |  | note | ○ Bituminous tack shall contain no more than two parts of cutter or other hydrocarbon solvent.
label | 27b9e1ba-4075-532d-95f8-084d1385249d |  | note | ○ From 1 July 2022 only trackless tack coat will be permitted.
label | 1e21a43a-3a56-5658-8dc1-75e7e56b7a05 |  | note | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
label | 52c5ff43-85ed-5b87-ac15-ac595419fd0d |  | note | ○ The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen (except for joints and chases where rates shall be doubled).
label | b7367d9d-7af0-54d4-8a83-b48c26650c12 |  | note | The tack coat shall be:
label | 42f05195-6862-52b0-9e2c-e4dfad649b3d |  | note | • applied only to a clean, essentially dry surface, free from surface water
label | c60533b2-f858-5ad0-83a6-2427723edcc0 |  | note | • applied uniformly over the entire road surface
label | d6721b1a-638d-5dbd-95de-d8ed0ed9c513 |  | note | • intact at the time of placing the asphalt.
label | 9da9ef6a-b9fb-5c52-8ad2-119207ebc323 |  | note | Photographic evidence that includes an identifiable landmark relevant to the lot, shall be supplied to show that tack has been applied uniformly over the lot.
button | 7b4d0e60-0998-5bc9-a183-f75558e717ee |  | button | Has all of the above been completed? | Yes,No,N/A
label | 950546bc-91dc-50a3-a773-4c8d649ef3e3 |  | note | Key - R H I
label | 04c10e51-c1ee-5359-954d-52286cc84a02 |  | note | Resp - SE
label | 5afefb4e-ddce-5995-b515-6e143fe9e04a |  | note | SI Key - H
date | 4bd0b046-2370-5e43-baf3-5b3225996e77 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Verification of Delivery Dockets
label | 8385ef7d-0035-5eea-82ee-adc9b10e8002 |  | note | Ref docs - VR407.20
label | 7757e0fc-5895-5d47-88c8-9831d97808d4 |  | note | Acceptance criteria - Asphalt deliveries to be made only during hours listed for possession of site.
label | 5272cd55-031f-5225-b7bd-3d71a4ac208c |  | note | • Check asphalt upon delivery for specification, segregation, separated binder, evidence of exposure to temperatures which are too hot or too cold to retain adequate workability and strength, and uncoated particles. Reject all non-compliant asphalt.
label | bc9af528-8fe7-5e98-941c-b02757e1cf06 |  | note | • At point of delivery, delivery dockets must be sighted to conform with the requirements of VR Section 407.20(b). Reject unconforming loads.
date | d3112710-e1b0-5ee4-bf22-4d2a3ab360a1 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.6 - Construction - Jointing
label | ff5fc386-a31e-50fa-9b0d-85be94344287 |  | note | Ref docs - VR407.17, VR407.21
label | 9e1779d1-b38b-5e6b-8063-90159608add6 |  | note | Acceptance criteria - All transverse joints shall be offset from layer to layer by at least 2 m.
label | e3048c29-6e81-55dd-b693-c4dbf0d91588 |  | note | • Location of all joints shall be planned before work commences and provided to the Superintendent.
label | b19dc940-2fc9-599e-a200-27022c226cb7 |  | note | • Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
label | d52f2df9-2bcb-52ff-a65d-dfe7d62e0a4a |  | note | • Longitudinal joints shall be parallel to the traffic lanes.
label | 397778b5-8b45-521b-b52b-2ec9f5c0a9f1 |  | note | • Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
label | a8c144ce-a810-570c-9d1e-0616282ab666 |  | note | • Cold joints shall be avoided
label | e979caa3-dfb1-5a4e-90bd-a106d6574a97 |  | note | • Upon completion of each work day, and prior to opening to traffic, the following shall be adopted for treatment of exposed asphalt edges:
label | c97f141d-8993-5856-b14a-6fc0fa6040d7 |  | note | (i) Longitudinal edges
label | b5fb5e3b-8245-5036-892a-a41e9cb9db5f |  | note | All longitudinal joints within the trafficked area shall be matched up between paver runs, except for a short section required to achieve minimum offset between transverse joints, unless otherwise approved by Superintendent. Exposed longitudinal edges within trafficked area are to be ramped down at a slope of not steeper than 5 horizontal to 1 vertical, by means of constructing a temporary wedge of dense graded or cold mixed asphalt.
label | 4d4f227b-d64f-53f9-a745-9c3143d4eeea |  | note | (ii) Transverse edges
label | 17fc87a7-8b0c-540e-a90e-ceb8717cc7da |  | note | At the end of paving run in the transverse directions, new asphalt mat shall be squared up to a straight line and ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Ramping shall not be exceed grade indicated in VR407.211 Table 407.211.
label | 7f9d3a37-9f2f-56a3-905d-9b6f74f30d7d |  | note | (iii) Removal of Temporary Ramping
label | 2e4aadae-0219-5cfb-a41d-57b22bdc2b12 |  | note | Prior to commencing each day’s work, temporary ramping shall be removed via means of cutting back along a straight line to expose a vertical face of fully compacted asphalt at specified depth.
button | f1861ce1-9f5e-5cc5-a7d0-73390566dff9 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 24b3431e-a0f2-5abd-93db-bd9e79f45c5c |  | note | Freq - Each lot
label | 98bac0c4-58bb-5732-81e2-ef44cbc43b0c |  | note | Key - R I
label | 62737117-9036-54a1-8605-58805c8bc504 |  | note | Resp - SE
label | 0a8c3880-21ad-53c0-b770-a3b636e3be7c |  | note | SI Key - R
date | 5a443bea-e95b-5489-8d70-bc202fdcf7ea |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.7 - Matching Existing Pavement Surface at Junctions
label | 8a1f488d-71a7-599c-a8cd-3900cb741a80 |  | note | Ref docs - VR407.21 (e)
label | 95440612-004b-5e0c-809d-9dbb4c2b15a9 |  | note | Acceptance criteria - New Asphalt Layer to match the existing pavement surface.
label | c41c2bea-01d5-5fc6-b6e8-de760cd452a6 |  | note | • A chase shall be cut from existing pavement by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times.
label | 6f4db35b-18de-588f-bd95-6c112fe3b644 |  | note | • The width of the chase shall be as follows.
label | dbeac044-7020-515c-9c5e-3c2ae5c0a150 |  | note | (iii) at side streets and median openings – 600 mm
label | 693ffd4e-8828-5834-80af-3e1c0f831955 |  | note | (iv) on through carriageways with a speed limit of 80 km/h or less – 3 m
label | 95517914-6076-5aec-a7a6-a1fdf2c4cfdf |  | note | • On through carriageways with a speed limit of more than 80 km/h – 6 m.
button | 739ab68c-a597-5aa4-a3ff-b5577d3e6791 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 8989ce64-d596-5624-bb27-83cd595864e9 |  | note | Freq - Each lot
label | c30d71c9-5e52-5b27-a682-a7f6f2104565 |  | note | Key - R I
label | e2e9b487-f628-5c5c-aae0-94007aa94ce4 |  | note | Resp - SE
date | 180e27a4-77ab-55c5-b776-de699a0374c8 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.8 - Spreading
label | d9ac1763-a4b6-54b9-9733-438f03a8d025 |  | note | Ref docs - VR407.25
label | bd94380b-64f4-529c-b421-2f61131bab0e |  | note | Acceptance criteria - Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified. All asphalt shall be spread with an asphalt paver except for small areas where use of a paver is not practicable.
label | 195c4344-75dc-52dc-9082-706f04d289f9 |  | note | • All asphalt shall be spread with a purpose designed asphalt paving machine to form a uniformly smooth asphalt mat complying with the requirements of Clause 407.29 without segregation, tearing or gouging. In areas that are not accessible by a paver placement of asphalt by other means is permitted.
label | 10384da3-831d-512c-b076-45bcd655e245 |  | note | • Hand spreading shall only be used for small areas where it is not practical to use a paver.
button | 490fce41-3026-5bdf-88ae-2ca0aae9c4ce |  | button | Has all of the above been completed? | Yes,No,N/A
label | 9b263dca-5b95-565c-8e20-88241540f5eb |  | note | Freq - Each lot
label | a7b30ea7-2b4d-52dd-ac9d-bed9887848ee |  | note | Key - R I
label | 89cff8e0-2899-5c0b-aa39-0a6608928401 |  | note | Resp - SE
date | ecad88da-8081-5bfc-8260-4b9c82c228f4 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.9 - Trafficking or placement of asphalt over Type SF asphalt (If applicable)
label | 5085268e-d228-507e-addc-02571d2c0c80 |  | note | Ref docs - VR407.28
label | b0efed94-c71e-580d-b737-6a08b6cbeb2d |  | note | Acceptance criteria - Trafficking or placement of asphalt over Type SF asphalt is not permitted unless the majority of the Type SF asphalt has a surface temperature of 50˚C or less and falling. (Table 407.281)
button | 5fcb3d5e-43f2-5890-9175-2d2dab3aef37 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 84fa350e-ca9b-5f24-a502-76f49d8e62b4 |  | note | Freq - Each lot
label | ddb62960-aebc-5892-bbff-38788eff5e8e |  | note | Key - R I
label | 6e429cc4-f371-5118-860c-6a8f27cba851 |  | note | Resp - SE
date | b9695443-fabb-54d3-98aa-ab846f8bfa6c |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Performance Testing
checkpoint-status |  |  | checkpoint | 3.1 - Compaction Testing– (For Six Tests Lot)
label | 30e80748-940e-55e4-b357-e557da717283 |  | note | Ref docs - Table 407.271
label | 59a0d8d3-92db-5463-8f74-4f8dbdad6ec1 |  | note | Acceptance criteria - Thickness < 50 mm: 95.0% Characteristic Value of the Density Ratio. Accept lot subject to no other non-conformances raised for the lot.
label | 4f877622-0725-5841-b0ba-21bdb9f86e10 |  | note | • Thickness < 50 mm: 94.9% to 93.0% Characteristic Value of the Density Ratio. Lot will be accepted at a reduced rate calculated by P = 15 Rc -132
label | a75395c0-ad55-53bd-80aa-bf4e2b37295e |  | note | • Thickness < 50 mm: 92.90% or less Characteristic Value of the Density Ratio. Remove and replace asphalt.
label | 20d616c7-191e-54da-aff0-ce91c4be2ee6 |  | note | • Thickness > 50mm: 96% Characteristic Value of the Density Ratio. Accept lot subject to no other non-conformances raised for the lot.
label | a43b1beb-2a00-53f2-b6f3-908efcac1c06 |  | note | • Thickness > 50mm: 95.9% to 94.0% Characteristic Value of the Density Ratio. Lot will be accepted at a reduced rate calculated by P = 15 Rc - 1340
label | 4e120a26-aa02-52c4-946c-bee8c0aaac27 |  | note | • If Characteristic Value of the Density Ratio is less than 93.9.0% then the layer shall be removed and replaced
button | eef27930-e758-555e-be15-c3734c76ec82 |  | button | Has all of the above been completed? | Yes,No,N/A
label | 1161b17a-d0ed-5c7b-836d-7539e739da9f |  | note | Freq - Each lot
label | da61591c-7205-5ea5-91a5-cca6e8ad33cb |  | note | Key - R
label | 5984240b-e9b0-5f14-9f7d-49a4417b78cc |  | note | Resp - SE
label | cae0430a-ae8d-5f7e-baeb-c9814beba33c |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 5f3a7e9c-fd2e-5976-bd66-418201337040 |  | button | NATA Test Report: Compaction Tests | Yes,No
date | 00ba4eb5-e367-5f27-a27f-51cc7138ee46 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Compaction Testing – (Less than Six Test)
label | 5196cd22-c113-5ddc-90f5-9648a4e088dd |  | note | Ref docs - Table 407.273
label | edb79061-1e04-5cac-af4c-34736b83b4ba |  | note | Acceptance criteria - Thickness < 50 mm: 95.5% Mean Density Ratio
label | 97962a18-0e7f-5918-b41c-40c5245b2ff5 |  | note | • Thickness > 50 mm: 97.0% Mean Density Ratio
label | c43e30b3-e268-54ab-b82c-a1b56d926b88 |  | note | • Signed Test Certificate
label | 688df790-b0a0-56c9-a84a-44706b216156 |  | note | • If Mean Value of the Density Ratio is less than 92.5% for < 50 mm layer or is less than 92.0% for > 50 mm layer then the layer shall be removed and replaced.
button | e6ba202c-b3e8-5745-a4a6-70f44a793d1c |  | button | Has all of the above been completed? | Yes,No,N/A
label | 2165c5b8-0e89-54c0-9698-e4bd5b0a4bbe |  | note | Freq - Each lot
label | 8d943c28-1310-5f28-ab9f-acfa19ccc233 |  | note | Key - R
label | 4077835d-1ddf-5c7e-be51-4397cbd38f26 |  | note | Resp - SE
label | 0c699035-d18c-5559-b2cf-a2e2c42a1f94 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | e70de662-bec9-5e64-8f2a-7b18d4fc1be3 |  | button | NATA Test Report: Compaction Tests | Yes,No
date | f9a785e0-e15f-54e8-8748-3edaef6ec456 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Compaction Testing on a Lot Basis
label | fcaa8301-d48f-519c-82a7-1a975d53f2d6 |  | note | Ref docs - VR407.27 PS3040.06
label | 26ea0cd8-ae8c-536c-8209-709c2b54af36 |  | note | Acceptance criteria - All asphalt layers are to be tested and accepted for compaction on a Lot basis, unless otherwise specified by Superintendent, Small Lots are to be assessed under the clauses of Section 173 of the VicRoads Standard Specification Sections for Roadworks and Bridgeworks.
label | 2e6d0253-01ec-5924-ba8f-b0dadee89122 |  | note | Test Requirements:
label | 2c47672b-e907-5c33-87df-7dc70df12858 |  | note | • A lot which has been presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogenous in respect to placement methods, materials and appearance.
label | f10c3d38-69a6-5385-8a64-42842ca4ccfb |  | note | • Sites presented for density testing of the lot shall be randomly selected as per RC 500.16. No sites are to be selected that are within 200 mm of a joint constructed against a cold edge.
label | ac595a1f-a293-5452-9ec8-4bcc676e28b4 |  | note | • Lots > 500 m2 shall have density testing of the longitudinal edge strips of the wearing course and have results reported as a separate lot. Sites for this testing shall be as laid out in VR407.27 (b).-
label | 322e257f-c41d-5ee3-bd38-44c3c7a8c865 |  | note | Lot Size:
label | 893ee33f-f5d3-5bb9-bc83-bdc6662a4c68 |  | note | • For Lot < 50 m2, the acceptance of compaction shall be based on the contractor’s own asphalt quality procedures.
label | a676b13e-bd24-5484-8bb1-5ff26fb28f78 |  | note | • For 50 m2 < Lot < 500 m2, the procedure for testing small areas specified in VR173.04 shall apply.
label | f5ffc741-0035-585d-9e5c-5ed63f592ead |  | note | • For lots exceeding 500 m2, compaction is to be assessed using the characteristic value of density ratio.
label | 8fa05e10-6414-5ad7-80f9-58b684c134bf |  | note | Minimum thickness of cores extracted from the pavement:
label | 167a2280-dd73-5e1f-9535-0a8cd4d1e352 |  | note | • For asphalt of size 7, the individual core thickness extracted from pavement must be >20 mm
label | 0d6e12c8-8d33-5afd-9895-bcd9c11d490d |  | note | • For asphalt of size 10, the individual core thickness extracted from pavement must be >25 mm
label | a8a37bc3-bb62-5616-922b-428fd9619a45 |  | note | • For asphalt of size 14, the individual core thickness extracted from pavement must be >35 mm
label | 0e7fdc16-dd67-58c9-901a-f6f4562c06ec |  | note | • For asphalt of size 20, the individual core thickness extracted from pavement must be >50 mm
button | 67ca6df9-9d7c-50b7-921b-3ebd12c730f0 |  | button | Has all of the above been completed? | Yes,No,N/A
label | ea9d66b3-b29b-52d9-a216-2ded0b33015d |  | note | Freq - Each Lot
label | 70cd82a6-4b16-5e78-b192-413c3d0155ec |  | note | Key - R
label | 44121113-d164-5bb9-bb62-52439c48d492 |  | note | Resp - SE
date | bbad26bb-808b-5692-96e9-d34fad4d36bb |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Completion and Compliance
checkpoint-status |  |  | checkpoint | 4.1 - Finished Surface Levels
label | b4c5b789-87b4-5479-ada8-d5d83e49a3ef |  | note | Ref docs - VR407.29 Table 407.292, Table 407.293 PS3040.023
label | 5ff9c5f0-8ac2-521e-afbd-a3b3ef57e074 |  | note | Acceptance criteria - The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements of Table 407.232 and 407.231.
label | 8d41d2c6-0bf8-5830-941e-21845ea56e52 |  | note | Asphalt Layers
label | 14709416-c8d5-5f11-85b0-0faa230d5e73 |  | note | • Scale A: ± 5 Max.S 8mm (80 points min.)
label | 71af61cb-396b-5f36-8b22-1cbaaee8c311 |  | note | • Scale B:  8 Max. S 8mm (40 points min.)
label | 6f547dfb-c614-5441-811d-e2be9fba822e |  | note | • Where min. average or nominal thickness of overlay specified, average thickness to be calculated as per VR 407.23 (c).
label | a90ffc5a-391e-5219-86d7-13637d11e4fb |  | note | • The minimum number of level measurements to be taken per lot is specified in table 407.292. Mean surface level tolerances for sub-base and pavement courses are specified in Table 407.293.
label | d6f0f7db-542a-5b43-b3d7-5c34249c28d9 |  | note | Sub-base
label | 11b93614-c526-56b2-bb0f-929e4c55b3fa |  | note | • Scale A: +4 to -8 Max.S 8mm (80 points min.)
label | 447010bc-2ca5-521d-a35b-1193da7153f8 |  | note | • Scale B: +6 to -12 Max. S 13mm (40 points min.)
label | bc4ca0de-dfb0-5468-baa4-08bc71d32b1d |  | note | • Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent.
label | 3d4a1908-32f4-5869-bc4f-bb888710a1ea |  | note | Scales for measurement of surface level are to be taken as specified:
label | 0a00818d-0356-562e-b42d-1ab55b04164d |  | note | • Scale A – 80 random measurements with statistical assessment
button | ee2d6937-5bf2-5cc1-ba47-4e66e8755c6e |  | button | Has all of the above been completed? | Yes,No,N/A
label | 244021ee-cf07-50c9-a6da-3fda8462ae77 |  | note | Key - R H
label | e9fe772d-7a9d-5a08-804c-abc40b4c72a9 |  | note | Resp - SV SE
label | c50e438f-8c0c-5efe-97eb-8131f822aea2 |  | note | SI Key - H
label | 2cba35cc-a3ab-5f3f-9510-fef6fa80bcc8 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | 226b218b-04e3-5257-9281-64d9e82809ef |  | button | Conformance Report (Finished surface level and thickness) | Yes,No
date | 9a94f1e9-fab1-5e9b-916e-6dd04512d83a |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Finish Surface/Shape
label | b4342159-41a1-5b5c-9da6-89ae884e61bb |  | note | Ref docs - 407.29 (a), 407.29 (a) (iv), 407.29 (a) (v)
label | 78cbf7f6-62a6-59bb-b419-837534f3ea48 |  | note | Acceptance criteria - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
label | dcebc7fa-5425-578b-826b-38a34cf51488 |  | note | • Flush or not more than 5mm above lip of channel
label | 97a2e884-1a1e-59e2-93eb-97c82a13e4f1 |  | note | • No point on the finished surface of wearing course to be greater than 4 mm below a 3 m straight edge.
label | 965d8bb9-a7b9-5008-ad67-2f742f1bd44a |  | note | • Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside.
label | f2e7ee13-1a55-5dab-8f79-b2d92afbc9e0 |  | note | • Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm.
label | 49f0d871-fa8e-50ed-a889-5e1e18e1fb80 |  | note | • The average width over any 300 m shall not be less than the design or specified width.
label | 813d0368-eb60-5171-8883-39557564225f |  | note | • For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm, respectively.
button | 2fbd9f75-859c-5340-9b88-59da03f43c5e |  | button | Has all of the above been completed? | Yes,No,N/A
label | 1ed38527-15e5-5a25-9d29-bd138a9cb158 |  | note | Freq - Each lot
label | eb79bdf6-73df-524b-8615-aff1d19c4562 |  | note | Key - R
label | 5091c478-8680-53aa-8f68-bc551eb3dbfd |  | note | Resp - SV
label | 7c202c85-1dd3-560d-a31d-ebfc1e0343df |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | efc1b895-face-5aac-80a0-f072dae09fc6 |  | button | Conformance report on finish surface/shape | Yes,No
date | 7eac7df6-3ee0-573c-b13b-1cb51b457d5b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Perform Ride Quality (Final Layer Only)
label | ee4e1878-0ea7-5396-811f-7e52032354e8 |  | note | Ref docs - PS3040.02
label | 522e80ef-c98b-5f24-a559-a4039979c4ba |  | note | Acceptance criteria - (i) The finished pavement surface including the surface of any open graded asphalt must be measured in accordance with the Technical References, including section 180 of the VicRoads Standard Specification Sections for Roadworks and Bridgeworks.
label | bee80e43-d24f-5e8e-886a-3bc4ee145c07 |  | note | (ii) The measured ride quality expressed in terms of the international roughness index (IRI) must meet the maximum values for individual lane roughness and mean lane roughness as specified in Table PS3040.021 (fig 7).
label | 9fcdcac9-36bf-5759-b1e7-2e5fd57cf29e |  | note | (iii) The locations shown in Table PS3040.022 (fig 8) are exempt from ride quality assessment.
label | 8f44dbde-a6b7-5307-bac0-9521f468954b |  | note | (iv) Ride quality measurements must be undertaken as follows:
label | 9c9fa0e3-9e6a-5fa1-b5b3-df64e5bfe8d6 |  | note | (A) within 1 month after the application of the final surfacing and prior to opening of each completed section of new carriageway to traffic;
label | fc303e7a-b96a-5e59-82ba-f7b500ba4172 |  | note | (B) within 12 months following the Date of Practical Completion for any area that exceeded the specified maximum values for ride quality and was accepted by the Superintendent; and
label | 7f01b03e-7f14-5ecd-9c90-a1ba0c3f65c9 |  | note | (C) no earlier than 3 months and no later than 1 month before the end of the Defects Liability Period.
button | 01012acd-5bd5-5b1f-bb15-b7f9916c32a6 |  | button | Has all of the above been completed? | Yes,No,N/A
label | ae93e15f-73b6-5a9c-8bb6-259134c75e6c |  | note | Freq - Each lot
label | 84e5844f-5dc9-5fe2-b2e9-301df2d41547 |  | note | Key - R
label | 39b73226-4db3-59d4-add5-3b9dd1d76a13 |  | note | Resp - SE
label | c36c023f-974a-5a09-9ba8-5f9145054eb3 |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | a613f437-42b2-5a56-882b-39743049fd7e |  | button | Ride Quality Completion | Yes,No
date | 8883c83a-5599-5f5f-8366-25acb9c09942 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0017 Water Relocation | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0017 Water Relocation | c9bea6da-ee4b-424d-a5c4-7dfcb71781f6
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Check Survey Set-out
label | 5c37ec68-e1b5-5ef8-831e-ba40edb5c3bc |  | note | Ref docs - IFC Drawings
label | fdf725a0-5dd8-50df-af08-abe94a24f236 |  | note | Acceptance criteria - Ensure alignment setout has been completed and pegged.
button | a7ebfbb3-dd6c-5723-9422-df1a34d13698 |  | button | Has all of the above been completed? | Yes,No
label | 1534840c-68f4-5b0c-a02e-f86e8ff89e88 |  | note | Freq - Prior to start of works
label | 1aa8ceb6-a135-5d36-be14-0c2ba90733cc |  | note | Key - H
label | 61c9df7a-3fe2-52ea-80ff-42ceaa4dd7cd |  | note | Resp - SE
date | 3ef396a2-774f-57bd-a0c3-fd8553b704e4 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 1cdc1255-fe76-56ae-8290-9626fff6e145 |  | button | Lot map | Yes,No,N/A
date | 8c6d788c-d9bc-5a6f-863c-179b21de01d1 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 97d0d0f7-4932-52f3-9815-0c67cd6426d2 |  | button | Environmental permit | Yes,No,N/A
date | 70a1118c-fd50-5f5b-ae8e-40021c1a5b3f |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 97c8ed84-c213-58e6-9417-a05e82ee5d63 |  | note | Ref docs - AS4130
label | 01b51e89-a3fc-5ffb-83b2-bfb484137f45 |  | note | Acceptance criteria - Assets installed are correct type, class & diameter and comply with AS4130 (as relevant) unless noted otherwise.
label | 021b32a3-985c-570e-86fe-11fe6f388b4a |  | note | Freq - Each Lot
label | 94293c92-cab3-57a2-b3f2-2065d56b0ced |  | note | Key - R
label | f8b46672-4bfc-594e-996e-a5319d132cd5 |  | note | Resp - SE
button | 82b2d7ee-ee1c-5fee-9add-b07c402f7e45 |  | button | Remarks/record | Yes,No,N/A
date | 6ef506d2-8398-50d3-9d56-8c4551d9c400 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Depth of Cover
checkpoint-status |  |  | checkpoint | 3.1 - Depth of Cover Requirements
label | 181a976e-ab35-5be1-a2bb-81a7b9c6907b |  | note | Ref docs - VR Clause 706.03
label | d18354ed-95da-539a-949e-72d16a346b5e |  | note | Acceptance criteria - Cover requirements for water assets shall be:
label | 3089d800-710a-55e6-a837-32453a18534d |  | note | • Pavement surface to top of conduit minimum 1200 mm.
label | 76cceaf8-0ec9-59f5-9e28-210d3d63385d |  | note | • Invert of open drain to top of conduit minimum 750 mm.
label | 14933dab-9753-55c2-afa4-7c25b5f2fba9 |  | note | • Unpaved areas to top of conduit minimum 600 mm.
label | 520f34e6-5f04-5f45-82c8-dc50b6709620 |  | note | • As per asset authority requirement for cover to other assets
label | 3eb1f525-677a-5ed8-9f70-c442f8c0c66e |  | note | Freq - Each Lot
label | cb76b358-4484-5f0c-b95a-235c46bfbf6f |  | note | Key - S
label | f94d81a4-69c0-522b-8ce0-34dad6184e9f |  | note | Resp - SE
button | dedd1621-d686-5988-9dcc-170d050ccee9 |  | button | Remarks/record | Yes,No,N/A
date | fc8dbdb3-3a6f-5520-bb08-88f0251feb69 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Backfill of Excavated Trenches
checkpoint-status |  |  | checkpoint | 4.1 - Bedding / Embedment Material Properties
label | 58f831da-cc95-5cd2-b808-80561223b4ab |  | note | Ref docs - VR Clause 706.06 Table 706.061
label | 5c8c9a63-2531-5fb2-aef7-f3f2cc115012 |  | note | • VR Clause 706.07
label | 595024d1-b5a6-5c39-8330-c596ec83abb6 |  | note | • VR Clause 706.09
label | dd395429-3fee-54df-866b-1ea5935b2252 |  | note | Acceptance criteria - Bedding / embedment requirements are to be as specified by VR706 and VR Table 706.061.
label | f9e93ab9-d25d-58dc-a0a8-3153dda1766a |  | note | Freq - Each Lot
label | 75a3804a-5452-558b-8c57-76a9374506fc |  | note | Key - R
label | 8803825f-6317-5323-9226-0d4991ccf09d |  | note | Resp - SE
label | f43c6948-81f6-51d2-9d6d-05d944f67be9 |  | note | Remarks/record -
button | b2ead47f-45f5-5df7-b30e-e2ba878d0095 |  | button | • Test Report (if applicable) | Yes,No,N/A
date | d50fa01f-8385-51c9-8d83-111143ad26d9 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Bedding / Embedment Placement
label | 5b89141a-31c1-5c78-9069-9cdb5684b8b4 |  | note | Ref docs - VR Clause 706.07
label | b36c8235-9d11-598f-8a28-699fd7d4859e |  | note | Acceptance criteria - Placement of bedding / embedment is to be as per VR 706.07.
label | 607c841d-17ea-5e08-9f7f-7c20d5bbbeae |  | note | Freq - Each Lot
label | 86bdaf50-762f-506e-9118-dead22738d53 |  | note | Key - R
label | 3ea15c82-0b62-5f67-a305-eae99f233e4a |  | note | Resp - SE
date | 43dc06d7-e749-5e6a-86ae-f8323ad9d1b1 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Backfill Material Properties (under paved areas)
label | 43610fe3-6804-5dcc-ad68-34de47b51b0e |  | note | Ref docs - VR Clause Table 706.061
label | 5781045e-3920-54ad-bf97-ed792f38df10 |  | note | Acceptance criteria - Backfill material properties to be as per Table 706.061 (See figure 1).
label | 837f580d-a55d-577d-9a96-9766819336e9 |  | note | Freq - Each Lot
label | cb4b7be2-b0cb-5a6c-9191-5de0e2b0a746 |  | note | Key - R
label | 614b7a6b-c4c4-52f6-9f20-babd90fbcb81 |  | note | Resp - SE
label | 0097b327-a16d-5bd2-a37b-a333e685fde0 |  | note | Remarks/record -
button | 1a3743db-da78-5afc-a232-856d9cf4ef57 |  | button | • NATA Test Report (if applicable) | Yes,No,N/A
date | 82084a36-886a-546b-874b-0ebb991f05c0 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.4 - Backfilling (under paved areas)
label | 6853bcd0-ca63-5f79-bb33-6e979957386c |  | note | Ref docs - VR Clause 706.06, 706.08, 706.09
label | ceb50a80-34c0-5212-9eaf-94eec08a63a7 |  | note | Acceptance criteria - Backfilling requirements and placement to be as per VR706.08 and VR706.09:
label | 89df92e8-786e-5ea4-9889-636f7a7240cf |  | note | – Trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness, and above that level with common backfill material.
label | 2e9e2b97-1be4-54f5-8677-97ec35bb461e |  | note | – Moisture Content between 85-115% as determined in the Modified compactive effort.
label | 615cd5a0-4d0b-57c5-86d7-694b56683956 |  | note | – The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97% based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
label | a6252f8b-448b-5595-8a7e-c5645770b2ce |  | note | – Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
label | 71ace6ee-bb27-5734-8d81-342608e43d53 |  | note | – Detailed proposals for compaction of backfill materials of nominal size greater than 40mm shall be submitted to the Superintendent for review before commencing work
label | 4c69c822-0257-52db-8f10-58d80e8b5edb |  | note | Freq - Each Lot
label | 587bfbf1-09f7-501a-ba47-d6fa7bd398c8 |  | note | Key - R
label | ca5d97cc-30cc-5f0b-ad6d-9d7a1c85c9f9 |  | note | Resp - SE
label | 88c0d166-72c3-52ec-a1a9-a71906147bfc |  | note | SI Key - H
label | 7aa53b1f-e8c6-5b55-8ea9-3a987ce21374 |  | note | Remarks/record -
button | 48f3f04d-3060-54f8-bd71-050b2ca59b69 |  | button | • NATA Test Report (if applicable) | Yes,No,N/A
date | 00e19fb1-4616-5f5c-a8cc-0f91b8e6dd29 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 5.1 - Test Reports
label | 87103499-947b-507d-a579-035f92ac1827 |  | note | Ref docs - VIC Roads Specifications
label | c0755c01-a383-5158-8711-cd94c5dc9280 |  | note | Acceptance criteria - All Test reports received and reviewed.
label | 2ef97ba1-2c1f-5e6c-8f0b-b133e8095d80 |  | note | Any specific asset owner QA documents available to be submitted attached.
button | 1bfcb786-66fa-52f0-97a1-b737c12c1770 |  | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | dab4390a-b40e-587f-8d3b-fa32d11bc09e |  | note | Freq - Each Lot
label | 345ac42a-c520-5291-b1c8-16cd4fbe622a |  | note | Key - R
label | 883a4b5c-fbea-5239-9edf-b1aca23fedf4 |  | note | Resp - SE
date | b045ee02-acf9-55a3-a16b-abddca504703 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - As-built Information
label | ca30e46f-90fc-54b8-94a7-74f1cd5ed600 |  | note | Acceptance criteria - Where applicable, as-built pickup or as constructed drawing been provided to the authority.
button | 8ce72f20-c8ec-5625-8bca-fb3c518f7ddf |  | button | Has all of the above been completed correctly | Yes,No,N/A
label | c5f2498d-a397-5b1c-a95a-b0e1727eefc5 |  | note | Freq - Each Lot
label | b38b161a-54f0-5edf-ab8f-68576f678512 |  | note | Key - R
label | c19e7065-6db9-5836-8757-6593f2785a3a |  | note | Resp - SE
label | 0cc2287e-c1ae-5168-a519-ed50c082bbde |  | note | Remarks/record -
button | 227e9692-0787-58f2-bb4e-961b47c2db30 |  | button | • Survey Conformance Report or as-built drawings to authority | Yes,No,N/A
date | 8ca70d04-d385-586a-a7de-c4a4b1084d51 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Product Non-Conformance
label | 7f3e57a7-5b1d-54b2-88fc-2dbe8f4e316e |  | note | Ref docs - CQMP
label | 5318d2ef-1644-5cf6-8fab-a99155eb2aa0 |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
button | 354bcc64-4db7-587b-a928-5e37e7894845 |  | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | 102f9edf-0f3e-574f-9ead-13857ebd60ea |  | note | Freq - Each Lot
label | 03534d69-9ddb-51fa-86ab-ea056510067a |  | note | Key - R
label | 29a9362e-4c84-5f0d-878b-db3e5983065b |  | note | Resp - SE
label | d402e5d1-5ff3-5f9e-9eed-13df18084d14 |  | note | Remarks/record -
button | a6e16a2b-29ec-5521-b515-1fba4277a98e |  | button | • NCR reports | Yes,No,N/A
date | 4468bf4a-b4d2-5380-bd23-d4d23914d969 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.4 - Quality Representative to check the above criteria and records to confirm
label | 380eeed4-3db3-5801-8d6a-ad4f546d46a1 |  | note | Ref docs - CQMP Lot Records
label | b8b30523-ceaf-56b3-88c7-e8f592c20ba1 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
button | b47d150a-51ef-5d79-886b-9b3f654f4fef |  | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | ab959837-0d81-5ef5-a82c-60832f4d9463 |  | note | Freq - Each Lot
label | aafa4b40-6fb8-54ec-86ef-2769a4bbcbd6 |  | note | Key - R
label | e38de800-2379-552c-b4e5-668e58dad2be |  | note | Resp - SE
label | 63c16381-020e-54ae-9806-0fddfde1dad7 |  | note | Remarks/record -
button | 717ff71e-1839-5030-b6a2-1fc48043140b |  | button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No,N/A
date | ec2aa53a-2ec7-5e33-94cf-972ccc979e32 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.5 - Authority Asset Install Acceptance
label | 93d71fe4-b318-53bc-9f71-76bfcc903357 |  | note | Acceptance criteria - Audit and approval received from accredited SEW consultant.
label | c144a07f-bbaa-5d56-955a-50659bb868a7 |  | note | Freq - Each Lot
label | 99d06fd5-2918-5353-99e9-41c8d03d0799 |  | note | Key - R
label | e2479f30-1897-5a03-9f2b-99e91c77d6ad |  | note | Resp - SE
date | 092aabd0-8573-50e2-9a0f-c0b5c40debfa |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0011 | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0011 Stormwater Drainage Installation | ccc57c69-be54-489e-a816-5f790a03cd1b
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Relevant permits acquired
label | 3e3ce95f-8bf8-5295-bc59-4cc85cbd240b |  | note | Ref docs - SMP
label | c336aa15-5a15-5e79-bd8e-d8a82bfa0b4b |  | note | Acceptance Criteria - DBYD
boolean | 7e103913-b86b-55de-9ff4-e67c042b47b5 |  | tickbox | Permit to Work
boolean | 0abf54bc-0745-51a4-9ac4-f18f5eeccdac |  | tickbox | Penetration Permit
boolean | 0ebdef58-1950-5bd6-b0d2-cf519363d9b8 |  | tickbox | Working at Heights
boolean | c29c96eb-9838-51fa-8ea9-1a8e9d022d31 |  | tickbox | Lifting Permit
boolean | 590dbf08-40df-5f1d-9b73-b9f5736f5cce |  | tickbox | VESI Permit
boolean | bbf85ca0-09a5-50ec-8932-dc541f7d7f1e |  | tickbox | Excavation Permit
button | 9b592494-3a68-5fd0-838e-ca1deed3dc80 |  | button | Have any/all of the above permits been acquired/completed and signed off? | Yes, No, N/A
label | 593ed7e9-f28a-5f6d-9be7-9353dc4daeec |  | note | Frequency - Prior to start of works
label | 9f54d782-febe-5149-b304-fb719c07fdb2 |  | note | Symal Key - H
label | 41097e65-1df6-583d-b4f7-694a244f3faf |  | note | Responsibility - SE
date | de1e3d0e-7cfe-57f5-b80d-74114716367e |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | b150e568-f8ca-563c-8d4b-0a88b7873ae2 |  | button | Lot map | Yes,No,N/A
date | 379a9a3f-e109-534c-8d67-5ac896097a54 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Define Work Lot
label | fb6ccb51-c664-58c1-8150-59545667968e |  | note | Ref docs - VR Clause 173.02 701.20 701.10 IFC Drawings QMP
label | 7fdb66ff-c6aa-5e20-b3b8-361574703792 |  | note | Acceptance Criteria - Survey boundaries clearly define the Underground Drainage Construction works. Lot shall be defined from pit to pit (or endwall, where applicable).
button | f7acedbb-67cc-5ed4-a91a-ef861924293b |  | button | Has all of the above been completed and approved? | Yes, No
label | a7539811-bfca-5cae-9e18-f921ac37f5c9 |  | note | Frequency - Prior to start of works
label | 2694c475-8d30-5438-987f-9e1da313204a |  | note | Symal Key - R
label | 4bdbc060-f784-5083-8864-2eef7f7e6f7d |  | note | Responsibility - SE
date | cab3915b-1931-52d7-ab4e-62c5d1c947ea |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.3 - Conformity with Drawings
label | 0a05cd57-1c7a-5d62-813e-8aa0bb6c0dd7 |  | note | Ref docs - VR Clause 701.10
label | da46cf08-4d9e-570e-b9c1-40d5343d37e8 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
button | 8f6e3fb1-54dc-541b-b2b0-b9a4d3da607e |  | button | Approval to proceed? | Yes, No
label | 9aed9d59-50d6-5f62-8c5e-9bcae9e23063 |  | note | Frequency - Prior to start of works
label | 1bf8e45f-444a-5c89-9789-fa8753148422 |  | note | Symal Key - H
label | 30aad421-f295-5e91-8253-9e541009156e |  | note | Responsibility - SE
label | 7cbfdd7f-a51f-54fe-970a-77494c6935e6 |  | note | Superintendent - H
date | f6421d1a-1692-549f-b629-731d0bb5981e |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Acceptance of Box Culverts
label | 0b92e4b7-d21e-5bda-8183-579faece015b |  | note | Ref docs - VR Clause 619.22 IFC Drawings
label | ff4c98f8-07f0-574b-86ac-059a53b0d978 |  | note | Acceptance Criteria - Complies with specified requirements and free of defects and to drawing dimensions. Box culverts shall be accepted on the basis of full compliance with the requirements of this section and AS 1597.1. Documentation supporting the following quality requirements shall be submitted for review by the Superintendent upon transport and delivery of units to site: (a) visual inspection. (b) dimensional measurements. (c) measurements of clear cover to steel reinforcement. (d) concrete compressive strength test results. (e) proof load test results. (f) ultimate load test results.
button | 881dd912-726a-5904-9f0b-1e7af7d27f64 |  | button | Has all of the above been checked for compliance and approved? | Yes, No, N/A
label | c6e6b180-dde9-5ef1-8796-5215e12ecf2b |  | note | Frequency - Prior to start of works
label | 7b883aed-b03b-5972-8676-bb67769c04ca |  | note | Symal Key - I
label | da4f008e-69c8-538f-9ad9-db245c170f09 |  | note | Responsibility - SE
label | 4597c725-dd2b-58a7-a19f-d3d667d2e8a1 |  | note | Superintendent - R
button | c5e61072-8cf5-5de0-87ef-102070a142a4 |  | button | Remarks/record - Manufacturing Process Records | Yes, No, N/A
button | 558eef68-bdb5-5371-9e5c-089d720d7bd9 |  | button | Manufactures Compliance Certificate | Yes, No, N/A
date | aaf277b3-cb5b-5524-955c-610b6d9fb9d9 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.5 - Acceptance of Precast Reinforced Concrete Pipes
label | 817a3ca8-1655-54c1-b00d-1274a8ea5858 |  | note | Ref docs - VR Clause 701.05 VR 610 IFC Drawing
label | 126fa51a-6e40-582f-9a6d-7da27cd565a7 |  | note | Acceptance Criteria - Precast reinforced concrete shall be of the required sizes and load classes as shown on the drawings. Rubber ring joints shall comply with the requirements of AS 1646. Aggregates for precast reinforced concrete pipes shall comply with the requirements of Section 610 Any steel reinforced concrete pipes that have cracks wider than 0.2 mm or are damaged prior to laying and backfilling shall be rejected.
button | 1163769b-62f1-5ac1-9c19-2265a042990f |  | button | Has all of the above been checked for compliance and approved? | Yes, No, N/A
label | 1d38de52-6c87-5b60-962e-4c4f42f550ea |  | note | Frequency - Prior to start of works
label | 59a401fc-f6aa-5e07-8f92-ccebacfd3823 |  | note | Symal Key - I
label | ed1db58f-d896-5150-ac3a-181b7da111eb |  | note | Responsibility - SE
button | a56c341d-8bf2-5147-96f6-bfce9d3f93db |  | button | Remarks/record - Manufacturing Process Records | Yes, No, N/A
text | adb8abbd-cd90-5f0f-bed9-76ec9aa5b74a |  | textbox | RFI NUMBER:
date | 60f309ee-93d9-5d05-8408-3729a9ca99da |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.6 - Repairs to damaged pipes and box culverts
label | 4fefd570-dd00-5186-b3e2-4e48a3e4f4da |  | note | Ref docs - VR Clause 701.31
label | 860c6137-1602-5612-9255-3080b267358c |  | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance: · cracks wider than 0.5 mm · spalling of concrete · exposed reinforcement · joints that are not fully engaged. Any pipes with defects greater than the following limits shall be removed and replaced: · longitudinal cracks greater than 2 mm · circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm · circumferential cracks around part of the circumference with width greater than 4 mm · penetrations with area greater than 400 mm2 · pipe joints that are separated. Other types of pipes which exhibit defects or are otherwise damaged prior to laying and backfilling shall be rejected. Box culverts which do not comply with the requirements of clause 619.14 prior to laying and backfilling shall be rejected and removed from the site. The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans. No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 9820b0b6-2bda-529a-bd5e-a04ab3aad11b |  | note | Frequency - Each lot
label | 372fca06-cc3c-59f3-9315-e233644f4aee |  | note | Symal Key - H
label | b1a3c738-afa4-59e2-b833-39f55802d870 |  | note | Responsibility - SE
label | bb4ee23f-c1a0-5ac1-8cd0-306f5fa31b77 |  | note | Superintendent - H
date | 15102dff-1b06-5688-840f-363466bf4852 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Bedding and Backfill Materials
label | 9da0459f-dfe1-5d7d-b3ab-3e561c0ef7b8 |  | note | Ref docs - VR Clause 701.09(d) Table 701.091 Table 701.092
label | d74c2c8b-5724-51b1-bed3-0f900fa56e28 |  | note | Acceptance Criteria - Materials used for bedding and selected/ordinary backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
button | f3e9f265-22f1-56bf-8fb4-569e22dfecfa |  | button | Has all of the above been checked for compliance and approved? | Yes, No, N/A
label | 880be642-5fe9-56b9-b3c1-c6bd8eb5a55e |  | note | Frequency - Prior to start of works
label | 1cbe8169-3f05-5994-9f02-3cbd7d8bf6f5 |  | note | Symal Key - R
label | c20f52f4-495e-5257-84d1-cd03d7636ba9 |  | note | Responsibility - SE
button | a28cb48e-8d7c-513d-8b5b-181d5e898c40 |  | button | Remarks/record - Bedding and Backfill Material Conformance | Yes, No, N/A
button | 2c709bf5-a993-5c74-9836-d3072d2fccda |  | button | NATA Test Report: Grading and PI. | Yes, No, N/A
date | 158fe23b-4801-59be-a2a0-9a7d2146b964 |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Excavation
checkpoint-status |  |  | checkpoint | 2.1 - Excavation of Trench
label | 16fd4093-fa6d-5e73-b618-56fff83fe2fd |  | note | Ref docs - VR Clause 701.15 Table 701.151 701.08
label | 95e04f64-ceba-5896-8314-cb5bcf3e8008 |  | note | Acceptance Criteria - Excavate to required depth which shall also include excavation necessary to prepare the culvert/pit foundation & provide the full specified depth of culvert/ pit bedding. Maintain trench width clearances as per table 701.151.
button | 1fd0fc04-214d-5c05-b134-169e09c663f0 |  | button | Has all of the above been completed? | Yes, No, N/A
label | d7ab89eb-f776-51c7-97fc-fe9a20a5d3ab |  | note | Frequency - Each lot
label | f2067392-be01-5f32-a700-fd8613719e7b |  | note | Symal Key - I
label | ab159ed6-7a21-5783-a11e-604bc5bec22a |  | note | Responsibility - SE
date | 89307b3d-77ea-51ad-898b-27aba95fcd97 |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Bedding
checkpoint-status |  |  | checkpoint | 3.1 - Bedding – Layer Thickness
label | 9ff8cca5-1d22-5c02-90e0-9ebd5e7aa40d |  | note | Ref docs - VR Clause 701.16
label | e04600b9-ee12-51cd-983c-0fea97b63b9f |  | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench or where the pipe/culvert is to be placed without trenching to a width 0.8 m greater than the overall width of the culvert or pipe. Bedding to be the compacted thickness of 100 mm where D < 1500 mm 200 mm where D ≥ 1500 mm (D = Pipe Diameter/Culvert Width)
button | a649dc24-9c03-5052-9116-2b2d1a6ec62d |  | button | Has the above been completed? | Yes, No, N/A
label | 66811e2c-d66e-5d83-9d74-1fa57d6d878e |  | note | Frequency - Each lot
label | 671db894-c338-5a21-929d-bd466a7a367e |  | note | Symal Key - R
label | 8c7eb5d9-4644-5b8b-a6ad-f989d21820a6 |  | note | Responsibility - SE
date | 4ffaea03-1deb-589d-9936-15c42f40d24e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Bedding Material - Compaction
label | ea2f9a9d-c894-5b92-bdb7-a6ea3b73a987 |  | note | Ref docs - VR Clause 701.20
label | 253d1729-f8df-556e-8b30-16357f8357aa |  | note | Acceptance Criteria - Compact bedding to refusal using handheld mechanical equipment. If expansive (Swell greater than 2.5%) material is utilised as bedding material, then it shall be tested for its swell properties and have the following criteria met. · Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
button | 435f758d-6452-54a8-90a0-e30971606bc7 |  | button | Has the above been completed? | Yes, No, N/A
label | 6e70bb5f-296d-5d3d-9a69-4be8b1fe07cc |  | note | Frequency - Each lot
label | 768206c5-53a1-5bd3-b1e5-67eb6164b25a |  | note | Symal Key - I
label | 1414b3ab-550d-57bf-a15f-7d8cff0fcbfe |  | note | Responsibility - SE
button | e499b68f-fdb3-5595-a8a0-f63d56c487c7 |  | button | Remarks/record - NATA Test Report: Swell | Yes, No, N/A
date | 0c3bdafd-2f07-5d64-ae69-e25cf75fb523 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Installation of Pipes
checkpoint-status |  |  | checkpoint | 4.1 - Laying of Pipes
label | 70eaa458-1ed8-562c-87c3-0ca08b6c3964 |  | note | Ref docs - VR Clause 701.17 (a) 701.17 (b)
label | 30d24b65-e6f0-5499-83da-5e75604bb075 |  | note | Acceptance Criteria - Laying of Pipes shall not commence until it is verified that pipe bedding complies with the specified lines and levels and compaction requirements.
button | d605a5e8-ed54-5cc0-83d2-1511436d4a35 |  | button | Approval to proceed? | Yes, No, N/A
label | 84163be0-15a0-5c2a-832f-9ba519bf26de |  | note | Laying of pipes shall commence from the downstream end. Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered. The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
button | 8512786e-39a8-5f59-94ed-f851c88b27fe |  | button | Has all of the above been completed correctly and to a high standard? | Yes, No
label | b2ee439a-c08e-5267-9776-e59fbfc3167c |  | note | Frequency - Each lot
label | b030ec9e-519b-5c8d-82db-b56bde38fe01 |  | note | Symal Key - R
label | f381fefe-527f-5bb5-ac4e-7bb8098b60d6 |  | note | Responsibility - SE
label | 1657b275-d6aa-5b74-b778-7624b1ec46a4 |  | note | Superintendent - I
button | 0b4414b8-f8b9-5bd7-97bd-7f9190190830 |  | button | Remarks/record - NATA Test Report: Compaction | Yes, No, N/A
button | 19bc0469-9e9f-5ea9-980a-3670de0c4722 |  | button | Survey Conformance Report | Yes, No, N/A
date | 9d720abb-42f6-526a-81a7-95e58b2fc290 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - As-built Survey
label | 6e12c65b-5ddf-576c-9314-05cc301bc800 |  | note | Ref docs - VR Clause 701.10
label | 2c897431-7284-50e3-9237-56e591900c3a |  | note | Acceptance Criteria - The location and grade of each run of underground drainage shall be verified by a survey certificate prior to backfilling the underground drainage. Invert level of pipes at pits ±50 mm Departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250.
button | 77921ba9-68a7-539b-8279-605f95af3eb3 |  | button | Has the above been completed? | Yes, No, N/A
label | 328d684f-32ec-59f0-aa27-46c6664f1257 |  | note | Frequency - Each lot
label | 7640bd2a-db5f-545d-9de8-1ba89ddc5e68 |  | note | Symal Key - R I
label | 48604a72-b4c7-58b5-bc0c-9a9d74c646bd |  | note | Responsibility - SE
button | 4bf43727-044e-5157-af6f-950f8d5407da |  | button | Remarks/record - Survey Conformance Report | Yes, No, N/A
date | e5112387-7ffb-5050-bd15-74ae2f22c794 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.3 - Jointing and Lifting Holes
label | 9547b334-e5e8-5d7c-aa02-e36272a0d1db |  | note | Ref docs - VR Clause 701.18
label | b9b3ebfd-7ca0-51c7-ac3c-896a43168417 |  | note | Acceptance Criteria - All interlocking joint reinforced concrete pipes shall be mortar jointed or wrapped with a 200 mm wide external joint rubber band. External rubber bands shall be manufactured from natural rubber and have a minimum tensile strength of 18 MPa and a minimum elongation of 400% at break. Rubber ring joint pipes shall be jointed with rubber rings. Ensure rubber rings are clean prior to installation. Verify joints by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket against the values specified by the manufacturer. Where lifting holes are provided, the pipes shall be laid with the hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
button | a0ed39f0-9c59-5dd9-a971-4fae27aeb952 |  | button | Has the above been completed? | Yes, No, N/A
label | a19ccfb7-7bd9-5f7c-9d82-de6479f4e919 |  | note | Frequency - Each lot
label | df50412d-69d7-51f7-a338-2bb8deb7567f |  | note | Symal Key - W
label | 4f26b960-2868-54c7-8159-302b6f70b204 |  | note | Responsibility - SE
button | 0ed3d00c-d355-561f-9982-e8b2e86346e4 |  | button | Remarks/record - Visual Inspection: Joint Overlap | Yes, No, N/A
date | 0e4d6c96-f3b6-5dd9-902f-97fe1dc2ad83 |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Installation of Box Culverts
checkpoint-status |  |  | checkpoint | 5.1 - Laying Box Culverts
label | c69de127-104a-5c88-b77f-185ce33ffdb7 |  | note | Ref docs - VR Clause 701.17 (a) (c) (d)
label | bba0f3e4-e937-546b-9068-e49f13f9066d |  | note | Acceptance Criteria - Consecutive sections of box culverts shall be firmly butted together. The top sections shall match to the bottom sections and shall not be lapped over adjoining bottom section. The contact areas between the top and bottom sections shall be mortared.
label | 81a35443-0121-55ae-8cbc-53704d0c2c6f |  | note | Frequency - Each lot
label | 5a14df36-f74a-54e5-9b34-e8a74ce03560 |  | note | Symal Key - R
label | 9a341a59-0cc5-50fb-9b57-b520513d0e37 |  | note | Responsibility - SE
date | 1da8659f-ea0a-5b1e-be25-e426415029ae |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Mortar
label | 1967c5a8-dc31-5b26-a8f1-51ad72c705d9 |  | note | Ref docs - VR Clause 701.09(f) VR610.32
label | 28915878-94fd-513e-9aac-5ed79b3dab29 |  | note | Acceptance Criteria - Mortar used in the laying of box culverts sections shall comply with the following requirements: - Shrinkage compensating proprietary product. - Min 28-day compressive strength not less than 40 MPa. - Cementitious grouts shall be min Type C Class dual shrinkage compensating. Testing requirements: - Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Following (2 x 7-day cubes, 1 x 28-day cube).
button | c6b1d890-da5f-5fe2-a505-e5041ae7cc36 |  | button | Has the above been completed? | Yes, No, N/A
label | 853dabe2-5567-583c-920c-08d22493d437 |  | note | Frequency - Each lot
label | 566f126a-2626-5a28-84a1-49bb978da407 |  | note | Symal Key - R
label | 59726324-ddd6-5662-a710-1583466a0d0b |  | note | Responsibility - SE
button | 832c10df-9dbd-5f7b-b2f6-054a9b20b60e |  | button | Remarks/record - Technical Data Sheet | Yes, No
date | c18d9560-4d45-50d1-a3ed-74fd73737a0a |  | date | Inspection Date:
checkpoint-group |  |  | section | 6.0 Completion of Works and Backfilling
checkpoint-status |  |  | checkpoint | 6.1 - Backfill Underground Drainage
label | 1ac722dd-1787-5dce-8eb5-21f0e3f442be |  | note | Ref docs - VR Clause 701.19
label | 93a60095-9f2b-51c1-b968-f38d39960304 |  | note | Acceptance Criteria - Place and compact backfill material in max loose layer thickness of 150 mm. (i) Under area to be paved: Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material. Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material. (ii) Under area not to be paved: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
button | e44ace2a-cc18-58ea-a48d-b6e07e09cc0e |  | button | Has all of the above been completed? | Yes, No, N/A
label | 8e2b3b88-1c67-56cf-9997-b8e07ce20ce6 |  | note | Frequency - Each lot
label | f71855bf-2828-5499-aa33-333118453646 |  | note | Symal Key - R I
label | b2e8b369-3ac0-5535-9529-83137cb7f6f9 |  | note | Responsibility - SE
date | 5a2697ad-73f7-5261-b58a-88b877c10bcf |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.2 - Backfill with Cement Stabilised Sand
label | 9a277b18-0627-5097-ba58-153324320713 |  | note | Ref docs - VR Clause 701.19 (c)
label | 2564b59f-a640-5c35-b8d1-feb169dbf727 |  | note | Acceptance Criteria - Culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
button | d5dc4df8-cdae-5d81-985f-d21be2f8cdb3 |  | button | Has the above been completed? | Yes, No, N/A
label | 437bf655-cc9a-5421-9971-4fe700f082cf |  | note | Frequency - Each lot
label | 1fac3d64-5433-5235-b55e-5ed59645b84e |  | note | Symal Key - H
label | 4b6759fb-8fda-54b4-a08c-7424f33403ae |  | note | Responsibility - SE
date | 722ffcfa-5d66-5600-90c1-c3c755ae6b70 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.3 - Compaction: Backfill
label | 60cee991-aa0a-5c29-867e-9afba152f6d4 |  | note | Ref docs - VR Clause 701.20
label | 901db299-582e-5544-a517-6b5719213cc0 |  | note | Acceptance Criteria - One lot is to be raised for backfill for a culvert length (between adjacent pits or end-walls). 3 tests required per layer and a minimum of 20% of all layers for each culvert shall be tested. Material nominal size 40 mm or less after compaction: Mean density ratio not less than 97%. Material nominal size greater than 40 mm after compaction: Submit RFI compacted using a grading, mixing, watering, and rolling procedure that has been trialled, tested and proven.
button | ed42dcd9-17af-51d1-adc8-c85a6879022d |  | button | Has the above been completed? | Yes, No, N/A
label | 68971648-630e-5786-9271-6d9e95cef325 |  | note | Frequency - Each lot
label | a6a8fe40-450b-557a-941b-13b91ea7546e |  | note | Symal Key - R
label | 7e668821-e967-5a75-8bcd-60b567d4ce0a |  | note | Responsibility - SE
label | a737edb7-22c6-543b-b31b-709d990840db |  | note | Superintendent - R
button | 1a8e9a97-d23a-5cd4-a330-ebcd529ab0c3 |  | button | Remarks/record - NATA Test Report: Compaction and Moisture Content | Yes, No
date | b60c385c-d827-5a56-ad45-ddee5d48f552 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.4 - Construction Loading on Culverts
label | c7770f86-1b28-57f7-9409-dc300eb5aa3d |  | note | Ref docs - VR Clause 701.14 Table 701.141
label | 15c42cc7-4dd7-54ca-8a06-ddd1ebc0d766 |  | note | Acceptance Criteria - Construction Traffic shall not be allowed until the minimum cover achieved as per table 701.141
label | 67f3662b-6d3f-5651-8ba2-29c9bc22b8cd |  | note | Frequency - Each lot
label | ac6dcdd4-57ed-5997-bd1e-13d1cd8d4ed2 |  | note | Symal Key - S
label | c769462e-69e8-51b9-a14c-e98123771a5e |  | note | Responsibility - SE
date | 6c633a72-d804-5efa-b876-262d0a1f7652 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.5 - Testing – Backfill Material
label | d52ea478-b888-506e-aaf4-1a358f494d7d |  | note | Ref docs - VR Clause 701.29
label | 6e68582e-2617-5a3c-9f1b-7e019421c2d6 |  | note | Acceptance Criteria - Grading and Plasticity Index– one test per 1000 tonnes or part thereof.
button | a8d4e477-8fe2-58d9-8d16-0e54585d63d8 |  | button | Has the above been completed? | Yes, No, N/A
label | 09b45919-3825-5243-b0bd-a353825d34c2 |  | note | Frequency - Each lot
label | 571e0dc4-eb6d-5239-a8af-fa2f8c1eedbd |  | note | Symal Key - R
label | f78c92cd-c946-521c-a5c3-08eddab13b5e |  | note | Responsibility - SE
button | d6f21c61-3f28-57b7-b33a-fb5122a9c6ab |  | button | Remarks/record - NATA Test Report: Grading and PI | Yes, No, N/A
date | 3486c316-aa92-5012-a4bf-73819b33bb73 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.6 - Existing Pipes Inspection
label | 2500650b-cbba-593e-afe9-3b2cb3a93dda |  | note | Ref docs - 1630-P200-SYM-CVD-DRG-0003
label | eda908f9-dcc3-54da-a2cd-8901ceb9ebe2 |  | note | Acceptance Criteria - Where existing pipes are to be retained, Symal are to undertake CCTV to confirm that pipes are in a satisfactory condition and clear of silt and debris. If necessary, the existing pipe and culverts are to be replaced.
label | 16885002-aa2c-58b9-be34-7f7aa8adc0f6 |  | note | Frequency - Each lot
label | 37bbeed7-0f2d-5633-a571-4a30bef783ce |  | note | Symal Key - R
label | ff8c88c0-76ad-56c3-8c20-8c5222d2e656 |  | note | Responsibility - SE
date | a807c656-bfc0-598c-8187-af1246bd4f5a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.7 - CCTV Inspection
label | f2bc0632-501e-5951-be77-7b80496d6f8d |  | note | Ref docs - 701.3
label | ad7c3558-c42a-54d7-9471-ffe9e9962695 |  | note | Acceptance Criteria - All drainage lines constructed shall be visually inspected using CCTV by an independent testing organization for the full length between pits after completion of earthworks to subgrade level and before commencement of pavement construction. Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia. Upload to the work lot, the report and the CCTV footage. The report shall include a summary of the location of any defects detected by the survey. The lot diagram shall clearly identify the length of drainage pipes for which the CCTV footage was inspected
button | 4e9c5a0a-284b-569b-ab10-a5476bf38c1c |  | button | Has the above been completed? | Yes, No, N/A
label | edd73e40-92c1-5bcf-b269-0273fb46f018 |  | note | Frequency - Each lot
label | 72d5d6d9-8615-5d80-b3e9-50e92c5c1041 |  | note | Symal Key - H
label | db3f966d-ef04-54cb-a489-bb285c74b0b6 |  | note | Responsibility - SE
label | 0efd2075-e802-5bb4-a818-7f6f9584637c |  | note | Superintendent - H
button | b6497061-db96-598a-af3a-e0c71b7c851e |  | button | Remarks/record - CCTV Inspection Report | Yes, No
date | 717af590-9eb1-526f-8de6-558f07ee9bb2 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.8 - Flushing of culverts
label | de7d5d74-e310-5597-9186-ae6b50c7e8fb |  | note | Ref docs - 701.28
label | 2dad93d9-e35f-5f3d-bb7a-ad02fb11f89e |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order
button | dfb7da26-e04f-5358-92ef-1dcec7c46d4e |  | button | Has the above been completed? | Yes, No, N/A
label | fc681951-1739-5dca-906e-9b4de584da09 |  | note | Frequency - Each lot
label | 6d0062d4-2352-5346-8b3d-97254f62ccf9 |  | note | Symal Key - W
label | 8bd3f642-58ea-5e1c-91a7-e7e0d8a870b6 |  | note | Responsibility - SE
date | a805702f-ca85-56f7-842b-74c1fbc6d87d |  | date | Inspection Date:
checkpoint-group |  |  | section | 7.0 Close-Out
checkpoint-status |  |  | checkpoint | 7.1 - Test Reports
label | ae5e8e2a-8c9e-551d-b72d-55ea41210bbc |  | note | Acceptance Criteria - All Test reports received and reviewed
label | 01e310d2-804e-5c4d-9f7f-8999aa9d5309 |  | note | Frequency - Each lot
label | 7dc6c953-a2b8-5993-bd12-0b02b7227787 |  | note | Symal Key - R
label | c59e6fea-a63b-514c-b798-b2d016d3773a |  | note | Responsibility - SE
label | ea993db2-a585-57bc-8b21-0c23de5b24a0 |  | note | Remarks/record - NATA Endorsed Test Reports
date | c6079cb4-9fbc-5c60-8776-5eea44e9fa2d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.2 - Product Non-Conformance
label | ad92ef92-0c27-54cf-bc74-e38737df25a8 |  | note | Ref docs - QMP
label | a4318a47-dd46-57a5-9084-c571f819b501 |  | note | Acceptance Criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 88f92d79-2cad-5341-92c5-30c13f834b32 |  | note | Frequency - Each lot
label | 7c6091af-8aa0-5f42-a29a-6334aed66aa9 |  | note | Symal Key - R
label | ee909513-f5ce-597d-98b3-f3f5b9a8e892 |  | note | Responsibility - SE
label | b73746b1-adfc-503c-81bc-9b7b18ea9b30 |  | note | Remarks/record - NCR No___________ NCR reports
date | 13b14f83-ee64-512d-aec0-dc3490214796 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
label | 74d8a171-f66b-53fc-bf90-d590bff6af61 |  | note | Ref docs - CQMP Lot Records
label | 8a6a1a10-e5b6-5e83-816f-fb2992e388f4 |  | note | Acceptance Criteria - All above criteria met, and records identified attached.
label | 53687fb8-c622-5e58-88cf-664c3b647873 |  | note | Frequency - Each lot
label | ec378c0c-a587-514e-9ec3-d379afe9b1ec |  | note | Symal Key - R
label | 83c8edb3-f86b-5450-ad90-384f739ac113 |  | note | Responsibility - SE
label | 094b45f0-982f-5aaf-9314-d16ac70cfc5c |  | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
date | 622184ad-a528-5444-ac0b-5240bad47051 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0055 Public Lighting Electrical Installation REV 01 | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0055 Public Lighting Electrical Installation REV 01 | cf0c9986-7e55-4ad9-9e37-e8c540dd8a8f
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Services
label | 346bdec9-b869-5249-9651-7e7035f96cec |  | note | Ref docs - VR Clause 731.05
label | be5d996b-716d-5d06-b2e8-46c19135373b |  | note | Acceptance criteria - The location of all existing underground and above ground services has been proven and confirmed on site by the Contractor before commencement of any works.
label | 2159a3be-2487-5cec-bb41-45af65c1a95a |  | note | Freq - Prior to start of works
label | ce955b9e-7a0f-5524-bd90-cece81b3975c |  | note | Key - H
label | f9e300e0-6e9c-5896-b6cb-cd133236ec59 |  | note | Resp - SE/SS
label | 73498b28-da19-56f4-8886-9d54d7b1ceb5 |  | note | Remarks/record - Lot Map
date | b196b724-6c50-5a73-86c6-fa64690664d9 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | cd41955f-348e-5426-8d23-af5b5b4a5087 |  | button | Lot map | Yes,No,N/A
date | 36d89477-569d-5f4a-90a1-0006d9765171 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | 3ee00e3a-4085-5a03-bd07-be5233b290ec |  | button | Environmental permit | Yes,No,N/A
date | a29eedc4-6c37-5544-b288-958bde33e778 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Check Survey Set-out
label | 0aab3828-052c-51cd-8d55-11dcb8bd3cf0 |  | note | Ref docs - IFC Drawings
label | e00ddd32-37db-569f-bf9c-176c07a559da |  | note | Acceptance criteria - Survey set out including frame, benchmark, and recovery points in place.
label | d87feff1-ba18-5e20-89b0-26282f0580c1 |  | note | ○ Set-out to include height of finished surface and checks to be completed to ensure pole is clear of any obstructions (such as future guardrail).
label | 5cd014b9-4023-5f0c-b583-a6ca78a19ba3 |  | note | Freq - Prior to start of works
label | 2373b6d7-cb97-5cfb-8f21-c89b660563c8 |  | note | Key - H
label | 8cd1ad52-659b-50b6-8d7b-43f319569808 |  | note | Resp - SE/SS
date | ff6fec29-9d2f-5960-91b5-a2ba2f44d349 |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Poles and Outreach Brackets
checkpoint-status |  |  | checkpoint | 2.1 - Installation of Frangible, Impact Absorbing (IA) and Slip Base (SB) Poles
label | f9f07576-ed3f-54cc-bfb0-9a093d0169e4 |  | note | Ref docs - VR Clause 731.06 (b) AS/NZS 3000 IFC Drawings Pole Manufacturer Specifications
label | 457b4a82-784a-5853-b44c-452f5c6ca4ed |  | note | Acceptance criteria - Frangible poles are VicRoads type approved, and conform to VicRoads Specification TCS 014 Supply of Frangible Street Lighting Poles and to drawings TC 1064 and TC 1065. These poles were transported to the site of the works in one piece with the base section securely bolted to the upper section.
label | b75b45c6-5259-5372-9873-f4fd2bf33ac2 |  | note | ○ Pole foundations were constructed in accordance with manufacturers requirements.
label | 388e0097-0e5a-5044-a52e-13f2e5c2f03a |  | note | ○ All frangible poles are installed in a vertical position +/- 2 degrees and in accordance with AS/NZS 3000.
label | d772a32b-a8c6-55b0-a44a-e5f35d423a99 |  | note | ○ All absorbing poles are installed so that the joint between pole and base is located at 75 mm ±25 mm above the finished ground surface level.
label | 022d2600-c733-576c-87c4-e105f27176a4 |  | note | ○ All slip planes for slip base poles are located 75 mm ±25 mm above the finished ground surface level to allow proper movement of the pole if involved in a vehicle impact.
label | b6183a69-c47f-55b7-8461-1b870e46e589 |  | note | ○ The Contractor backfilled around the pole and reinstated the ground around the pit and pole. Where a concrete mowing pad has been formed around the pole at ground level, the Contractor ensured that the bolt heads are kept clear of the concrete.
label | f852f769-2013-5b3b-b7dc-51ff85c93118 |  | note | Freq - Each Lot
label | 34b353a9-37fb-5d20-90cd-bf4ac2eb9ac2 |  | note | Key - I
label | ed8127f1-f6a9-5d10-ba5b-2de0b6c82aef |  | note | Resp - SE/SS
boolean | 5fa0c79b-9946-5c31-968f-1dcb2b1fddba |  | tickbox | Remarks/record - Installation Records from Subcontractors
date | cf2fc465-02be-54de-abf7-930ca2078553 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - Installation of Outreach Brackets
label | b233b3ec-3631-53a8-9e05-cf5f60f7c8dd |  | note | Ref docs - VR Clause 731.06 (a) Table 731.061
label | 647ee612-bca3-54d4-8c79-af45f8f81a75 |  | note | Acceptance criteria - All outreach brackets are firmly attached to the pole spigot using the clamping bolt assembly which is supplied with the outreach bracket (refer TCS 050, TC 1060, TC 1061). The bracket and luminaires are aligned as shown in the road lighting design at right angles to the vehicle path on the road, and installed and plumbed the pole and luminaire(s) to within the tolerances specified in Table 731.061
label | eeedd2da-04be-59ed-84e0-94dff4d9d2b1 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 7640acfe-c543-5ca5-a9c0-a409625979af |  | note | Table 731.061 Pole and Luminaire Orientation Details
label | 1c893e66-effb-5915-98e2-c970ddeead3d |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | db9cfd16-614f-534f-9de9-cd885f9c3e0b |  | note | Pole Height SB/IA Metres ¦¦ Lantern Mounting Height Metres ¦¦ Lantern Type (LED) ¦¦ Max Bracket Length Metres ¦¦ Lantern Angle to Road Degrees ¦¦ Lantern Upcast Angle Degrees ¦¦ Lantern Spin Angle Degrees
label | 6e66ffbb-4de3-5ced-823c-a5301264e750 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 0e4f57eb-09e3-524d-a2d2-5224e9243ca3 |  | note | 8.5 ¦¦ 10.0 ¦¦ L1 ¦¦ 3.0 ¦¦ 90 ± 5 ¦¦ 5 ± 1 ¦¦ 0 ± 1
label | 3e99205b-c1e1-5117-8979-562c81f83d4d |  | note | 11.0 ¦¦ 12.5 ¦¦ L2 ¦¦ 5.0 ¦¦ 90 ± 5 ¦¦ 5 ± 1 ¦¦ 0 ± 1
label | 3459d971-1815-5b93-9595-c80527ea51a6 |  | note | 13.5* ¦¦ 15.0 ¦¦ L4 ¦¦ 5.0 ¦¦ 90 ± 5 ¦¦ 5 ± 1 ¦¦ 0 ± 1
label | 59072747-7cdf-55c6-b5b8-5fa54bd1d1e7 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 1ecf5306-4668-5e8c-ba18-df3cc1ba1e1a |  | note | Freq - Each Lot
label | 496a48f2-e79c-5f1c-8170-70fdf60e7be3 |  | note | Key - I
label | b6a5f524-dee5-500c-b805-5a66e2915586 |  | note | Resp - SE/SS
boolean | 785d74aa-64b4-50dd-98c4-cb8ecc7ff620 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | c8c4f175-1544-59f1-8919-6fcb425d992d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.3 - Torque
label | f8cd5ed4-3f28-5bba-9661-5779695b0439 |  | note | Ref docs - VR Clause 731.06 (d) TCN 006
label | 9e2a2870-c8c8-50a0-8567-22d937cbc516 |  | note | Acceptance criteria - Slip base poles are installed in accordance with the following requirements:
label | 2e9b964a-e442-546c-bf45-88450774e61a |  | note | (i) The pole bolt and nut assembly were installed such that the nuts are placed in the upper position to enable ease of access for correct torque installation and for subsequent 30 day cycle torque maintenance checking for slip base poles only as per Work Instruction TCN 006 - Work Instruction Retighten Slip Base Pole Flange Bolts
label | f9faf6a4-1695-5e38-9f67-49c7293685b5 |  | note | (ii) The bolts and nuts have been re run after galvanising and are free of excess galvanising in the threads
label | e5c86bcc-c23a-520b-a8c0-885161f87d02 |  | note | (iii) The thin slip plane washer has been supplied flat and free of kinks, bends, deformation and warping - a damaged slip plane washer can result in incorrect torque and eventual pole failure and shall not be used
label | 41d81f79-f695-5bb6-be5d-edfe1d5f8c46 |  | note | (iv) The slip-plane flange nuts have been slackened off ONE AT A TIME and re-tightened as specified in TCN 006 Work Instruction Retighten Slip Base Pole Bolts.
label | 1f44b6e6-a101-5a1e-8242-a5645a95e16c |  | note | The torque wrench used to tighten the bolts and nuts shall have a current calibration certificate (i.e. not more than 12 months old). The Contractor shall provide a copy of the calibration test report upon request by the Superintendent.
label | 042cf498-6c08-5441-ba72-ef7916ace18c |  | note | Freq - Each Lot
label | 8ccd91f1-d685-5109-91bd-328d830c4dc2 |  | note | Key - I
label | 5a7de021-ad3b-5f7d-86c2-84d9af5d7af1 |  | note | Resp - SE/SS
label | cbedcfe7-d85d-5ab8-a18b-52f91f7c50cb |  | note | SI Key -
boolean | b67e6023-15f2-5ce9-9c96-f3ee5385f906 |  | tickbox | Remarks/record - Installation Records from Subcontractor
boolean | 64244d2b-66da-5d09-9238-95d0fbe3a08b |  | tickbox | Remarks/record - Calibration Certificate for Torque Wrench
date | da3b4341-844e-53bc-9851-076b1fe0643c |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Luminaire Orientation
checkpoint-status |  |  | checkpoint | 3.1 - Luminaire orientation
label | 6ac8bc1b-0d7b-5084-a86c-3d72ac10c97f |  | note | Ref docs - VR Clause 731.07 Table 731.061
label | 74cb4c0a-87a9-5ce5-94d6-f06e6ee76ff1 |  | note | Acceptance criteria - The Contractor installed luminaires such that they meet the mounting and orientation requirements of Table 731.061.
label | 34af7e8e-29b1-5318-8b3e-3ca9aea7ca66 |  | note | Freq - Each Lot
label | ca17b86e-2c59-59ba-b75f-12d9dda5b659 |  | note | Key - I
label | 54513b59-32e8-598b-8455-d40e7651dd27 |  | note | Resp - SE/SS
boolean | 695b4b5f-943c-51dd-81df-a1bfadf6a6f0 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | 6345c3c7-60bc-5424-b37b-e702fe078fe2 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Conduits and Pits
checkpoint-status |  |  | checkpoint | 4.1 - Conduits and Pits
label | d92b01dc-e4c4-5220-92cf-deacc9f0dcde |  | note | Ref docs - VR Clause 731.08
label | b0b7f008-c561-5cc2-8d70-da2810680764 |  | note | Acceptance criteria - Pits are generally located 1 metre in advance of, and 1 metre off the line of, each pole. A two metre spare length of each cable has been left coiled in each pit.
label | c6643b1f-e3f3-509f-ba13-28ac47242ea8 |  | note | Freq - Each Lot
label | ef6e8d46-855a-530a-8cd5-83a7c9268eb3 |  | note | Key - I
label | 47535069-d00f-5226-96b6-869b4e622200 |  | note | Resp - SE/SS
date | de61ad37-c9c0-505a-b36c-120509a4650b |  | date | Inspection Date:
checkpoint-group |  |  | section | 5.0 Electrical
checkpoint-status |  |  | checkpoint | 5.1 - Wiring Rules
label | d865fd9b-676b-5d5f-b367-119348b1b74a |  | note | Ref docs - VR Clause 731.11 (a) AS/NZS 3000
label | 0085f133-12a0-51d0-872c-160c8af17a6e |  | note | Acceptance criteria - All electrical works, electrical fittings, materials and installations fully conform to the requirements of the latest edition of AS/NZS 3000.
label | fb6b5d1a-ee2d-5bff-9101-eaf995f9c0b0 |  | note | ○ Where AS/NZS 3000 did not cover a specific aspect of the electrical works (e.g. such as pits) all works were undertaken in conformance to the requirements of the Energy Safe Victoria.
label | 6c98a3a9-38e8-5d2b-b651-a7a7965308c9 |  | note | Freq - Each Lot
label | c980aee0-81f1-5522-ae97-80bb95691fe2 |  | note | Key - R
label | 1b489711-a377-51e8-b802-171b77a17df7 |  | note | Resp - SE/SS
boolean | 0c6d70fb-1fa1-509f-8e8a-9775a5d84333 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | fe6358ea-7621-5338-bef9-32d240b5eafb |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.2 - Registered Electrical Contractor
label | c559a99a-985f-58e6-bc24-517db635d8a2 |  | note | Ref docs - VR Clause 731.11 (b)
label | ecb79759-a5a0-5d20-a0e1-0a47e224f955 |  | note | Acceptance criteria - The electrical contractor engaged to carry out electrical works on any VicRoads road lighting installation (Public Lighting Site) were a Registered Electrical Contractor, being registered in accordance with:
label | a4ad32c1-a350-5fc1-80b7-7f99affc61fa |  | note | (i) Part 3 of the Electricity Safety Act 1998; and
label | 150d9b44-b128-5280-abf9-6502b05bbc05 |  | note | (ii) Electricity Safety (Installations) Regulations 2009.
label | dd87d51a-7c17-522b-9a99-ffe154ccb1b0 |  | note | The electrical contractor was also prequalified within the VicRoads prequalification scheme at the level of ‘Traffic Control System Installation and Maintenance; Traffic Control Equipment (STCE)’.
label | 8d99a209-cdc9-5cd5-8766-5fab5402ac02 |  | note | Freq - Each Lot
label | 308877d1-9119-5989-a7d3-70bcf4905a05 |  | note | Key - R
label | 5e1962f6-11d6-5e56-8822-1b13c7b94863 |  | note | Resp - SE/SS
boolean | f675f223-aad1-5615-baf3-fa468e44b251 |  | tickbox | Remarks/record - Compliance Certificate of Electrical contractor
date | d30b63cb-3581-5692-951a-e93c91cc5fd7 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.3 - Electrical Design
label | ed096afe-274f-549a-a836-74929626d90e |  | note | Ref docs - VR Clause 731.11 (c)
label | 5c6f14bc-5f9a-50b3-8c14-16626e80b325 |  | note | Acceptance criteria - Where practicable, all above ground electrical installations and works, such as point of power supply and the distribution cabinet, have been located a minimum of 5 m from any carriageway.
label | 058265eb-a7e8-59f2-a2c2-ad30321e347e |  | note | Freq - Each Lot
label | ac81ca6b-a22f-549e-a4b4-0b7fefc0ee14 |  | note | Key - R
label | e43a441f-6762-5384-a720-024aaa2f6967 |  | note | Resp - SE/SS
date | 94f53ec7-8af3-5fa2-96df-25040b54d7c5 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.4 - Power Supply
label | 4c9669ae-e338-5c64-91df-042b3ac0349e |  | note | Ref docs - VR Clause 731.11 (d)
label | 6aa478e5-a548-59a3-a2bd-5281c6c131d5 |  | note | Acceptance criteria - The supply of electricity is in accordance with the following:
label | 05e3d31d-d878-5339-9991-dfb2151cdf8d |  | note | (i) The ‘Point of Supply’ has been determined in conjunction with the relevant power distribution company. The supply of electrical power from the point of supply to the meter in the distribution cabinet has been in accordance with the requirements of the relevant power distribution company.
label | 3e5255c3-8bb5-56ff-999d-fbf085a3e039 |  | note | (ii) The electricity supply has been a 415 volt 3 phase AC supply. Single phase power may only be supplied with the prior written approval of the Superintendent. The low voltage power supplies has been strategically placed to minimise the maximum load on each lighting circuit and to limit the extent of voltage drop.
label | 61c18044-68a8-5002-9401-4b3140ff1415 |  | note | (iii) In accordance with the wiring design, copper consumer mains cable have been provided in underground conduit to the base of each LV supply point pole mechanically protected to 2.4 metres above ground level (on the pole) with 6 metre tail to power distribution company requirements for final termination by the power distribution company into a 3 phase, 100 amp, Fused Mains Box, 4 metres above ground in accordance with the Victorian Service and Installation Rules (SIRs). The cable for trunk electricity supply from the ‘point of supply’ to the road lighting distribution board or the appropriate road lighting power supply pit (where no distribution board is installed) as appropriate, is not less than 16 mm square 4 core, 3 phase plus earth, copper XLPE cable.
label | 83c43b93-60ae-581f-883f-8ae9b5bec06c |  | note | Freq - Each Lot
label | 1f8e65db-16b8-5cfe-879a-8a5626cb6c08 |  | note | Key - I
label | 3dc48f1e-29c1-5b8a-af86-e1bbcdfa4c5f |  | note | Resp - SE/SS
boolean | 1021aa0b-5e07-55d0-a4ad-79ef086a7f5e |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | 22ad9b13-7e6e-5574-83dc-366751ebbfbd |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.5 - Electrical Distribution Cabinet
label | a3eff2c9-a147-5752-885e-7be23030ae32 |  | note | Ref docs - VR Clause 731.11 (e) TCS 043
label | 8c035f20-6e7a-5c33-9ae2-05db4fd2c060 |  | note | Acceptance criteria - (i) The distribution cabinet is in accordance with VicRoads Specification TCS 043.
label | db2330ce-7159-50ec-852a-cbe1c65162c9 |  | note | (ii) A distribution cabinet may be used to supply electricity to road lighting assets only or it may be used to supply a combination of road lighting assets and other ITS assets.
label | 2450eff9-fa2e-5546-ab35-9a36105da2d1 |  | note | (iii) Unless specifically approved by the Superintendent, each site or installation shall include one only distribution cabinet.
label | 2c2c9f64-f61d-5b19-8da6-e0a246f43d1e |  | note | (iv) Where an existing distribution cabinet does not have sufficient spare capacity for additional assets, a new distribution cabinet with sufficient capacity has replaced the existing distribution cabinet.
label | d7774609-91c0-550d-b014-21885b3cf8da |  | note | (v) Two or more distribution cabinets at the same location are not installed.
label | 3805126f-38f8-53fb-9857-f9af71294ef7 |  | note | (vi) The cabinet is located not less than 5 metres from any carriageway, and where possible, beyond the clear zone. For any distribution cabinet located within the clear zone, the Contractor has provided traffic barriers to protect the cabinet.
label | 39a488a1-4796-53a3-a540-3c7f849ba212 |  | note | (vii) The PE cell has been located so as to not be affected by light spillage at night.
label | b8e377b6-34fd-52fa-9d30-935dd7a20dbf |  | note | Freq - Each Lot
label | bd0ff36a-5c77-5053-9698-f1cc96a0b82a |  | note | Key - R
label | c3fe155a-f611-5cca-b42d-50baac235319 |  | note | Resp - SE/SS
boolean | 8f9193ad-1b89-5e04-aa80-1b6657f119d1 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | a1fe6fba-2813-5d41-bb0d-7ff22c38a1cd |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.6 - Earthing Requirements
label | 2f196ccd-87b1-5cee-9c6f-d266d673c299 |  | note | Ref docs - VR Clause 731.11 (g) AS/NZS 3000
label | a249a326-78cf-5f19-bda2-c57a5ab670e5 |  | note | Acceptance criteria - An earth rod has been installed in the earth rod inspection pit in the concrete base of the distribution cabinet as shown on VicRoads Standard Drawing TC 1062.
label | 314da189-96d4-5cf6-870b-d27ced5faf96 |  | note | ○ An earth cable attached to the earth rod has been provided and installed in all VicRoads lighting circuits from the distribution cabinet. All earths have been terminated within the lighting distribution cabinet in accordance with Wiring Rules AS/NZS 3000 for the M.E.N. (multiple earthed neutral) system of earthing.
label | fb44a443-8600-5bc2-89b2-497d800750e2 |  | note | ○ Where necessary, and in accordance with the wiring design, a separate PVC insulated and sheathed earth cable has been provided to ensure compliance with AS/NZS 3000.
label | 59838d71-6d0e-5292-8d47-c1811a988985 |  | note | ○ All poles have been individually earthed to the earth cable in the pit in the case of frangible poles and to the earth cable in the pole in the case of rigid poles.
label | aa4abbc8-d4c2-58f0-8d7c-ca77aeedc319 |  | note | ○ All luminaires have been individually earthed.
label | ea96d7ee-0fb4-58c3-a5ad-599793e8decd |  | note | ○ The size of earth cable is to be designed to ensure a Fault Loop Impedance ‘low enough to allow sufficient current to flow in the fault loop to cause the protective device to operate within the disconnection time’ in accordance with AS/NZS 3000.
label | 49abf547-54d8-55e2-ada3-430f738ae099 |  | note | Freq - Each Lot
label | ab1c7232-3af8-5641-b2ab-91187d0cd844 |  | note | Key - I
label | a5084c9f-3de8-5ab9-ac16-bafb037c9413 |  | note | Resp - SE/SS
boolean | 19703fe0-e4a6-555e-a805-309d42e80655 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | c1a02d3e-5c10-5b03-a619-d6979c763c8d |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.7 - Trunk Cabling
label | db1fd457-9e1f-58f1-909a-fedbcc822d79 |  | note | Ref docs - VR Clause 731.11 (h)
label | 9f37023e-b79d-5bb4-97b9-760a583462c3 |  | note | Acceptance criteria - The cable used to connect the distribution cabinet to the first lighting pole and between lighting poles is one of the following methods:
label | b843e4a4-31ea-53d5-a9ac-a6d5cb245751 |  | note | (i) Orange circular, 4 core and earth
label | 9d37a217-4979-5229-a604-5fc5bb6e3be3 |  | note | (ii) XLPE, 4 core and earth.
label | bf1dd18d-77c0-5f3d-944f-033aaa8cc5d2 |  | note | For each trunk cable entering a cable pit, a minimum of 2 m of spare cable has been coiled and left in each cable pit. This is to provide spare cable length for maintenance purposes.
label | f067b8bc-c96e-575e-ae48-0d15082a754c |  | note | Freq - Each Lot
label | fc87f4ef-6d6d-5e29-a6d8-fe580d4a31f2 |  | note | Key - I
label | 3439e6d2-6d6d-56e5-8f1f-148001f9c10b |  | note | Resp - SE/SS
boolean | a2a886d0-e290-555e-b421-4782765080cb |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | fab57f9f-2c51-5d8c-bcd5-1122995ae7ac |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.8 - Jointing
label | 046e6e07-acc8-5a54-b31c-3fae4eb56012 |  | note | Ref docs - VR Clause 731.11 (i)
label | d23b1e28-6a5b-5e88-b213-f6ae6cc581f7 |  | note | Acceptance criteria - All electrical cable joints in pits are waterproof.
label | 6479f3d0-cec7-53c9-9b04-0a65d0ab52ae |  | note | ○ Jointing is only allowed when connecting the pole wiring to the trunk cable as detailed in (i) and (ii) below.
label | ad2c58b1-9625-5fcb-9b29-5aeca913f367 |  | note | ○ Joints in the trunk cable for any other purpose (e.g. to extend a cable length) are not allowed without approval from the Superintendant.
label | ae10ad14-dcb9-5c30-b69e-f5fc7ad32fe6 |  | note | ○ Connection of the ‘trunk’ wiring to the ‘pole’ wiring in the cable pit has been achieved in one of the following manners:
label | efa99aa7-60ef-5e8a-afbd-a481a5d0e5ad |  | note | (i) Bell Style Enclosure
label | 4c883116-2e6a-50ef-96cd-80fbb41f464c |  | note | An appropriate sized, VicRoads approved, ‘bell style’ enclosure with an ingress rating of not less than IP68. The cables to be fitted into the enclosure and sealed with heat-shrink or similar in accordance with the enclosure manufacturer’s directions. The enclosure is to include:
label | 2f9a0615-fc1a-5636-9ef5-6657733b2761 |  | note | (i) Active connector
label | b5ee3245-569a-5b49-80c4-ee14646e4b15 |  | note | (ii) Neutral connector
label | b4cf14b4-0643-5081-890c-f7cb1c204a01 |  | note | (iii) Earth connector
label | 720b8839-2ff3-5263-84cb-01f6e3af1cae |  | note | (iv) In-line, 8 amp, waterproof fuse to enable complete isolation of pole for maintenance purposes to enable complete isolation of pole for maintenance purposes.
label | 4b0ed9fe-f20a-5d37-8b00-44970fd3a1ce |  | note | All connectors are further protected from water ingress by use of a water-displacing gel filled cap.
label | a3a1e355-4be4-542f-bd8b-2647f5447124 |  | note | The enclosure is designed to be held in place on the side of the pit, just under the pit lid, using a suitable mounting bracket. See Standard Drawings TC 1071 and TC 1072.
label | 173922af-1405-5e4c-a652-e955163dc8c6 |  | note | (i) Underground Insulation Piercing Connectors
label | 542b2747-d2fd-58b3-9cb1-e6e3b4ff1e88 |  | note | Suitable sized, insulation piercing, low voltage, waterproof connector. Such connectors are the type that use torque controlled, shearing type bolts. This type of connection also uses an ‘in line’ submersible 8 amp fuse to enable complete isolation of pole for maintenance purposes.
label | 3586bd0b-4ea3-5f9a-8d0d-45e5fd0a868b |  | note | Freq - Each Lot
label | 9e26412c-fc9a-520b-bb9d-f312f09127ab |  | note | Key - I
label | 387fb727-148e-502f-bb44-3dce59762bb3 |  | note | Resp - SE/SS
boolean | 866d4aee-7d60-5e86-81d6-10ad6928e6ed |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | 94f83def-d8ab-5723-af64-48d40979b63c |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 5.9 - Pole Cabling
label | 818adcaa-77c8-5003-920d-70eae1fdf844 |  | note | Ref docs - VR Clause 731.11 (i)
label | c8eda293-19eb-56ff-ae91-b9fef2cc0544 |  | note | Acceptance criteria - Each pole has been cabled from the cable joint in the adjacent pit to the luminaire located at the limit of the bracket arm using one of the following methods:
label | 86f1479d-8d74-5dba-98c1-9c375dd43b09 |  | note | (i) 2 m2 core, power industry cable with separate earth cable
label | 4f103154-e0bd-5e3e-8206-602088b579b2 |  | note | (ii) 2.5 mm2, 2 core and earth, TPS (between luminaires on a double outreach only)
label | f0b69b9b-d4c4-5171-8a1a-08b5ba19dc7d |  | note | Note: The use of 2.52 TPS within the pole is no longer an approved wiring method.
label | 01251473-a949-5948-816a-d30533b6548f |  | note | In an impact absorbing pole the cable has been supplied through the flexible conduit fitted inside the pole from the cable termination access door to the pole spigot, as shown in Standard Drawing TC 1064. Where a double bracket arm is used, 1.5 m of cable has been looped between the luminaires.
label | a330c534-2453-562c-ba6f-91eeae1cf423 |  | note | Freq - Each Lot
label | d1a411bf-c5f7-55df-bc7f-e71b944d2476 |  | note | Key - I
label | 31020e61-d5d6-5ce6-b3cb-a8928b096b1e |  | note | Resp - SE/SS
boolean | e75014cc-8da9-5c76-9e07-eab8f2bc4400 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | 3817a121-40b5-5429-a032-798ec13fb335 |  | date | Inspection Date:
checkpoint-group |  |  | section | 6.0 Labelling of Installed Assets
checkpoint-status |  |  | checkpoint | 6.1 - Distribution Cabinet Labeling
label | 46d7a501-1fd5-5abb-abb6-d336e989a360 |  | note | Ref docs - VR Clause 731.12 (a)
label | a392423d-a60c-5e4c-9e32-79c37be76400 |  | note | Acceptance criteria - A cabinet identification label conforming to VicRoads Standard Drawing TC 2100 has been affixed to the distribution cabinet. The Superintendent will advise of the site number. The Contractor has maintained the cabinet label(s) to be clean, free of graffiti and clearly legible. The label has been located such that is can be viewed from the roadway.
label | cca87296-5c6f-57d8-a988-1b4a179856d6 |  | note | Freq - Each Lot
label | f63530e1-2942-514a-9518-8613667a1754 |  | note | Key - I
label | 4590b21a-6216-5534-963a-e93c27adb839 |  | note | Resp - SE/SS
boolean | b0277041-87f8-53e4-8364-f1b438cb4f22 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | fcc63ed9-dd2d-5e16-b435-1fee51055327 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 6.2 - Pole Labelling
label | 7d51996c-036f-5c9a-9829-5a2ef431df8d |  | note | Ref docs - VR Clause 731.12 (b)
label | ee31aac7-835c-56b2-a7d8-f13cd643aa0a |  | note | Acceptance criteria - Each lighting pole has a label affixed to it in accordance with drawing number TC 2106. A VicRoads full asset number consists of a 5 digit site asset number followed by a 3 digit pole number. The string of 8 numbers is considered the full pole number. The pole location identifier provides for additional information to be coded. See standard drawings TC 1076 and TC 1077.
label | 1e3a70c4-d3e5-5ce2-a3a0-e05896e5e4a3 |  | note | ○ Each label installed has the correct number overlays stuck on - matching the pole identification as per plans and inventory information provided by the Superintendent. There has been no blank squares/boxes on a pole identification label and each square contains a number from 0 to 9.
label | 2b413832-bb52-50a9-bbda-145677b8d92d |  | note | ○ The pole label directly faces oncoming traffic at approximately a 45 degree angle between 2.5 m to 3 m above the surrounding ground level. For any lighting pole with a single outreach, one label has been installed. For any lighting pole with a double outreach and/or lighting up multiple passageways, two labels have been installed so that they are facing oncoming traffic, allowing it to be readable from either direction. See standard drawing TC 1078.
label | 2679c94f-cbce-5737-a517-94899e7457ac |  | note | Freq - Each Lot
label | 8a9befb0-0c5f-5542-93d1-84dedaa801e9 |  | note | Key - I
label | 41e74fbf-05a7-5d92-8f4c-229cfcb86cd2 |  | note | Resp - SE/SS
boolean | ed5dc787-0fd1-52bd-a1db-6cd78bf6fb81 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | 2ab4535a-06c7-5a14-81c6-2fa7885e3202 |  | date | Inspection Date:
checkpoint-group |  |  | section | 7.0 Completion
checkpoint-status |  |  | checkpoint | 7.1 - Backfilling, Re-Instatement and Clean-Up Works
label | 139e4a7b-b114-589a-9f94-ca9f2a7265eb |  | note | Ref docs - VR Clause 731.15
label | 8573cda5-2e84-5c8e-bbd5-674d606feb50 |  | note | Acceptance criteria - The Contractor has undertaken backfilling in accordance with Section 733 Conduits and Pits for Underground Wiring and Cabling, clause 733.06 Backfilling.
label | 1eb00f15-44f7-5298-9018-bd98c16f5a03 |  | note | ○ On completion of all excavation and reinstatement works, the Contractor has ensured that all rubble, surplus crushed rock, surplus pavement materials, surplus concrete and all other surplus materials are removed from the site. The Contractor has left the work site in a clean and safe condition.
label | 9d2ff5b5-c3ec-532e-adb8-b390ceccf6c1 |  | note | Freq - Each Lot
label | 31a16953-be16-585d-a3b4-de925f7cba68 |  | note | Key - I
label | c84447ad-1105-544c-8c45-f3aa66d733b2 |  | note | Resp - SE/SS
date | 3c1f0e07-4629-5372-80b6-66eb7db8470e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.2 - Compliance
label | c08fa630-3a0f-5ea3-aeae-e17a08c118df |  | note | Ref docs - VR Clause 731.16 AS/NZS 3000
label | 7a04bfde-8af4-5a13-a0be-d7e67830792d |  | note | Acceptance criteria - Following implementation of the installation phase of a stand-alone VicRoads lighting installation under this standard section, the Contractor has:
label | a49c5676-084e-5db9-b437-b8dbde33f262 |  | note | (i) Checked and adjusted luminaire orientation as required
label | df818fe4-d7e4-56b5-9fe2-e409f43e7a9a |  | note | (ii) Replaced all luminaires containing PE cells, or with the approval of the Superintendent, bypassed the PE cells in the luminaires
label | dfdd53e9-d262-513e-9051-5e651644cd52 |  | note | (iii) Replaced all damaged or non-functional luminaires, ballasts, and external igniters
label | d1d85c16-be17-52ee-8c6e-610921a68ffa |  | note | (iv) Checked all brackets for type, size, shape and tolerance and replace any not in conformance with the VicRoads standard drawings and within the specified tolerance limits
label | a0097c8b-4c78-585b-8848-8bb9523f4f08 |  | note | (v) Checked and adjusted all brackets for fixing and for orientation
label | bd4107e6-193e-5d0a-8a5e-f3d29aa45a79 |  | note | (vi) Inspected all joint use poles and joint use mast arms for proper installation and functioning, and rectified all faults
label | fcac683d-a3d7-5131-a056-46f4d29daca5 |  | note | (vii) Checked all lighting poles for type, size, location, orientation, bolt washers, bolt torque, slip plane washer, verticality, and ground clearance, and where not in compliance replaced, adjusted or reinstalled as appropriate
label | f877d1e9-58ad-5d40-832a-d9803f86329c |  | note | (viii) Inspected all pits, conduits, cables, and all other components, and where faulty repaired or replaced as necessary
label | 043a1826-dc5c-57c2-a4b6-f27f83d3987d |  | note | (ix) Checked all electrical circuitry, materials, components, and equipment for conformance with AS/NZS 3000, and rectifed where full compliance has not been achieved
label | ebe1c018-8d3e-5df7-8188-6e682745ff03 |  | note | (x) Checked and confirmed that the distribution cabinet has been properly installed and sealed from pests and moisture and rectifed as necessary
label | e9af99e5-3fd9-5b05-94ca-d80a58efa2e7 |  | note | (xi) Inspected and tested the distribution cabinet for faults and non-complying components
label | fe45cb26-f57a-5f76-a360-a27234769222 |  | note | (xii) Tested the PE Cell and switching gear and replaced if found to be faulty or performing unsatisfactorily
label | d9096f99-0709-5bfd-bd62-c5f69b79604b |  | note | (xiii) Checked circuit diagrams for accuracy of each respective circuit
label | bfdb3e94-1443-5cb0-99df-d0b2d1ef87de |  | note | (xiv) Placed a copy of circuit diagrams in the distribution cabinet.
label | 9d9a98b1-57ac-57f0-8cb1-ddd7ccef076b |  | note | Freq - Each Lot
label | 80f3c063-7c26-50ad-ac3f-e3f6fce5fefb |  | note | Key - I
label | bb74758a-9d34-584d-9cd5-e20cfd307e90 |  | note | Resp - SE/SS
boolean | 6af6afaa-e528-58e4-9d7d-1e52a0aebe54 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | 0b2a4133-586d-5229-a6da-50fc6aba95e4 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.3 - Testing and Certificate of Electrical Safety
label | 56463a92-a662-5bc8-bed7-efc83856768b |  | note | Ref docs - VR Clause 731.16 (b)
label | 82e1b884-3243-5584-87a9-724e2a35eb53 |  | note | Acceptance criteria - Prior to final acceptance, the Contractor has tested all distribution cabinets, circuits, switches, PE cells, luminaires, and all other electrical and electronic components for correct installation and operation.
label | 92b4b043-5c52-5248-9205-351496536945 |  | note | ○ The Contractor has been responsible for arranging for the issuing of a Certificate of Electrical Safety for the electrical installation. The Superintendent will not accept the lighting installation as complete until such time as the Certificate of Electrical Safety has been issued.
label | 0d263555-c3b1-5280-a453-d7ed977df502 |  | note | Freq - Each Lot
label | 98171afc-0725-533a-bcbe-0e12bfbd356e |  | note | Key - R
label | ef30ed09-a357-588b-910d-309992d47996 |  | note | Resp - SE/SS
label | b65ab7a6-5a53-5d44-bd3e-c7278ecd386a |  | note | SI Key - W
boolean | b06bcb48-dd96-5a95-a39d-273350379826 |  | tickbox | Remarks/record - Certificate of Electrical Safety
date | 4289c36a-b3d8-5675-8134-48ab064c7312 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.4 - Commissioning
label | e34204a1-e0b5-5378-ac02-1b8af3fa4d18 |  | note | Ref docs - VR Clause 731.16 (c)
label | 2847bbb3-dd81-518d-a19b-484c43770a39 |  | note | Acceptance criteria - Upon final acceptance, the Contractor has switched on the lighting installation at the distribution cabinet in automatic mode, and recorded the time, date and meter reading for contractual, warranty and power supply purposes and supplied this record to the Superintendent within 48 hours.
label | 1d473a99-6575-5a0c-8fe0-120bcce894ba |  | note | Freq - Each Lot
label | a78e69f7-1339-5f80-a55c-66e01bb7e67f |  | note | Key - R
label | b614357c-af88-5406-9d29-def3623c67bb |  | note | Resp - SE/SS
label | ec2c7ef4-5068-5e97-8ab4-962b153cefd9 |  | note | SI Key - W
boolean | 9d86e954-d6e1-51bc-b15c-0faafa2be962 |  | tickbox | Remarks/record - Installation Records from Subcontractor
date | 865b8888-7ab0-5580-870b-8d0a099b7037 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 7.5 - As-Built Information
label | 0c874654-c2fb-5fe8-aaf4-447f3a7fd74d |  | note | Ref docs - VR Clause 731.16 (d)
label | d084b6a4-fbef-5c1b-9378-1273c50965ad |  | note | Acceptance criteria - The Contractor has supplied to the Superintendent a copy of ‘As Constructed’ plans
label | 6d1612ff-1de3-5b24-9520-542c454af400 |  | note | Freq - Each Lot
label | 6fc744ad-d446-53ef-bd4d-8409827cddc5 |  | note | Key - R
label | 5da57530-4d3c-5a66-a942-26c35bf82129 |  | note | Resp - SE/SS
boolean | 65b0d542-4dcd-5641-ba32-3a0108a0b522 |  | tickbox | Remarks/record - Survey Report
date | 23101e78-1f12-5ee4-b042-4732bbfdf262 |  | date | Inspection Date:
checkpoint-group |  |  | section | 8.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 8.1 - Test Reports
label | e36400ea-74c5-5fa7-bf18-ca6efc6fdaa5 |  | note | Ref docs - VIC Roads Specifications
label | c68ad0e0-3b1b-50b0-9361-dc59ab8ba60a |  | note | Acceptance criteria - All Test reports received and reviewed.
label | 78f239ec-38a4-5428-a03d-368e8643c001 |  | note | Freq - Each Lot
label | 74c79cb2-71e8-5dc5-8f2a-b6c76fa2815c |  | note | Key - R
label | 29f6e316-e07e-5163-8f92-009f25323f7a |  | note | Resp - SE/SS
boolean | 5a22966e-f2b0-50da-b935-1c3315a8b2bb |  | tickbox | Remarks/record - NATA Endorsed Test Reports
date | 3842a632-a7bf-5d54-9b66-6f8c0cda85c4 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 8.2 - Product Non-Conformance
label | 09e981c6-9b49-5ab4-ab94-98fecb314239 |  | note | Ref docs - CQMP
label | e2702454-b7c4-5efc-93c0-f514b5f9120d |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 09af3c4e-b3d8-540a-83b4-51b9181f1dd6 |  | note | Freq - Each Lot
label | f03cb2ac-b12c-5c96-b349-74999c68bebe |  | note | Key - R
label | da04126a-1d6d-5311-8037-54f5397a5954 |  | note | Resp - SE/SS
boolean | 251725a1-e041-57da-b150-0cf6307d5d5f |  | tickbox | Remarks/record - NCR reports
date | 0c1fe23b-7353-563c-bac9-6bcf6b380451 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping | e9007ad5-8686-4cfd-9689-41b829945f13
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Commencement of Work
label | 354d4795-24bc-5065-8ceb-48d5e3a49155 |  | note | Ref docs - VR Clause 160.C1 General condition of Contract
label | 3604b9c5-db0f-5d37-a313-662a65afb029 |  | note | Acceptance criteria - Works shall not commence on site before the following documents have been submitted:
label | a2f3cb45-2f2e-558f-87ca-453e0f657632 |  | note | a. Evidence of public liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
label | b51d1b8c-0fe0-5d99-988d-5917794f9d27 |  | note | b. Third party property damage insurance in accordance with Clause 160.G1
label | 3cbaafe7-b65f-5a84-bc10-df42fc0ce6fd |  | note | c. Health and Safety Management Plan
label | a8777f84-cd15-5f8b-8fed-a7c578cf98ab |  | note | d. Construction Environmental Management Plan
label | cf0d5e50-678a-5153-8ffd-8e63e15a55b2 |  | note | e. Traffic Management Strategy and Traffic Management Plans for the initial works
text | 746ebbb4-4050-5c7c-8aab-a3fcc36b41fc |  | textbox | CHAINAGE FROM
text | e8c3a184-a8f4-5272-82a3-11f5dea72b87 |  | textbox | CHAINAGE TO
button | 845c6684-e4f9-5b0f-96c7-708a92b78f54 |  | button | Has all of the above been completed and approved? | Yes, No, N/A
label | 20dac91e-ef6e-5e5e-8ffa-37400f1d0c16 |  | note | Freq - Once (Pre-Start)
label | fe244820-2108-5934-ab99-c1a8cb1ff05d |  | note | Key - H
label | 3d7c06fa-ab1a-5a17-a992-73a2cc6cb403 |  | note | Resp - SE
date | af5aa3dd-5878-5b85-98ec-fd59f4ceab0c |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 7a23205e-ea04-5fa3-a339-47099e0014fe |  | button | Lot map | Yes,No,N/A
date | 506daf4b-2b5b-5461-b76e-2deb8d233501 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.2 - Safety
label | ab550148-a0da-5865-99b3-d3e81ed2fbb7 |  | note | Ensure that the following items have been actioned:
label | 858b8e46-6323-5fe7-a78a-8195315895fa |  | note | – SWMS if applicable
label | 802b698e-9f4f-585f-b64c-44224b503f97 |  | note | – Plant Pre-start Inspection
label | aee3ad6f-2789-54a5-beb7-2ae34e363e63 |  | note | – Service locations identified
label | d6d6148a-cec1-5c75-b757-64ca8569ac01 |  | note | – Traffic Management Plans (if required)
label | 53102884-5190-5c72-a305-f4f39aa0d7eb |  | note | – All staff inducted
label | 467d9bbd-b7af-54df-a720-1e52b06a19a2 |  | note | Ref docs - SMP
label | 6813e853-7c23-5fad-a934-c334791f559b |  | note | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
label | e8eaa971-6a14-516e-a927-f2a9f7730503 |  | note | • Plant inspections completed and entered.
label | 13dfd283-88d5-5589-b85c-87703defbfb2 |  | note | • TSA training completed. Pre-work briefings completed.
label | 9e6322b5-8a22-5416-8f48-9187111411cd |  | note | • Service Diagrams available and services located.
button | 3401e531-3b6a-53c1-844e-9a977d104998 |  | button | Has all of the above been completed and approved? | Yes, No, N/A
label | 7dd98b5c-d093-5144-b283-b8ac082aefc0 |  | note | Freq - Once (Pre-Start)
label | 38691c0e-e2fa-509d-b301-d94c743604b2 |  | note | Key - H
label | eb6f0e05-79c8-54f9-b15f-8ae740922568 |  | note | Resp - SE
date | e2511b9c-4776-565f-b999-720c9cd48dbe |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 1.3 - Survey Set-out and TBM’s
label | c34585a1-238d-5da7-8dfd-537d2b57c11b |  | note | Ref docs - IFC Drawing
label | f913eb0e-f647-5bba-9aa8-9446a18c6acc |  | note | Acceptance criteria - Record existing and established TBMs. Survey set out including frame, benchmark, and recovery points in place.
button | 3af33cda-3a1b-5e28-a1fd-4225d5b71fd7 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 6519fc63-0e60-5cff-af9b-3840ea887760 |  | note | Freq - Prior to start of Works
label | 66258eb7-fd9d-5092-9b65-23c89f706a84 |  | note | Key - H
label | f3c38956-1ef6-5604-a24c-1983d15461ab |  | note | Resp - SE SV
date | 22faa7db-d081-5679-bf8c-52ed8096cef1 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.3.1 - Surveyor Report Reference
button | 09f688dd-aa34-5f4f-8cbc-ac625aef672f |  | button | Surveyor report reference | Yes,No,N/A
date | a19e0ee5-cfaf-5b63-b16c-3a8abf9d72ef |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Construction
checkpoint-no-status |  |  | checkpoint | 2.0.1 - Incoming Material Docket
button | 03a4e44f-00e7-590a-964e-4a5cf4e4d3b4 |  | button | Incoming material docket | Yes,No,N/A
date | 3f3044d0-c5aa-5ac0-b809-7b89e63c19ef |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.1 - Topsoil Stripping
label | b78056f9-eb0a-5953-b395-d43fab4429df |  | note | Ref docs - VR Clause 204.05
label | d4271cca-3256-59a3-a32d-4c9a5f196de4 |  | note | Acceptance criteria - Topsoil is to be stripped to an appropriate depth removing surface topsoil in a way to leave the surface evenly graded and free draining.
label | 4f018ea4-fbff-5c2f-a722-eb4288acda14 |  | note | • Topsoil to be reused onsite is to be stockpiled in an agreed location. All stockpiles shall be maintained in a neat, well-shaped state capable of shedding water.
button | 45a75409-28f4-56a0-99fb-520c552a9c37 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 7e4bce7f-f710-50ec-9fac-f027c0f60c90 |  | note | Freq - Each Lot
label | 8fda29b4-19e6-5859-b55b-dfa2005a36f1 |  | note | Key - R
label | d01857fa-f4df-5ae3-a305-843bef5f790e |  | note | Resp - SE
date | aaceb6b1-ca28-551b-b1aa-5769126f56df |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - Site Excavation
label | 3dbca08e-003d-5324-adf5-0c8ea834c548 |  | note | Ref docs - VR Clause 204.06
label | 26145cf0-a388-5b28-bb51-e7b5aca2fa02 |  | note | Acceptance criteria - Prior and during excavation work, the Superintendent will be notified to inspect all material encountered for material classification, subject to verification by laboratory testing.
label | 4da4d0d2-4596-5db3-88a2-de1794556e17 |  | note | • The areas of rock subgrade shall be presented to the Superintendent for acceptance.
button | 11ff03e0-5769-5659-8555-fa91069a1d5c |  | button | Has all of the above been completed? | Yes, No, N/A
label | 8bbcd9ee-fac7-5547-851c-99d46787a713 |  | note | Freq - Each lot & Each possession
label | c9c30a26-d7ea-5272-8bdf-6dcc3c20cb89 |  | note | Key - H I S
label | 69ab45c6-0d80-5d75-914b-74d5750af34a |  | note | Resp - SE
label | 2ca9c33b-0b10-5043-a676-00b29b77b27a |  | note | SI Key - H
button | f140015f-9544-5a17-acbf-c61c6962d731 |  | button | NATA Test Reports (as required): | Yes, No
label | 1eeb59c8-7cb9-5cb0-b222-fad81728a2b3 |  | note | – CBR and Swell
label | 3e19371f-2051-5b89-8b7d-b5c082dc5e72 |  | note | – PI
label | b547beb7-6f63-5981-ace3-f27a7017d5f5 |  | note | – Permeability
date | e02f7690-097e-511a-8e42-6a228417995a |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Groundwater / Seepage (if applicable)
label | 71e5f216-2ecc-5d84-842c-f6a2ac75ff92 |  | note | Ref docs - VR Clause 204.06 (h)
label | d7503594-bcb2-5ad7-a828-3b3fd3b71809 |  | note | Acceptance criteria - If groundwater or seepage is encountered, notify the Superintendent, and create a course of proposed action.
label | 4d8cc251-9c73-5622-bbc3-5c2224d5b4ce |  | note | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
button | 8fbc0d1b-cea8-58ca-a282-ffd65476b0e3 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 43e8fa9a-3acb-52d6-9c1c-d09bec99a386 |  | note | Freq - Each lot & Each possession
label | 8dde038c-78af-589e-843f-02cfcbd813a7 |  | note | Key - H I S
label | 7d8fb756-d231-5a81-8cc0-11f22a3054a0 |  | note | Resp - SE
label | 1d4e1dea-25a1-55fc-b1f5-75b147ced990 |  | note | SI Key - H
text | 71f126af-dbb5-5d0e-a81e-c4bae4b69a51 |  | textbox | Dewatering Permit No.:
button | 36b9c9ca-1e9e-5fd6-97cd-f50e04e32803 |  | button | Written Approval from Authorities | Yes,No
date | 643389a5-8775-51e4-b8c5-da1963a46b17 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Treatment of Unsuitable Materials (if applicable)
label | 6e5ebc13-ebdb-5975-b7f3-c00e48e4fb90 |  | note | Ref docs - VR Clause 204.07 (d)
label | 4c386842-4811-5f84-82fc-1a56ee50cf06 |  | note | Acceptance criteria - If unsuitable material is encountered, submit proposal for in-situ treatment or excavation and replacement with conforming material.
button | c999ed12-ea6d-51b4-b60f-583d0bd2e54e |  | button | Has all of the above been completed? | Yes, No, N/A
label | 00e7c125-26f5-5fbf-9ca4-c1acf6226440 |  | note | Freq - Each lot & Each possession
label | 94792577-2bb8-5a86-b8ec-3e497604eabb |  | note | Key - H
label | 8aad049c-99a1-51fb-b5a9-1b74159378d4 |  | note | Resp - SE
label | b589bb22-544c-5af5-b12e-1530b0e05944 |  | note | SI Key - H
button | 91fc756b-208f-594d-a1ad-c52a8b917225 |  | button | Survey Report (Extent of Area) | Yes,No
date | 650b2b09-f4fc-5afb-859d-d4374d4978e5 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Treatment of Cut / Rock Subgrade
checkpoint-status |  |  | checkpoint | 3.1 - Treatment of Rock Subgrade
label | dc46f4b8-3f7f-50a3-96fb-35a3211330b0 |  | note | Ref docs - VR Clause 204.06 (f)
label | cfd6d02c-6f33-5584-a11f-7ace2d67d67b |  | note | Acceptance criteria - Where rock exists in a cut below subgrade level but within the designed capping or selected material layer:
label | c2df1d1f-3a42-5db2-96ea-162d40546085 |  | note | • Excavate minimum 150 mm below subgrade level in all areas on which pavement is to be placed.
label | 8c02cdf2-f17c-502a-be42-aed6f00afbbc |  | note | • Remove loose material and soil from the rock floor.
label | 674927fe-90ce-524f-8824-85cfb305ffa4 |  | note | • Any resulting depressions lower than 150 mm below subgrade level shall be cleaned of loose material and backfilled with 20 mm Class 3, 3% cement treated crushed rock and compacted as specified.
label | 719f4a96-b270-510c-9f4f-d35d8b04f122 |  | note | ○ Present the above to Superintendent for inspection.
label | b5bcad0f-4589-5ff7-8f23-0b4282dc02bc |  | note | ○ Contractor is to submit details of any necessary adjustments to the subsurface drainage design, including transverse subsurface drainage at all interfaces to the Superintendent for inspection and review.
button | 73479a87-bdf1-52bb-857d-d3c85d9c1426 |  | button | Has all of the above been completed? | Yes, No, N/A
label | f425aa4b-24b9-5544-a64a-9a5784477d35 |  | note | Freq - Each lot & Each possession
label | e7a44e25-8613-5538-a8b7-f99f4214f978 |  | note | Key - H W S
label | 45af8726-8d29-58ba-966a-713b42c2caa0 |  | note | Resp - SE
label | 13aca8c9-2d27-50df-8239-4077197e6400 |  | note | SI Key - H
button | defeafc4-308c-58f0-9355-502284218a09 |  | button | Evidence of VicRoads Registered Mix | Yes,No
button | a04b5e9c-55e7-5571-be53-98d640a71176 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
date | 3116e02d-2d87-513f-8257-2198d1212b42 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Regulating Layer for Rock Subgrade
label | e53644c0-6d45-5e79-861b-0b04ee49d2b9 |  | note | Ref docs - VR Clause 204.06
label | e2bd0d62-8680-552e-a466-bf615aa7814e |  | note | Acceptance criteria - Following inspection of rock subgrade by Superintendent, place 150 mm regulating layer of Class 4, 20 mm Crushed to subgrade level in lieu of the specified capping or selected material.
button | d0c31cfb-3e79-58f4-901d-21b3e64bc8b1 |  | button | Has all of the above been completed? | Yes, No, N/A
label | e7c25b1e-c2d2-5f8a-a416-663bb3fcd878 |  | note | Freq - Each lot & Each possession
label | a8085c19-1495-599b-8707-612a219a19aa |  | note | Key - W S
label | abf77ff0-fb0c-5b8a-b6f8-bf1fb1404819 |  | note | Resp - SE
button | e74dfb76-bfac-5a95-9f1d-e178756c5065 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
date | 68f684a0-8171-5573-914a-fd46a1f7c6c3 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Testing In-situ Material in Cuts
label | d19e9362-2436-5eda-ae14-ede3d36d21d7 |  | note | Ref docs - VR Clause 204.07 PS3020.05 (c)
label | 95eb85db-9635-5592-9cc1-d069d0d51eaa |  | note | Acceptance criteria - Undertake 1 Lot test initially to determine Assigned CBR and % swell for in-situ material in cuts within 400 mm below capping layer.
label | 52b3800a-aa7b-5ee2-aa3a-c7f196ed4b55 |  | note | • Where the assigned CBR and % swell conform to the requirements of Cl. 204.04, seek the Superintendents ’s approval for minimum frequency of testing.
label | f1f02e00-9f19-5fc3-8c4f-c1bd673cddad |  | note | • Assigned CBR must be equal to or greater than 2.5% and must be no more than 10%.
label | e053a484-9e84-5867-8c77-46baf3f19112 |  | note | • Assigned percent swell must be less than 2.5%
label | 121ff1b6-5ce9-5c25-92fc-2f4e85cdb1fb |  | note | • Where Superintendent approves minimum testing frequency, proceed to conduct 1 single CBR and % swell test to confirm Assigned CBR and swell every 4 lots.
label | 8f7e6ba2-7a09-5f72-a268-279d9c46ed42 |  | note | • Where unsuitable material is encountered on site, the contractor shall submit proposed treatment plan to the superintendent for evaluation.
button | 1f310865-f0a2-52a5-b9ed-5efd69f1e4de |  | button | Has all of the above been completed? | Yes, No, N/A
label | dd19ff20-4c7e-5d4a-823c-347e77f704d1 |  | note | Freq - Each lot & Each possession
label | f170c8e9-9499-5195-9231-865b5afabea1 |  | note | Key - W S
label | 8eef8029-68cd-56b8-ba0d-9eba64294b96 |  | note | Resp - SE
button | bb76e712-5fea-51b3-8e86-c3431ca52423 |  | button | NATA Test Report: CBR and Swell | Yes,No
date | a7763117-158d-5bfe-a74d-81f3728440ae |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Treatment of Cut (if applicable)
label | 13c7d6eb-566e-5ef5-bb11-40514a98c06b |  | note | Ref docs - VR Clause 204.06 (e)(ii) 204.10 (b) 204.12
label | 263ff6d1-d670-512e-8edf-ef5704dd79f2 |  | note | Acceptance criteria - The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm.
label | 188662a4-b8b1-5771-90ee-cea6ff90ca0f |  | note | • Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with Type B material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
button | f41ef56a-f579-5fc9-8fb5-67f5e62d5d07 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 419ed413-bd9e-513b-9b3c-2991b7a7eb06 |  | note | Freq - Each lot & Each possession
label | 4c934a84-3d28-534b-a5e5-0d3bfdfc260e |  | note | Key - W S
label | 7c0c504e-9ce1-5648-a1f2-2d83830fa3e5 |  | note | Resp - SE
date | f3deb7c8-f10d-5ce9-885b-ccee5e9365bf |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Compaction and Moisture Requirements (material of nominal size < 40 mm)
label | 4c0558d5-2dbf-5e33-ab3f-9e01534fef0c |  | note | Ref docs - VR Clause 204.13 (para 1) 204.13 (b) 204.15
label | 3702e6a1-eeee-50c3-a15a-d8364f238983 |  | note | Acceptance criteria - Undertake 6 tests per lot (except for small lots).
label | 309dbdf3-8fbd-55b6-a17d-f48bc67df3b5 |  | note | • Ripped and re-compacted material below CFL: minimum CDR 99% (Scale A)
label | 3667c525-8d48-50ab-8bf2-e05dea9f1d10 |  | note | • Top 150 mm of areas where fill is to be constructed: minimum CDR 97% (Scale A)
label | 9b2aa876-1447-5483-8302-1e4033166390 |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer above.
label | ba086768-31c2-586b-ab0c-c1a2512ae333 |  | note | • The moisture ratio shall be determined using the material which passes the 37.5 mm sieve, where the material contains less than 20% oversize material. If the material contains more than 20% oversize material, the moisture ratio shall be determined using an alternative method in accordance with the appropriate test method or Code of Practice.
button | a00c3d9c-a330-5e2d-8552-a6a903d9b73e |  | button | Has all of the above been completed? | Yes, No, N/A
label | 6d090dd2-21ba-5777-bd0d-ac8bd55d2bbf |  | note | Freq - Each lot & Each possession
label | c96f9750-b33f-5913-b71c-aa56b3318804 |  | note | Key - W S
label | fc8c429f-b71a-5759-a225-a5e156c3bfe1 |  | note | Resp - SE
button | a7baaf89-94d3-5839-bb11-92b0bb04e593 |  | button | NATA Test Report: Compaction and Moisture Content | Yes,No
date | aa06e39a-1217-5a83-ad2a-d136cfe787fd |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.6 - Compaction and Moisture Requirements (material of nominal size > 40 mm)
label | e5713da6-0202-59df-af38-1c0a212b7f4d |  | note | Ref docs - VR Clause 204.13 204.15
label | 6cf35207-f719-54ef-b24b-3f022973a7d6 |  | note | Acceptance criteria - All fill material and material below the Cut Floor Level shall be compacted at minimum moisture ratio of 80%. Place and compact material in accordance with approved procedure.
label | 534cd735-9926-5ca2-9608-4c4c2083f12a |  | note | • Any unstable areas detected by test rolling shall be rectified. Where unstable areas exceed 20% of the area being test rolled, the whole of the area shall be ripped, re compacted as specified above, and re-presented for test rolling.
button | 81f8a26a-fe89-5a8b-a9ca-f2341f7935fa |  | button | Has all of the above been completed? | Yes, No, N/A
label | 2e18ad7f-1650-55a5-b7f3-65dd92bf69db |  | note | Freq - Each lot & Each possession
label | f4e77a1f-07b9-52c0-9e3b-423c7293c460 |  | note | Key - W S
label | 158c3fef-8bbc-5cc5-a262-e3092516f966 |  | note | Resp - SE
date | eb565063-19a5-53a9-ae69-f182c7d900de |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.7 - Surface Level Conformity – Fills and Prepared Surfaces
label | 517b58a4-cd13-5202-8843-6f3b7574a963 |  | note | Ref docs - VR Clause 204.03 (a),(b),(c),(d),(e),(f),(g),(i),(j) & (K)204.15
label | 02c6bd54-5239-5c37-aad6-a14a6cb8337e |  | note | • VR Clause 204.12
label | cfb65c17-b056-5982-829b-cc270e587283 |  | note | Acceptance criteria - Where capping and/or selected material is to be placed above the Cut Floor Level to subgrade level, the level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
label | fbf2949c-b9e7-54dd-af5e-7e3808610224 |  | note | • Where capping and/or selected material is not required, the Cut Floor Level shall be prepared to the appropriate tolerance for the subgrade. (See figure 1)
button | f016296c-c9bd-5b5d-81ef-1bec01e06269 |  | button | Has all of the above been completed? | Yes, No, N/A
label | caa8cc8a-1fdb-5daa-8da8-9452cc75dd47 |  | note | Freq - Each lot & Each possession
label | 7564ccc7-b44d-5cfe-b858-b2ac681a997b |  | note | Key - I S
label | bbbfc94f-2aab-592f-b3c8-54ee7d519da1 |  | note | Resp - SE
button | 35b12cf9-d6c0-5325-b11e-3655abe375c3 |  | button | Survey Conformance Report | Yes,No
label | 20ebf3e3-187e-5847-8a80-e4664a75c3f0 |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | ff889095-5a80-596a-a74b-79eb81ad4af3 |  | note | Figure 1.
label | 6a8f1ba9-79e5-5c88-895c-c9da96f415b2 |  | note | Table 204.031 Minimum Number of Level Measurements and Tolerances
label | 10a3701e-7be7-5be0-90e7-afaaf9e3788b |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | 6ad71462-cf0c-5bc3-a17c-90ab6eee099c |  | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̄ Range (mm) ¦¦ Tolerance: Maximum S (mm)
label | 4d49f4e8-d7cf-5442-9426-aecb66c4a12a |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | ac3dd7ba-e12c-5f27-9962-f711f8795fcf |  | note | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
label | e5d5aea4-adcf-5f14-bc61-7f0cf0f51121 |  | note | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
label | 3f744d3b-386b-5cea-811d-03e65d832e8f |  | note | – – – – – – – – – – – – – – – – – – – – – –
label | c05453e2-8510-56b5-a1eb-923c899e0ef1 |  | note | Notes:
label | 33378fdf-1b0e-5fd7-8cdb-a743c5ed8561 |  | note | 1. x̄ is the mean value of all level readings taken in the lot
label | 16c761b7-d084-5b00-9c03-a81db5facd61 |  | note | 2. S is the standard deviation of all level readings taken in the lot
label | 1c6d8b14-6eb4-5370-82d4-acb374136121 |  | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
date | d68dba6b-ee3d-50dd-ad99-33d3dafa1986 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.8 - Test Rolling
label | 2df1ed7a-3f9e-58de-b541-ecf8f1e8736a |  | note | Ref docs - VR Clause 204.12
label | faa97184-a15a-5b06-8759-5d9da28419c4 |  | note | Acceptance criteria - Test Roll in accordance with Section 173.
label | ed057fd5-5646-5b6a-9feb-760dff8e743f |  | note | • The Contractor shall provide for the Superintendent to be present during all test rolling.
label | 6ae69317-d944-5705-8af1-20894256f4a4 |  | note | • Surface shall withstand test rolling without visible deformation or springing.
button | eef470b0-9d49-5204-8b25-964221af9fb7 |  | button | Has all of the above been completed? | Yes, No, N/A
label | 97ded3ae-34a4-5064-88ae-58153bfec0cf |  | note | Freq - Each lot & Each possession
label | 74e0d21d-c552-5dd5-8465-4f0fecfcd990 |  | note | Key - W S
label | e140ed56-b79d-53b2-af93-0280d4428121 |  | note | Resp - SE
label | d6c70eda-971c-5781-873d-f941dc7d37e5 |  | note | SI Key - H
date | b931b56b-168d-5bc5-9b39-66a33171675c |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-no-status |  |  | checkpoint | 3.8.1 - Proof roll if applicable
button | 9af9148c-76ed-5486-a207-1cac2fa80380 |  | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
text | d8a339f5-31c1-52e8-8467-959132686604 |  | textbox | Chainage
date | f255f7c2-6ec4-5ab2-8b00-7fba0f541756 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.9 - Maintenance of Cut Floor Level
label | 7759a58f-fb5b-5c17-a11a-775b50759477 |  | note | Ref docs - VR Clause 204.15
label | 9c3afb80-a414-5352-8f93-ea14a15ec8c4 |  | note | Acceptance criteria - Visual inspection to confirm that surface is produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | 50431e93-6315-5693-893f-b29e79663935 |  | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
button | 75d270ab-b993-55cd-9ce6-4d9a0ba6fd7a |  | button | Has all of the above been completed? | Yes, No, N/A
label | 939d98dd-c561-5ca7-8265-ec96bf4ad7fc |  | note | Freq - Each lot & Each possession
label | 2891a4a3-aaee-5713-80c0-1d501857cb12 |  | note | Key - W S
label | 331b886e-9a67-5851-bce8-308e774caabe |  | note | Resp - SE
date | df1cc46b-ff17-54aa-a7be-bfe093369446 |  | date | Inspection Date:
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Test Reports
label | b190ccef-1ea1-5964-b59e-b33ae19a291e |  | note | Ref docs - VIC Roads Specifications
button | 34232b75-da6c-53e2-aa25-51ae3844ab67 |  | button | Acceptance criteria - All Test reports received and Reviewed. | Yes, No, N/A
label | 530678c3-b60d-5b84-9051-7a5f5e02cf74 |  | note | Freq - Each lot
label | 81302774-d031-5f9e-a3af-dfadc79a9982 |  | note | Key - R
label | 43cb3c08-fa9a-598c-948a-863187ae379b |  | note | Resp - SE
button | 34b18927-742a-556e-a974-7efc3474d1ce |  | button | NATA Endorsed Test Reports | Yes,No
date | 2cc51b6c-37c4-584d-b5c2-180fe37846b9 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Product Non-Conformance
label | 440ede72-b716-5c21-b481-e8ce125fb51d |  | note | Ref docs - CQMP
button | 544e2d5c-6070-56a9-b017-a94410256f62 |  | button | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable) | Yes, No, N/A
label | d272dd55-8d73-5999-b921-4232ad0bd0ae |  | note | Freq - Each lot
label | f12d9070-98c4-5e5e-a9e5-d393f6675078 |  | note | Key - R
label | a2764a93-086b-5613-9770-d9e227ba285c |  | note | Resp - SE
text | 406a12de-d985-508a-acf6-f29296fe8f43 |  | textbox | NCR No:
button | 25b65892-8b52-5646-87e1-0abb1a91f2ce |  | button | NCR reports | Yes,No
date | f9a0dc43-43d6-5f73-bbe1-e392c4d92243 |  | date | Inspection Date:
checklist-sectioned |  |  | checklist | 1630-P200-SYM-QAC-ITP-0013 Subsurface Drainage | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0013 Subsurface Drainage | f2d3d3ba-04aa-4fb7-88d1-d230b4fdf57e
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Procedure for method of compaction and placement of no fines concrete filter material
label | f91c4160-0901-5ff0-84dc-a01402165585 |  | note | Ref docs - VR702.09
label | baf26de6-f23c-5528-ab0f-0aeb0cb4c2fe |  | note | Acceptance criteria - The method of compaction shall be in accordance with the Contractor’s quality procedures and shall be submitted for review by the Superintendent.
label | 7c40b4fa-1629-59a8-96a7-88137761989f |  | note | Freq - Prior to start of works
label | a819febb-b549-5ecc-bdf0-1472f4aed0fd |  | note | Key - H
label | f51c384c-1295-527c-94f7-74760bb6bc44 |  | note | Resp - SE
label | c7f819e0-781f-53a1-b6b5-003f52b7bf2c |  | note | SI Key - R
label | 8580071f-66d5-53ab-9a24-aefce84bfb87 |  | note | Remarks/record - As per approved Construction Document
date | 94ebb247-6372-532a-bacb-12916f3e8d67 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.1 - Lot Map
button | 47ea718a-9139-5084-860d-d61fe2a4b303 |  | button | Lot map | Yes,No,N/A
date | 59291681-34b5-54fc-97c2-46050f528754 |  | date | Inspection Date:
checkpoint-no-status |  |  | checkpoint | 1.1.2 - Environmental Permit
button | c6c85b1f-bd88-5b7d-ab61-320bb0242f3a |  | button | Environmental permit | Yes,No,N/A
date | 67223c57-d86a-530a-ace3-8846eb9a43ba |  | date | Inspection Date:
checkpoint-group |  |  | section | 2.0 Materials
checkpoint-status |  |  | checkpoint | 2.1 - Supply of Pipes & Geocomposite Drains
label | 8f7feb94-1e20-503f-80a9-464aabb7aa7a |  | note | Ref docs - VR702.04 PS3030.05 IFC Drawings
label | cf4f7680-b046-5462-bd22-538d537a9831 |  | note | Acceptance criteria - All subsurface drainage pipes supplied shall be Category 1 (Class 1000)
label | 273d6d78-1063-5fbf-bbbb-59ed1dfbdce5 |  | note | • Perforation size must be a maximum width of 1.5 mm and a minimum length of 150 mm per m2
label | ac1cebec-1090-5106-8541-42a4bd3543c0 |  | note | • Plastic pipes and geocomposite drains shall be handled appropriately to reduce sunlight exposure during delivery, storage, and installation.
label | 614cbcd9-5e0e-5a02-aaf7-ed818f827c33 |  | note | Freq - Each Lot
label | ce6a6110-e5a7-5ad4-8143-0e600ede901a |  | note | Key - R I
label | 0b5476dc-1756-5c17-b07a-6565e21cdd00 |  | note | Resp - SE
button | 97e5a096-2c3a-5d9c-a980-ccc89c03ee38 |  | button | Remarks/record - Manufactures Compliance Certificates (AS2439) | Yes,No
date | eeab3f9c-cfbf-5131-bcbe-d01fa4e73256 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.2 - Supply of Pits & Flushout Risers
label | ec9d882f-aaaa-579c-a3f6-e5370a651b6d |  | note | Ref docs - SD1631 SD1611 PS3030.5 IFC Drawings
label | 151e6603-94c4-5a87-8b11-ba064be9a25f |  | note | Acceptance criteria - Flushout risers for geocomposite drains shall consist of a preformed riser fitting, or a pipe of diameter not less than 100 mm.
label | 3ae307c4-e1e8-5a40-8e2d-9760a3071c98 |  | note | • Flushout risers shall have surface fittings as shown on the drawings.
label | 77b32c0c-1d36-5a2d-9a66-e5198ee404f7 |  | note | • Pits shall be supplied in accordance to SD1611.
label | 38168700-4b13-534f-affe-b942331ae85d |  | note | Freq - Each Lot
label | 114cc5da-9d61-51c0-94d4-65f9a4d2e2c8 |  | note | Key - R
label | 683e20dc-f300-5288-82a7-d63a2f4e6daa |  | note | Resp - SE
button | 07491c3d-4a88-5428-a91a-5330a038a49c |  | button | Remarks/record - Supplier Compliance Certificate | Yes,No
date | 59a57c73-f745-5b0a-bcbf-0ae0d9c6138f |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.3 - Granular Filter Material – Sand
label | 3811133f-0710-5ad4-9f62-2440cd05d933 |  | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
label | 1a2aaf02-1b0c-534a-ac5f-b810c5b7abcf |  | note | Acceptance criteria - Granular filter material must meet the below requirements:
label | 971b6d87-a765-5b8a-8084-12ad0e12e63f |  | note | • Grading: As per Table 702.051,
label | f3242474-0e4c-52cb-91c3-a2b386631e93 |  | note | • pH: 6.0 – 10.0.
label | 3c9df138-e52c-5e6d-918c-b33d8a3e3c2f |  | note | • For glass fines: be thoroughly washed and retested prior to use, where the measured Total Dissolved Solids (TDS) of the granular filter material exceeds 1500 mg/L.
label | af0da553-1d01-5b9f-8e68-f87b83693fa3 |  | note | ○ pH and total dissolved solids (glass fines only) must be tested at a rate of one test per 5000 tonnes of product.
label | 88af118c-2df4-5ab4-81ac-6b8df59be9ef |  | note | Freq - Each Lot
label | d358e849-b700-59e5-940e-36d5c7a3096b |  | note | Key - R
label | 9567219c-eff3-5084-8596-0b2350b26097 |  | note | Resp - SE
label | 07528748-56e8-59fc-b9c0-24769d992cb7 |  | note | SI Key - R
button | 60df4f2c-a2a9-5302-91dd-4b443ad6ca57 |  | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
button | d68c2f31-bd15-5a6c-bbf2-8ab7b63b93ec |  | button | Remarks/record - NATA Test Report: Grading | Yes,No
date | 555a2d59-268f-55ff-b64e-c0e294652989 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.4 - Granular Filter Material – Crushed Rock
label | 09176e86-dd31-58a6-91c3-638a86822827 |  | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
label | 2f29afd7-ab07-5300-9835-e5cb85f0166f |  | note | Acceptance criteria - Granular filter material must meet the below requirements:
label | faa1e1c3-dc3c-5a53-a82b-ec80e7a4ab5b |  | note | • Grading: As per Table 702.051,
label | 3d822aad-c10d-511e-9cc2-274c2598bb03 |  | note | • Unsound Rock Content: < 5% by mass,
label | 558bc1b8-7c21-5d47-8b37-b6471d434a2c |  | note | • pH: 6.0 – 10.0.
label | e2a27c78-4276-55c8-823a-9933b4caae98 |  | note | ○ Crushed Rock Components: The percentage by mass of unsound and marginal rock in that fraction of an aggregate retained on a 4.75 mm AS sieve shall not exceed the values specified in Table 702.052.
label | 85cc2d29-e21b-5167-91d2-0d6dda96d518 |  | note | ○ Granular filter material must be tested for grading, unsound rock content on each production day or at a rate of one test per 500 tonnes of material as per Table 702.131.
label | 52502764-001a-5415-874c-a6c4c2d4d3a9 |  | note | Freq - Each Lot
label | c58d5326-9211-5273-b4e8-bd72094ec365 |  | note | Key - R
label | 3bacf34b-b730-5897-a716-4c4f7810985d |  | note | Resp - SE
label | 145d03e5-0484-5c17-b0ff-b3338c8d3351 |  | note | SI Key - R
button | 5dae040e-c748-5b49-99f6-49b0ffba19df |  | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
button | 904bb841-333b-5335-a8f5-b6c3dfd0a15d |  | button | Remarks/record - NATA Test Report: Grading | Yes,No
date | 72bd4e05-e7b8-5d86-b992-37502a20eda0 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.5 - Granular Filter Material – No Fines
label | c8221dc3-b527-5ab6-b679-6fa0e0e68227 |  | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
label | f645cf26-faf8-5e49-bf10-24b898b5aa57 |  | note | Acceptance criteria - Granular filter material must meet the below requirements:
label | 655ae7c5-03c0-5013-a36a-a14518988859 |  | note | • Grading: As per Table 702.051,
label | 4369bf76-c723-591f-92f6-5b460a1ca42c |  | note | • Unsound Rock Content: < 5% by mass,
label | 36e349d0-ad0b-50cd-887a-1b7dc700bb8c |  | note | • pH: 6.0 – 10.0.
label | 7fdf8164-4230-5e22-8547-2fc64c48c1f1 |  | note | ○ No fines concrete shall consist of B4 filter as defined in Table 702.051 and mixed with 4.0% by mass of cement and 3.5% by mass of water in a mixing plant.
label | a37d3119-0e1e-5974-9442-1b2c46224f1d |  | note | ○ Granular filter material must be tested for grading, unsound rock content on each production day or at a rate of one test per 500 tonnes of material as per Table 702.131.
label | 992b1f2a-8a17-56df-9683-7fddad9acbe1 |  | note | Freq - Each Lot
label | d91f44ec-dd2c-5517-92b7-1e2f3d9e3df8 |  | note | Key - R
label | 3c49ec8e-2bd4-5adf-9fbf-f24783c33ba0 |  | note | Resp - SE
label | d69c2e96-659a-5b1c-ac6a-c1525d4f4661 |  | note | SI Key - R
button | e4a24350-e40f-5bc5-88a1-63111416f486 |  | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
button | 5c8c87f9-545c-542d-bee3-679123d090a9 |  | button | Remarks/record - NATA Test Report: Grading | Yes,No
date | 5d2b4e78-05c3-5fc9-bd5c-b08eb2bc44a9 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 2.6 - Geotextile Filters
label | c3a6be97-0579-50bd-9b72-d47682cca111 |  | note | Ref docs - VR702.06 Table 702.061
label | ac0ef425-9491-543e-9d83-3c542cb681a4 |  | note | Acceptance criteria - Geotextile filter shall consist of a fabric manufactured from synthetic fibres of a long-chain polymer such as polypropylene, polyethylene, polyester or similar material and shall be stabilised against deterioration due to ultraviolet light.
label | f2df2df4-f8c1-55eb-811e-28a56c7309c0 |  | note | • The geotextile shall be free from defects or flaws which significantly affect its physical and/or filtering properties.
label | 580ad5ff-e4bf-58c0-84cb-b3d39b75265f |  | note | • A geotextile filter may be non-woven or knitted fabric and shall comply with the requirements of Table 702.061 relevant to the geotextile filter type specified in clause 702.12.
label | efda487c-7a9e-5e78-8490-521fc56b2282 |  | note | Freq - Each Lot
label | 5c522407-8aab-5258-ad15-4176c21becc4 |  | note | Key - R
label | fb8d4874-42d2-5c63-9286-4bb92c7ca5ab |  | note | Resp - SE
button | 69e30fae-1e79-5946-bca0-9deba2d8acf1 |  | button | Remarks/record - Manufactures Compliance Certificates | Yes,No
date | 19d4a568-60e9-5112-b47c-ea803ee7c83a |  | date | Inspection Date:
checkpoint-group |  |  | section | 3.0 Installation of Subsoil Drainage
checkpoint-status |  |  | checkpoint | 3.1 - Excavation of Trench
label | 7bd9f9d0-c738-50b6-8134-ea48c0b64d18 |  | note | Ref docs - VR702.08 VR702.09
label | 59693f08-14d9-52b7-b868-f19c105e1005 |  | note | Acceptance criteria - Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile
label | b7a0263d-0c14-5c12-84ec-85e544ae7a6e |  | note | • Trench base shall not be more than 50mm below the specified level of invert of the pipe.
label | 5ae1fde6-c02b-59dd-ab3d-add57cf912ae |  | note | • The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations.
label | fd41dc9b-8f15-5e81-9a58-9a0423cb30f5 |  | note | • Subsurface drainage pipes or geocomposite drains shall be laid to the depths or levels shown on the drawings. The top of any subsurface drainage pipe shall be at least 200 mm below subgrade.
label | 6d91e3cf-9858-5531-8866-57e3e859ea0f |  | note | Freq - Each Lot
label | 89749f10-a14e-5114-a627-c63c8e6758ea |  | note | Key - S
label | e6b1b70e-b0bf-586d-ac3c-a74a7af0de38 |  | note | Resp - SE
label | 1a0fa295-08a4-5441-856d-f331b8dd4004 |  | note | SI Key - I
date | 0bcaf511-1b10-5055-978a-2dd8498ad739 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.2 - Excavation of Trench in Expansive Material
label | 36ebc5e6-44e5-57f7-89c6-85aef457d46c |  | note | Ref docs - PS3030.07 (b)
label | 2539ff39-cf33-541e-84fc-c43a021c6e18 |  | note | Acceptance criteria - Subsurface drainages laid in expansive materials with swell ≥2.5% shall conform to the following requirements:
label | e86ed7cd-919a-5968-b417-0a185f2eedaa |  | note | • Pipes shall not come into contact with material.
label | 357e4d7c-199d-51d8-9df5-078839accc88 |  | note | • At least 100mm of capping materials provided below the floor of the subsurface drainage trench.
label | 0ec4b5a0-d9d2-5018-9ccb-f79e7a778fc9 |  | note | Freq - Each Lot
label | 4944e6d4-903e-5d2a-8b80-87b35bbb86df |  | note | Key - I
label | 83ea4b76-4cbc-5e61-b7ac-d1ff492d4c11 |  | note | Resp - SE
date | a99cf87a-5d09-590c-a9b1-5fb74a8d3576 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.3 - Placement of Bedding
label | 4619c392-f4f4-563e-ad61-13b47e6888be |  | note | Ref docs - VR702.09
label | 71b8d399-22b2-5b59-bb6c-50cd521898d4 |  | note | Acceptance criteria - A bedding of granular filter material of thickness between 25 mm and 50 mm shall be placed across the bottom of the trench. The bedding shall be tamped and screeded or graded to level. Bedding is not required for geocomposite drains.
label | 1aea52bf-ab14-5a51-bb08-174f980f4833 |  | note | Freq - Each Lot
label | d1fd14e3-15cf-556f-b21d-603e33490153 |  | note | Key - H
label | 56718f78-4ed8-5b98-b388-0cc39341615a |  | note | Resp - SE
date | 4aed806a-ed52-535f-a5fc-59a38b754fa2 |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.4 - Construction – Pipe and Geocomposite Installation
label | 640b623a-18fe-5036-9a3c-d79a417332c1 |  | note | Ref docs - VR702.09 702.03
label | 22d4f3a1-7df1-5571-8dc4-58da82d3367a |  | note | Acceptance criteria - The grade of pipes or geocomposite drains shall be not flatter than 1 in 250.
label | 92d3920d-1ef9-536b-a744-3bdc643e2bd9 |  | note | • Pipes shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the openings in the lower half of the pipe.
label | 4a3a04dc-9119-5826-a93d-18a3b2d33fc2 |  | note | • The minimum width of geotextile used for wrapping shall be 450 mm.
label | 3a18cfc0-2363-53e0-9039-65ed15fc4d98 |  | note | • Lap joints in geotextile used as first stage filters shall consist of an overlap of not less than 900 mm longitudinally and 150 mm transversely. Lap joints in geotextile used as second stage filters shall consist of an overlap of not less than 300 mm.
label | 5dc695c8-7277-5219-88d8-601bedec6f21 |  | note | Freq - Each Lot
label | e5977556-0fed-5fa6-89f2-7edfca848cf1 |  | note | Key - S
label | 960f5792-99fb-52c9-84cf-7aa09d35a30d |  | note | Resp - SE
date | b9abaf08-5f31-50bd-a7e2-dbf232e2e2ef |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.5 - Construction – Access points and Inspection Openings
label | 88c7d12c-694d-5bad-9137-47d947e7f75f |  | note | Ref docs - VR702.10 IFC Drawing
label | 03ab2281-19a2-5318-9168-08142fa539e5 |  | note | Acceptance criteria - Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located minimum 100 mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100 m and 150 m intervals unless noted otherwise on drawings.
label | 9434db44-af8a-5f1c-91c0-d365c259d7a1 |  | note | Freq - Each Lot
label | c0bc77e5-0398-571e-a636-95651ff05829 |  | note | Key - R I
label | 6434209d-949a-5dd4-a3a8-ff001f141861 |  | note | Resp - SE
date | 2f3949f6-688a-5cd0-b669-8ce26a2be45a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.6 - Construction – S1 Pit, Batter Outlet & Flush Out Riser Installation
label | 97e6b5ce-212c-50b0-851d-b0a8cb219cdd |  | note | Ref docs - VR702.10 SD1611 IFC Drawings PS3030.05
label | 83acf61d-16ac-5572-bbb6-ff8fc03b21b7 |  | note | Acceptance criteria - Flushout risers for drainage pipes shall have the same diameter as the pipe.
label | b67903ae-0ce6-5e72-94d3-4a4c74742166 |  | note | • Flushout risers for geocomposite drains shall consist of a preformed riser fitting, or a pipe of diameter not less than 100 mm.
label | 644b19b8-00f0-5050-bb83-ef8f9158b8ab |  | note | • Flushout risers shall be installed in accordance to SD1631.
label | 3ed2cc6c-620c-5c52-ba33-91534094a228 |  | note | • Pits shall be installed in accordance to SD1611.
label | a45d8c32-220a-56c9-99a7-b74e9e97b207 |  | note | • Pits deeper than 1m shall be fitted with step irons.
label | 80c5a124-76f6-56de-b599-bc0f5d89d843 |  | note | • Batter outlets into a swale must maintain min. 200mm clearance to the invert of the swale.
label | a59eb6cc-7c95-5ad9-8a17-88405ba259d4 |  | note | Freq - Each Lot
label | 12742cf6-a07f-58d5-9155-00a8e8293a0e |  | note | Key - R I
label | db61ae89-269d-56b8-b13c-ee11e102599c |  | note | Resp - SE
date | 09868bfa-09c1-51a3-a729-e9ca00aed51e |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 3.7 - Inspection of Drainage Lines & Pits
label | 55f7f2c5-a08b-5dfc-ac6e-3df9c9df9df9 |  | note | Ref docs - PS3030.07 (iv)
label | f953710e-fca7-519d-8e21-97f6c2730cfa |  | note | Acceptance criteria - The superintendent must inspect subsoil drainage trenches, subsoil drainage lines, and associated pits, endwalls and risers, prior to the commencement of backfilling
label | 86832d77-623b-5f6b-87a9-b6677a4b12ab |  | note | Freq - Each Lot
label | eb506233-9ac2-5b02-be31-28c3bc7815f9 |  | note | Key - H
label | fc4e10fd-e8d6-570d-a34b-c364965e2fa0 |  | note | Resp - SE
label | 7627a78c-0f51-52e5-935f-dcf76510f065 |  | note | SI Key - H
date | 0e35589a-ec1d-5472-9ff2-1c05f0a42140 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Construction – Granular Filter Backfill
label | d173159f-d06b-5b96-92b7-ea83a8ce2f2e |  | note | Ref docs - VR702.09(g), Approved procedure in Construction Document - Drainage
label | 442dd08f-a2f3-5796-85c3-b30d6e0bb83e |  | note | Acceptance criteria - Material shall be placed moist and compacted in layers not exceeding 300 mm. Material shall be compacted with minimal disturbance to pipes, geocomposite drains, geotextiles and trench walls.
label | a9148e6e-3beb-5399-9e15-70c6acf1fa10 |  | note | • The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Superintendent.
label | 2dcf837b-3bde-5dc2-bbfa-3d2de5159829 |  | note | Freq - Each Lot
label | 89bc7873-f56b-5872-b69b-1153b18a7268 |  | note | Key - H
label | eeeecb47-e895-5d1e-99ae-adab1babf10f |  | note | Resp - SE
label | c1cb9778-e45f-563d-a042-5b8b07155991 |  | note | SI Key - H
date | 334c723f-53c5-511f-a33e-b3c7cc5c3ae3 |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Construction – Granular Filter Backfill (No Fines)
label | 2072a448-e3f9-5a31-b5ca-9e19c2b26ca9 |  | note | Ref docs - VR702.09(g), Approved procedure in Construction Document – Drainage
label | 0f1b448f-0228-511f-84a7-837ff37ff37b |  | note | Acceptance criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
label | 7fcd070c-39ea-56a6-b0ef-2274a6ffa241 |  | note | • Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
label | 8b131465-ab7c-5e4d-83fb-f063837f51eb |  | note | Freq - Each Lot
label | 215b8604-b8db-5534-b02e-ebb68e963a48 |  | note | Key - H
label | 1bdafb71-abb4-5d6d-818a-300a60a66cb9 |  | note | Resp - SE
label | a81da753-6320-52da-a355-de68779ffc02 |  | note | SI Key - H
date | d6cc53ee-ba9d-5f10-8aae-a3eb48f1f21e |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 4.1 - Flushing of Subsoil Lines Flushed after Completion of Flushers, Outlets
label | 953a5cbb-8349-5e39-9042-4d803aa17ab1 |  | note | Ref docs - VR Clause 702.09 (h)
label | 07b39d41-7e5f-56dd-bffb-b34e313c7c1a |  | note | Acceptance criteria - Subsoil Lines Flushed to ensure Drainage Lines are free from obstruction.
label | 698100be-8a9d-5139-8767-864369e947b6 |  | note | • Location, Date & Time for subsoil line recorded on lot map.
label | d0c1e9e7-5fa9-5b34-a298-8f2d86f1a17b |  | note | • The flushing test shall be witnessed by a representative nominated by the Superintendent.
label | b85f5998-6ec3-570f-b3c5-4fc19aca9ab0 |  | note | Freq - Each Lot
label | 92bed01e-f772-55bc-85b8-ebe282a07b51 |  | note | Key - R
label | 3604ea2a-9d1a-591d-93f9-10c32b0c6e20 |  | note | Resp - SE
label | 184ce42a-684e-5459-a54e-52926cb989b6 |  | note | SI Key - W
date | 7ec27c17-99a6-5402-a6b6-178ece75c28b |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.2 - Inspection of Subsurface Drainage Lines
label | b7e3b1ce-a873-5bba-8162-8e666cf7e7e9 |  | note | Ref docs - DoT Clause 702.09(i)
label | 9536df01-d8fc-58fc-a61e-0770a774c8b9 |  | note | Acceptance criteria - All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television
label | bfc087df-b2d0-50f6-8b10-2ad780631d49 |  | note | • (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | f93d71b7-43ac-5dad-8932-55f49d2612eb |  | note | • The report shall be provided to the Superintendent, with a copy of the CCTV record including any video recordings and a summary of the location of any waste construction materials, obstructions and defects detected by the survey.
label | c1d7a9b8-efba-5b26-8a2f-71501b79c513 |  | note | • Any sections of damaged or deformed subsurface drainage pipe shall be removed and replaced. A further CCTV survey shall be undertaken to verify that the damaged or deformed subsurface drainage pipes have been replaced and are defects free.
label | 58c2ad75-7e0a-53a6-988f-665f8e88ebea |  | note | • Placement of Asphalt shall not proceed until the CCTV inspection and flushing test has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage line has been verified by the superintendent.
label | e02bb468-4e29-5d0e-83c0-50e27df55e59 |  | note | Freq - Each Lot
label | 82078bef-9e64-5ede-bc2c-333011a712ab |  | note | Key - H
label | be6019c5-5539-5af0-b230-cd9e0d33f962 |  | note | Resp - SE
label | 255aa015-f272-53c8-b41e-e21c1295692f |  | note | SI Key - H
date | 88650c06-b6cd-523a-a9a1-601929b9c4bd |  | date | Inspection Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - As built
label | 14911955-1a54-575f-a05f-1141b5e948f1 |  | note | Ref docs - DoT Clause 702.03
label | aee2fc8c-9e05-5d50-8de2-6ff808ddc91f |  | note | Acceptance criteria - Subsurface drains to be constructed true to line, level and depth, as shown on the drawings.
label | f16a35b3-b8d9-5d02-934a-e59a1efac3f5 |  | note | • The invert of the subsurface drainage to be < 25 mm from the specified level and not more than 50 mm from the specified line.
label | e581257d-15d3-5db1-bd84-8a4b38636448 |  | note | • Grade < 10mm in any 3m length or lead to ponding of water within the drainage pipe.
label | 935a5baa-5625-5e37-b445-b57fb147ff2e |  | note | • Changes to design shall be recorded.
label | daaac9b5-5f46-55bb-878f-50a727c980b6 |  | note | Freq - Each Lot
label | 8bdb13ba-d1da-5ce5-809a-b4fc7f060842 |  | note | Key - H
label | ec629d6f-8558-5e66-b944-1e1b07e0709b |  | note | Resp - SE
date | ac36f896-7cf6-5857-b3b9-ef1a9f7ade0a |  | date | Inspection Date:
checkpoint-status |  |  | checkpoint | 4.4 - Product Non-Conformance
label | e2a54873-2016-5acb-ac85-a68fc99f48a4 |  | note | Ref docs - CQMP
label | d20b3537-49c2-507a-a9ac-3d6dde75ea5b |  | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | 19a0207c-729a-5575-a06b-ef1d9ba76281 |  | note | Freq - Each Lot
label | 903bf4b5-fa73-5e5b-a424-50f307c39790 |  | note | Key - R
label | 7e5a2076-fabd-55e2-a470-b22c6ab8c33c |  | note | Resp - SE
button | dc40bfc9-fa82-51da-bea9-4fc996016e04 |  | button | Remarks/record - NCR | Yes,No
text | fe1dabd7-951f-53a8-b600-7784d85088aa |  | textbox | NCR No:
date | 7eb1b486-dc2e-5165-b763-681df0fba6e1 |  | date | Inspection Date: