## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0017 Water Relocation REV01 | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0017 Water Relocation REV01
section | ITP Details
checkpoint | ITP Details
label | ITP No. 1630-P200-SYM-QAC-ITP-0017 Water Relocation
label | Rev No. 01
label | Date of Issue 27/10/2023
label | ITP Type - New
section | 1.0 Pre-start activities
checkpoint | 1.1 - Check Survey Set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Ensure alignment set out has been completed and pegged or sprayed painted.
button | Has all of the above been completed? | Yes,No
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
section | 2.0 Materials
checkpoint | 2.1 - Material Conformance
label | Ref docs - AS4130
label | Acceptance criteria - Assets installed are correct type, class & diameter as per design. Procured asset complies with AS4130 – Polyethylene pipes for pressure applications (as relevant) unless noted otherwise.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
section | 3.0 Depth of Cover
checkpoint | 3.1 - Depth of Cover Requirements – Design Check
label | Ref docs - VR Clause 706.03
label | Acceptance criteria - Cover requirements for water assets design comply with the following:
label | ○ Pavement surface to top of conduit minimum 1200 mm.
label | ○ Invert of open drain to top of conduit minimum 750 mm.
label | ○ Unpaved areas to top of conduit minimum 600 mm.
label | ○ As per asset authority requirement for cover to other assets
label | Freq - Each Lot
label | Key - S
label | Resp - SE
section | 4.0 Backfill of Excavated Trenches
checkpoint | 4.1 - Bedding / Embedment Material Properties
label | Ref docs - VR Clause 706.06 Table 706.061
label | Acceptance criteria - Bedding / embedment materials are to be uniform in composition and free from perishable matter. Further the size and plasticity index must comply with VR Table 706.061 (Figure 1 on page 4).
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.2 - Bedding / Embedment Placement
label | Ref docs - VR Clause 706.07
label | Acceptance criteria - Placement of bedding / embedment is to be as per VR 706.07 requirements below:
label | ○ No less than 25mm of compacted depth shall be placed below
label | ○ Bedding shall be placed below, around, and above pipe
label | ○ No less than 150mm of bedding shall be placed above
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.3 - Backfill Material Properties (under paved areas)
label | Ref docs - VR Clause Table 706.061, VR Clause 706.08
label | Acceptance criteria - Backfill materials are to be uniform in composition and free from perishable matter. Further the size and plasticity index must comply with VR Table 706.061 (See Figure 1 on page 4).
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.4 - Backfilling placement and compaction (under paved areas)
label | Ref docs - VR Clause 706.08 & 706.09
label | Acceptance criteria - Backfilling placement and compaction is as per VR706.08 and VR706.09:
label | ○ Trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness
label | ○ Optimum Moisture Content between 85-115% as determined in the Modified compactive effort.
label | ○ The number of tests per lot shall be three.
label | ○ Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97%
label | ○ Noting density ratio shall be based on Standard compactive effort.
label | ○ Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
section | 5.0 Work Lot Close Out
checkpoint | 5.1 - Test Reports & Other QA Documents
label | Ref docs - VicRoads Specifications 706
label | Acceptance criteria - All Test reports received and reviewed. All required material dockets has been received and reviewed.
label | ○ Any specific asset owner QA documents available to be submitted attached.
button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 5.2 - As-built Information
label | Acceptance criteria - Where applicable, as-built pickup or as constructed drawing been provided to the authority.
button | Has all of the above been completed correctly | Yes,No,N/A
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Survey Conformance Report or as-built drawings to authority | Yes,No,N/A
checkpoint | 5.3 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | NCR reports | Yes,No,N/A
checkpoint | 5.4 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP, Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No,N/A
checkpoint | 5.5 - Authority Asset Install Acceptance
label | Acceptance criteria - Audit and approval received from accredited SEW consultant.
label | Freq - Each Lot
label | Key - R
label | Resp - SE