## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Native Grass Protection Airside Early Works | itp |  |  |  |  | ITP - Native Grass Protection Airside Early Works
section | 1.0 Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
note | Frequency: Prior to site establishment
note | Acceptance Criteria: Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified.
note | Reference Documents: Consultant reports
note | Inspection/ Test Method: Visual inspection
note | Record of conformity: This Signed ITP
note | HP*
note | Responsibility: FH Project Engineer
textbox | Print Name:
textbox | Date Completed:
checkpoint | 1.2 - Check the Google Earth Mapping
note | Frequency: During site establishment
note | Acceptance Criteria: Review the Google Earth mapping which outlines the boundary of the native grasses at the time they were mapped.
note | Reference Documents: Google Earth Mapping
note | Inspection/ Test Method: Visual inspection
note | Record of conformity: This Signed ITP
note | HP*
note | Responsibility: FH Project Engineer
textbox | Print Name:
textbox | Date Completed:
section | 3.0 Implementation of Controls to Protect the Native Grasses
checkpoint | 3.1 - Mark out the exact Significant Native Grass Boundary area
note | Frequency: Prior to commencing any activity
note | Acceptance Criteria:
note | • Work with the surveyor to mark out the Significant Native grass boundary.
note | • Signage will be placed onto the bollards stating ‘Native Grass Boundary Area.’ NTGVVP Nationally Significant Grasses to protect within this area.
note | Reference Documents: EMP
note | Inspection/ Test Method: Inspect
note | Record of conformity: This Signed ITP
note | HP*
note | Responsibility: Surveyor
textbox | Print Name:
textbox | Date Completed:
checkpoint | 3.2 - Use temporary fencing and signage to block access to the Significant native grasses where we are working in close proximity.
note | Frequency: Prior to commencing any activity
note | Acceptance Criteria:
note | • The Botanist report may define what type of protection is required for the Native grasses. For works in close proximity to the native grasses, use temporary fencing to block access with signage stating “Vegetation Protection – No Go Zone.”
note | • This fencing will be installed at a distance away from the actual native grass boundary to act as a ‘buffer zone’ but still allows works to progress.
note | Reference Documents: Biosis report, ECP
note | Inspection/ Test Method: Inspect
note | Record of conformity: This Signed ITP
note | HP*
note | Responsibility: FH Project Engineer
textbox | Print Name:
textbox | Date Completed:
checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
note | Frequency: Prior to commencing any activity
note | Acceptance Criteria:
note | • An exclusion zone will be set up with bollards and signage stating “Vegetation Protection – No Go Zone” between our works area and the native grass boundary area to act as a ‘buffer zone.’
note | • Allow a minimum 2.5m buffer zone.
note | Reference Documents: Biosis Zulu report, EMP
note | Inspection/ Test Method: Inspect
note | Record of conformity: This signed ITP
note | HP
note | Responsibility: FH Project Engineer
textbox | Print Name:
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 APAM Hold Point Release - Second Inspection
checkpoint | 4.1 - Release of Hold Point for Native grass Protection
note | Frequency: Prior to commencing construction
note | Acceptance Criteria:
note | • Arrange an APAM inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required.
note | • All parties are to sign off on this Hold Point Release document
note | Reference Documents: CEMP, ECP, Botanist report
note | Inspection/ Test Method: Visual
note | Record of conformity: This Signed ITP
note | HP
note | Responsibility: APAM, Fulton Hogan Environmental Manager or Project Manager
textbox | Print Name: |  |  | FH / Surveyor
textbox | Date Completed: |  |  | FH / Surveyor
textbox | Print Name: |  |  | APAM
textbox | Date Completed: |  |  | APAM
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | FH Environmental Team
textbox | Print Name: |  |  | FH Environmental Team
textbox | Position: |  |  | FH Environmental Team
textbox | Date: |  |  | FH Environmental Team
label | FH Project Manager
textbox | Print Name: |  |  | FH Project Manager
textbox | Position: |  |  | FH Project Manager
textbox | Date: |  |  | FH Project Manager