## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QA_TEM_019_MCC's | [5 empty] | QA_TEM_019_MCC's
section | Check the Following
checkpoint | Main fuse type and size & Correct fuse type and size
checkpoint | Contactor make & size
checkpoint | Thermal O/L make & size
checkpoint | Thermal O/L setting & relay make
checkpoint | Trip value & Reset value in OHMS
checkpoint | Isolation switch make & model
checkpoint | Motor megger readings
textbox | Phase 1
textbox | Phase 2
textbox | Phase 3
checkpoint | Resistance between windings
textbox | 1
textbox | 2
textbox | 3
checkpoint | Condition of Bars
checkpoint | Connections Insulation
checklist | QA_TEM_021_Electrically Continuous Reinforcing | [5 empty] | QA_TEM_021_Electrically Continuous Reinforcing
section | Electrically Continuous Reinforcement (ECR) Test results
checkpoint | Reference Drawing attached:
checkpoint | Embedded Earthing Conductors (reinforcement bar)
label | Continuity measured between all external connection points associated with the slab under construction, i.e. from one external point to all other external connection points.
label | External Connection to External Connection - Less than figure nominated in specification i.e., 100 mΩ
checkpoint | Rebar couplers (welded connections) connection continuity
label | Where rebar couplers are used for ECR purposes they shall be tested as follows:
label | a. From the ECR test reference location, measure the resistance to the connecting rebar element approximately 50mm from the coupler.
label | b. Take an additional measurement to the coupler.
label | c. Compare the two results: and ensure difference is - no greater than figure nominated in specification i.e., 100 mΩ
section | Tests
checkpoint | T-01
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-02
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-03
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-04
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-05
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-06
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-07
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-08
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-09
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-10
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-11
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-12
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-13
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-14
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-15
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-16
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-17
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-18
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-19
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-20
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-21
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-22
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-23
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-24
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-25
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-26
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-27
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-28
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-29
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-30
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-31
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-32
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-33
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checkpoint | T-34
textbox | Ref Point ID
label | to
textbox | Test Point ID
textbox | Max Value mΩ
textbox | Measured Value mΩ
label | Attach Hi Res Photo
checklist | QA_TEM_026_MATV Cabling | [5 empty] | QA_TEM_026_MATV Cabling
section | Confirm following items comply with requirements
checkpoint | Check that cable to be installed matches Job Spec Requirement ie. Brand and Class
checkpoint | Check that all cable pathways comply with ACA and Vendor requirements.
checkpoint | Install cables, making sure of all strain and bend radius requirements, label cables correctly.
checkpoint | Bundle sizes to be checked to Specification and number of cables not exceeded.
checkpoint | Cables to be tied in with Cable Ties as per specified distance between ties.
checkpoint | All Clearances between power and other services to be maintained as per requirements.
checkpoint | Corro to be extended to outlet position if segregation is required from power in same cavity.
checkpoint | Install Components (splitters, Taps Amps etc) onto Backboards as per design.
checkpoint | Install all cable links and Terminators as required to backboard components
checkpoint | Install Back boards in riser or designated position.
checkpoint | Loom cables neatlt to back board, make sure that the cables are loomed to the correct component.
checkpoint | Terminate cables in Riser or nominated backboard location.
checkpoint | Check position of outlets on Architectural plans if available.
checkpoint | Terminate cables in the field as per regulations and Vendor requirements
checkpoint | Label all field outlets correctly
checkpoint | Set up Head End as per Design and terminate cables.
checkpoint | Check Signal with aerial and meter on roof to determine the best location for mounting.
checkpoint | Install aerials in the designated location and connect cables.
checkpoint | Test all outlets to the relevant standards and Vendor requirements.
checkpoint | Supply test results and Asbuilt plans to Office.
checklist | QA_TEM_038_Instrument Cable Installation | [5 empty] | QA_TEM_038_Instrument Cable Installation
section | Confirm following items comply with requirements
checkpoint | Type and configuration is as specified
checkpoint | Has correct origin and destination
checkpoint | Has correct number of cores
checkpoint | Cores are of correct Cross Sectional Area
checkpoint | Follows the correct route
checkpoint | Meets minimum bending radius requirements
checkpoint | Is clear of heat sources
checkpoint | Is clear of power cables
checkpoint | Is secured as specified
checkpoint | Is installed in a neat and orderly manner
checkpoint | Is routed to minimise crossovers
checkpoint | Mechanical protection is correct
checkpoint | Inter cable spacing/segregation is correct
checkpoint | Cable is correctly supported
checkpoint | Cable marked with cable number
checklist | QA_TEM_039_Dekron Cable Commissioning | [5 empty] | QA_TEM_039_Dekron Cable Commissioning
section | Cable Install
checkpoint | Type, configuration, number of cores & cross sectional area is as specified
checkpoint | Cable has correct origin and destination & follows the correct route
checkpoint | Meets minimum bending radius requirements with minimal crossovers
checkpoint | Is clear of heat sources with mechanical protection fitted if required
checkpoint | Is secured properly & correctly supported as specified
checkpoint | Is installed in a neat & orderly manner with inter cable spacing/segregation
section | Origin Termination, Location
checkpoint | Gland is correct type & size, & also fitted & secured properly.
checkpoint | Cable numbers fitted correctly & securely.
checkpoint | Cores loomed neatly with correct identification
checkpoint | Cores in the correct terminals & correctly tensioned
checkpoint | Cores correctly lugged & insulated
section | Destination Termination, Location
checkpoint | Gland is correct type & size, & also fitted & secured properly.
checkpoint | Cable numbers fitted correctly & securely.
checkpoint | Cores loomed neatly with correct identification
checkpoint | Cores in the correct terminals & correctly tensioned
checkpoint | Cores correctly lugged & insulated
section | Point to Point, Continuity test of each cable of every pair
checkpoint | Screen
checkpoint | Pair 1
checkpoint | Pair 2
checkpoint | Pair 3
checkpoint | Pair 4
checkpoint | Pair 5
checkpoint | Pair 6
checkpoint | Pair 7
checkpoint | Pair 8
checkpoint | Pair 9
checkpoint | Pair 10
checkpoint | Pair 11
checkpoint | Pair 12
checkpoint | Pair 13
checkpoint | Pair 14
checkpoint | Pair 15
checkpoint | Pair 16
checkpoint | Pair 17
checkpoint | Pair 18
checkpoint | Pair 19
checkpoint | Pair 20
checklist | QA_TEM_044_Fire Stop Penetration | [5 empty] | QA_TEM_044_Fire Stop Penetration
section | Fire Stopping Penetration Schedule
checkpoint | Details
textbox | Installation Reference:
textbox | Drawing No:
textbox | Certified By:
date | Date Inspected
textbox | Fire Resistence Level State FRL:
textbox | Type of protection smoke or fire:
textbox | Type of Substarte Slab, Partition:
textbox | Thickness of building element:
textbox | Type & manufacturer of fire rated product:
textbox | Seal deemed to satisfy comply with BCA & or AS:
textbox | Test Report #
date | Date Installed
checklist | QA_TEM_045_Busduct Installation & Testing | [5 empty] | QA_TEM_045_Busduct Installation & Testing
section | Confirm following items comply with requirements
checkpoint | Compare equipment nameplate data with drawings and specifications.
checkpoint | Inspect physical, electrical, and mechanical condition. (Look for signs of moisture penetration)
checkpoint | Inspect bus for physical damage and proper connection in accordance with single-line diagram
checkpoint | Inspect for proper bracing, suspension alignment, and enclosure ground. (Verify that the bus duct is properly braced between floors and horizontal runs.)
checkpoint | Verify tightness of accessible bolted electrical connections by calibrated torque wrench method in accordance with manufacturer’s published data.
checkpoint | Mark the head of the bolt with a permanent marking pen. (Lose connections will cause heating and damage to connection.)
checkpoint | Check for proper physical orientation per manufacturer’s labels to ensure proper cooling. (prevents bus duct from heat damage when at full load)
checkpoint | Perform continuity tests on each conductor to verify a proper phase relationship exists. (This is especially important when transition sections are used.)
checkpoint | Check outdoor busway for removal of “weep-hole” plugs, if applicable, and the proper installation of joint shield. (Failure to remove plugs will cause moisture build up and bus duct failure.)
checkpoint | Check for proper fire blocking material and installation between floors.
checklist | QA_TEM_046_Intercom Testing | [5 empty] | QA_TEM_046_Intercom Testing
section | Check for correct type (T), position (P), clearances (C), & attachment (A) of
checkpoint | Master Stations
textbox | T
textbox | P
textbox | C
textbox | A
checkpoint | Door Stations
textbox | T
textbox | P
textbox | C
textbox | A
checkpoint | Sub Stations
textbox | T
textbox | P
textbox | C
textbox | A
checkpoint | Handsets
textbox | T
textbox | P
textbox | C
textbox | A
section | Check Door Activation (D), Relay Activation (R), Call Button Functions (C), Auxillary button functions (A)
checkpoint | Master Station
textbox | D
textbox | R
textbox | C
textbox | A
checkpoint | Door Station
textbox | D
textbox | R
textbox | C
textbox | A
checkpoint | Sub Stations
textbox | D
textbox | R
textbox | C
textbox | A
checkpoint | Handsets
textbox | D
textbox | R
textbox | C
textbox | A
section | Check Picture Quality (P), Audio Quality (A), Names and numbers (N)
checkpoint | Master Station
textbox | P
textbox | A
textbox | N
checkpoint | Door Station
textbox | P
textbox | A
textbox | N
checkpoint | Sub Stations
textbox | P
textbox | A
textbox | N
checkpoint | Handsets
textbox | P
textbox | A
textbox | N
section | Confirm following items comply with requirements
checkpoint | Check all control devices power supplies are correct type and size
checkpoint | Check volatage of system at furtherest point.
checkpoint | Check that all cables are the correct type, size, configuration, length & quantity
checkpoint | Visually check all terminations for correct colour codes and acceptable looming
checklist | QA_TEM_047_Electrical Sub Metering | [5 empty] | QA_TEM_047_Electrical Sub Metering
section | Meter Installation - Check that the meter is
checkpoint | Correct type
checkpoint | Installed in correct location on switchboard in accordance with drawing
checkpoint | Positioned squarely and correctly fitted
checkpoint | Labelled correctly
checkpoint | Has been terminated and termination is correct
section | Meter Checks
checkpoint | Confirm that factory calibration certificate has been supplied (attach to ITP)
checkpoint | Confirm CT type, size and direction are correct
checkpoint | Connect load,apply clamp tester and confirm meter reading against clamp tester
checkpoint | Confirm meter reading in location simultaneously with metering head end reading
checkpoint | Confirm meter reading in location simultaneously with BMS head end reading
checkpoint | Confirm meter reading from BMS independently. Result equals previous test
checklist | QA_TEM_048_UPS | [5 empty] | QA_TEM_048_UPS
section | Confirm following items comply with requirements
checkpoint | 1
checkpoint | 2
checkpoint | 3
checkpoint | 4
checkpoint | 5
checkpoint | 6
checkpoint | 7
checkpoint | 8
checkpoint | 9
checkpoint | 10
checklist | QA_TEM_050_Hazardous Area | [5 empty] | QA_TEM_050_Hazardous Area
section | Equipment - Inspections (AS/NZS60079.14/60079.0/60079.17)
checkpoint | Equipment is Appropriate to the EPL/Zone Requirements of The Location (AS/NZS60079.14 Clauses 5&6)
checkpoint | Equipment Temperature Class & Gas Group Are Correct for The Classification (AS/NZS60079.14.5.6)
checkpoint | Equipment Circuit Identification is Available & Correct (AS/NZS60079.17.4.12.4)
checkpoint | Enclosure Glass Parts & Glass-to-Metal Sealing Gaskets and/or Compounds are Satisfactory (AS/NZS60079.17.4.12)
checkpoint | There is no Damage or Evidence of Damage or Unauthorised Modifications (AS/NZS60079.17.5.3.4 & 4.12)
checkpoint | Bolts Cable Entry Devices (Direct & Indirect) & Blanking Elements Are of The Type and Are Complete & Tight (AS/NZS60079.17.3.1)
checkpoint | Lamp Rating Type & Position Are Correct (AS/NZS60079.17.4.6.1) (60079.14.11.4)
checkpoint | Electrical Connections Are Tight (AS/NZS60079.14.9.6.6)
checkpoint | Condition of Enclosure Gaskets Is Satisfactory (AS/NZS60079.17.4.3.1)
checkpoint | Motor Fans Have Sufficient Clearance to Enclosure and Or Covers (AS/NZS60079.14. H.4)
checkpoint | Breathing & Draining Devices Are Satisfactory (AS/NZS60079.17.4.7)
section | Installation Requirements (AS/NZS60079.14) (AS/NZS60079.17) (AS/NZS3000)
checkpoint | Type of Cable Is Appropriate (AS/NZS60079.14.9.3&Table 6)
checkpoint | The Cables Are Adequately Supported and There is no Obvious Damage to Cables (AS/NZS60079.14.9.3.9)
checkpoint | Sealing of Trunking Ducts, Pipes, and/or Conduits is Satisfactory (AS/NZS60079.14.9.6.8)
checkpoint | The Integrity of The Conduit System and Interface with Mixed System is Maintained (AS/NZS60079.14.9.3.12&9.4)
checkpoint | Earthing Connections Including any Supplementary Earthing Bonding Connections Are Satisfactory (e.g. Connections Tight & Conductors of Sufficient CSA) (AS/NZS60079.14.6.2 &6.3 &6.4)
checkpoint | There is no Evident Damage or Degradation That Indicates the Fault Loop Impedance (TN-Systems) or Earthing Resistance (TT-Systems) is Not Satisfactory (AS/NZS60079.17.4.12.8)
checkpoint | There is no Evident Damage, or Degradation That Indicates the Insulation Resistance is Not Satisfactory (AS/NZS3000.8.3.6 &60079.6.4)
checkpoint | Automatic Electrical Protective Devices Operate Within Permitted Limits (AS/NZS60079.14.7.)
checkpoint | Automatic Electrical Protective Devices Are Set Correctly (Auto-Reset Not Possible) (AS/NZS60079.14.7)
checkpoint | Specific Conditions of Use Are Complied With (Suffix "X" on a Certificate Denotes Special Requirements (AS/NZS60079.17.5.3.2) (AS/NZS60079.0.3.3.8)
checkpoint | Cables Not in Use Are Correctly Terminated (AS/NZS60079.14.9.6.3)
checkpoint | Variable Voltage/Frequency Installation in Accordance with Documentation (AS/NZS60079.14.10.6 & 11.3.4 & 13.2)
section | Environment Requirements
checkpoint | Equipment is Adequately Protected Against Corrosion, Weather, Vibration and Other Adverse Factors (AS/NZS60079.17.4.7)
checkpoint | No Undue Accumulation of Dust & Dirt (AS/NZS60079.17.4.7)
checkpoint | All Equipment Housings Are Clean & Dry (AS/NZS60079.17.4.7)
section | Extra Ex d Checks (AS/NZS60079.1) (AS/NZS60079.14)
checkpoint | Confirm that Ex d Conduits Seals are Fitted to all Conduits and Satisfactorily Sealed (AS/NZS60079.14.10.5)
checkpoint | Confirm That Cable Glands are of the Barrier Type and Correctly Installed (Where Applicable) (AS/NZS60079.14.10.4.2)
checkpoint | Confirm That Adaptors, Nipples, Tees, etc. Are all Certified Ex d (AS/NZS60079.14.10.4)
checkpoint | Confirm That no Obstacles Within 10mm (IIA), 30mm (IIB) or 40mm (IIC) of Flange Joints (AS/NZS60079.14.10.2)
checkpoint | Confirm That Flame Paths are Clean and Undamaged (AS/NZS60079.14.10.3)
checkpoint | Confirm That Flange Gap Dimensions are Within Tolerances (AS/NZS60079.1.5.2)
section | Extra Ex e Checks (AS/NZS60079.7) (AS/NZS60079.14)
checkpoint | Confirm that all Equipment is Ex e certified (including components within Enclosure) (AS/NZS60079.7.8)
checkpoint | Confirm That Enclosure Entries Maintain the Degree of Ingress Protection of the Equipment or Area Whichever is The Greater (AS/NZS60079.14.11.2.2)
checkpoint | Confirm that the No. of Components within Enclosure does not exceed permitted max. (AS/NZS60079.14.11.2.4)
checkpoint | Confirm that bridging links do not reduce creepage / clearance and are allowed (AS/NZS60079.7.4.2.3&4.3)
checkpoint | Confirm that power conductors are not bunched together causing possible hot spots (AS/NZS60079.14.11.2.4)
checkpoint | Confirm that Electrical Connections Are Tight and in Accordance With (AS/NZS60079.14.11.2.3&4) (AS/NZS60079.7.4.2)
section | Extra Ex n Checks (AS/NZS60079.15) (AS/NZS60079.14)
checkpoint | Confirm That the Insulation of The Conductor Is Maintained Up to The Metal of The Terminal and That Each Conductor Is Adequately Clamped (AS/NZS60079.14.14.3.3)
checkpoint | Confirm that bridging links do not reduce creepage / clearance Distances and are allowed (AS/NZS60079.15.6.4.5)
checkpoint | Confirm that hermetically sealed and Enclosed Break devices are undamaged (AS/NZS60079.15.18)
section | Extra Ex nR Checks (AS/NZS60079.15) (AS/NZS60079.14)
checkpoint | Confirm that gaskets and seals are in good condition (AS/NZS60079.15.20.2.7)
checkpoint | Confirm Cable Entries to Restricted Breathing Apparatus Not Part of The Certificate Maintain the Restricted Breathing Properties of The Enclosure (AS/NZS60079.14.14.3.2.2)
checkpoint | Confirm that restricted breathing properties are satisfactory (pressure or vacuum test) (AS/NZS60079.15.23.2.3)
checkpoint | Confirm that label attached indicating time delay before opening (AS/NZS60079.15.6.2 & AS/NZS60079.0.6.3)
section | Extra Ex p Checks (AS/NZS60079.2) (AS/NZS60079.14)
checkpoint | Confirm That Protective Gas Pressure/Flow & Type & Temperature Is Adequate (AS/NZS60079.14.13.1.6)
checkpoint | Confirm that actual pressure is within maximum and minimum settings for Equipment (AS/NZS60079.14.13.1.3)
checkpoint | Confirm That the Purging Time Is in Accordance with Documentation (AS/NZS60079.14.13.1.5)
checkpoint | Confirm That the Wiring Systems Prevent Ingress of Combustible Gas or Prevent Leakage of Protective Gas (AS/NZS60079.14.13.1.7)
checkpoint | Confirm That Condition of Spark & Particle Barriers of Ducts for Exhausting Are Satisfactory (AS/NZS60079.14.13.1.3.3)
checkpoint | Confirm That Alarms and Trip Functions Operate Correctly as per Certification Documentation (AS/NZS60079.13.1.3)
section | Extra Ex i Checks (AS/NZS60079.11) (AS/NZS60079.25) (AS/NZS60079.14)
checkpoint | Confirm That All Apparatus Is Reasonably Identified As An I.S. System (AS/NZS60079.14.12.2.1&12.2.2.6)
checkpoint | Confirm There is No Evident Indication or Degradation That the Point to Point Connections Are Not Correct (AS/NZS60079.14.12)
checkpoint | Confirm Earthing Continuity Is Satisfactory (e.g. Connections are Tight, Conductors Are of Sufficient CSA) For Non-Galvanically Isolated Circuits (AS/NZS60079.14.12.2.4)
checkpoint | Confirm That Cable Screens Are Earthed in Accordance with Documentation (AS/NZS60079.14.12.2.4)
checkpoint | Earth Connections Maintain the Integrity of The Type of Protection (AS/NZS60079.14.12.2.4)
checkpoint | Confirm that separation and segregation is maintained between IS and non-IS Circuits (AS/NZS60079.14.12.2.3)
checkpoint | Confirm That There Is No Evident Damage or Degradation That Indicates That the Intrinsically Safe Circuit Earthing & Insulation is Not Satisfactory (AS/NZS60079.14.12.2.2)
checkpoint | Confirm That Short-Circuit Protection of The Power Supply Is in Accordance with Documentation (AS/NZS60079.14.12.2.1)
checkpoint | Confirm That Cables Not in Use Are Correctly Terminated (AS/NZS60079.14.12.2.2.5.3)
checkpoint | Confirm That A Descriptive System Document is Available for Each Intrinsically Safe Circuit if a System Certificate Is Not Available (AS/NZS60079.14.12.2.5)
checklist | QA_TEM_055_Flood Lighting Lux Levels | [5 empty] | QA_TEM_055_Flood Lighting Lux Levels
section | Stop Bar
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 5m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 10m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 15m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 20m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 25m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 30m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 35m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 40m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 45m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 50m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
section | 55m
checkpoint | Lux Meter Position - Vertical North
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Vertical South
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checkpoint | Lux Meter Position - Horizontal
textbox | 30m
textbox | 25m
textbox | 20m
textbox | 15m
textbox | 10m
textbox | 5m
textbox | Centre Line
textbox | 5m
textbox | 10m
textbox | 15m
textbox | 20m
textbox | 25m
textbox | 30m
checklist | QA_TEM_059_Switchboard Maintenance | [5 empty] | QA_TEM_059_Switchboard Maintenance
section | Confirm following items comply with requirements
checkpoint | Clean & vacuum the outside of the switchboard
checkpoint | Inspect the switchboard for signs of moisture, flora, fauna ingress
checkpoint | Clean & vacuum the inside of the switchboard
checkpoint | Check seals and gaskets to ensure they're sealing correctly
checkpoint | Check components and wiring for any signs of deterioration or overheating
checkpoint | Visual inspection of conatctors for signs of arcing
checkpoint | Check door isolator interlocking is working correctly
checkpoint | Check pole fillers are in place
checkpoint | Check screws and bolts for tightness. (Pull test on cables after tightening check)
checkpoint | Thermoscan switchboard
checkpoint | Functional test of circuits
checkpoint | Check calibration of circuit breaker settings
checkpoint | Check operation of RCD's. (Record results on QA_FRM_009_RCD Test Register)
checkpoint | Test supply changeover
checkpoint | Check power switching components are within design life
checkpoint | List of defects found:
checklist | QA_TEM_060_ACB Maintenance | [5 empty] | QA_TEM_060_ACB Maintenance
section | Project Details
checkpoint | Project Details
textbox | Customer
textbox | Site
textbox | Project
textbox | Job Number
textbox | Switchroom ID
textbox | Switchboard ID
textbox | Circuit ID
textbox | Maintenance Level
section | Test Equipment Details
checkpoint | Test Equipment 1
textbox | Asset ID:
textbox | Make and Model:
checkpoint | Test Equipment 2
textbox | Asset ID:
textbox | Make and Model:
checkpoint | Test Equipment 3
textbox | Asset ID:
textbox | Make and Model:
checkpoint | Circuit Breaker Details:
textbox | Make:
textbox | Type:
textbox | Serial Number:
textbox | Rated Current:
textbox | Rated Voltage:
textbox | Protection Type:
textbox | Close Coil Voltage:
textbox | Open Coil Voltage:
textbox | Spring Charge Volts:
textbox | Undervoltage Coil:
textbox | Op Counter as found:
textbox | Op Counter as left:
section | Section 1 - Energised Inspection (1.0 Visual Inspection)
checkpoint | 1.1 Condition of Exterior Components
checkpoint | 1.2 Control Cables and Connections
checkpoint | 1.3 Indication Lights on Switchboard
checkpoint | 1.4 Abnormal odours
checkpoint | 1.5 Infrared inspection
checkpoint | 1.6 Ultrasonic inspection
checkpoint | 1.7 Circuit identification
checkpoint | 1.8 Protective covers
section | Section 2 - De-Energised Inspection (1.0 Visual Inspection)
checkpoint | 1.1 Main Bus Bar Connections
checkpoint | 1.2 Earth Connection
checkpoint | 1.3 Main Contact Assembly
checkpoint | 1.4 Arc Control Devices
checkpoint | 1.5 Insulation
checkpoint | 1.6 Operating Mechanism
section | Section 2 - De-Energised Inspection (2.0 Mechanical and Electrical Operation)
checkpoint | 2.1 Unit Racks into isolated position
checkpoint | 2.2 Unit Racks into service position
checkpoint | 2.3 Perform 5 manual open operations
checkpoint | 2.4 Perform 5 manual close operations
checkpoint | 2.5 Operate Spring Charge Motor
checkpoint | 2.6 Operate Close Coil
checkpoint | 2.7 Operate Open Coil
checkpoint | 2.8 Operate Undervoltage Coil
section | Section 3 - General Items
checkpoint | 3.1 Clean, Oil and Adjust Operating Mechanism
checkpoint | 3.2 Check Auxiliary Contacts
checkpoint | 3.3 Control Cables and Connections
checkpoint | 3.4 Check Local and Remote Switches
section | Section 4 - Maintenance Tests (4.1 Main Current Path Low Resistance Test)
checkpoint | Main Current Path - Before Maintenance Pole 1 (µΩ)
textbox | A Phase
textbox | B Phase
textbox | C Phase
textbox | Neutral
checkpoint | Main Current Path - After Maintenance Pole 1 (µΩ)
textbox | A Phase
textbox | B Phase
textbox | C Phase
textbox | Neutral
checkpoint | Main Current Path - Before Maintenance Pole 2 (µΩ)
textbox | A Phase
textbox | B Phase
textbox | C Phase
textbox | Neutral
checkpoint | Main Current Path - After Maintenance Pole 2 (µΩ)
textbox | A Phase
textbox | B Phase
textbox | C Phase
textbox | Neutral
section | Section 4 - Maintenance Tests (4.2 Insulation Resistance Test)
checkpoint | Insulation Resistance Test - CB Open - Load Side (GΩ)
textbox | A - B+C+E
textbox | B - A+C+E
textbox | C - A+B+E
textbox | N-ABCE
checkpoint | Insulation Resistance Test - CB Open (GΩ)
textbox | A - B+C+E
textbox | B - A+C+E
textbox | C - A+B+E
textbox | N-ABCE
section | Section 4 - Maintenance Tests (4.3 Protection Relay Test)
checkpoint | Protection Relay Details
textbox | Make:
textbox | Type:
textbox | Serial Number:
textbox | Rating:
textbox | Test Type:
textbox | Test Equipment:
checkpoint | Protection Relay Settings: Phase Overcurrent
textbox | Pickup
textbox | TMS
textbox | Curve
textbox | Instantaneous
checkpoint | Protection Relay Settings: Earth Fault
textbox | Pickup
textbox | TMS
textbox | Curve
textbox | Instantaneous
section | Section 4 - Maintenance Tests (Phase Overcurrent)
checkpoint | Pickup (A)
textbox | A Phase Result
textbox | B Phase Result
textbox | C Phase Result
checkpoint | Injected Amps (2x)
number | Expected Time in Milliseconds (ms)
number | Actual Time in Milliseconds (ms)
textbox | A Phase Result
textbox | B Phase Result
textbox | C Phase Result
checkpoint | Injected Amps (3x)
number | Expected Time in Milliseconds (ms)
number | Actual Time in Milliseconds (ms)
textbox | A Phase Result
textbox | B Phase Result
textbox | C Phase Result
checkpoint | Injected Amps (5x)
number | Expected Time in Milliseconds (ms)
number | Actual Time in Milliseconds (ms)
textbox | A Phase Result
textbox | B Phase Result
textbox | C Phase Result
checkpoint | Instantaneous Pickup (A)
number | Time in Milliseconds (ms)
textbox | A Phase Result
textbox | B Phase Result
textbox | C Phase Result
checkpoint-no-status | Overall Result
section | Section 4 - Maintenance Tests (Earth Fault)
checkpoint | Pickup (A)
textbox | Earth Fault Results
checkpoint | Injected Amps (2x)
number | Expected Time in Milliseconds (ms)
number | Actual Time in Milliseconds (ms)
textbox | Earth Fault Results
checkpoint | Injected Amps (3x)
number | Expected Time in Milliseconds (ms)
number | Actual Time in Milliseconds (ms)
textbox | Earth Fault Results
checkpoint | Injected Amps (5x)
number | Expected Time in Milliseconds (ms)
number | Actual Time in Milliseconds (ms)
textbox | Earth Fault Results
checkpoint | Instantaneous Pickup (A)
number | Time in Milliseconds (ms)
textbox | Earth Fault Results
checkpoint-no-status | Overall Result
section | Section 4 - Maintenance Tests (Test items)
checkpoint | 4.1 Main current path low resistance test
checkpoint | 4.2 Insulation resistance test
checkpoint | 4.3 Protection relay test
checkpoint | 4.4 Electrical Functionality
section | Section 5 - E-Check Safety Sign Off
checkpoint | All modifications to the installation during maintenance has been returned to as the originally found state
date | Date:
textbox | E-Check Technician:
section | Q Electrical Overall Condition Assessment
checkpoint | Q Electrical Overall Condition Assessment
textbox | Rating:
textbox | Recommendation: