## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
58b4fcc5-f228-4a9d-a7d0-b34d1b40da1b | checklist | ITP - Road Marking | itp | ITP - Road Marking
a6d51dca-922b-4dd5-8ea8-d49fad11ce5b | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
5dcd1f18-b7d6-4ee1-a2b2-45f1dee7f8b3 | checkpoint | 01.01.01 - Construction Pack
686075c4-1b64-534e-b587-c3ee15773a49 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
da91e32a-fae2-59b8-9331-cf354acfd22b | note | Standard / Specification - Downer
8022610f-bf1c-5e8c-99f7-e1941fbed5c9 | note | Verifying Document - Construction Pack
86bdcbed-a2a6-5a63-8a95-f05529429627 | note | Frequency - Prior to Works
0240c0eb-c0a8-5fba-a741-880a9fb0ed28 | note | Verification Activity: Activity - H
fcb13dd7-4631-5d25-93ef-9f004c82e0d4 | note | Verification Activity: By - PE
| checkpoint | 01.01.02 - Inspection and Test Plan
| note | Acceptance / Conformance Criteria - Approval of ITP
| note | Standard / Specification - Downer
| note | Verifying Document - Acceptance Correspondence
| note | Frequency - Prior to Works
| note | Verification Activity: Activity - H
| note | Verification Activity: By - ENG
dda079ad-9fa2-4a79-b0e5-84da11f3df00 | checkpoint | 01.01.03 - Survey Setout
02fb62de-21a1-56cb-94e5-353c84aa7d5f | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
34495400-e517-52f3-8bc5-f6c31b6aae26 | note | Standard / Specification - Downer
52c7c54f-0be9-5c9d-8061-483af90e3688 | note | Verifying Document - Survey Records
3430efec-4665-5d7d-94e4-e846683488a3 | note | Frequency - Prior to Works
8f5ae75c-57a7-5cc9-9fcd-b7ca3ced67c8 | note | Verification Activity: Activity - H
a8d3ea04-b1e5-5ea6-b500-253b77e285e4 | note | Verification Activity: By - SV
3c0a7aa8-e65a-4a88-adfc-48316a33c21e | checkpoint | 01.01.04 - Approved Construction Drawings
e3f643e9-fafd-52f3-a0cd-a91db9a544ad | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
0c83b059-e3aa-5301-aeeb-cd75c8cceb17 | note | Standard / Specification - Downer
24cd8588-fb07-5eff-80dd-4424f4c10e25 | note | Verifying Document - IFC Drawings
c59375f9-173a-58b5-bd6f-d0e78b9f061f | note | Frequency - Prior to works start
a83a98ea-f3bd-56b8-aefb-29b473042d85 | note | Verification Activity: Activity - H
6289f4aa-0b15-5e35-b9f0-c878581cdf49 | note | Verification Activity: By - PE
eb4b6292-f361-4cf4-896f-ad7ca5ff6f6c | section | SECTION 2 – ENGINEERS HOLD POINTS
d6ef3554-1e84-47d4-aa04-951147b8e72a | checkpoint | 02.01.01 - Pavement Marking Inspection
f21a95e8-cc67-526e-ae59-3b5730f7d29b | note | Acceptance / Conformance Criteria - After set-out and prior to installation of signs and pavement markings.
51e1d473-1347-5e79-83c3-75f4cff0b7ff | note | Standard / Specification - PS - 2.2.16
b757efa9-dbcf-55ad-841c-a9334e7d1f21 | note | Verifying Document - Hold Point Release
48829a4d-4a52-5a29-b1bb-89e0bf3d115f | note | Frequency - Min 48h Notice
788d300d-8643-5b14-9839-9a44eb67020b | note | Verification Activity: Activity - HP
ff95013b-b530-5f2f-b0fe-f3854751f9ca | note | Verification Activity: By - ENG
123384db-0908-4362-975e-0d56b9d5a4ab | signoff | AUTHORITY HOLDPOINT
114e0983-8867-4326-854f-46953dc8a448 | section | SECTION 3 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – ROADMARKING
e4bfad2a-3b21-446d-84d2-21f99e168cc5 | checkpoint | 03.01.01 - Approval of Road Marking Materials
e24b923d-4539-5aa9-8b09-8668a47a6300 | note | Acceptance / Conformance Criteria - Paint shall comply with NZTA M/7 – Specification for Road Marking Paints & material to be included under the list of NZTA road marking approved products
f7cd97a2-773c-5846-aefa-625e63759622 | note | Standard / Specification - MOTSAM
b58ce365-39eb-5783-b406-955fcb07c163 | note | Verifying Document - Certificate / Delivery Dockets
cb14b890-6a0c-51cf-8ed2-6d7ed7dcdede | note | Frequency - Before Marking
7ca87db3-e409-5bd6-b0dc-a6b8d45f2435 | note | Verification Activity: Activity - R
8f021eb7-bf1c-5431-bdbb-eda8740eb599 | note | Verification Activity: By - SE
| checkpoint | 03.01.02 - Certification of Road Marking Equipment
| note | Acceptance / Conformance Criteria - NZTA T/12 certification for line marking equipment (RITS 3.5.3)
| note | Standard / Specification - RITS
| note | Verifying Document - Certificate
| note | Frequency - Before Marking
| note | Verification Activity: Activity - R
| note | Verification Activity: By - SE
beda96bd-30ce-44f7-bda7-d0863b83a58a | section | SECTION 04 – CONSTRUCTION ACTIVITY – ROADMARKING
21aa7bac-66ed-4cbc-b7ad-75579492a2a2 | checkpoint | 04.01.01 - Pavement Marking Inspection
44c1c0c0-376e-56f1-99ae-a6948b8ff869 | note | Acceptance / Conformance Criteria - After set-out and prior to installation of signs and pavement markings.
bff63840-8147-5d19-b99d-7b394a1971d5 | note | Standard / Specification - PS - 2.2.16
c5d7a7a4-b0f8-5c29-9c81-40a8101bef78 | note | Verifying Document - Written Correspondence
03687df0-81da-5dc3-b6ed-a01a3e47e773 | note | Frequency - Min 48h Notice
0530ed6c-f897-553a-b2aa-684d6a599188 | note | Verification Activity: Activity - HP
38a8c947-9594-5687-a229-8276b863b06b | note | Verification Activity: By - ENG
0ce050aa-4e9a-40ea-93c1-e365f5c652b5 | signoff | AUTHORITY HOLDPOINT
3af5bb97-8a9f-48fe-8e22-1b4aa6dcdc1e | checkpoint | 04.01.02 - Pavement Marking
73ca0b7a-f6c4-565b-8e6b-ecdeb90ecef8 | note | Acceptance / Conformance Criteria - The design and location of the markings shall be in accordance with MOTSAM and the details on the Drawings. Markings shown on the Drawings shall have precedence over any MOTSAM details however the Contractor shall advise the Engineer of any ambiguities prior to setting out.
6178bcd9-ee36-5a21-9397-4e0a91ce2fe5 | note | Standard / Specification - MOTSAM
a112aa54-f416-59dd-ac42-250129424252 | note | Verifying Document - Site Notes
5288d5ff-fbaf-5107-b5bc-ab301cba4d9d | note | Frequency - Before Marking
366524c0-e8b4-5432-8fb1-94d26b7361b2 | note | Verification Activity: Activity - R
282a14b9-b0a6-52fb-87c1-9325f7b9afe4 | note | Verification Activity: By - SE
9bd2d1c5-beaf-4ffc-8030-8d9df63418a1 | checkpoint | 04.01.03 - Surface Prep
f8586ad0-56cb-53ca-a084-a1b51ddeee22 | note | Acceptance / Conformance Criteria - The surface to be marked must be swept and cleaned so not to have any dirt, loose chip or detritus sitting on top of it. The surface must be checked and accepted by the Engineer prior to any marking being carried out.
b15087f1-db66-5688-b1d5-3832160ec05b | note | Standard / Specification - PS - 8.4
77be5609-3504-577d-b601-cc80e048bec9 | note | Verifying Document - Photos
43cdd3f2-14d8-5e68-a2e2-e27697a5e9fd | note | Frequency - Before Marking
3c4f4081-18bc-5e85-be41-9d84eaac9014 | note | Verification Activity: Activity - R
fa7b4231-c6a2-5e41-b33d-182a0bacb2bf | note | Verification Activity: By - SE
626deb3b-4080-41af-be99-51d9d7dfbcea | checkpoint | 04.01.04 - Removal of existing pavement marking
3cc4eafc-5122-5f66-ab4c-b6ecb631363c | note | Acceptance / Conformance Criteria - Removal of existing pavement marking shall be carried out in accordance with The New Zealand Road markers Federation Line Removal Guide (http://www.nzrf.co.nz). The method selected shall ensure that old markings are not visible, especially in the wet.
d9c33370-3200-586c-b1bb-0ef9de74f2b4 | note | Standard / Specification - PS - 8.4
fbf167b9-eeb8-5890-8f25-a3e5210a0ad3 | note | Verifying Document - Methodology
63a255f7-123e-5e14-ad5b-641bacb6d1e8 | note | Frequency - Before Works
19ba5799-c4f1-5a69-9cee-b1b52203c552 | note | Verification Activity: Activity - R
caca6fe4-edd3-59fd-8d0a-cb8ba3ef62b5 | note | Verification Activity: By - SE
| checkpoint | 04.01.05 - Application Records
| note | Acceptance / Conformance Criteria - Daily record sheet to be completed as per section 16 of TNZ P12
| note | Standard / Specification - TNZ P12
| note | Verifying Document - Daily Record Sheet
| note | Frequency - After Marking
| note | Verification Activity: Activity - R
| note | Verification Activity: By - SE
| checkpoint | 04.01.06 - Redline Drawings
| note | Acceptance / Conformance Criteria - Electronic points file to be provided.
| note | Standard / Specification - PS - 2.2.17
| note | Verifying Document - Total Station asbuilts
| note | Frequency - After Marking
| note | Verification Activity: Activity - A
| note | Verification Activity: By - SV
9db75062-73e7-42b3-8451-79fdbfe0a9e3 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b1062313-b1ae-564b-b5da-e1c79811a888 | textbox | Contractor's Rep Name:
2691820a-901c-57f8-9445-f676d0af16bb | textbox | Engineer's Rep. Name:
1e6a120b-22ec-5c91-a359-57b4413d729a | date | Date:
275dae9b-f8fb-4357-a487-178ddd6bb459 | signoff | Add Signature