## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
Project Name: | SH58 Safety Improvements, Stage 2B | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | TBC | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi (NZTA) | [5 empty] | B | Report by Breach | CM | Construction Manager | Jamie Nisbet. | JN
Contract Number: | TBC | [5 empty] | C | Check | ER | Engineers Representative (Assisstant)
Area/ Sub-System: | Reinforced Concrete - In-Situ |  |  | Lot ID Number: | TBC |  | D | Dimension Inspection | IP | Inspection Personnel | N/A | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A | N/A
ITP Number: | DS2681-SH58-ITP-M-005 DS2681-SH58-ITP-C-001 |  |  | Version: | 2 |  | H | Hold Point | OP | Operations Manager | N/A | N/A
ITP Description: | Pautahunui Bridge 7 - Substructure works. | [5 empty] | I | Inspection | PM | Project Manager | Gordon Lemon | GL
Discipline: | Infrastructure (Substructures) | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | SH58 Safety Improvements, Stage 2B – Harris Road to East of Moonshine Road including additions for Flighys Road to Transmission Gully Contract No. 7269 | [5 empty] | O | Operation | QA | Quality Advisor | Lissa Gatehouse | LG
[7 empty] | R | Review | QM | QA Manager
Drawings: | 80510096-02B-330 Series. | [5 empty] | S | Subcontractor | SP | Supervisor
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Falakiko Veatupu |  |  | Date: | 2023-04-29 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [6 empty] | T | Field Testing | WS | Welding Supervisor | tbc | tbc
SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2024-08-01
Downer Approval |  | Name: | Diliban Sengottian |  |  | Signature: |  |  |  |  | Date: | 2024-08-01
Customer Approval |  | Name: | Purvik Patel |  |  | Signature: |  |  |  |  | Date:

## Materials
SECTION 1 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location/ Hold Points
1.1 | Concrete Mix - Mix Design | Mix design submission to Engineer | Specification Cl 26.1.11 | Mix Design to be forwarded to the Engineer for review and approval. | Concrete Mix Design Document | 14 Days Prior to use | Hold Point | H | ER
1.2 | Reinforcing Steel | Reinforcing Steel | Specification Cl 26.3 | Reinforcing bars shall be cut and bent according to NZS 3109, Section 3 and NZS 3101, Section 8.4 to the dimensions and shapes as shown or indicated on the Drawings. Bend diameters for longitudinal reinforcing shall be in accordance with Table 3.1, NZS 3109 and Table 8.1, NZS 3101. Stirrups shall be bent to standard shapes as shown in NZS 3109. | Mill Certificates & bar bending schedule | Prior to & after delivery | Hold Point | W | SE

## Construction
SECTION 2 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location/ Hold Points
2.01 | Method Statement | Prior to works | PS Cl. 24.1.18 | The Contractor shall supply a method statement to the Engineer at least 10 working days before the supply of concrete to the project site. The method statement(s) shall clearly demonstrate that the Concrete Supplier and Contractor have carefully considered the Quality Assurance requirements, requirements of this Specification. | Method Statement | 10 Days prior to use | Hold Point | H | ER
2.02 | Reinforcing & Formwork - Cover | Reinforcing cover to formwork | PS Cl. 24.1.13 Table 20.2.2 |  | Photos | Per Pour | Witness Point | W | SE
2.03 | Reinforcing & Formwork - Reo placement and bar bending | Reo placement and bar bending | Ensure reinforcing bends comform to NZ standards and project specifications | Bars shall be cut and bent in accordance with NZS 3109 to the shapes indictated in the drawings and placed correctly in the arrangement shown; Unless noted on drawings reinforcing bars to be bent to min bend diameters outlined in NZS3101; Heat bending of bars is prohibited | Photos Bar bending schedule | Per Pour | Witness Point | W | SE
2.04 | Reinforcing & Formwork - Formwork | Formwork | AS/NZS 4671: 2001, 'NZS 3109 PS Cl. 24.1.16 | Formwork to be constructed so that finished concrete will be to the shape, lines and levels shown on the drawings; All forms shall be designed such that exposed concrete edges have a min 20mm chamfer unless otherwise indicated on the drawing; Interior surfaces of the forms shall be treated with a release agent. Any reinforcement in contact with the release agent shall be cleaned thoroughly; Forms to be sufficiently watertight to prevent grout loss | Photos | Per Pour | Witness Point | W | SE
2.05 | Pre-pour inspection | Pre-pour Inspection | PS Cl 24.1.17 | Pre-pour inspection - Engineer acceptance | Pre-Pour Inspection | Per Pour | Hold Point | H | ER
2.06 | Formwork and Pour - Finishes | Formwork and Pour | PS Cl. 24.1.16 |  | Photo & Pre-pour Inspection | Per Visible Surface | Documentation | W | SE
2.07 | Concrete Pour | Concrete Placement | AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing | Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer. Concreting to be a continous operation between ends of members and/or properly formed construction joints. Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m. | Pre-Pour Inspection | Per Pour | Documentation | W | SE
2.08 | Concrete Pour | Concrete Test Cylinders | PS Cl.24.1.14 | A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days. Strength of concrete = Dependent on Mix Design. | Lab Report | Per batch | Report | W | SE
2.09 | Concrete Pour | Approved Concrete Mix Design | PS Cl 24.1.3 | Confirm correct mix design brought to site Concrete Docket Showing: • Mix Design Item Code • 28 day specified strength = 45MPa • concrete placement method that the mix was designed for - Pump Mix • type of supplementary cementitious materials (if used); • slump (target and actual slump when measured); • Order and Delivery Quantity • Load Time out of plant • To site time • Unload Time • Associated Products e.g. cement and additives | Concrete Docket | Each truckload | Documentation | W | SE
2.1 | Concrete Pour | Slump Test | PS Table 9.1 | Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm. Slump test tolerances: | Visual/Photos | Each truckload | Test | W | SE
2.11 | Concrete Pour | Time Limits | PS Cl 24.1.17 | Incorporated in the works within 90minutes of batching. Incorporated in the works within 30minutes of discharge from concrete truck/agitator | Dockets & pour sheet | Each truckload | Dockets | W | SE
2.12 | Concrete Pour | Concrete Vibration | Clause 7.6 of NZS 3109 | All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: - All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured. | Visual/Photos | Per Pour | Visual | W | SE
2.13 | Post Concrete Works | Curing | AS/NZS 4671: 2001, 'NZS 3109 | Concrete to be cured for min 3 days; | Pre-Pour Inspection | Per Pour | Documentation | W | SE
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No sign-off required here - only on line item 2.05
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No sign-off required here - only on line item 2.05
Note on J7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No sign-off required here - only on line item 2.05

## Final Inspection and Handover
SECTION 3 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.1 | Survey As-built | Survey as-built | Specification Cl 26.4 & AS2159 (Page 167) | As-built survey CAD File | As-built survey CAD File |  | Documentation | C | SE/ER/SV
SECTION 6 – COMMENTS
Customer Release Granted: ☐ Yes ☐ No |  |  |  | Comments
Certificate Number: |  |  | Date: