## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-M-005 Concrete Materials | itp |  |  |  |  | DS2681-SH58-ITP-M-005 Concrete Materials
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 1.1 - Concrete Mix - Mix Design
label | Inspection Point: Quality Control Activity - Mix design submission to Engineer
label | Specification Reference - Specification Cl 26.1.11
label | Acceptance Criteria - Mix Design to be forwarded to the Engineer for review and approval.
label | Verifying Document - Concrete Mix Design Document
label | Frequency - 14 Days Prior to use
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Reinforcing Steel
label | Inspection Point: Quality Control Activity - Reinforcing Steel
label | Specification Reference - Specification Cl 26.3
label | Acceptance Criteria - Reinforcing bars shall be cut and bent according to NZS 3109, Section 3 and NZS 3101, Section 8.4 to the dimensions and shapes as shown or indicated on the Drawings.
label | ○ Bend diameters for longitudinal reinforcing shall be in accordance with Table 3.1, NZS 3109 and Table 8.1, NZS 3101. Stirrups shall be bent to standard shapes as shown in NZS 3109.
label | Verifying Document - Mill Certificates & bar bending schedule
label | Frequency - Prior to & after delivery
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE