## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-015
Revision : 1
Client: |  | Surf Coast Shire |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Fischer St Road Saftey Project |  | Concrete Paving |  | Name: | Jackson Kay | Name: |  |  | Name: | Simon Jawoski
Contract No: |  | T24-015 |  | Specifications: VicRoads Standard Specification – Section 703
|  |  |  | Structure / Component: Footpath |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Fischer St / Nautical Rise |  | Date : |  | Date : |  |  | Date :
Lot No: | 1 |  | Lot Details: | Nautical Rise |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to start | Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works. | 703.17 | Verify | ITP Signed | HP | Project Engineer/ Superintendent
2.2 | Temporary Drainage Provisions |  | If Required | If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. | Cl 703.18 | Visual inspection | ITP Signed | WP | Project Engineer/ Site Foreman | N/A |  | N/A
2.3 | Bedding |  | Each lot | All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted. | Cl 703.21 | Visual inspection | ITP Signed | WP | Project Engineer/ Superintendent | N/A
2.4 | Pre-concrete check |  | Each lot | Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Concrete extrusion machines have minimum cement content of 320kg/m3. | Cl 703.08 | Verify | ITP Signed Ambient Temperature..... °C Concrete Temperature...... °C | HP*/ WP | Project Engineer/ Superintendent | N/A
2.5 | Reinforcement |  | Each Lot | Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm | AS/NZS 4671 | Visual inspection | ITP Signed | IP | Project Engineer | N/A
2.6 | Concrete Placement |  | Each lot | Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches | VicRoads Spec Cl 703.23 | Site Inspection | ITP Signed | IP | Project Engineer | N/A
2.7 | Finish Surfaces |  | Each Lot | Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour | 703.25 | Visual inspection | ITP Signed | IP | Site Engineer/ Site Foreman | N/A
2.8 | Joints |  | Each joint | Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen | 703.26 | Verify | ITP Signed | IP | Project Engineer/ Site Foreman | N/A
2.9 | Backfilling |  | Each Lot | Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified. Layers shall not exceed 150mm compacted depth | 703.29 | Verify | ITP Signed | IP | Project Engineer | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.