## ITP-011
|  |  | Inspection and Test Plan - Guard Fence | [7 empty] | Document # ITP-011
Revision : 1
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Spout Creek Bridge Replacement |  | Type B Guard Fence Installation |  | Name: | Jarrod Rodrigues | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: |  | DOT33479 |  | Specifications: VicRoads Standard Section 708, VicRoads Standard Drawings SD3661 & SD4081
|  |  |  | Structure / Component: Type B Guardfence |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Great Ocean Road |  | Date : | 2024-07-25 | Date : | 2024-07-25 |  | Date : | 2024-08-05
Lot No: | 1 |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Design Drawings & Drawings Register | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Materials |  | Prior to commencing any activity | All materials are to be used must be on VicRoads current accepted products list (RDN06-04) and confirm with the detailed design. The contractor shall submit to the Superintendent all test certificates related to the supply of steel for the works at least 14 days prior to commencement of installation. | VR Section 708.04 & 708.05 | HP | ITP Signed, Certificate of Materials | HP | Project Engineer/ Superintendent
2 | Construction Works
2.1 | Identification of Services |  | Prior to commencing any activity | Ensure any locations have been identified and marked on site. Ensure any approvals are in place with service providers prior to commencing install. | DBYD | Witness Point | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
2.3 | Setout |  | Prior to commencing any activity | Contractor to confirm with the superintendent the required location and length of all guard fence alignments. | Design Drawings, VR Section 708.08 | Visual inspection | ITP Signed | HP | Project Engineer/MRPV Superintendent |  |  | N/A
2.4 | Installation |  | Each Lot | Guard fence system to be installed in accordance with design drawings, manufacturer guidelines, and within tolerances set out in VicRoads Standard Section 708.07 (d). | Design Drawings, Manufacturer Guidelines, VR Section 708.07. | Visual inspection | ITP Signed | IP | Project Engineer/ Site Foreman | N/A |  | N/A
2.5 | End Treatments |  | Each Lot | Guardrail end treatments are to be installed in accordance with design drawings, manufacturer guidelines, and specifications. | Design Drawings, Manufacturer Guidelines, VR Section 708.07. | Visual inspection | ITP Signed | IP | Project Engineer/ Site Foreman | N/A |  | N/A
2.6 | Installation of Delineators |  | Each Lot | Contractor to supply and fasten delineators on left hand side (red) and right-hand side (yellow). | VR Section 708.07 | Visual inspection | ITP Signed | IP | Project Engineer/ Site Foreman | N/A |  | N/A
3 | Testing and Quality Control
3.1 | Submission of Certificate of Compliance (CoC) |  | Upon completion of install | Contractor to submit the CoC to the Superintended from guard fence supplier. | VR Section 708 | Test Point | ITP Signed | TP | Project Engineer/ Superintendent |  |  | N/A
3.2 | Submission of Material Test Certificate |  | Each Lot | Contractor to submit test certificate to superintendent from guard fence supplier. | VR Section 708 | Test Point | ITP Signed | TP | Project Engineer/ Superintendent |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.