## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-002 - Underground Stormwater Drainage BC | itp |  |  |  |  | ITP-002 - Underground Stormwater Drainage BC Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Precast Materials Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | REFERENCE DOCUMENTS: 701.04b
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.4 - Precast Pipe Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
label | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl.619
label | ○ Cl. 701.04(a)
label | ○ Cl. 701.04(b)(i)
label | ○ Cl. 705.04(d)
label | ○ Cl. 705.11
label | ○ AS4058
label | ○ AS4680
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.5 - Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 19mm sieve.
label | ○ 5%-40% passing 0.075mm.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e
label | ○ Table 701.041
label | ○ Table 701.042
label | ○ Table 701.231
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.6 - Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 37.5mm sieve.
label | ○ 5%-40% passing 0.075mm sieve.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e
label | ○ Table 701.041
label | ○ Table 701.042
label | ○ Table 701.231
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set out drainage
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.15, Table 701.151
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.4 - Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.5 - Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
label | ○ 100mm under pipes.
label | ○ 80mm (earth foundation)
label | ○ 150mm (rock foundation)
label | REFERENCE DOCUMENTS: 701.19
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Place pipes
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings 701.17
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Jointing Box culvert sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: Consecutive sections of box culverts shall be firmly butted together. The top sections shall be matched to the bottom sections and shall not be lapped over adjoining bottom sections. The contact areas between the top and bottom sections shall be mortared. Multi-row box culverts shall be laid with the sections in each row in contact with the sections in the adjacent rows.
label | REFERENCE DOCUMENTS: 701.17
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Place & compact backfill material over pipes
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
label | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.14, 701.15
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Repairs to damaged pipes
label | FREQUENCY: Each damaged pipe
label | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
label | ○ All repair procedures undertaken in accordance with Cl 701.25
label | REFERENCE DOCUMENTS: 701.31
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | FREQUENCY: as required/requested
label | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
label | ○ Bedding material shall be compacted using a compaction plated to refusal.
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-002 - Underground Stormwater Drainage RCP | itp |  |  |  |  | ITP-002 - Underground Stormwater Drainage RCP Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Precast Materials Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | REFERENCE DOCUMENTS: 701.04b
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.4 - Precast Pipe Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
label | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl.619
label | ○ Cl. 701.04(a)
label | ○ Cl. 701.04(b)(i)
label | ○ Cl. 705.04(d)
label | ○ Cl. 705.11
label | ○ AS4058
label | ○ AS4680
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.5 - Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 19mm sieve.
label | ○ 5%-40% passing 0.075mm.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e
label | ○ Table 701.041
label | ○ Table 701.042
label | ○ Table 701.231
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.6 - Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 37.5mm sieve.
label | ○ 5%-40% passing 0.075mm sieve.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e
label | ○ Table 701.041
label | ○ Table 701.042
label | ○ Table 701.231
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set out drainage
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.15, Table 701.151
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.4 - Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.5 - Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
label | ○ 100mm under pipes.
label | ○ 80mm (earth foundation)
label | ○ 150mm (rock foundation)
label | REFERENCE DOCUMENTS: 701.19
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Place pipes
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings 701.17
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Place & compact backfill material over pipes
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
label | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.14, 701.15
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Repairs to damaged pipes
label | FREQUENCY: Each damaged pipe
label | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
label | ○ All repair procedures undertaken in accordance with Cl 701.25
label | REFERENCE DOCUMENTS: 701.31
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | FREQUENCY: as required/requested
label | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
label | ○ Bedding material shall be compacted using a compaction plated to refusal.
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-004 - Fill with Material Type A | itp |  |  |  |  | ITP-004 - Fill with Material Type A
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Bellarine Hwy Safety Upgrade
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Verify Material
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and FH shall inspect each type of material encountered and subject to verification by appropriate laboratory testing and agree on the category of the material.
label | ○ Type A material shall be totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel or steel by-products.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(c), Cl.204.04(c)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Results, Material Ctegory agreed with Superintendent
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Placing Type A Material
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Fill Construction
label | FREQUENCY: Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Keyed fill layers
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Layer thickness
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
label | ○ A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Proof Roll
label | FREQUENCY: Each Lot (one day's production or 5,000m2, whichever is lesser)
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173.
label | ○ Superintendent to be present during all test rolling.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Proof Roll Form completed & signed.
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Preparation of final surface
label | FREQUENCY: Prior to construction of subgrade layer
label | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15, Cl. 204.03(g)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Conformity with Drawings
label | FREQUENCY: Prior to construction of subgrade layer
label | ACCEPTANCE CRITERIA: Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.03(f)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction Testing
label | FREQUENCY: Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142 of VicRoads must be agreed with Superintendent.
label | ACCEPTANCE CRITERIA: Type A Material placed more than 400 mm below top of Type A Material should be compacted to 97% of MDD. Type A Material placed within 400 mm of top of Type A Material should be compacted to 99% MDD.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl.204.13(a)
label | ○ Cl.204.13(b)
label | ○ Table 204.131
label | ○ Table 204.142
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compaction Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Maximum Particle Size
label | FREQUENCY: Test every lot (one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements.
label | ACCEPTANCE CRITERIA: Maximum particle size should be 150mm when soil is within 400mm of the top of Type A soil, and 400 mm at depths greater than 400 mm below the top of Type A material.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c), Cl.204.14(a)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Maximum Particle Size Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - CBR/Swell
label | FREQUENCY: The initial lot (one day's production or 10,000m2, whichever is lesser). Reduced testing frecuency (every 8 lots) for future lots shall be agreed with the Superintendent
label | ACCEPTANCE CRITERIA: CBR: ≥ 7%, Swell: < 1.5% swells greater than or equal to 2.5% shall be classified as expansive and approved by the Superintendent).
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl. 204.14
label | ○ Cl. 204.04(c)
label | ○ Table 204.141
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: CBR/Swell Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Atterberg Limit Tests
label | FREQUENCY: 1 Test per 2 lots (each lot is one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. Reduced testing frecuency (1 test per every 4 lots) for future lots shall be agreed with the Superintendent
label | ACCEPTANCE CRITERIA: Ensure that soil post-compaction is not classified as silt
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14, Table 204.141
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: PI Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-005 - Crushed Rock Class 3 | itp |  |  |  |  | ITP-005 - Crushed Rock Class 3
section | 1 - Preliminary Works
checkpoint | 1.1 - Crushed Rock Mix design
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Placing Fill
checkpoint | 2.1 - Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl.304.07 (a)
label | ○ Cl.304.07 (d)
label | ○ Cl.304.07 (e)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii), Table 304.111
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.4 - Proof Roll
label | FREQUENCY: After placing material
label | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Project Engineer & Superintendent
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
label | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
label | VicRoads Spec.
label | ○ Cl.304.08 (a)
label | ○ Cl.304.11 (b)
label | ○ Cl.304.11 (c)(i)
label | ○ Table 304.111
label | INSPECTION / TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.2 - Modified Compactive Effort
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.3 - Survey Level Conformity
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: Scale B:
label | — Minimum number of measurements per lot: 40 For Upper
label | — Upper Subbase: Mean + 6mm to - 12mm with a maximum Standard Deviation of 8mm
label | — Lower Subbase: Mean +8mm to -16mm with a maximum Standard Deviation of 10mm.
label | — Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-008 - Cement Treated Subbase | itp |  |  |  |  | ITP-008 - Cement Treated Subbase Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Material proposed for import for 3% Class 3 CTCR (20mm) meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for approval
label | REFERENCE DOCUMENTS: Cl 812.04 Section 820.04 to 820.09 RC 500.02
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval - Quarry Dockets
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Materials
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
label | REFERENCE DOCUMENTS: Cl 306.04
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Moisture Content
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
label | REFERENCE DOCUMENTS: Cl 306.05
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Jointing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
label | (a) material shall be spread in such a manner as to minimise the number of joints;
label | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: Cl 306.08
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Survey Conformance
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
label | (a) Width and Alignment - The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
label | (b) Surface Level of Subgrade and Pavement - The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.031 and 306.032
label | ○ Surface level tolerances: Scale B - Range x = +6, -12mm:
label | ○ Scale of Surface level measurement: Scale B - Minimum 40 points per Lot
label | REFERENCE DOCUMENTS: Cl 306.031 and CL 306.032
label | INSPECTION / TEST METHOD: String Sheets
label | RECORD OF CONFORMITY: String Report / Visiual and ITP Signoff
label | SCP
label | RESPONSIBILITY: Engineer / Superintendent / foreman
date | Date Completed:
checkpoint | 3.2 - Compaction
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time specified in Table 306.091 depending on the binder type and the time of year the subbase is being placed.Except for the purpose of curing, no water shall be added to the cementitious treated material.
label | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
label | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent.
label | REFERENCE DOCUMENTS: CL 306.09 and 306.031
label | INSPECTION / TEST METHOD: Compaction test and Visual
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Engineer / Superintendent / foreman
date | Date Completed:
checkpoint | 3.3 - Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
label | ○ The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
label | ○ The subbase shall be kept in good order and condition and free from contamination.
label | REFERENCE DOCUMENTS: Cl 306.11 and 306.06
label | INSPECTION / TEST METHOD: Compaction test and Visual
label | RECORD OF CONFORMITY: This ITP signed off;
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 3.4 - Test Rolling / Proof Rolling
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
label | ○ Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification. Proof roll will need to withstand test rolling without visible deformation or springing
label | REFERENCE DOCUMENTS: CL 306.09
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Engineer / Superintendent / foreman
date | Date Completed:
checkpoint | 3.5 - Dockets
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Where material is measured by other means and for Lump Sum Contracts, the Contractor shall make delivery dockets available for inspection on request.
label | REFERENCE DOCUMENTS: CL 306.07
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Engineer / Superintendent / foreman
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-011 - Guardfence Installation | itp |  |  |  |  | ITP-011 - Guardfence Installation Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Drawings Register
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All materials are to be used must be on VicRoads current accepted products list (RDN06-04) and confirm with the detailed design.
label | ○ The contractor shall submit to the Superintendent all test certificates related to the supply of steel for the works at least 14 days prior to commencement of installation.
label | REFERENCE DOCUMENTS: VR Section 708.04 & 708.05
label | INSPECTION / TEST METHOD: HP
label | RECORD OF CONFORMITY: ITP Signed, Certificate of Materials
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Identification of Services
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure any locations have been identified and marked on site. Ensure any approvals are in place with service providers prior to commencing install.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION / TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Setout
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Contractor to confirm with the superintendent the required location and length of all guard fence alignments.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 708.08
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/MRPV Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Guard fence system to be installed in accordance with design drawings, manufacturer guidelines, and within tolerances set out in VicRoads Standard Section 708.07 (d).
label | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.5 - End Treatments
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed in accordance with design drawings, manufacturer guidelines, and specifications.
label | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.6 - Installation of Delineators
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Contractor to supply and fasten delineators on left hand side (red) and right-hand side (yellow).
label | REFERENCE DOCUMENTS: VR Section 708.07
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
section | 3 - Testing and Quality Control
checkpoint | 3.1 - Submission of Certificate of Compliance (CoC)
label | FREQUENCY: Upon completion of install
label | ACCEPTANCE CRITERIA: Contractor to submit the CoC to the Superintended from guard fence supplier.
label | REFERENCE DOCUMENTS: VR Section 708
label | INSPECTION / TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | TP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 3.2 - Submission of Material Test Certificate
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Contractor to submit test certificate to superintendent from guard fence supplier.
label | REFERENCE DOCUMENTS: VR Section 708
label | INSPECTION / TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | TP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-015 - Construction of Concrete Paving | itp |  |  |  |  | ITP-015 - Construction of Concrete Paving Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | FREQUENCY: If Required
label | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | REFERENCE DOCUMENTS: Cl 703.18
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
label | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | REFERENCE DOCUMENTS: Cl 703.21
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre-concrete check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
label | REFERENCE DOCUMENTS: Cl 703.08
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
label | REFERENCE DOCUMENTS: AS/NZS 4671
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Concrete Placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.23
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.7 - Finish Surfaces
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Concrete to have a neat appearance and uniform colour
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Backfilling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
label | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
label | ○ Layers shall not exceed 150mm compacted depth
label | REFERENCE DOCUMENTS: 703.29
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-015 - Construction of Kerb and Channel | itp |  |  |  |  | ITP-015 - Construction of Kerb and Channel Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | FREQUENCY: If Required
label | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | REFERENCE DOCUMENTS: Cl 703.18
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
label | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | REFERENCE DOCUMENTS: Cl 703.21
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre-concrete check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
label | REFERENCE DOCUMENTS: Cl 703.08
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Concrete Placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.23
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Finish Surfaces
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Concrete to have a neat appearance and uniform colour
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Backfilling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
label | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
label | ○ Layers shall not exceed 150mm compacted depth
label | REFERENCE DOCUMENTS: 703.29
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP