## Table 1
|  | D'Aguilar Highway - Wide Centre Line Treatment | [6 empty] | Doval Project No. |  |  | 24 015 |  | Inspection and Test Plan
[9 empty] | Client Project No. |  |  | CN 22433
|  | Lot Number | Description |  |  | Sprayed Bituminous Surfacing | [5 empty] | Date Opened
[12 empty] | Date Started |  | 11.01 |  |  | MRTS11 May 2022 & MRTS22 July 2020
Location | [5 empty] | Control Line | Chainage |  |  | - |  | Date Finished
No. | Activity Description |  |  |  | Acceptance Criteria & Frequency (Project Specific) |  |  | Check Item |  | Inspection | [7 empty] | NCR | Related Lot #
[8 empty] | Reference |  |  | SS/QA |  | Client/Rep |  | Date
1 | Document Submissions As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan |  |  |  | Check that proper safety procedures are being followed and environmental controls are in place, including traffic management |  |  | Check Item
2 | Traffic and Safety Controls Traffic and safety controls are in place (eg. PPE, daily plant check) |  |  |  | Check traffic & safety controls have been implemented as per plan |  |  | Check Item
3 | Construction Procedures The contractor shall documented procedures for all required processes in reference to Clause 5.2 MRTS11 to be submitted not less than 7days, these procedures and ITP shall not be implemented until permission has been granted |  |  |  | Approval |  |  | MILESTONE/HOLD POINT
Clause 5.2 MRTS11
4 | Seal Design - Binder Substitution The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying. |  |  |  | Approval |  |  | MILESTONE
Clause 6.1.2 MRTS11
5 | Seal Design By Principal Testing shall be completed by the Contractor at the test locations and minimum test frequencies detailed in Table 6.2. (Particle Size Distribution, Flakiness Index and Avegrade Least Dimension, Texture Depth and Ball Penetration.) - Test results for the cover aggregate and texture depth has been submiteed at least 7 days - Ball penetration testing has been undertaken in accordance with Table 6.2 and Clause 10.1.2 and passed on to the Administrator on the day of testing. - Spraying shall not commenced until Designed Spray Rate and Designed Spread Rate has been confirmed. |  |  |  | Approval |  |  | MILESTONE/HOLD POINT
Clause 6.2 MRTS11
6 | Seal Design By Contractor Where the Contractor is nominated to undertake the Seal Design, the Contractor shall inspect each site and shall select inputs and associated design factors. The seal design reports shall include all inputs stipulated in the nominated clause. |  |  |  | Check |  |  | Check Item
Clause 6.3 MRTS11
7 | Seal Design Report A seal desin report shall be submited to the Administrator at least 7 days prior to commencing bituminous spraying operations. The Seal Design Report shall include the requirements of Clause 6.3.2 MRTS11. The Administrator shall have 3 days to consider the seal design report and spraying operations shall not commence until release of the hold point |  |  |  | Approval |  |  | MILESTONE/HOLD POINT
Clause 6.3.2 MRTS11
8 | Quarry Registration Certificate Cover aggregate shall be supplied by a registered quarry comply with TMR Quarry Registration System. Certificate to be sent to the Administrator 7 days before material supply. Material from a quarry shall neither be supplied,nor used in the Works prior to written permission by the Administrator |  |  |  | Approval |  |  | MILESTONE/HOLD POINT
Clause 6 MRTS22
9 | Cover Aggregate Cover aggregate shall not be exposed to contaminant agents and to be handle to avoid any contamination / deleterious effects. It shall be protected with a light plastic or similar material to prevent the ingress of moisture and other contaminants. |  |  |  | Visual |  |  | WITNESS POINT
Clause 8.2 MRTS11
10 | Bituminous Materials Binder shall be delivered to the Works in accordance with Clause 8 MRTS17 Bitumen or Clause 8 of MRTS18 Polymer Modified Binder. Temperature at delivery to site shall be measured and recorded. |  |  |  | Visual |  |  | WITNESS POINT
Clause 8.3.1 MRTS11
11 | Bituminous Material Heating Strict controls shall be applied to heating of bituminous material and in accordance to Austroads AP-G41Bitumen Sealing Safety Guide, the heating requirements shall strictly be observed. |  |  |  | Visual |  |  | WITNESS POINT
Clause 8.3.2 MRTS11
12 | Precoating Agents Cover aggregate shall be precoated with one of the nominated approved products listed in Clause 2 of Annexure MRTS22.1 The Contractor shall submit to the Administrator details of the precoating agent procedures 7 days prior commencing |  |  |  | Check & Verify |  |  | MILESTONE
Clause 7.1.4 MRTS22
13 | Compliance Testing The Administrator shall receive at least 15 working days a preliminary sample of 40kg of each type of cover aggregate to be used in the contract as per the requirments of Clause 3 MRTS22.1 |  |  |  | Check & Verify |  |  | MILESTONE
Clause 8.1 MRTS22
14 | Plant & Equipments On site documentation of required plant will be provided no less than 3 days prior to sealing operations and shall satisfied as per Table 9. Additional plant requirements shall apply in accordance of Clause 5 MRTS11.1 |  |  |  | Check |  |  | HOLD POINT
Clause 9 MRTS11
15 | Initial Bituminous Treatments (No Existing Bitumen Treatment) All foreigh and loose material, including lenses of pavement material shall be removed from the surface. The surface shall be swept with a road broom. Where a Ball Penetration test result exceeds 3.0 mm, the surface shall not be sprayed until approved by Administrator. |  |  |  | Verify |  |  | HOLD POINT
Clause 10.1.2 MRTS11
16 | Availability of Cover Aggregate Prior to commencement of bitumen spraying operations, the contractor shall provide the Administrator with evidence there is sufficient cover aggregate for the extent of bitumen spraying work to be undertaken that day. |  |  |  | Check & Verify |  |  | HOLD POINT
Clause 11.1 MRTS11
17 | Pavement Surface Temperature Spraying shall not commence until the temperature of the pavement surface is above the temperature given in Clause 6.2 of Annexure MRTS11.1. 10℃ for primes 15℃ for initial seals containing cutback bitumen (i.e AMC4 to AMC7) 20℃ for bitumen and polymer modified binders These limits do not apply to WP-A and SAMI treatments - placed over an existing seal or ashalt, and - overlaid with asphalt prior to trafficking. |  |  |  | Visual |  |  | WITNESS POINT
Clause 11.2 MRTS11
18 | Spraying Requirements Spraying shall not take place during rain of if rain is likely to fall prior to spreading cover aggregate and the completion of rolling. Further, spraying shall not take place during winds of greater than 30km/hr or during dust storms. |  |  |  | Check & Verify |  |  | Check Item
Clause 11.3 MRTS11
19 | Time Period Between Bituminous Treatments The minimum period of time between bituminous treatments shall be applicable as per the requirements of Clause 11.4 MRTS11 |  |  |  | Check & Verify |  |  | Check Item
Clause 11.4 MRTS11
20 | Spraying The spraybar nozzles used shall be appropriate for each spray run and shall comply with QSC. A copy of the Queensland Sprayer Certificate shall be provided. |  |  |  | Visual |  |  | WITNESS POINT
Clause 12.4 MRTS11
21 | Cutting Back Binder Incorporation of cutter oil into the binder shall be caried out in accordance with Clause 8.3.3. Prior to each operation, Seal Designer Delegate shall nominate the cutter oil adjustments, which shall be recorded. |  |  |  | Visual |  |  | WITNESS POINT
Clause 12.7 MRTS11
22 | Spreading of Cover Aggregate Wet cover aggregate containing free surface water shall not be loaded into the aggregate spreader. |  |  |  | Visual |  |  | WITNESS POINT
Clause 14.1 MRTS11
23 | Time Limit for Cover Aggregate Spreading of cover aggregate shall commence as soon as possible with the time limits specified below: - primerseals: 15 minutes - Cutback Bitumen, Bitumen and Multigrade Bitumen: 10 minutes, or - polymer modified binders including crumbed rubber binder: 5 minutes |  |  |  | Check & Verify |  |  | Check Item
Clause 14.3 MRTS11
24 | Early Trafficking Requirements The requirements of Clause 14.8 shall be complied and the road shall not be opened to traffic until the release of this Hold Point by the Administrator |  |  |  | Acceptance |  |  | HOLD POINT
Clause 14.8 MRTS11
25 | Delivery of Aggregate to Stockpile Site Prior to commencement of delivery of aggregate to any stockpile site, the Contractor shall obtain the Administrator’s authorisation to place aggregates on the stockpile site. |  |  |  | Check & Verify |  |  | HOLD POINT/WITNESS POINT
Clause 10 MRTS22
Responsible Officer | [6 empty] | Verifying Authority
Signature: | [6 empty] | Signature:
Print Name: |  |  |  | Date: |  |  | Print Name: | [8 empty] | Date:
Comments: