## Excavation and Subsoil Drainage
INSPECTION & TEST PLAN
|  | Contract Name: | [6 empty] | Rev: | Originator | Date | Approved | Date
|  | Resilience Improvements Arapohue Road |  |  | Hold Point (H) | Verify (V) |  |  | 0 | Cameron Hinge | 2024-04-03
ITP - Excavation and Subsoil Drainage |  |  |  |  | Submit (S) | Review (R) |  |  | 1
[5 empty] | Approve(A) | Witness (W)
Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL Signature | Engineer/ Client Signature | UCCL | Engineer/Client | DATE | COMMENTS
Materials
Hardfill GAP65 | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO203.4.3 | IANZ Test certificates | UCCL, KDC | 1 test per source submitted 2 weeks prior to MSE Construction | GAP65 shall meet the grading from Table 203.1, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA |  |  | H | R
Subbase GAP65 | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO209 | IANZ Test certificates | UCCL, KDC | 1 test per source submitted 2 weeks prior to MSE Construction and production testing frequency as per TNZ M4 Table 4.1 | GAP65 shall meet the grading from KDC Engineering Standard item 5.4.1.2b, crushing resistance greater than or equal to 120kN, a clay index greater than 3.5 and less than 8 and a lime reactivity as outlined in 5.4.1.2d |  |  | H | R
Basecourse TNZ40 | NZTA M/4 | IANZ Test certificates | UCCL, KDC | 1 test per source submitted 2 weeks prior to MSE Construction | TNZ40 shall comply with NZTA M/4 items 3.3 and 4.2 |  |  | H | R
F2 Drainage material | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.2.3 | IANZ Test certificates | UCCL, KDC | 1 test per source submitted 2 weeks prior to MSE Construction | Aggregate must comply with NZTA F/2 with the exception that 5% of material by weight may pass the 75 um test seive. |  |  | H | R
Riprap | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.2.5 | IANZ Test certificates | UCCL, KDC | 1 test per source submitted 2 weeks prior to MSE Construction | The shape of the rock shall be approximately cubical, the breadth shall not be less than 1/3 of its length. Density shall be 2.65t/m3 or greater. Crushing Resistance shall be 150kN or greater. Weathering resistance shall be AA, BA, AB or BB. Grading shall follow: D100<= 150mm, D50>= 100mm, D35>= 75mm and D10 >= 50mm |  |  | H | R
Geotextile | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.2.2 | Manufacturers certificates, Delivery Dockets | UCCL, KDC | Prior to placement of geotextile | Geotextile shall be Bidim A29 as shown on Drawing 3203158-260-GE-040 and 3203158-260-GE-041 |  |  | H | R
Geogrid | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.2.1 | Manufacturers certificates, Delivery Dockets | UCCL, KDC | Prior to placement of geogrid | Geogrid shall be Tensar RE560 type as shown on Drawing 3203158-260-GE-040 and 3203158-260-GE-041 |  |  | H | R
Terramesh | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.2.5 | Manufacturers certificates, Delivery Dockets | UCL,KDC | Prior to placement of terramesh | Green Terramesh shall be the product used and shall be protected using the appropriate grade galmac metallic coating and PoliMac polymer coating to provide a 50 year design life |  |  | H | R
Subsoil | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.2.6 | Manufacturers certificates, Delivery Dockets | UCCL, KDC | Prior to placement of subsoil | Subsoil drains shall be NZTA F/2 compliant Nexus Hi way products. No filter sock is to be used. |  |  | H | R
Manholes | Drawing S31 of KDC Engineering Srandards 2011 | Manufacturers certificates, Delivery Dockets | UCCL, KDC | Prior to placement of Manholes | Manholes to comply with Drawing S31 of KDC Engineering Standards 2011 |  |  | H | R
Pre Construction Site works
Tree Felling | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO201.2.2 | Visual Inspection | UCCL, KDC | Prior to Excavation | All surface objects, trees, etc. shall be cleared prior to construction. Branches of trees extending over the carrageway shall be cleared to allow a clear height of 6m above the carrageway. |  |  | V | Su
Temporary Works Design | Drawing 3203158-260-GE-040 & Drawing 3203158-260-GE-041, Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO100.12 | Temporary works drawings | UCCL, KDC | Prior to Excavation | Temporary works design shall be completed prior to excavation for the retaining of the cut face. Temporary work designs, signed by the designing CP Engineer shall be submitted to the Engineer |  |  | V | Su
Excavation and installation
Subgrade | Drawing 3203158-260-GE-040 | QF 021 | UCCL, KDC | 3 tests every 25m2 | Shear vanes shall be taken 3 times at a frequency of a 5 x 5 grid at depths of 150mm, 450mm, 750mm and 950mm below formation level for cohesive materials and are to average a minimum of 65kPa and be no less than 50kPa for a single test. Scalas shall be taken in cohesionless material or where a shear vane meets refusal and meet an average of 5 blows per 150mm with a minimum of 4 blows per 150mm for a single test. |  |  | H | R
Subsoil | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.3.7 | Photographs, asbuilts | UCCL, KDC | Prior to Backfill | Subsoil shall be placed at the line, grade and level shown on the drawings. F2 drainage material shall be installed as shown on the drawings. |  |  | V | W
Hardfill | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO203.4.9 | QF 046 | UCCL, KDC | 1 Set per 0.6m lift | Hardfill shall be placed and compacted in layers no greater than 300mm. Hardfill shall be tested at a rate of 1 set per 200m3 or at least 1 set per 0.6m lift and shall meet a 95% of the MDD average with no tests less than 92% of the MDD |  |  | V | W
Geotextile | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.3.3 | Photographs, asbuilts | UCCL, KDC | Prior to Backfill | Geotextiles shall be placed in structurally continuous, longitudinal strips and orientated In the main direction as shown on the drawings. No jointing shall occur in the main direction of strength otherwise a minimum overlap of 0.1m shall be obtained. Geotextile shall be tensioned as backfilling occurs. Each layer shall be offset by 1/2 a roll width. Geotextile shall be covered within 3 days of placing. Geotextile shall be place within +/- 0.5m of the design elevation and shall have 150mm of backfill prior to being trafficked. |  |  | V | Su
Geogrid | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.3.4 | Photographs, asbuilts | UCCL, KDC | Prior to Backfill | Geogrid shall be placed in a continuous strip with no joints in the strength direction other than a bodkin connection. Geogrid strips shall butt eachother in all other directions and in the vertical plane, be staggered. Geogrid shall be placed on level compacted fill. Geogrid shall be tensioned as backfilling occurs using pins or small fill volumes and shall not be trafficked until 150mm of fill has been placed on top. |  |  | V | W
Terramesh | Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO405.3.6 | Photographs, asbuilts | UCCL, KDC | Prior to Backfill | Terramesh shall be installed following the product manufacturers guidelines. Terramesh shall be handled with care to protect the coatings and units. No damaged units shall be used in the construction of the MSE Wall. |  |  | V | Su
Subbase | NZTA B/2, KDC Engineering standards 2011 Part 5 | QF 046 | UCCL, KDC | 1 Set per 0.6m lift | Subbase shall be placed and compacted in layers no greater than 150mm. Subbase shall be tested at a rate of 1 set per 200m3 or at least 1 set per 0.6m lift and shall meet a 95% of the MDD average with no tests less than 92% of the MDD |  |  | V | W
Basecourse | NZTA B/2, KDC Engineering standards 2011 Part 5 | QF 046 | UCCL, KDC | 1 Set per 0.6m lift | Basecourse shall be placed and compacted in layers no greater than 200mm. Basecourse shall be tested at a rate of 1 set per 200m3 or at least 1 set per 0.6m lift and shall meet a 98% of the MDD average with no tests less than 95% of the MDD |  |  | V | W
Tolerances | NZTA F/1, NZTA B/2, Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification 405.3.8 | Asbuilts | UCCL, KDC | Each Stage of construction | Subgrade: 0mm - -30mm Subbase: -25mm - + 5mm Basecourse: -5mm - +15mm Terramesh walls - as per table 405.3 of spec |  |  | V | W
Post Construction
As builts and Redline Markup | CON 1025 CL 5.20 | Asbuilt file | UCCL, KDC | Following completion of construction | As built drawings, redline markups and RAMM sheets |  |  | S | A