## Sealing
INSPECTION & TEST PLAN
|  | Contract Name: | [6 empty] | Rev: | Originator | Date | Approved | Date
|  | Resilience Improvements Arapohue Road |  |  | Hold Point (H) | Verify (V) |  |  | 0 | Cameron Hinge | 2024-04-03
ITP - Excavation and Subsoil Drainage |  |  |  |  | Submit (S) | Review (R) |  |  | 1
[5 empty] | Approve(A) | Witness (W)
Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL Signature | Engineer/ Client Signature | UCCL | Engineer/ Client | DATE | COMMENTS
Materials
Sealing Chip | NZTA M/6, C0213.3 | IANZ Reports | UCCL, KDC | 2 Weeks prior to sealing | Less than 10% fines produced under a 230kN load, Weathering resistance of AA or BA, Polished stone vaue >= 100 x SR + 0.00663 x HCV + PSF, Cleanliness >= 89 and 85, A size and shape as per table 3 item 5.2, only one source of supply shall be used for each grade of chip. |  |  | H | R
Bituminous Binder | NZTA M/1 C0213.3 | Test reports registered under AS/NZS ISO 9001 | UCCL, KDC | 2 weeks prior to sealing | Binder shall comply with table 5.1 of NZTA M01 |  |  | H | R
Diluents | TNZ M/1, TNZ P/3 C0213.3 | Test report | UCCL, KDC | Records and tests to be taken prior to sealing | Diluents shall comply with TNZ M/1, P/3 and P/4. Diluents shall not exceed table 1 of TNZ P/3 |  |  | H | R
Adhesion Agent | TNZ M/13 C0213.3 | Test report | UCCL, KDC | 2 weeks prior to sealing | Adhesion Agent shall comply with NZTA M/13 |  |  | H | R
Blending | TNZ P/4 C0213.3 | Blending certificates | UCCL, KDC | Records and tests to be taken prior to sealing | Blending shall follow complience with the maufacturers guidelines. Blending certs shall be provided to the engineer |  |  | H | R
Pre Construction Site works
Sealing Period | TNZ P/3 item 3 & 4 | Visual Inspection | UCCL, KDC | Prior to sealing | Sealing may be carried out during any period of the year when fair settled weather conditions are being experienced and the shade air temperature is not less than 10 degrees C. All binder spray shall be completed at least 90 minutes before the official time of sunset and all plant shall be clear of the sealed area by sunset. |  |  | V | Su
Excavation and installation
Edge Definition | TNZ P/3 Item 2, C0213.5 | Photos/ visual inspection | UCCL, KDC | Prior to sealing | The edges of sealing shall be clearly defined by stringlines with no ragged or irregular edges to the seal |  |  | V | W
Surface Prep | TNZ P/3 C0213.5 | Photos/ visual inspection | UCCL, KDC | Prior to sealing | All loose or caked material shall be removed from the surface without distubing the compacted basecourse. The surface shall be clean of loose aggregate, dust, dirt, etc. The surface shall be clean, dry, free of ice or frost , be tightly compacted and present a clean stone mosaic. |  |  | H | W
Binder and application Temp | TNZ P/3 C0213.5 | Test records | UCCL, KDC | During sealing | The binder temp shall comply with table 2 Item 14 of TNZ P/3 |  |  | V | Su
Application Rate | TNZ P/3 C0213.5 | Test strip | UCCL, KDC | Prior to sealing | The application rate shall be calculated from the guidelines of the TNZ "bituminous Sealing Manual" and confirmed using a test strip prior to sealing. Further test strips are to be done if there is a significant difference in the road surface during sealing |  |  | V | Su
Sealing Application - Double Layer | C0213.5.7d | Visual Inspection | UCCL, KDC | During sealing | The sealing application shall follow tbe outline of item CO0213.5..7d |  |  | V | Su
riding surface | C0213.5.8 | Visual Inspection | UCCL, KDC | Following completion of construction | A smooth and even ride, free of bumps and undulations is required. |  |  | H | R
Post Construction
As builts and Redline Markup | CON 1025 CL 5.20 | Asbuilt file | UCCL, KDC | Following completion of construction | As built drawings, redline markups and RAMM sheets |  |  | S | A
Maintenance and acceptance | C0213.6, TNZ P/17 |  | UCCL, KDC | 12 months following construction | Acceptance at the end of the maintenance period shall be based on surface texture and chip retention and shall be in accordance with TNZ P/17 |  |  | H | R