## ITP Cover Page
Retaining Wall 2 - Permanent Works - Magnum Stone Installation
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - SP2 - 007-003 - Rev 2
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 | [5 empty] | ITP Number: |  |  | 007-003
Project Number: |  |  | DN1210 - SP2 | [5 empty] | ITP Status: |  |  | IFC
ITP Description: |  |  | Retaining Wall 2 - Permanent Works - Magnum Stone Installation | [5 empty] | Revision: | 1000 |  | 2
Contract Number: |  |  | 8287 | [5 empty] | Drawing Sets: |  |  | 2-32735.02-WSP-DR-GEO
Customer: |  |  | Waka Kotahi | [5 empty] | Specification: |  |  | Project specification (NOT PROVIDED)
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [10 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval |  |  | Nick Adams & Cordelia Girdler-Brown | [6 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[11 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved |  |  | Nick Adams & Cordelia Girdler-Brown |  | ITP item no 5.4 - Clarification on type of geogrid connection and ITP item no 5.5 - Clarification on cement stabilised fill |  |  |  |  | C | Check |  | PD | Project Director
[11 empty] | D | Dimension Inspection |  | PM | Project Manager
2 | Re-submit for approval |  |  |  |  | Line item 3.15 and 5.8 were addeed to the ITP to cover cement stabilised work. |  |  |  |  | E | Examine |  | OP | Operations Manager
[11 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[11 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[11 empty] | I | Inspection |  | PE | Project Engineer
[11 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[11 empty] | O | Operation |  | QE | Quality Engineer
[11 empty] | R | Review |  | SUP | Superintendent / Supervisor
[11 empty] | S | Subcontractor |  | SV | Surveyor
[11 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[11 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [8 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: |  | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 2025-09-09 |  | Downer PM
Downer QM |  | Cordelia Girdler Brown |  |  |  |  | 2025-09-09 |  | Downer QM
Client (If Applicable) | [8 empty] | Client (If Applicable)

## ITP Master Body
Retaining Wall 2 - Permanent Works - Magnum Stone Installation
0
Number and Revision: DN1210 - SP2 - 007-003 - Rev 2
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
3.1 | Methodology | The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to construction | HP | ENG
3.2 | Erosion & Sedimentation Controls | Confirm that Erosion and Sedimentation Controls bunds are in place | As-built Completed | Internal Hold Point | ESC As-built | Prior to construction | H | PE
3.3 | Geotextile | The Contractor shall submit the full details of the Class C non-woven geotextile fabric to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Material certificate/NTC | Results to Engineer for Approval | HP | ENG
3.4 | Geogrid | The Contractor shall submit the full details of the stratagrid SGU180 to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Material certificate/NTC | Results to Engineer for Approval | HP | ENG
3.5 | Macmat R or similar product | The Contractor shall submit the full details of the MacMat R to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Material certificate/NTC | Results to Engineer for Approval | HP | ENG
3.6 | Crushing Resistance: Drainage aggregate | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII PS.17.6.2 | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.7 | Partical size distribution: Drainage aggregate | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | DM40/20 OR DM20/7 Grading Envelope | Appendix XVIII PS.17.6.2 | IANZ Accredited Report | 1 Test per 100m3 Results to Engineer 2wks before importing | HP | ENG
3.8 | Weathering Resistance : Drainage aggregate | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | Appendix XVIII PS.17.6.2 | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.9 | Crushing Resistance: Structural Fill | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII PS 17.4.3 | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1 | Partical size distribution: Structural Fill | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Max Particle Size 53mm Max 10% passing 13.2mm sieve | Appendix XVIII PS 17.4.3 | IANZ Accredited Report | 1 Test per 100m3 Results to Engineer 2wks before importing | HP | ENG
3.11 | Weathering Resistance : Structural fill | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | Appendix XVIII PS 17.4.3 | IANZ Accredited Report | 3 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.12 | Magnum Stone Block | Magnum Stone blocks are to be supplied by an approved supplier. Concrete Compressive Strength Moisture Absorption Defects, chips and cracks | Minimum 28-day Compressive Strength of 30MPa (min.) Less than 6% Every Block | NZS 3104: 2003 AS/NZS 4456:2003 Method 14 | Supplier to provide QA Documents Visual Inspection | Prior to construction | H | PE
3.13 | Subsoil Drainage | Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated pipe with filter sock | Engineers Approval | P.S. 21.5.17 | Material certificate/NTC | Prior to construction | HP | ENG
3.14 | Concrete Footing | Concrete strength shall be min. 17.5MPa | Engineers Approval | A s per Drawing (232735.02-WSP-DR-GEO-0412) | Material certificate/NTC | Prior to construction | HP | ENG
3.15 | Cement-stabilised fill | Cement stabilised fill to the bottom 1.2m of the wall, the material to meet a UCS of 1Mpa. | UCS of 1Mpa or more | DN1210-WSP-GCO-0488 DN1210-WSP-NTC-0817 | Test reults | Prior to construction | HP | ENG
SECTION 4 – CONSTRUCTION - CUT SUBGRADE TESTING
4.1 | Cut Subgrade Inspection | Engineer to inspect all foundation surface inspections | Engineers Approval | Appendix V | Visual Observation | Across stripped area | HP | ENG
4.2 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa Single Test Min SU: >50kPa 2-3m deep | Appendix XVIII | Shear Vane Report | 0.5m interval 4 test per 400M2 | I | SE
4.3 | Cut Subgrade - Import Structural fill Release of Hold Point | To release the subgrade hold point and be able to start placing the Magnum Stone Blocks, the Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6 | Engineers Approval | PS 16.9.3 | CONQA Approval | Engineers Approval | HP | ENG
SECTION 5 – MAGNUM STONE BLOCK
5.1 | Leveling Pad and Duraflow Drainage | • The levelling pad should be 900 mm wide and 150 mm deep. • A 100 mm diameter highway nexus pipe will be placed with a minimum of 200 mm of drainage fill followed by placing class C non-woven geotextile on the top of the fill. | Engineers Approval | As per Drawing (23273502-WSP-DR-GEO-0412) | Site Photo | Prior to Magnum Stone Block installation | I | SE
5.2 | Installation of blocks | Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances | Engineers Approval | As per Drawing (23273502-WSP-DR-GEO-0412) | Site Photo / Checksheet | Each layer | W | ENG
5.3 | Drainage fill at the back of the wall | Minimum 200mm thick wrap in filter fabric drainage fill trench at the back of the wall | Engineers Approval | As per Drawing (23273502-WSP-DR-GEO-0412) | Site Photo | Each layer | W | ENG
5.4 | Geogrid | Place stratagrid SGU 180 from the back of the magnum stone blocks. Based on DN1210-WSP-GCO-0468 connection type to be positive connection | Engineers Approval | DN1210-WSP-GCO-0468 | Site Photo / Checksheet | During Insallation | W | ENG
5.5 | Backfill Installation | All backfill is to be installed in 300mm lifts and tested. first 1.2m of structural backfilling to be cement-stabilised fill (2% by dry weight of the fill). | Engineers Approval | DN1210-WSP-NTC-0817 As per Drawing (23273502-WSP-DR-GEO-0202) | Site Photo / Checksheet | Each layer | W | ENG
5.6 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Structural Fill Min CIV 18 Ave CIV 20 Non-Structural Fill Min CIV 10 Max CIV 12 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
5.7 | Compaction - NDM (AP65) | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD Non Granular Material Max Air Voids 8% | Appendix XVIII | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE
5.8 | 1.2m Cement-stabilised fill | Cement-stabilised fill (2% by dry weight) for the first 1.2 m from the base of the wall, between CH57 and CH78 | UCS of 1Mpa or more | DN1210-WSP-GCO-0488 DN1210-WSP-NTC-0817 | Delivery dockets | 1.2m base of the wall from CH57 to CH78 | I | SE
SECTION 6 – AS-BUILTS
6.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. | As-build record | PS 16.7.6 | Survey Records/redpen markups | During Earthworks | D | SV