## Sheet1
1.1 | Approved JMF for Asphalt Base or Wearing Course | JMF reference in here | H | Before Works commence | Confirm requirements are followed | JMF Validated in accordance with NZTA P11:2023 | Mix Design Report | Paving Contractor | JMF expiry date and validation details in here | A | I | R | 1.1 - Approved JMF for Asphalt Base or Wearing Course | Detail of Activity / Test - JMF reference in here | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Confirm requirements are followed | Acceptance Criteria - JMF Validated in accordance with NZTA P11:2023 | Record documents (QCP - Quality Control Portal) - Mix Design Report | Responsibility - Paving Contractor | Project Specific Notes / Instructions - JMF expiry date and validation details in here | Designer - A | Eng. Rep / NZTA - I | Contractor - R | 1.1 - Approved JMF for Asphalt Base or Wearing Course
1.2 | Approved Quality Plan/Renewal Quality Plan | Prepare and Submit RQP | H | Before Works commence | Review /Acceptance by Engineer |  | RQP | Paving Contractor |  | I | A | R | 1.2 - Approved Quality Plan/Renewal Quality Plan | Detail of Activity / Test - Prepare and Submit RQP | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Review /Acceptance by Engineer | Acceptance Criteria - | Record documents (QCP - Quality Control Portal) - RQP | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - A | Contractor - R | Detail of Activity / Test - JMF reference in here
1.3 | TMP Approval | Prepare and Submit TMP | H | Before Works commence | Review /Acceptance by TMC |  | TMP | Paving Contractor |  | I | A | R | 1.3 - TMP Approval | Detail of Activity / Test - Prepare and Submit TMP | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Review /Acceptance by TMC | Acceptance Criteria - | Record documents (QCP - Quality Control Portal) - TMP | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - A | Contractor - R | Action (Hold, Monitor, Witness) - H
1.4 | Public Notification | Communication with affected parties | H | Before Works commence | Media/Letter Drops/TREIS | Letter drop to local residents/ Greater consultation as required | Letter | Paving Contractor |  |  | A | R | 1.4 - Public Notification | Detail of Activity / Test - Communication with affected parties | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Media/Letter Drops/TREIS | Acceptance Criteria - Letter drop to local residents/ Greater consultation as required | Record documents (QCP - Quality Control Portal) - Letter | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - A | Contractor - R | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
1.5 | Crew Briefing Plan | Prepare and submit CBP and VMP | H | Before Works commence | Written Plan | Approved by Responsible Manager | CBP | Paving Contractor |  |  | I | A | 1.5 - Crew Briefing Plan | Detail of Activity / Test - Prepare and submit CBP and VMP | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Written Plan | Acceptance Criteria - Approved by Responsible Manager | Record documents (QCP - Quality Control Portal) - CBP | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - A | Inspection / Test method - Confirm requirements are followed
1.6 | Site Conditions | Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place | H | Before Works commence | Confirm requirements are followed | Weather conditions and Site is suitable for paving | Site Diary/String Sheets | Paving Contractor |  |  | I | R | 1.6 - Site Conditions | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Confirm requirements are followed | Acceptance Criteria - Weather conditions and Site is suitable for paving | Record documents (QCP - Quality Control Portal) - Site Diary/String Sheets | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Acceptance Criteria - JMF Validated in accordance with NZTA P11:2023
1.7 | Roughness | Previous layer checked for suitability to achieve Specified Ride | H | Before Works commence | Confirm Specified Ride requirements can be met | Site is suitable for paving; The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP. | NASSRA Report | Paving Contractor |  |  | I | R | 1.7 - Roughness | Detail of Activity / Test - Previous layer checked for suitability to achieve Specified Ride | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Confirm Specified Ride requirements can be met | Acceptance Criteria - Site is suitable for paving; The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP. | Record documents (QCP - Quality Control Portal) - NASSRA Report | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Record documents (QCP - Quality Control Portal) - Mix Design Report
1.8 | Traffic Loops | Communication with affected parties | H | Minimum of 7 days Before Works commence | Visual | Notify RC at least 7 days before surfacing is programmed | Communication | Paving Contractor |  |  | A | R | 1.8 - Traffic Loops | Detail of Activity / Test - Communication with affected parties | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence | Inspection / Test method - Visual | Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed | Record documents (QCP - Quality Control Portal) - Communication | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - A | Contractor - R | Responsibility - Paving Contractor
1.9 | Paving Plan | Paving Plan to be completed | H | Before Works commence | NZTA P11:2023 Clause 12.2 | Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonnages, compaction plant (type/weight/no. of rollers) and established rolling pattern, production and transport plan including mix type (code), binder grade (with product name) to be ordered. | String Sheet Paving Plan Placement Trial Records | Paving Contractor |  |  | I | R | 1.9 - Paving Plan | Detail of Activity / Test - Paving Plan to be completed | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - NZTA P11:2023 Clause 12.2 | Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonnages, compaction plant (type/weight/no. of rollers) and established rolling pattern, production and transport plan including mix type (code), binder grade (with product name) to be ordered. | Record documents (QCP - Quality Control Portal) - String Sheet Paving Plan Placement Trial Records | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Project Specific Notes / Instructions - JMF expiry date and validation details in here
2.1 | Temperatures | Mixing of aggregates and bitumen | M | Constant monitoring of temperature by calibrated euipment | Plant temperature probes | PG64H binder Mixing range 135 - 145°C PG64 V/E (Flexiplus Bind) binder mixing range: 145 to 155 deg.C NZTA P11:2023 states max. 15°C above mixing temperature and +/- 10°C on leaving the plant | Plant site diary | Asphalt Manufacturer |  | I | I | R | 2.1 - Temperatures | Detail of Activity / Test - Mixing of aggregates and bitumen | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment | Inspection / Test method - Plant temperature probes | Acceptance Criteria - PG64H binder Mixing range 135 - 145°C PG64 V/E (Flexiplus Bind) binder mixing range: 145 to 155 deg.C NZTA P11:2023 states max. 15°C above mixing temperature and +/- 10°C on leaving the plant | Record documents (QCP - Quality Control Portal) - Plant site diary | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Designer - A
2.2 | Production Asphalt | Particle Size Distribution | M | 1 per 200t at asphalt plant | NZS 4407 Test 3.8.1 | NZTA P11:2023 Refer to Table 5 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R | 2.2 - Production Asphalt | Detail of Activity / Test - Particle Size Distribution | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant | Inspection / Test method - NZS 4407 Test 3.8.1 | Acceptance Criteria - NZTA P11:2023 Refer to Table 5 | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Eng. Rep / NZTA - I
2.3 | Production Asphalt | Binder Content | M | 1 per 200t at asphalt plant |  | NZTA P11:2023 Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R | 2.3 - Production Asphalt | Detail of Activity / Test - Binder Content | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant | Inspection / Test method - | Acceptance Criteria - NZTA P11:2023 Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Contractor - R
2.4 | Production Asphalt | Max. Specific Gravity (MSG) of mix | M | 1 per 600t at asphalt plant |  | Report | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R | 2.4 - Production Asphalt | Detail of Activity / Test - Max. Specific Gravity (MSG) of mix | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant | Inspection / Test method - | Acceptance Criteria - Report | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | 1.2 - Approved Quality Plan/Renewal Quality Plan
3.1 | Milling | Surface strung to ensure milling Depth is achieved | H | Before Works commence | Confirm requirements are followed | Site is suitable for paving | String Sheet | Paving Contractor |  |  | I | R | 3.1 - Milling | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Confirm requirements are followed | Acceptance Criteria - Site is suitable for paving | Record documents (QCP - Quality Control Portal) - String Sheet | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Detail of Activity / Test - Prepare and Submit RQP
3.2 | Tack Coat, OR | Application of Tack Coat | M | Per Lot | Dip bitumen emulsion tank before and after | Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate | Site Diary | Paving Contractor |  | I | I | R | 3.2 - Tack Coat, OR | Detail of Activity / Test - Application of Tack Coat | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot | Inspection / Test method - Dip bitumen emulsion tank before and after | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Action (Hold, Monitor, Witness) - H
3.3 | Membrane Seal | Application of Membrane Seal | M | Per Lot | Sealing Records | Application rate, chip type and binder as per membrane seal design | Sealing Records | Paving Contractor |  | I | I | R | 3.3 - Membrane Seal | Detail of Activity / Test - Application of Membrane Seal | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot | Inspection / Test method - Sealing Records | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design | Record documents (QCP - Quality Control Portal) - Sealing Records | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
3.4 | Temperature | Pavement Surface | M | Start of shift and every 1 hour until temperature rising | Infrared gauge | ≥ 10 °C or as otherwise agreed with NZTA | Site diary | Paving Contractor | Must get NZTA approval if CHAR(LESS) 10°C | I | I | R | 3.4 - Temperature | Detail of Activity / Test - Pavement Surface | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising | Inspection / Test method - Infrared gauge | Acceptance Criteria - ≥ 10 °C or as otherwise agreed with NZTA | Record documents (QCP - Quality Control Portal) - Site diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - Must get NZTA approval if CHAR(LESS) 10°C | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Inspection / Test method - Review /Acceptance by Engineer
3.5 | Temperature | Asphalt Delivery temperature | M | Every Load on delivery to the Paver Hopper | Temperature Probe | Target ≥ 130° deg.C. in the Paver Min. ≥ 120 deg.C in the Paver CHAR(LESS)110°C to be Rejected | Site Diary | Paving Contractor |  | I | I | R | 3.5 - Temperature | Detail of Activity / Test - Asphalt Delivery temperature | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper | Inspection / Test method - Temperature Probe | Acceptance Criteria - Target ≥ 130° deg.C. in the Paver Min. ≥ 120 deg.C in the Paver CHAR(LESS)110°C to be Rejected | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Acceptance Criteria -
3.6 | Temperature | Compaction Temperature | M | During compaction | Temperature Probe/Infrared gauge | ≥ 110°C at commencement of compaction. CHAR(LESS) 80°C - Stop Rolling | Site diary | Paving Contractor |  | I | I | R | 3.6 - Temperature | Detail of Activity / Test - Compaction Temperature | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - During compaction | Inspection / Test method - Temperature Probe/Infrared gauge | Acceptance Criteria - ≥ 110°C at commencement of compaction. CHAR(LESS) 80°C - Stop Rolling | Record documents (QCP - Quality Control Portal) - Site diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Record documents (QCP - Quality Control Portal) - RQP
3.7 | Mat | Load Locate | M | Each load | P/11 | Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Paving Run Sheet | Paving Contractor |  | I | I | R | 3.7 - Mat | Detail of Activity / Test - Load Locate | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Each load | Inspection / Test method - P/11 | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Record documents (QCP - Quality Control Portal) - Paving Run Sheet | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Responsibility - Paving Contractor
3.8 | Mat | Thickness Monitoring | M | Continuously | Dipping | Target Loose Thickness -0mm / +10mm |  | Paving Contractor |  | I | I | R | 3.8 - Mat | Detail of Activity / Test - Thickness Monitoring | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Continuously | Inspection / Test method - Dipping | Acceptance Criteria - Target Loose Thickness -0mm / +10mm | Record documents (QCP - Quality Control Portal) - | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Project Specific Notes / Instructions -
3.9 | Mat | Shape | M | Continuously | 3m Straight edge | Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA P11:2023 - Section 14 Not more than 5mm under a 3m Straight Edge. | Straight Edge Record | Paving Contractor |  | I | I | R | 3.9 - Mat | Detail of Activity / Test - Shape | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Continuously | Inspection / Test method - 3m Straight edge | Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA P11:2023 - Section 14 Not more than 5mm under a 3m Straight Edge. | Record documents (QCP - Quality Control Portal) - Straight Edge Record | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Designer - I
3.1 | Paving Quality | Texture | M | Per Site (If Required) | Sand Circle or HSD | NZTA T/10: 2013 | IANZ accredited test cert. | Paving Contractor |  | I | I | R | 3.1 - Paving Quality | Detail of Activity / Test - Texture | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required) | Inspection / Test method - Sand Circle or HSD | Acceptance Criteria - NZTA T/10: 2013 | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert. | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Eng. Rep / NZTA - A
3.11 | Paving Quality | Level | M | Per Site (If Required) | As Built Survey | -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. NZTA P/11:2023 - section 14.1 | Survey As builts | Paving Contractor |  | I | I | R | 3.11 - Paving Quality | Detail of Activity / Test - Level | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required) | Inspection / Test method - As Built Survey | Acceptance Criteria - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. NZTA P/11:2023 - section 14.1 | Record documents (QCP - Quality Control Portal) - Survey As builts | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Contractor - R
3.12 | Paving Quality | Alignment | M | Per Site (If Required) | As Built Survey | ±50 mm from drawings | Survey As builts | Paving Contractor |  | I | I | R | 3.12 - Paving Quality | Detail of Activity / Test - Alignment | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required) | Inspection / Test method - As Built Survey | Acceptance Criteria - ±50 mm from drawings | Record documents (QCP - Quality Control Portal) - Survey As builts | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | 1.3 - TMP Approval
3.13 | Paving Quality | Ride Quality - Wearing Course only | W | Continuous every lane | NAASRA | Max 100m Rolling Average 60 Counts/km Max 20m NASSRA 70 Counts/km Refer TNZ TM 7003 v1 (2006) | IANZ accredited test cert. | Paving Contractor | For structural mixes, refer clause 1.7 of this ITP - Hold Point must be observed on this layer before proceeding to a final Surfacing Layer | A | I | R | 3.13 - Paving Quality | Detail of Activity / Test - Ride Quality - Wearing Course only | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - Continuous every lane | Inspection / Test method - NAASRA | Acceptance Criteria - Max 100m Rolling Average 60 Counts/km Max 20m NASSRA 70 Counts/km Refer TNZ TM 7003 v1 (2006) | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert. | Responsibility - Paving Contractor | Project Specific Notes / Instructions - For structural mixes, refer clause 1.7 of this ITP - Hold Point must be observed on this layer before proceeding to a final Surfacing Layer | Designer - A | Eng. Rep / NZTA - I | Contractor - R | Detail of Activity / Test - Prepare and Submit TMP
3.14 | Post Paving Completion Checks | Site clear and cleanup | W | Each Site/Shift | Visual | Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete | Site Diary | Paving Contractor |  |  | I | R | 3.14 - Post Paving Completion Checks | Detail of Activity / Test - Site clear and cleanup | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift | Inspection / Test method - Visual | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Action (Hold, Monitor, Witness) - H
3.15 | Post Paving Completion Checks | Pavement Marking | W | Each Site/Shift | Visual | Roadmarking is complete | Site Diary | Paving Contractor |  |  | I | R | 3.15 - Post Paving Completion Checks | Detail of Activity / Test - Pavement Marking | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift | Inspection / Test method - Visual | Acceptance Criteria - Roadmarking is complete | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
3.16 | Post Paving Completion Checks | Cold Joint Bandaging | W | Each Site/Shift | Visual | Cold joint bandaging is complete | Site Diary | Paving Contractor |  |  | I | R | 3.16 - Post Paving Completion Checks | Detail of Activity / Test - Cold Joint Bandaging | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift | Inspection / Test method - Visual | Acceptance Criteria - Cold joint bandaging is complete | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Inspection / Test method - Review /Acceptance by TMC
3.17 | Post Paving Completion Checks | Service Covers Checked | W | Each Site/Shift | Visual | Check that service covers are cleared and level with the pavement | Site Diary | Paving Contractor |  |  | I | R | 3.17 - Post Paving Completion Checks | Detail of Activity / Test - Service Covers Checked | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift | Inspection / Test method - Visual | Acceptance Criteria - Check that service covers are cleared and level with the pavement | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Acceptance Criteria -
3.18 | Post Paving Completion Checks | Traffic Loops Reinstated | W | Each Site/Shift | Visual | Check that affected traffic loops have been reinstated | Communication | Paving Contractor |  |  | I | R | 3.18 - Post Paving Completion Checks | Detail of Activity / Test - Traffic Loops Reinstated | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift | Inspection / Test method - Visual | Acceptance Criteria - Check that affected traffic loops have been reinstated | Record documents (QCP - Quality Control Portal) - Communication | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Record documents (QCP - Quality Control Portal) - TMP
4.1 | Assessment of all test results for conformity | Review against ITP Requirements | H | For each site on the project | Review | Reporting of any non-conforming results to Engineer via NCR | NCR | Paving Contractor |  | I | A | R | 4.1 - Assessment of all test results for conformity | Detail of Activity / Test - Review against ITP Requirements | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project | Inspection / Test method - Review | Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR | Record documents (QCP - Quality Control Portal) - NCR | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - A | Contractor - R | Responsibility - Paving Contractor
4.2 | RAMM pavement and surface records | RAMM surfacing pavement data spreadsheet updated | W | For each site on the project | Prepare Data | Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. | RAMM Spreadsheet | Paving Contractor |  | I | A | R | 4.2 - RAMM pavement and surface records | Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project | Inspection / Test method - Prepare Data | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. | Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - A | Contractor - R | Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - A
Contractor - R
1.4 - Public Notification
Detail of Activity / Test - Communication with affected parties
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
Inspection / Test method - Media/Letter Drops/TREIS
Acceptance Criteria - Letter drop to local residents/ Greater consultation as required
Record documents (QCP - Quality Control Portal) - Letter
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - A
Contractor - R
1.5 - Crew Briefing Plan
Detail of Activity / Test - Prepare and submit CBP and VMP
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
Inspection / Test method - Written Plan
Acceptance Criteria - Approved by Responsible Manager
Record documents (QCP - Quality Control Portal) - CBP
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - A
1.6 - Site Conditions
Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
Inspection / Test method - Confirm requirements are followed
Acceptance Criteria - Weather conditions and Site is suitable for paving
Record documents (QCP - Quality Control Portal) - Site Diary/String Sheets
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
1.7 - Roughness
Detail of Activity / Test - Previous layer checked for suitability to achieve Specified Ride
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
Inspection / Test method - Confirm Specified Ride requirements can be met
Acceptance Criteria - Site is suitable for paving; The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP.
Record documents (QCP - Quality Control Portal) - NASSRA Report
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
1.8 - Traffic Loops
Detail of Activity / Test - Communication with affected parties
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence
Inspection / Test method - Visual
Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed
Record documents (QCP - Quality Control Portal) - Communication
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - A
Contractor - R
1.9 - Paving Plan
Detail of Activity / Test - Paving Plan to be completed
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
Inspection / Test method - NZTA P11:2023 Clause 12.2
Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonnages, compaction plant (type/weight/no. of rollers) and established rolling pattern, production and transport plan including mix type (code), binder grade (with product name) to be ordered.
Record documents (QCP - Quality Control Portal) - String Sheet Paving Plan Placement Trial Records
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
2.1 - Temperatures
Detail of Activity / Test - Mixing of aggregates and bitumen
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment
Inspection / Test method - Plant temperature probes
Acceptance Criteria - PG64H binder Mixing range 135 - 145°C PG64 V/E (Flexiplus Bind) binder mixing range: 145 to 155 deg.C NZTA P11:2023 states max. 15°C above mixing temperature and +/- 10°C on leaving the plant
Record documents (QCP - Quality Control Portal) - Plant site diary
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
2.2 - Production Asphalt
Detail of Activity / Test - Particle Size Distribution
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
Inspection / Test method - NZS 4407 Test 3.8.1
Acceptance Criteria - NZTA P11:2023 Refer to Table 5
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
2.3 - Production Asphalt
Detail of Activity / Test - Binder Content
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
Inspection / Test method -
Acceptance Criteria - NZTA P11:2023 Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
2.4 - Production Asphalt
Detail of Activity / Test - Max. Specific Gravity (MSG) of mix
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
Inspection / Test method -
Acceptance Criteria - Report
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.1 - Milling
Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
Inspection / Test method - Confirm requirements are followed
Acceptance Criteria - Site is suitable for paving
Record documents (QCP - Quality Control Portal) - String Sheet
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
3.2 - Tack Coat, OR
Detail of Activity / Test - Application of Tack Coat
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
Inspection / Test method - Dip bitumen emulsion tank before and after
Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.3 - Membrane Seal
Detail of Activity / Test - Application of Membrane Seal
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
Inspection / Test method - Sealing Records
Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
Record documents (QCP - Quality Control Portal) - Sealing Records
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.4 - Temperature
Detail of Activity / Test - Pavement Surface
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
Inspection / Test method - Infrared gauge
Acceptance Criteria - ≥ 10 °C or as otherwise agreed with NZTA
Record documents (QCP - Quality Control Portal) - Site diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions - Must get NZTA approval if CHAR(LESS) 10°C
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.5 - Temperature
Detail of Activity / Test - Asphalt Delivery temperature
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
Inspection / Test method - Temperature Probe
Acceptance Criteria - Target ≥ 130° deg.C. in the Paver Min. ≥ 120 deg.C in the Paver CHAR(LESS)110°C to be Rejected
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.6 - Temperature
Detail of Activity / Test - Compaction Temperature
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - During compaction
Inspection / Test method - Temperature Probe/Infrared gauge
Acceptance Criteria - ≥ 110°C at commencement of compaction. CHAR(LESS) 80°C - Stop Rolling
Record documents (QCP - Quality Control Portal) - Site diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.7 - Mat
Detail of Activity / Test - Load Locate
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Each load
Inspection / Test method - P/11
Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
Record documents (QCP - Quality Control Portal) - Paving Run Sheet
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.8 - Mat
Detail of Activity / Test - Thickness Monitoring
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Continuously
Inspection / Test method - Dipping
Acceptance Criteria - Target Loose Thickness -0mm / +10mm
Record documents (QCP - Quality Control Portal) -
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.9 - Mat
Detail of Activity / Test - Shape
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Continuously
Inspection / Test method - 3m Straight edge
Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA P11:2023 - Section 14 Not more than 5mm under a 3m Straight Edge.
Record documents (QCP - Quality Control Portal) - Straight Edge Record
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.1 - Paving Quality
Detail of Activity / Test - Texture
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
Inspection / Test method - Sand Circle or HSD
Acceptance Criteria - NZTA T/10: 2013
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.11 - Paving Quality
Detail of Activity / Test - Level
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
Inspection / Test method - As Built Survey
Acceptance Criteria - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. NZTA P/11:2023 - section 14.1
Record documents (QCP - Quality Control Portal) - Survey As builts
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.12 - Paving Quality
Detail of Activity / Test - Alignment
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
Inspection / Test method - As Built Survey
Acceptance Criteria - ±50 mm from drawings
Record documents (QCP - Quality Control Portal) - Survey As builts
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.13 - Paving Quality
Detail of Activity / Test - Ride Quality - Wearing Course only
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - Continuous every lane
Inspection / Test method - NAASRA
Acceptance Criteria - Max 100m Rolling Average 60 Counts/km Max 20m NASSRA 70 Counts/km Refer TNZ TM 7003 v1 (2006)
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
Responsibility - Paving Contractor
Project Specific Notes / Instructions - For structural mixes, refer clause 1.7 of this ITP - Hold Point must be observed on this layer before proceeding to a final Surfacing Layer
Designer - A
Eng. Rep / NZTA - I
Contractor - R
3.14 - Post Paving Completion Checks
Detail of Activity / Test - Site clear and cleanup
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
Inspection / Test method - Visual
Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
3.15 - Post Paving Completion Checks
Detail of Activity / Test - Pavement Marking
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
Inspection / Test method - Visual
Acceptance Criteria - Roadmarking is complete
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
3.16 - Post Paving Completion Checks
Detail of Activity / Test - Cold Joint Bandaging
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
Inspection / Test method - Visual
Acceptance Criteria - Cold joint bandaging is complete
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
3.17 - Post Paving Completion Checks
Detail of Activity / Test - Service Covers Checked
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
Inspection / Test method - Visual
Acceptance Criteria - Check that service covers are cleared and level with the pavement
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
3.18 - Post Paving Completion Checks
Detail of Activity / Test - Traffic Loops Reinstated
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
Inspection / Test method - Visual
Acceptance Criteria - Check that affected traffic loops have been reinstated
Record documents (QCP - Quality Control Portal) - Communication
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
4.1 - Assessment of all test results for conformity
Detail of Activity / Test - Review against ITP Requirements
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
Inspection / Test method - Review
Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR
Record documents (QCP - Quality Control Portal) - NCR
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - A
Contractor - R
4.2 - RAMM pavement and surface records
Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
Inspection / Test method - Prepare Data
Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer.
Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - A
Contractor - R