## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
05f899ee-c8a4-4a8f-9816-583f2c1dc9a3 | checklist | ITP - M32 EME - Construction Rev A | itp | ITP - M32 EME - Construction
8a7a1a24-43fd-4ad2-86a4-4c5dd094e487 | section | 2.0. MANUFACTURE OF ASPHALT
fde9c9a0-acd8-4873-8670-9aaf9d20b1a3 | checkpoint | 2.1 - Temperatures
1c963784-cc31-5e30-a18f-0f6cb4087783 | note | Detail of Activity / Test - Mixing of aggregates and bitumen
1096d8b6-fe52-5d26-a2a9-692ebee68dbc | note | Action (Hold, Monitor, Witness) - M
03ac21b7-05ae-5f1c-8827-00933899b8b4 | note | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated equipment
46ad836c-c353-549d-8d85-08c300824f93 | note | Inspection / Test method - Plant temperature probes
6b0e0b78-86b0-5e13-8ef8-dbeb137a0210 | note | Acceptance Criteria - EME2 binder Mixing range 170 - 190°C
4f1afacc-19c8-5163-bd66-0cb7098ad2db | note | ○ NZTA M/32:2021 states max. 190 deg.C
05017ed9-01d7-52f2-869d-e7aff75f75fa | note | Record documents (QCP - Quality Control Portal) - Plant site diary
d6f8053d-615c-5e69-b49c-8da4b2c3e1fc | note | Responsibility - Asphalt Manufacturer
b12d8dab-5ac3-5e16-84fd-703d55a8d783 | note | Designer - I
3e2dac62-f3e9-5b97-b9dc-e3ef7b2ad457 | note | Eng. Rep / NZTA - I
9b3451f9-d400-5dbb-97b3-26fbc9f7465b | note | Contractor - R
324d23ee-952a-41c4-87cb-0a3eb27f47f0 | checkpoint | 2.2 - Production Asphalt
3f269921-5c42-5633-88a7-37af3ab111f5 | note | Detail of Activity / Test - Particle Size Distribution
497532da-aab3-56c2-b5a6-89be7244a64b | note | Action (Hold, Monitor, Witness) - M
bd525244-5888-53ac-8ae9-dda23e092ed3 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
f3d619cf-b17f-5a98-ab0c-4e52d00a677b | note | Inspection / Test method - NZS 4407, Test 3.8.1
f8272479-fb08-5209-bc0b-9d2d77628065 | note | Acceptance Criteria - NZTA M/32:2021, Refer to Table 5.3
8c451370-cb0e-5b82-9a42-97038e15b717 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
f6d26b00-022d-5cc9-bffa-eab106f0ce02 | note | Responsibility - Asphalt Manufacturer
d4484aca-678d-5a10-89cd-51e4e2d1f77c | note | Designer - I
d171033b-a4e3-5584-a3ac-3bdcde2ce230 | note | Eng. Rep / NZTA - I
75e01b6a-367a-5fbf-9166-d69f5b634c63 | note | Contractor - R
6d45c94e-63f7-4c1a-a5a2-133b044a146b | checkpoint | 2.3 - Production Asphalt
4fd5c935-a8db-517b-a702-36823f95e3c9 | note | Detail of Activity / Test - Binder Content
b4fbaad4-bc24-5a9e-86cc-71f77778eb30 | note | Action (Hold, Monitor, Witness) - M
30d4e5f5-d1d6-50c0-a650-dfee422f50e4 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
2c078bb3-0a55-5cc6-bfe9-d9673d28be26 | note | Acceptance Criteria - NZTA M/32:2021
6500903b-e1bf-5761-88ca-478c6241af8a | note | ○ Individual Test Result: ± 0.5
12c11672-4ac7-5c11-a65e-a6c6c9b80ec0 | note | ○ Mean of Three Test Results: ± 0.3
9b823123-47e8-56cb-a32c-9092b610f6df | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
648745c7-79e8-5ecd-8d60-70cd42c4cea6 | note | Responsibility - Asphalt Manufacturer
d7540135-cb01-59d4-b529-21edec353525 | note | Designer - I
a2dd6ac3-3518-56a0-9f0f-9b4e7fd992a2 | note | Eng. Rep / NZTA - I
ef457cae-bbee-5a64-901f-8b97123008c8 | note | Contractor - R
65977536-6aa0-4771-9d9d-8665b7483fd8 | checkpoint | 2.4 - Production Asphalt
3f0f89d5-8f46-599f-912d-849e4eed8241 | note | Detail of Activity / Test - Max. Specific Gravity (MSG) of mix
58ea1bc6-6f55-5624-8551-8383635f63e8 | note | Action (Hold, Monitor, Witness) - M
68e48325-5013-588e-8cb1-3975b4ef7226 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
167b7b8c-4da8-5411-a123-6b7c9a904a94 | note | Acceptance Criteria - Report
e4b173f6-cac5-54f5-853a-a27d81015b4b | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
7cf4302a-31fa-53e3-8f07-8949e15f1169 | note | Responsibility - Asphalt Manufacturer
2d4c6a3d-95ff-55ec-97c7-570a02263710 | note | Designer - I
474c30c2-9ce5-5a87-a900-8a59bdcc987b | note | Eng. Rep / NZTA - I
d58d8eff-2411-5097-a32b-c0c9838d29a5 | note | Contractor - R
596934b1-10b5-44a3-a73d-4f39813d340e | checkpoint | 2.5 - Production Asphalt
4589bd71-29ba-5ec3-9ba5-c06ecbf18b2b | note | Detail of Activity / Test - Air Voids at lab design compaction
34a6c147-312f-5e0a-bdb8-535bb280003a | note | Action (Hold, Monitor, Witness) - M
fdd93cd8-1a3a-5537-8404-d526b1d7bc3b | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
b81078f9-31a8-583f-a4e9-81ec3305518e | note | Acceptance Criteria - NZTA M/32:2021
f83da4c2-5e3f-5b0f-a463-d391ee18e858 | note | ○ Individual Test Results: +2.0, -1.0
9d5b52e3-ed0c-5e59-8a96-69246ec828ec | note | ○ Mean of Three Test Results: +1.2, -0.6
be814ffd-093e-5264-b00c-aa7dfea77ab9 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
f5a56234-1704-567e-9d15-034c685747ea | note | Responsibility - Asphalt Manufacturer
5f225489-1459-5cab-8440-2a06e056ac2c | note | Designer - I
9f1775f6-f6d8-52f8-9387-88d91e083829 | note | Eng. Rep / NZTA - I
3718ae33-7000-5405-ab37-070b7ce410e9 | note | Contractor - R
b9accf2f-5f1b-4c55-81b5-c030ad022747 | section | 3.0. PLACING AND FINISHING
97b6b980-a449-4f78-b7a9-84e91b14789e | checkpoint | 3.1 - Milling
933f01bc-4e1b-5959-8374-edc64c04f128 | note | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
c3596408-c056-5af7-af42-0875ad954d0e | note | Action (Hold, Monitor, Witness) - M
95742d62-38ee-5c1f-9376-a1e3a6b1c6d4 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Asphalt placement commences
979d836a-ad84-59ed-a076-e3866290c180 | note | Inspection / Test method - Confirm requirements are followed
92cbb156-9bdd-5409-a659-85489d3da8b5 | note | Acceptance Criteria - Site is suitable for paving
37abf4c4-0a72-5edf-a6b7-777b102e0cf5 | note | Record documents (QCP - Quality Control Portal) - String Sheet
621dc404-0569-503a-a28e-ad9058bba023 | note | Responsibility - Paving Contractor
0da7d2b9-10c8-5e99-97d7-c3b85f8b22e0 | note | Eng. Rep / NZTA - I
252e166a-fac3-5dfe-b515-d8c2394df915 | note | Contractor - R
98d5dc3b-9251-42b7-a2a1-40c063f38834 | checkpoint | 3.2 - Tack Coat, OR
c5a043db-aeb9-5a73-92a4-6ac5726f24eb | note | Detail of Activity / Test - Application of Tack Coat
dd27fab4-1fe1-5918-aeea-94b3a79ccd11 | note | Action (Hold, Monitor, Witness) - M
1b2742fc-46a4-5b59-9743-9a54817c3a0a | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
f03cf3ec-6f16-5766-ab9b-18f177971622 | note | Inspection / Test method - Dip bitumen emulsion tank before and after
6c0da469-e47b-5e1c-97e9-3e23cd117f2b | note | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
713371a2-6247-5806-a64d-f427c9fa101d | note | Record documents (QCP - Quality Control Portal) - Site Diary
21eae612-8821-5f61-8176-ad9bfaf60b0e | note | Responsibility - Paving Contractor
bffbf0e4-d526-5a8f-a53e-1ac6200b5b87 | note | Designer - I
33272e1a-ac8c-5538-96e4-90cf499cce91 | note | Eng. Rep / NZTA - I
6dbdd612-5c12-55e5-8647-bec4df73db32 | note | Contractor - R
4b5e9488-9a37-45e9-9ccd-479bb2d09f33 | checkpoint | 3.3 - Membrane Seal
3b89281a-1edc-5cce-9349-5cc1482ae5c5 | note | Detail of Activity / Test - Application of Membrane Seal
b51a3fe5-d348-5934-bf5f-299724a1de45 | note | Action (Hold, Monitor, Witness) - M
fcedbb04-d711-59ed-a2f6-b7d2af059b7c | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
6f86e262-d7bc-5c58-ad71-def7204911cf | note | Inspection / Test method - Sealing Records
bd4e53b6-4a24-5e0e-b693-452aceffe2f3 | note | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
ce1f84df-d05d-5f5c-b420-51a9e7d7117e | note | Record documents (QCP - Quality Control Portal) - Sealing Records
ff25d3ea-f351-5c5e-8f73-105d788bea65 | note | Responsibility - Paving Contractor
9494bb8c-f045-5552-a94c-47d541d53e3e | note | Designer - I
e2f64b2a-ac34-5e7f-9d97-4c9831170163 | note | Eng. Rep / NZTA - I
b2c323ba-4e72-5306-94db-3befd05a45d2 | note | Contractor - R
a81dbf1f-65d2-4079-be59-a5d9125606a0 | checkpoint | 3.4 - Temperature
9dbc61be-fd2d-56f1-abc2-757ba1c726b6 | note | Detail of Activity / Test - Pavement Surface
3c091d8f-9772-56bd-ba3a-e5258898aeda | note | Action (Hold, Monitor, Witness) - M
0a3cc68c-d0f7-5781-96bd-7e9a68be4999 | note | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
11fb6c73-b4ac-5508-aa2e-eff0c2c1199d | note | Inspection / Test method - Infrared gauge
6291af07-e568-5b21-a281-731f5563389d | note | Acceptance Criteria - ≥ 5°C for Structural, or as otherwise agreed with NZTA
e8448b12-364d-5ffc-8a4f-785742f76256 | note | Record documents (QCP - Quality Control Portal) - Site diary
67fab153-7b5b-5a36-8df1-6a164e6634a5 | note | Responsibility - Paving Contractor
74d0a4c9-6bb4-51dd-a73f-1aa36c127ad8 | note | Project Specific Notes / Instructions - Must get NZTA approval if < 5°C for Structural
52c36170-add1-5987-977e-4dff8f0f6b3a | note | Designer - I
717ff785-813f-5de6-94cd-27e85a4110b7 | note | Eng. Rep / NZTA - I
d199dbbf-dd1e-532d-8dc3-53a31980c591 | note | Contractor - R
8549e331-8b70-42e8-aaaf-a0e19c19e0ae | checkpoint | 3.5 - Temperature
66a3aeaf-cb18-590d-8ef5-7e0c2550cc9a | note | Detail of Activity / Test - Asphalt Delivery temperature
d1ae9e2f-4aab-5fe7-8f35-8b34442909bc | note | Action (Hold, Monitor, Witness) - M
2b1d6d84-3ed7-5bf2-8bf4-b2c7dc95beb5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
50af91e1-9dd7-552c-b4d5-a02fc4f328bd | note | Inspection / Test method - Temperature Probe
968e7e90-c38c-53f4-a9f6-4c94647382e8 | note | Acceptance Criteria - Target ≥ 170 deg.C. in the Paver
28cf2d79-b8c1-50d4-80a6-832ef146ef8d | note | ○ Min. ≥ 150 deg.C in the Paver
63c977af-d2f9-5358-b882-e2d48245774a | note | ○ <130°C to be Rejected
2859d353-2ea1-5900-ab0d-96b62eb2a09c | note | Record documents (QCP - Quality Control Portal) - Site Diary
f3598ce4-c759-5cc6-a82c-7843ccd9fa9f | note | Responsibility - Paving Contractor
13ba983d-2f05-54f4-a2c1-7a813b929d6e | note | Designer - I
35982c33-0a27-51ef-b32d-0db03037cd85 | note | Eng. Rep / NZTA - I
5b59125a-40be-5dc3-a7a6-250cab9c9fc6 | note | Contractor - R
4c878496-968b-4147-8615-62b5e5a9c49e | checkpoint | 3.6 - Temperature
39f4c314-3ee6-5699-bf2e-87dc5b4d22b2 | note | Detail of Activity / Test - Compaction Temperature
1b1766d1-da20-502c-81f2-51f44eac42e1 | note | Action (Hold, Monitor, Witness) - M
cab56dee-fa00-599b-aa7a-0fd6f5ad568d | note | Minimum Test Frequency (Lot = 1 day’s production) - During compaction
143a3d78-71fc-5f3f-820c-77d17bfd56db | note | Inspection / Test method - Temperature Probe/Infrared gauge
a3bf54e3-0d57-54b7-bfac-267a48ff22f0 | note | Acceptance Criteria - ≥ 135°C at commencement of compaction.
daf14a2f-309f-524b-88c8-1725b167d881 | note | ○ < 80°C - Stop Rolling
89848251-482e-5c1d-a090-3d5495a08fae | note | Record documents (QCP - Quality Control Portal) - Site diary
9229cbf0-a6e3-5e58-bb66-b4e2467b2fa9 | note | Responsibility - Paving Contractor
51f00421-ffba-5f2a-a556-fa192bd3251d | note | Designer - I
27568ac8-8d02-5500-b438-e55f66c31074 | note | Eng. Rep / NZTA - I
f7bdb96f-1f91-547b-aab6-ab2383e474cc | note | Contractor - R
a67dc46a-a734-4ea0-9827-d413f8f935f2 | checkpoint | 3.7 - Mat
1de35b7a-7e6c-5003-991c-69c4923265f6 | note | Detail of Activity / Test - Load Locate
6f58da84-bdad-5a92-b8af-80f704409e50 | note | Action (Hold, Monitor, Witness) - M
976815db-fdb2-5eee-8852-a457868676eb | note | Minimum Test Frequency (Lot = 1 day’s production) - Each load
a18de7c9-7483-5189-9bfd-65b801a48674 | note | Inspection / Test method - M/32
9f8ba22b-3f4c-50f4-a742-da97f595e00a | note | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes:
b8a1c5f6-7627-52d2-a22e-fa37bea32bf6 | note | — Truck ID/Rego/Driver
ac6d307a-cfba-5f15-989e-bcc7a46efdd6 | note | — Depart Plant Time
a7b8c027-e4c7-5088-b164-de5255836e3a | note | — Arrive Site Time
43541ef4-14fd-50c9-a529-7bcfa74c5057 | note | — AC Temp on Arrival
7a41b14f-b702-5c5c-8f40-32d2ed713098 | note | — Tonnage
270cdf9d-efd4-52dc-81b9-d210c498cffa | note | — Run Width
c48c52d6-97d7-563a-8aa1-90dd2d3222de | note | — Estimated Run Length
94aa79f3-8ab1-59da-a0dd-025b6faed537 | note | — Calculated Area
95ae1f7a-4ff4-5348-a0b0-36fa2a0b29d8 | note | — Calculated Average Depth
d9be4c25-cc42-5c36-bdf2-7c464e78af63 | note | Record documents (QCP - Quality Control Portal) - Paving Run Sheet
10298879-b0f9-5214-831d-4e9a25efbb6f | note | Responsibility - Paving Contractor
82ed7bc8-ef1b-5dbf-a582-c00b603981f8 | note | Designer - I
7db798fb-505b-54a0-8bbf-9d43c7a4f25e | note | Eng. Rep / NZTA - I
86fd0203-c3c5-5e9f-85e9-8ebb635e4acb | note | Contractor - R
bff30623-cdcf-464a-b1ea-f3239ae2ac5b | checkpoint | 3.8 - Mat
eba657d3-cf94-52cb-984c-f25ff6505215 | note | Detail of Activity / Test - Thickness Monitoring
862f4d31-a211-57c3-9dee-4ea3ec9713a5 | note | Action (Hold, Monitor, Witness) - M
979b30d2-7ee2-5a3b-80a4-1fa5a01ae7bf | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
634fcee6-d082-5642-bccb-987d8afbbc1a | note | Inspection / Test method - Dipping
f3a04684-414b-5b82-8cb7-c296c4355cb3 | note | Acceptance Criteria - Target Loose Thickness -0mm / +10mm
5ba5b4a2-1401-5bd5-ad12-9662ed513290 | note | Responsibility - Paving Contractor
4a2b1c72-93ac-52fc-a7d9-200fe8dd5cea | note | Designer - I
171c67ab-5164-5177-8e02-52ec4749008e | note | Eng. Rep / NZTA - I
dab4f44a-490e-58db-8acf-7639d2694c78 | note | Contractor - R
11480af5-eb4b-449b-a328-892b1a0715ba | checkpoint | 3.9 - Mat
e8df5b26-47ec-5b2b-a924-ed59992e06f9 | note | Detail of Activity / Test - Compaction - NDM
345158a2-61db-5c25-9dc5-f1e3092e82c5 | note | Action (Hold, Monitor, Witness) - M
9d5a3d48-f778-525d-90a9-be43a8e1aa12 | note | Minimum Test Frequency (Lot = 1 day’s production) - Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density.
e483d059-a17b-5c2e-9ee9-51e3f324413a | note | Inspection / Test method - Insitu density and air voids
081c2b19-e824-5d90-9c01-2f3e2089c85a | note | Acceptance Criteria - NZTA M/32:2021 - section 9.8
91daa0fc-12f3-5ad5-9101-351a4188446d | note | Responsibility - Paving Contractor
40aeeabb-b948-51e1-9bf3-1bfcca5b8fd6 | note | Project Specific Notes / Instructions - Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used).
8be4ce0f-119c-50ab-a297-48f57886b9c2 | note | Designer - I
4b3f7ba8-fc42-513c-8c84-7b24538369ec | note | Eng. Rep / NZTA - I
90317a75-0d86-5587-a5d8-cd165ebb720b | note | Contractor - R
9be93f4d-4b84-4a24-b14b-ebda372c400e | checkpoint | 3.10 - Mat
4e75cdae-a85f-526f-a068-288017391b51 | note | Detail of Activity / Test - Compaction
a65fbc9a-c123-50d3-8aed-9f1b4b89c2a4 | note | Action (Hold, Monitor, Witness) - H
08e86ec6-48af-578c-853c-3616be54b946 | note | Minimum Test Frequency (Lot = 1 day’s production) - Mat: 1 per 300m2/min. 8 per Lot Joint: 1 per 100m/min. 3 per Lot, In the event of a day's production being > 30t but < 2400m2, then it will be permissable to reduce the number of cores to; Mat: 1 per 300m2 with a minimum of 4 per Lot, and Joint: 1/100m with a minimum of 3 per Lot
40c014b4-af5d-5f7d-b4b6-bd35ec2777fc | note | Inspection / Test method - Insitu density and air voids
bcdb7adb-9bf1-5489-94e3-a1b4efe90a48 | note | Acceptance Criteria - NZTA M/32:2021 - section 9.8
ade2e00a-f243-53dc-8084-8d8c1c93505f | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
f93c6b4d-e351-5b19-b55b-233659c8f966 | note | Responsibility - Paving Contractor
dba787e0-b9d8-54a2-90ec-f7a02f1f52fe | note | Project Specific Notes / Instructions - A pavement lot shall be an essentially homogeneous section of work completed within a shift of production.
564cec2c-6658-5f3d-ab63-5a4054e5cce9 | note | ○ The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process.
891b589a-385c-537e-90e2-5705f57b3d49 | note | Designer - A
1997ca9e-14e3-5457-aa23-b31815624a37 | note | Eng. Rep / NZTA - I
8e79c8b1-7c4c-5106-b03a-f90941e775f1 | note | Contractor - R
867a9b61-22ea-4e9a-94ec-1f2c677a3c25 | signoff | AUTHORITY HOLDPOINT
eb5795b7-b901-444c-8ad0-e0c050d85336 | checkpoint | 3.11 - Mat
3a9b8ef8-32e3-50b9-843a-3eabed078d42 | note | Detail of Activity / Test - Thickness
2d635822-9907-5cda-b887-e03df4a3ab14 | note | Action (Hold, Monitor, Witness) - H
9a9d9084-1878-55c2-a2a6-2624990ae5cc | note | Minimum Test Frequency (Lot = 1 day’s production) - Average of 4 measurements per core
8a01b8dd-386c-5afa-b35a-d9f563792359 | note | Inspection / Test method - Measure Cores
b16886af-2d0f-53de-8a8e-3c8324aa680e | note | Acceptance Criteria - LCV ≥ Specified Depth (Minimum), NZTA M/32:2021 - section 9.7
f7b6df25-75f1-5898-955c-a13feae4ae78 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
fcab8ae4-9d32-591a-8458-4a41555fbefe | note | Responsibility - Paving Contractor
3253f899-cb6f-59c4-94de-8edf4673d92a | note | Designer - A
f143bcfc-05f0-5118-a7ce-41f08b1c094d | note | Eng. Rep / NZTA - I
a7728d5b-a2ae-537c-b5fd-2f4daaf0a62f | note | Contractor - R
96bd2412-3490-4fde-9e7b-ec7e5a8f4b9b | signoff | AUTHORITY HOLDPOINT
a957e246-ec27-4473-b23b-26437810362b | checkpoint | 3.12 - Mat
510dab66-b220-5996-9685-bcae853e955a | note | Detail of Activity / Test - Shape
7816b9db-b4c0-58e9-8aac-8ce7c38e136e | note | Action (Hold, Monitor, Witness) - M
b86a81af-cd95-5840-9eb8-c4bf0d706174 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
2fe81ac4-378e-50e4-9466-bdaca33a89eb | note | Inspection / Test method - 3m Straight edge
25f422c2-d368-5914-b718-5f42647f1bf8 | note | Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/32:2021 - section 10.
a4e68286-4df6-5288-9110-54aa0a7366f5 | note | ○ Not more than 5mm under a 3m Straight Edge.
b2f57d1b-d243-5542-b7ac-f6abbcd48921 | note | Record documents (QCP - Quality Control Portal) - Straight Edge Record
643eacaf-df4d-5cd6-a348-767ea03187ca | note | Responsibility - Paving Contractor
927e00a4-c3ab-544e-9c4d-9cdfaf8b30d7 | note | Designer - I
c5112867-c463-5464-a674-cc16c0c907d0 | note | Eng. Rep / NZTA - I
b846e3c1-339a-5084-a900-e4ff84c91352 | note | Contractor - R
5609b2a9-6ebf-4e0f-9a83-49b5bd8b9b0f | checkpoint | 3.13 - Paving Quality
1ca439ee-bbd8-5bf7-abe1-d90333ae1b07 | note | Detail of Activity / Test - Texture
92db3401-5d13-5428-9109-a9994f0c14c6 | note | Action (Hold, Monitor, Witness) - M
9973a669-807f-5141-8ce4-9f90c5ee48f2 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
551e1322-fe8f-538a-b059-0a8974428e82 | note | Inspection / Test method - Sand Circle or HSD
21f2ac98-c17e-5aad-93c9-a81b4d8ec095 | note | Acceptance Criteria - NZTA T/10: 2013
ca0a6f55-a727-5718-b628-b31572a93f47 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
d2bb6acd-80a9-571e-8530-2d0d6d0ef647 | note | Responsibility - Paving Contractor
16c4c63c-d286-522b-b285-8087575d02fa | note | Project Specific Notes / Instructions - Only required if EME will be the final wearing course or final road surface.
34696961-c58f-5014-99ee-356b4ea96dbc | note | Designer - I
822f19d4-1421-591a-818f-7e52b74e10d0 | note | Eng. Rep / NZTA - I
201e1248-fea0-5d01-b03d-6287b4db50fd | note | Contractor - R
f05d02a3-5171-4a4b-b21e-4dab99b108fc | checkpoint | 3.14 - Paving Quality
a60fce50-af80-549c-bdd0-420dc98eca12 | note | Detail of Activity / Test - Level
d7c83865-491a-55ba-ae8e-c56c553eaee5 | note | Action (Hold, Monitor, Witness) - M
2ce804ae-09ea-5df2-b79d-8a2f551639c4 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
f0b00b45-921b-554c-ac8e-d51b2c772579 | note | Inspection / Test method - As Built Survey
100bef9b-7f0c-5118-a0c2-52f81d8002db | note | Acceptance Criteria - The level at the top of each layer of EME 2 shall not be less than or more than 10mm higher than the specified level.
d9be41a8-fc38-50f0-aa70-1d0735c8b982 | note | ○ NZTA M/32:2021 - section 10.1
af3e5a37-d8fc-5923-9498-99f02129b108 | note | Record documents (QCP - Quality Control Portal) - Survey As builts
f106ada9-08c8-56f8-8777-ffd774216577 | note | Responsibility - Paving Contractor
1ca2bafd-e60e-5ef2-aa93-78e77baa91ff | note | Project Specific Notes / Instructions - Only required if EME will be the final wearing course or final road surface.
eb7d9a84-e7b1-559b-9c11-2ce19745d002 | note | Designer - I
e89b8ffc-32c6-5998-ab23-73b6640cc980 | note | Eng. Rep / NZTA - I
1d8e5678-fa68-5eb7-973c-c963cef216b3 | note | Contractor - R
9323d603-d61c-4c70-bfa1-59bcedb796b0 | checkpoint | 3.15 - Paving Quality
441b4eb6-0f56-587c-bb63-221b17b327d9 | note | Detail of Activity / Test - Alignment
94f1e1b8-93dc-5185-b39b-cca8a489f535 | note | Action (Hold, Monitor, Witness) - M
5451cff3-ac30-54cf-b50c-8d601f9f4f2e | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
397006f7-fbd5-5b53-821b-bde4e83dbc1d | note | Inspection / Test method - As Built Survey
76f8c86d-1a99-5f98-be71-8c7df65c2d2d | note | Acceptance Criteria - ±50 mm from drawings, NZTA M/32:2021 - section 10.2
5a4bc355-24cb-5ca5-b6a4-49891f636fb4 | note | Record documents (QCP - Quality Control Portal) - Survey As builts
b7607470-bbfb-5e14-9b47-bf1057511333 | note | Responsibility - Paving Contractor
83698182-9db3-5d2f-9559-6df3bf253173 | note | Project Specific Notes / Instructions - Only required if EME will be the final wearing course or final road surface.
568723bb-28d8-5258-a881-1fc771961548 | note | Designer - I
a3f8d394-aca8-575f-8d1b-e6616949817e | note | Eng. Rep / NZTA - I
bd4233b6-f9ce-5289-baf0-fd3bf1f533c0 | note | Contractor - R
8fb92ae3-e6b2-4452-88de-75a941af2c5f | checkpoint | 3.16 - Post Paving Completion Checks
929fd053-895a-53e6-9d9a-9ec1463039c9 | note | Detail of Activity / Test - Site clear and cleanup
96bd056b-3419-5b29-8514-25b7a48d9471 | note | Action (Hold, Monitor, Witness) - W
9cd9ab05-7005-5347-853d-4b92f23ff099 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
8ad7843d-6e5f-50cf-b403-78c9b956bf1f | note | Inspection / Test method - Visual
489efa5e-5857-59a3-a1a3-8fc385ffda47 | note | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
a6ce3c5f-0646-55aa-972c-dd88dc62ae3e | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
69b793c5-3326-5d77-bb9c-c8b3df663a32 | note | Responsibility - Paving Contractor
90c88205-e741-5000-a1d5-ef91c5bef4f7 | note | Eng. Rep / NZTA - I
1db3cdea-18ba-5f20-be64-2fb1e70a3ec8 | note | Contractor - R
822bee93-f263-43d2-8640-3dd0d970ae4a | checkpoint | 3.17 - Post Paving Completion Checks
c7852036-ef8a-5aa6-81cf-c06f561ac4f2 | note | Detail of Activity / Test - Pavement Marking
5ffb022b-deeb-5ba9-aa25-10ecbd67c58f | note | Action (Hold, Monitor, Witness) - W
1b711222-3ec0-5171-baa6-d7646bbcee19 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
f4878108-d345-57d8-8ce8-0eae71a4772b | note | Inspection / Test method - Visual
c946932a-9f4f-561a-b1c4-6dd950e6034b | note | Acceptance Criteria - Roadmarking is complete
b1a13de0-78d9-51a3-b303-1006984a035f | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
ee35970a-d367-595b-a6be-c4267cbec71e | note | Responsibility - Paving Contractor
3ffb8fa7-a202-54c8-83fc-dba1e5300e7a | note | Eng. Rep / NZTA - I
257cfa35-6e2b-543c-8a4c-1eaf0edd419d | note | Contractor - R
ae3ef5cb-4029-426c-9ab2-a2b15b1dbd2e | checkpoint | 3.18 - Post Paving Completion Checks
d8e800bd-fb55-5ed4-bc04-ec80f2416ba0 | note | Detail of Activity / Test - Cold Joint Bandaging
f16cb892-e543-5a17-9da8-b2cbbfff5647 | note | Action (Hold, Monitor, Witness) - W
cd0687d7-3582-5b62-952f-f25ca6468164 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
4e1977f4-adda-56bc-a9f6-a22ec230b80b | note | Inspection / Test method - Visual
54c4098d-02bf-5023-ab9b-054edaf386a9 | note | Acceptance Criteria - Cold joint bandaging is complete
ecf0f410-17b0-50b9-8574-31eba66700df | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
d2577911-7454-522a-ba73-8bee06cf26e4 | note | Responsibility - Paving Contractor
a0393874-af15-57f3-b682-670ceaa27609 | note | Eng. Rep / NZTA - I
e14e361d-73ae-5b94-a698-48963958a9fe | note | Contractor - R
76021f4c-ca68-460f-9ee6-b7cd616170e2 | checkpoint | 3.19 - Post Paving Completion Checks
fde34153-c587-508b-be9f-5d8508e08ac2 | note | Detail of Activity / Test - Service Covers Checked
254c27ce-16ab-5238-b19c-2d084c22ab92 | note | Action (Hold, Monitor, Witness) - W
2ed4b352-233d-5b9f-ad4d-6d3dbe9407f8 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
69aa1b7c-9238-5cc2-a3fb-723e1b664d76 | note | Inspection / Test method - Visual
0038577d-7ea2-53aa-94d7-2d1f117d6b25 | note | Acceptance Criteria - Check that service covers are cleared and level with the pavement
b72fccc9-8722-5367-a003-0ea4b7573ac9 | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
94dbe463-a880-5814-852b-a3416834ff84 | note | Responsibility - Paving Contractor
d7d8c229-08c9-5666-9858-f395e7f2f2d4 | note | Eng. Rep / NZTA - I
f36a603e-a637-5bbd-96a9-45533ed9b14c | note | Contractor - R
575db732-1271-4da5-83df-e4ca24f24269 | checkpoint | 3.20 - Post Paving Completion Checks
0959ec4e-7d8f-5baf-b125-5567eb623a16 | note | Detail of Activity / Test - Traffic Loops Reinstated
73d87075-9362-5de9-8847-80a23ae9189f | note | Action (Hold, Monitor, Witness) - W
ecf1c522-29ef-5295-8dc2-0d89b127ccd0 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
596d32c1-d17b-5a53-8ab9-51f07aa17be1 | note | Inspection / Test method - Visual
34d5484c-0e5a-5d10-9475-d89b0990c35b | note | Acceptance Criteria - Check that affected traffic loops have been reinstated
0ab3e9b9-8c04-5b0e-860b-46c5ad0168d1 | note | Record documents (QCP - Quality Control Portal) - Communication
53d80852-9f42-5b40-9618-a74eb00deed2 | note | Responsibility - Paving Contractor
e544cbc9-44a0-5a01-aaa3-d397530b1d38 | note | Eng. Rep / NZTA - I
b3e31fa5-8c91-5992-aca7-ead4ace684df | note | Contractor - R
f2e15d72-3c6e-48ab-87d1-316facbc7fa0 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7060ed43-b46a-56d3-ad19-8907df94bcf5 | textbox | Contractor's Rep Name:
5fdd9f29-dbfe-5ffe-b36b-629b960980fd | textbox | Engineer's Rep. Name:
8912e276-2567-51af-92db-7b640bdf8ced | date | Date:
61be02f2-93b2-4610-9a32-0ea7ae168a6b | signoff | Add Signature
a6fd2aff-1b50-4f9a-bb3c-2ef7c6d31ac7 | checklist | ITP - M32-EME - Construction - (with BB Test) Rev A | itp | ITP - M32 EME - Construction - (with BB Test)
be533bda-a6d4-444e-8259-0e0443da35af | section | 2.0. MANUFACTURE OF ASPHALT
978c7942-883c-4eac-a8dd-f24fada0f7e6 | checkpoint | 2.1 - Temperatures
e9f0bba2-e0ad-5f0e-ad47-0f5529f6039c | note | Detail of Activity / Test - Mixing of aggregates and bitumen
577cfad8-2dd3-54e1-bc5a-c88d4397a708 | note | Action (Hold, Monitor, Witness) - M
b2734f72-af3d-5527-9b20-066921817eb7 | note | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated equipment
a5ec2b40-aa05-5268-b654-e2881e12a41a | note | Inspection / Test method - Plant temperature probes
21be357c-9ce6-5da2-8a11-5620a606e68e | note | Acceptance Criteria - EME2 binder Mixing range 170 - 190°C
b495fe0e-e019-5675-b70b-fa5330cd2645 | note | ○ NZTA M/32:2021 states max. 190 deg.C
be3fff6d-b383-5ffd-8abc-ae03f1f004e6 | note | Record documents (QCP - Quality Control Portal) - Plant site diary
3dc6577e-e4f9-5eb4-8695-ebce188cebb5 | note | Responsibility - Asphalt Manufacturer
a1e3725a-e8dc-5ab9-8123-0df802eb3347 | note | Designer - I
9d097cb9-ea0c-56fd-ad96-54facaa152b8 | note | Eng. Rep / NZTA - I
36dc14f7-8a39-5ed2-bf84-2e5b94e5f847 | note | Contractor - R
fd4ff318-d9fa-4646-9870-0c89bc5b2698 | checkpoint | 2.2 - Production Asphalt
a9bafe0d-86c9-522d-870e-14999d84c115 | note | Detail of Activity / Test - Particle Size Distribution
11347051-d055-5db3-803e-ea26c2218efd | note | Action (Hold, Monitor, Witness) - M
a4add06f-1b33-5c88-a041-29e8a98998d2 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
9cd01446-1240-5193-b393-fe6d27b88aac | note | Inspection / Test method - NZS 4407 Test 3.8.1
a510a5d2-c3a2-5189-8cb8-1c39a0fe6392 | note | Acceptance Criteria - NZTA M/32:2021 Refer to Table 5.3
79588689-d50e-5ab6-bf9c-e41cc875eab7 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
dbc50231-398c-5291-a5c7-fde09aa50d37 | note | Responsibility - Asphalt Manufacturer
4bfe7b3b-222f-555f-9fdb-0a16904ec0ac | note | Designer - I
a17644fe-638d-518c-8cf5-e175ddfdcad8 | note | Eng. Rep / NZTA - I
c1ac1348-7826-5441-b9ad-78d293fa2604 | note | Contractor - R
8e3f6a64-6b0d-42cd-9653-1fb02e41a47c | checkpoint | 2.3 - Production Asphalt
4f8bb7b6-a25f-5bd9-9c50-6e554c1c5d54 | note | Detail of Activity / Test - Binder Content
318f6aba-01d5-5c8c-9927-7afdbf50b18c | note | Action (Hold, Monitor, Witness) - M
3f3e44aa-fd8a-58d1-bb96-e1076ba19708 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
49ee6c62-3f77-5148-bf4c-a09dd57861ce | note | Acceptance Criteria - NZTA M/32:2021
f834eabf-63e7-531a-94ce-517dce501a2a | note | ○ Individual Test Result: ± 0.5
d0137698-b123-53ed-a41f-ed27721404e2 | note | ○ Mean of Three Test Results: ± 0.3
1fcf80a6-223a-5e2f-8065-4a27a103296f | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
5ac7d6cd-ec95-5973-aac0-65ded5ada997 | note | Responsibility - Asphalt Manufacturer
b6c23559-8051-5699-8c55-385688f9f882 | note | Designer - I
01fb9ab7-3431-57ac-9cb1-91b5fc307b99 | note | Eng. Rep / NZTA - I
07623aff-e106-5221-8232-ad5f04d29356 | note | Contractor - R
f79763d2-90bf-49ec-ac60-e52361533eb9 | checkpoint | 2.4 - Production Asphalt
232c353a-d993-538a-8aab-1572dd996654 | note | Detail of Activity / Test - Max. Specific Gravity (MSG) of mix
30cbe208-1ac4-527c-80e6-0407d1845688 | note | Action (Hold, Monitor, Witness) - M
533a9bf3-4d6a-5e75-b1b9-a6baa56618bd | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
652a1af9-d4e0-524b-9075-c4bf6f3ecfc5 | note | Acceptance Criteria - Report
d200bb3b-1142-56df-b1be-523006cbc311 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
9ef0d9dd-c8c3-519b-8baf-c73c3e79e9d5 | note | Responsibility - Asphalt Manufacturer
a0e2bc20-4bb4-58b4-8a3d-a08cb2e838c9 | note | Designer - I
6c176222-1978-5414-9c57-91f61493fe0a | note | Eng. Rep / NZTA - I
71ddb005-e150-5197-9a1e-0d0772394575 | note | Contractor - R
ce1fe6e7-8699-4604-8f4e-692804f4b848 | checkpoint | 2.5 - Production Asphalt
7c2fcf3e-8448-550d-9c32-b73452c7197c | note | Detail of Activity / Test - Air Voids at lab design compaction
887aa951-0e33-50a2-8cbe-73833269b87c | note | Action (Hold, Monitor, Witness) - M
760fa3e8-f682-5f64-956a-45125d5a1ef1 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
c86b9066-29e7-5889-ac84-159ec785925e | note | Acceptance Criteria - NZTA M/32:2021
e351d641-2b8a-53cc-b91e-51cb2b0e6517 | note | ○ Individual Test Results: +2.0, -1.0
3c8a3b9d-d977-5e4b-b402-cdfb54252fd0 | note | ○ Mean of Three Test Results: +1.2, -0.6
0fa5b5ca-6759-52f2-9a32-dac30d945d25 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
48970123-06f0-5235-b0d0-b5d1822b983a | note | Responsibility - Asphalt Manufacturer
595aa75a-3237-5c5b-87e1-78df7f528d40 | note | Designer - I
887ec686-17a4-5274-8032-65e5f12da95f | note | Eng. Rep / NZTA - I
ac091f1d-61c7-53ad-ae2f-a6e96dde8521 | note | Contractor - R
c6a271ec-368c-469c-989a-fec4f53021f5 | section | 3.0. PLACING AND FINISHING
c01d1290-3de1-416e-aab1-dcff07fb0c59 | checkpoint | 3.1 - Milling
b8cb0e58-a093-5dc4-b30d-b0690fb89652 | note | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
fd564c6a-4790-5738-bca3-6d5c973305aa | note | Action (Hold, Monitor, Witness) - M
6c9f452d-3435-522f-957f-fb096c3b746c | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Asphalt placement commences
e4ad5ad3-c274-5ad6-94b7-b3e25144b723 | note | Inspection / Test method - Confirm requirements are followed
a0a17d30-669b-54a1-b699-65815ac3b970 | note | Acceptance Criteria - Site is suitable for paving
e14de628-af5b-52ba-803e-8807a866d463 | note | Record documents (QCP - Quality Control Portal) - String Sheet
17192bbf-e31f-5836-bbd9-f3a2800ca014 | note | Responsibility - Paving Contractor
f9960ad8-4e72-55cb-b1af-ca5b6db30f9d | note | Eng. Rep / NZTA - I
49db742b-557d-5758-b73b-1f170a4a7f01 | note | Contractor - R
268f15e0-1bf7-4a79-8267-eb552a834030 | checkpoint | 3.2 - Proof Roll and Benkelman Beam Testing
5cc28da9-921f-503f-a491-4924778f6c76 | note | Detail of Activity / Test - Treatment of identified soft spot based on proof rolling and Benkelman Beam Testing
d456a5a7-6cc9-5c9f-86b8-ac1ef1a61bc1 | note | Action (Hold, Monitor, Witness) - H
f8712a8f-1cb7-5eb0-9e4c-26356ebf63a2 | note | Minimum Test Frequency (Lot = 1 day’s production) - All identified soft spot
f0a5defd-d974-5a52-b6ad-a3e3c52f75a2 | note | Inspection / Test method - Proof roll/Benkelman Beam Testing
1d73c151-9b7d-5825-83f4-be67e275f50a | note | Acceptance Criteria - Refer to Pavement Rehabilitation Report under section 4.4 Pavement Contingency Measures
1660d0d6-3f08-5461-92f2-2fbfaa1f8a08 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
35674c9b-9678-549c-b23c-8727a41a84e0 | note | Responsibility - Paving Contractor
ef3e41d9-2ca2-5525-a215-39220a13c9f1 | note | Project Specific Notes / Instructions - Design specifications will be uploaded in CONQA.
b4cb39f7-9b7a-5dca-bd25-880849e4eed4 | note | Designer - I
40d82225-d489-5c1b-a401-c09278348a77 | note | Eng. Rep / NZTA - I
08723720-e074-5027-9879-260c2d49251f | note | Contractor - R
762c2dfd-daca-43a2-b1d4-df7a4dae2e35 | signoff | AUTHORITY HOLDPOINT
56ab584a-4016-4d5b-9820-d33f6f60758f | checkpoint | 3.3 - Tack Coat, OR
30540454-4cda-517b-a63b-be9ee22a7495 | note | Detail of Activity / Test - Application of Tack Coat
f0fb177e-140c-51df-97a0-88ce446c9869 | note | Action (Hold, Monitor, Witness) - M
b76cf616-f8f2-5316-932f-c6b3c8010bec | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
3aac08bc-9646-54c9-ab1f-44c0ab52bbd0 | note | Inspection / Test method - Dip bitumen emulsion tank before and after
53df3fad-74fc-5a0d-80ba-6f829797dd00 | note | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
f36e6abf-bed3-5353-9e59-a4ad9641e8b9 | note | Record documents (QCP - Quality Control Portal) - Site Diary
9332c3ff-202e-5b93-88e3-ead3bdb50e62 | note | Responsibility - Paving Contractor
99f8370b-75bc-5bd4-ad47-39c0b711b0f4 | note | Designer - I
bbee20ad-fd0b-5ccc-a841-47c55cfd0ac1 | note | Eng. Rep / NZTA - I
eb891ab2-f920-5379-9ede-5fb5e90fe112 | note | Contractor - R
e12bd076-8c67-4831-b29c-39f6c17e43b8 | checkpoint | 3.4 - Membrane Seal
7224e74d-6044-5e6c-97a2-c91a72ec9825 | note | Detail of Activity / Test - Application of Membrane Seal
8f084736-5029-5f97-917f-68fc4da53165 | note | Action (Hold, Monitor, Witness) - M
ee61a9f7-9533-56c9-bd3d-8eec3f2eae91 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
668e84ad-1424-5163-baed-93350e633628 | note | Inspection / Test method - Sealing Records
a1480090-af83-5267-a22b-8ddd209e44e7 | note | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
cc0b78dd-8931-5844-ae62-c6b88a539a3b | note | Record documents (QCP - Quality Control Portal) - Sealing Records
41947e4b-a983-5ac5-95cd-b70e7e7445ac | note | Responsibility - Paving Contractor
86c468f3-5b4f-5b8b-b0d5-8a97d2b74de6 | note | Designer - I
4fb71811-705d-55ed-977f-e772697aea67 | note | Eng. Rep / NZTA - I
e35d57cc-e77d-57aa-96e8-1c08879d8b74 | note | Contractor - R
24b9c218-4f7c-4603-a2eb-4b5b6b738677 | checkpoint | 3.5 - Temperature
63966eda-ad29-53aa-9acf-c9f9db93b6f4 | note | Detail of Activity / Test - Pavement Surface
aa58633a-0051-5934-befc-982b79a23cf0 | note | Action (Hold, Monitor, Witness) - M
214d0cda-442a-50d3-8d16-aac65377a511 | note | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
f1262e9a-e585-5771-8b51-b29c77207421 | note | Inspection / Test method - Infrared gauge
9a03ee9d-d875-519c-b898-9175d807a314 | note | Acceptance Criteria - ≥ 5°C for Structural, or as otherwise agreed with NZTA
52164595-94c0-5838-879b-fc6f580cd4e8 | note | Record documents (QCP - Quality Control Portal) - Site diary
ba6c5c47-cda0-528c-8173-85e5ae043a98 | note | Responsibility - Paving Contractor
0a6c8f2c-8e0d-55f9-81b9-658a64544fb6 | note | Project Specific Notes / Instructions - Must get NZTA approval if < 5°C for Structural
68dee379-169e-5330-a29c-e2337f1867b6 | note | Designer - I
7e7174f4-56f9-512d-b89f-ad8c9f380ae0 | note | Eng. Rep / NZTA - I
03f49151-951e-57a6-b8aa-909377fe37b5 | note | Contractor - R
b802b5c2-cb22-4c04-b148-d4428496bf0f | checkpoint | 3.6 - Temperature
0430b6e4-b83d-51eb-99fd-5aa5406aa038 | note | Detail of Activity / Test - Asphalt Delivery temperature
10aaf515-f5a9-5b6a-8ff5-e4457a54dbcb | note | Action (Hold, Monitor, Witness) - M
c8b4420c-47d6-5f11-8203-d3684286e7ef | note | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
f94fd2ca-af19-50c0-9fb0-4b81a4ca2c26 | note | Inspection / Test method - Temperature Probe
86aa65bd-e074-54f4-a900-3488d2878e50 | note | Acceptance Criteria - Target ≥ 170 deg.C. in the Paver
cf722ae6-9271-5768-b68a-7050309c7443 | note | ○ Min. ≥ 150 deg.C in the Paver
2caf6513-50d9-5e18-bd7c-298346c9d5d9 | note | ○ <130°C to be Rejected
916872fa-1ef7-5c13-8cf5-1bd796150073 | note | Record documents (QCP - Quality Control Portal) - Site Diary
86c920b2-b166-5bc9-9c4f-a86d87ff97c1 | note | Responsibility - Paving Contractor
92398f51-11b8-5981-ab20-ae1848761986 | note | Designer - I
a32f4992-6a2b-5007-bad5-3b1ee1b43e42 | note | Eng. Rep / NZTA - I
65be25d5-1ec7-5c01-864a-c805f56d6e9c | note | Contractor - R
31432bbd-ff7b-47fa-a5f8-557f6b0a3df7 | checkpoint | 3.7 - Temperature
39a3afd3-eb74-5a85-9cb8-4d10268fe1ef | note | Detail of Activity / Test - Compaction Temperature
90a9ce9b-1f8c-5edb-80ec-2f5acb097533 | note | Action (Hold, Monitor, Witness) - M
0f8eab28-3f2c-56aa-8e4d-f60e58938f33 | note | Minimum Test Frequency (Lot = 1 day’s production) - During compaction
07daafbb-3d6f-5688-8750-1090fc504d6d | note | Inspection / Test method - Temperature Probe/Infrared gauge
fe23a3c7-f3d2-5cfa-ab1e-1f6b2eb32123 | note | Acceptance Criteria - ≥ 135°C at commencement of compaction.
a2201a6b-a5eb-5107-bf58-9fd5908d5bb4 | note | ○ < 80°C - Stop Rolling
3c62043f-1848-5f39-b36c-4aa475ad9749 | note | Record documents (QCP - Quality Control Portal) - Site diary
60aea456-9ddb-5185-bef2-2e1f60e7af9e | note | Responsibility - Paving Contractor
6f31c68f-86fa-5cc6-8c91-12d22eec1ed7 | note | Designer - I
5eeff12c-76c0-56e2-921d-c7a51bb9d770 | note | Eng. Rep / NZTA - I
390b1df0-1140-575e-8bdd-1e4f21022741 | note | Contractor - R
8740551b-73bf-472e-b978-cf6fbcb4abae | checkpoint | 3.8 - Mat
8540b3f5-ddf9-56e3-a7f7-9937e8af32a5 | note | Detail of Activity / Test - Load Locate
921a27d0-611a-596d-b339-8799704d2f7a | note | Action (Hold, Monitor, Witness) - M
68ad4add-fffd-5569-8336-1bc1d885a20f | note | Minimum Test Frequency (Lot = 1 day’s production) - Each load
d70bc5bc-c461-522c-859c-02d842f8b149 | note | Inspection / Test method - M/32
de6dfb67-04bd-50da-975c-17cb11391a3c | note | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes:
229e92d8-5855-51c0-8d6b-c336ff2d5db7 | note | ○ Truck ID/Rego/Driver
842667c0-ebd0-598e-ba0b-8066eb1a2e19 | note | ○ Depart Plant Time
997c7620-6275-5662-acbe-8adfd44eeb67 | note | ○ Arrive Site Time
f4d78b80-f0ae-5d2c-8965-91e29df0083d | note | ○ AC Temp on Arrival
5a7a4f6a-41cd-5fa6-8785-49b5254ae889 | note | ○ Tonnage
7cf0539c-2e7e-5cae-ba75-469469d6e306 | note | ○ Run Width
615ff1aa-2539-54cc-976d-a992abbc1576 | note | ○ Estimated Run Length
20c03713-a8db-56d9-85ec-3b870bb5e521 | note | ○ Calculated Area
f8c5d3ab-2018-5aa5-9a47-6a38ad516542 | note | ○ Calculated Average Depth
f0986847-b71b-5b2e-841c-4cef512e8b59 | note | Record documents (QCP - Quality Control Portal) - Paving Run Sheet
d27e2751-2312-5a29-b25f-231ea74d7ac2 | note | Responsibility - Paving Contractor
02a0764c-4830-532a-a23a-33be63313712 | note | Designer - I
8d078699-0f16-5963-bedb-4fb2a46a404a | note | Eng. Rep / NZTA - I
c413b4b2-8c62-5cb0-b5e5-7cc6fd8376d3 | note | Contractor - R
8aa91572-1568-42c5-b646-0937f0b664d1 | checkpoint | 3.9 - Mat
831ffa94-e045-5ab2-b632-fbcdc612d358 | note | Detail of Activity / Test - Thickness Monitoring
ab186c82-2e14-5384-ac42-ab27eac1b58d | note | Action (Hold, Monitor, Witness) - M
6690ecda-4a41-5f0e-9d84-c7e0729af8e5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
9196144f-23c4-5d29-a6bf-a304a559f30e | note | Inspection / Test method - Dipping
52fd7fce-fb8c-55fc-9a52-8ed1cb9d9a10 | note | Acceptance Criteria - Target Loose Thickness -0mm / +10mm
627229cb-5b5f-5ed5-a900-469a35b7b524 | note | Record documents (QCP - Quality Control Portal) -
0a6e42e7-222f-58cb-b698-db6eee080b92 | note | Responsibility - Paving Contractor
134dea63-f6cf-545e-925b-a49dec89e2d7 | note | Project Specific Notes / Instructions -
0e41b252-9b89-57a3-a533-5176abb10e93 | note | Designer - I
fd040b3f-7af8-55b4-96d0-d27edfd0bbc9 | note | Eng. Rep / NZTA - I
392cdb93-c4e2-5186-bf6d-5c45c29cab41 | note | Contractor - R
c62d0248-a424-4640-9071-9791962c67f1 | checkpoint | 3.10 - Mat
2dc62e28-323d-5651-b853-d003cdae93eb | note | Detail of Activity / Test - Compaction - NDM
567206f9-3ba4-5ecf-9f29-a351d30f760d | note | Action (Hold, Monitor, Witness) - M
f679cbf4-aa4b-5c5a-b0c8-3daf31d3588e | note | Minimum Test Frequency (Lot = 1 day’s production) - Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density.
b08e2231-9c9f-54dd-8ed1-3d3ecd7dc9a6 | note | Inspection / Test method - Insitu density and air voids
af788528-af80-5bb4-9ae3-aca50d2d7107 | note | Acceptance Criteria - NZTA M/32:2021 - section 9.8
3babb303-b19a-5780-82b3-b93eaf4a6f7b | note | Record documents (QCP - Quality Control Portal) -
deddbf0c-404c-5a19-bcec-5af21e49e4ff | note | Responsibility - Paving Contractor
513813f1-8432-5a21-933c-1f872cfc3ad5 | note | Project Specific Notes / Instructions - Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used).
b666d327-d5c5-5a55-bf8a-bef581d87c73 | note | Designer - I
922a2caf-0419-5628-bd8d-a993ee6642f1 | note | Eng. Rep / NZTA - I
a4e8699f-d1b4-5223-a41e-6080c11ad7cc | note | Contractor - R
1ba56d8e-79e6-409e-9f0b-84248c55bc94 | checkpoint | 3.11 - Mat
aa971121-b942-5baf-8413-b725ec40ce2c | note | Detail of Activity / Test - Compaction
e9202e29-1ca7-5ffa-9752-9263dea1aa67 | note | Action (Hold, Monitor, Witness) - H
4a880ddd-c279-5cfe-8187-a887cd54767e | note | Minimum Test Frequency (Lot = 1 day’s production) - Mat: 1 per 300m2/min. 8 per Lot Joint: 1 per 100m/min. 3 per Lot, In the event of a day's production being > 30t but < 2400m2, then it will be permissable to reduce the number of cores to; Mat: 1 per 300m2 with a minimum of 4 per Lot, and Joint: 1/100m with a minimum of 3 per Lot
12f7b29c-26fd-5026-8c6c-17f667a8e235 | note | Inspection / Test method - Insitu density and air voids
709cd537-99c2-5c1f-8fd7-490921870e3b | note | Acceptance Criteria - NZTA M/32:2021 - section 9.8
4024956f-78f9-5533-b9f3-1ba9cf78808f | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
0da25091-9ef2-546f-ad69-6674ae4ae4a2 | note | Responsibility - Paving Contractor
84fa82e4-71b6-5c48-8cd5-e5cfc83912ea | note | Project Specific Notes / Instructions - A pavement lot shall be an essentially homogeneous section of work completed within a shift of production.
ee8a5a1c-6826-55fb-ae30-98fcca671dd4 | note | ○ The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process.
5e8517b8-18da-5b8e-8bbb-bcd5705f811e | note | Designer - A
b2aa2cc4-a226-5403-8a41-93d6d4964467 | note | Eng. Rep / NZTA - I
a51fc896-d579-5e99-adf7-368f929405f5 | note | Contractor - R
f38996ec-a64f-47d0-b061-bbe9f1ec9236 | signoff | AUTHORITY HOLDPOINT
a0137925-3fda-495f-8de6-791ba70dad65 | checkpoint | 3.12 - Mat
5f871131-70c7-5337-9682-181b760574d9 | note | Detail of Activity / Test - Thickness
b85add3a-e80d-5a46-a57b-f00b444de3d4 | note | Action (Hold, Monitor, Witness) - H
005cf495-c8cb-5498-b6ca-6d22d33ad291 | note | Minimum Test Frequency (Lot = 1 day’s production) - Average of 4 measurements per core
73d94051-c442-5e9a-9056-4d2266b01879 | note | Inspection / Test method - Measure Cores
68d61a9a-0d36-5c9b-a6de-24c515c7d714 | note | Acceptance Criteria - LCV ≥ Specified Depth (Minimum)
104014c3-3334-52d3-839e-93432848eb81 | note | ○ NZTA M/32:2021 - section 9.7
f8161459-2683-5af2-ae0c-334a0bf7c9d1 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
3504ca6d-eab1-5992-bcf7-9ed6d99673c2 | note | Responsibility - Paving Contractor
3eac6225-df98-51cc-916a-7617124dbfa8 | note | Designer - A
eb53a435-ee8a-59b4-a92b-3907f9aaa760 | note | Eng. Rep / NZTA - I
3b5acb7e-d20b-573a-a203-ddc1c4c8de75 | note | Contractor - R
9a3280d1-0a8c-4620-8758-b09e56e94ec4 | signoff | AUTHORITY HOLDPOINT
d068ff6e-8a93-42ae-811e-6a34d97dd546 | checkpoint | 3.13 - Mat
6c92c1d5-c421-5127-9f97-4d894bb4efc3 | note | Detail of Activity / Test - Shape
5bb0a0ef-fdfa-5c5d-a180-9f16b2bb019d | note | Action (Hold, Monitor, Witness) - M
4b4945a2-d7c2-5d4b-9a20-3b4c0e071eee | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
6c62f08d-9208-54ee-b3c5-5f54c73ee670 | note | Inspection / Test method - 3m Straight edge
72ae2e48-6f1f-5e31-9785-2c31352c3fe3 | note | Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/32:2021 - section 10.
a3c98b48-d2ef-5dbc-a2a6-81bd232a293e | note | ○ Not more than 5mm under a 3m Straight Edge.
94316749-0198-503d-a37e-804d3df1ac00 | note | Record documents (QCP - Quality Control Portal) - Straight Edge Record
f0c933eb-337a-5357-8424-1ff7898e9401 | note | Responsibility - Paving Contractor
19b73ecd-904a-54ef-ba45-7aa2798c4734 | note | Designer - I
d068f664-095e-5a5c-8030-1ec0b78c773b | note | Eng. Rep / NZTA - I
97958b05-69d2-54ee-9937-2992b5998287 | note | Contractor - R
c4be0577-a0e6-4e8a-ab50-cc4fc506e512 | checkpoint | 3.14 - Paving Quality
371b6438-f8c9-5e92-a466-adde7a8e9fc4 | note | Detail of Activity / Test - Texture
3cbe6af0-c011-55ad-8b14-f26b1963a444 | note | Action (Hold, Monitor, Witness) - M
51d3d0c1-96ff-58e3-bb19-8c6b795f234e | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
28776931-19a7-5408-80b5-fad0d7de28b4 | note | Inspection / Test method - Sand Circle or HSD
2f402eff-d6ff-53ce-aca9-73d6e6ca78c9 | note | Acceptance Criteria - NZTA T/10: 2013
2f540103-a60d-5703-b886-0958e0b41e6f | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
ecaeea30-a272-5d69-b5d0-252242584d7c | note | Responsibility - Paving Contractor
dc57e6d2-264f-54d7-8678-2fe6332e5623 | note | Project Specific Notes / Instructions - Only required if EME will be the final wearing course or final road surface.
1f92323a-a9e5-5954-9556-a06dde07acff | note | Designer - I
9080cc7c-8cac-5005-9236-0a29e44c1e45 | note | Eng. Rep / NZTA - I
ed699ea2-c427-5f99-ace3-aacbbaf941d2 | note | Contractor - R
31a01cf7-bcf2-4e47-82fb-842def0af169 | checkpoint | 3.15 - Paving Quality
04af0a65-cc3a-514e-99dc-ee1d55d01e7d | note | Detail of Activity / Test - Level
76059fdf-1e26-52c1-9079-dc5e53483a8c | note | Action (Hold, Monitor, Witness) - M
2d1c321f-7b6d-5d03-9c42-1e695d0107c6 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
b85c0481-f74c-5d34-9f81-1abc9577382f | note | Inspection / Test method - As Built Survey
35685de4-22b7-5d8f-8871-b4ad37921fb5 | note | Acceptance Criteria - The level at the top of each layer of EME 2 shall not be less than or more than 10mm higher than the specified level.
cb3fa4d3-8b84-52a0-b3f3-a71f922eb78a | note | ○ NZTA M/32:2021 - section 10.1
d0979bb0-72b6-512d-b498-e12ccca062ba | note | Record documents (QCP - Quality Control Portal) - Survey As builts
1bb5d83d-c8ae-5567-88b0-eecfd10a6d5d | note | Responsibility - Paving Contractor
242bf0fb-9892-5ebb-a7c1-d4708bf81fac | note | Project Specific Notes / Instructions - Only required if EME will be the final wearing course or final road surface.
5f96af32-0938-5152-92b2-89c029360283 | note | Designer - I
9dc46bf8-1028-5c4f-aba0-12a0fd5d6ce4 | note | Eng. Rep / NZTA - I
9c0667aa-986d-5d1d-9201-dcd8b22087b0 | note | Contractor - R
0489f6be-ed10-40ae-a7ee-34b8e6c468bf | checkpoint | 3.16 - Paving Quality
5436b9ad-a781-5114-93f7-02105d778182 | note | Detail of Activity / Test - Alignment
ffefe8b7-8fcf-51c4-8b3a-1b62ace41ecf | note | Action (Hold, Monitor, Witness) - M
1c33fef6-81d7-56bd-891a-568f6d0e3044 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
0847d910-94a3-531a-8ae9-f49a4586b86e | note | Inspection / Test method - As Built Survey
e4e1eb9e-63d9-591a-bf1c-85d630ac36d9 | note | Acceptance Criteria - ±50 mm from drawings
ba2b9271-6bcf-51aa-bdba-7af8cc2223d4 | note | ○ NZTA M/32:2021 - section 10.2
9c86a40b-dc32-524b-9e4a-e023605de296 | note | Record documents (QCP - Quality Control Portal) - Survey As builts
ab0d067e-e639-5037-a3cc-09d9498eb1d3 | note | Responsibility - Paving Contractor
cc4ac071-2507-5e36-8fdb-404c5c173bbb | note | Project Specific Notes / Instructions - Only required if EME will be the final wearing course or final road surface.
096e571f-8fca-5bca-8a3f-17360999f049 | note | Designer - I
9693139e-faaa-570b-aa67-62ec3577ed11 | note | Eng. Rep / NZTA - I
3ddc1189-1f21-54ed-a4a6-738180f1b4e4 | note | Contractor - R
a8c65870-3178-4484-bac7-e1150d06121b | checkpoint | 3.17 - Post Paving Completion Checks
9660340e-4ad3-5112-9316-0b7090a1e332 | note | Detail of Activity / Test - Site clear and cleanup
0a834401-1849-5d09-baba-4954a0253a1f | note | Action (Hold, Monitor, Witness) - W
836e8a33-c336-51f9-b04f-4a4aa954a7f0 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
8cbe02fe-239c-5b04-80a6-25ca61bbe433 | note | Inspection / Test method - Visual
09fba06d-7924-534f-9f94-afe6713e5059 | note | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
4f658545-54f2-5c10-9470-e6bd71f49ae0 | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
59eb29e1-f8e9-5a17-85f7-514e38a647c5 | note | Responsibility - Paving Contractor
6d8d7f1b-4d56-5684-bbd7-45e280cba1c2 | note | Eng. Rep / NZTA - I
eaaf2622-ff7a-5580-81f4-09b58aa523c9 | note | Contractor - R
24753725-9c63-4536-a5eb-86897ac70731 | checkpoint | 3.18 - Post Paving Completion Checks
e0f751f0-5b9e-5171-a637-dc1750328e84 | note | Detail of Activity / Test - Pavement Marking
c9be0203-a3f9-58b2-8451-daf7c958063e | note | Action (Hold, Monitor, Witness) - W
0c405dce-eb30-5947-876e-9af65cfe0df5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
f67baf67-841b-501d-a94d-183a01539925 | note | Inspection / Test method - Visual
6cfd85a3-19a3-59b9-ab67-47f24f223cdc | note | Acceptance Criteria - Roadmarking is complete
65427d92-d62a-5dfd-a0c4-9a9450b26e80 | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
9c20f048-7082-53a4-85e0-3e2247f50dc0 | note | Responsibility - Paving Contractor
b4efca23-2a1d-5b68-892d-5bca02b0f19b | note | Eng. Rep / NZTA - I
2165a6bb-776c-56d8-a102-64be6dcf9499 | note | Contractor - R
28eb9ffb-4d17-42c9-b301-df0ec8e4e505 | checkpoint | 3.19 - Post Paving Completion Checks
c2d9119d-ad4e-5d3f-a663-ad63b337d3c1 | note | Detail of Activity / Test - Cold Joint Bandaging
ed18e43b-62db-54f4-859a-c677e2509f57 | note | Action (Hold, Monitor, Witness) - W
66ae5a2b-8cbc-5330-b0ed-c77f4a284ded | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
e0675c13-18ca-54a8-9093-6839c3b512bb | note | Inspection / Test method - Visual
5eb73fbe-64ab-5daa-b6b9-2f9da0088b21 | note | Acceptance Criteria - Cold joint bandaging is complete
90a8a799-346c-529d-ad2b-e6e9a8e6a160 | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
9d222f77-add3-528e-a89b-63a3d0510d35 | note | Responsibility - Paving Contractor
1b9bdfd4-1144-5109-be2c-d75d58014494 | note | Eng. Rep / NZTA - I
610ad4bc-29a0-5d7e-be59-a3def38713b2 | note | Contractor - R
b2f33ee2-74b5-4dca-bfa2-742cf9f0cb0c | checkpoint | 3.20 - Post Paving Completion Checks
1a2b0de3-a55c-5769-9a2c-a09966be10e9 | note | Detail of Activity / Test - Service Covers Checked
40e960d8-3504-5b61-b1ae-f3f424926195 | note | Action (Hold, Monitor, Witness) - W
ba956f2d-2c78-5bc6-ae07-231d0ea69ffd | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
fa823aee-c38b-5679-b9d1-7cb90c4278f4 | note | Inspection / Test method - Visual
7fd9d4be-fcbc-5c2b-9993-e00109ec4da9 | note | Acceptance Criteria - Check that service covers are cleared and level with the pavement
df627163-5941-5a4e-9f91-02f83f43e8a6 | note | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
c717e6ec-20a4-5875-9608-1275990cb9bc | note | Responsibility - Paving Contractor
3e099201-c13d-5a35-941b-65e96e5b10a9 | note | Eng. Rep / NZTA - I
256216c1-dbe7-5061-a2c9-f5cfce0f2209 | note | Contractor - R
e1a70cd2-d1ee-4603-a4d2-decba17065ad | checkpoint | 3.21 - Post Paving Completion Checks
e3fcea5d-4889-5c49-9ea6-9262126e087e | note | Detail of Activity / Test - Traffic Loops Reinstated
00a8e80c-8445-55cf-9f9f-1012f0ea99e7 | note | Action (Hold, Monitor, Witness) - W
2c9b15df-8b95-5518-8fbe-781d15053e48 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
f9ecfcc5-7816-5b7e-b625-067abb14cb6c | note | Inspection / Test method - Visual
a17d6e05-0d9d-5954-96e1-3bf81e781e29 | note | Acceptance Criteria - Check that affected traffic loops have been reinstated
6385961e-671e-5786-b4c8-5c08f4e4f43d | note | Record documents (QCP - Quality Control Portal) - Communication
9bfb1325-78df-5197-a08b-7453e1f49511 | note | Responsibility - Paving Contractor
0e1484ab-10b8-5660-8437-9255bb873ade | note | Eng. Rep / NZTA - I
81fb8be2-dd9b-5b46-b5fa-de05a2084f0b | note | Contractor - R
6ffeee71-e781-41c6-818a-f813a6343d9e | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e82a31fd-e432-588e-8536-5efd7949df97 | textbox | Contractor's Rep Name:
eb34c9e2-89c2-5655-84eb-e8398a1b77d3 | textbox | Engineer's Rep. Name:
32aa4eb7-e75e-5098-b616-1ab20b0d8958 | date | Date:
5b0b1f84-0af7-4204-bf36-78264f830afd | signoff | Add Signature