## Sheet1
2.01 | Setout section | Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | H | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor | — | 3741 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | Electronic survey files (Quality Control Testing) | — | 2.01 - Setout section | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to each section | Inspection / Test method - Survey | Acceptance Criteria - Document existing furniture | Record documents (QCP - Quality Control Portal) - Electronic survey files | Responsibility - Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3741 | IDC specifications Frequency - — | Testing Type - Site Survey | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - Electronic survey files (Quality Control Testing) | Comments - — | 2.01 - Setout section
2.02 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Use grader's machine control and inspect shape | — | N/A | Stabilising Contractor | Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement | 3741 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe. | 2.02 - Pre-hoe, shape and proof roll | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to stabilisation per section | Inspection / Test method - Use grader's machine control and inspect shape | Acceptance Criteria - — | Record documents (QCP - Quality Control Portal) - N/A | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement | IDC - RFT Schedule of Price - 3741 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality Control Testing | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe. | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
2.03 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Visual check or Vibratory Roller's response meter | — | Stabilising Contractor confirm no obvious soft areas found | Stabiliisng Contractor | Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions | 3741 | self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller. | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe. | 2.03 - Pre-hoe, shape and proof roll | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to stabilisation per section | Inspection / Test method - Visual check or Vibratory Roller's response meter | Acceptance Criteria - — | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found | Responsibility - Stabiliisng Contractor | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions | IDC - RFT Schedule of Price - 3741 | IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller. | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality Control Testing | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe. | Action (Hold, Monitor, Witness) - H
2.04 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | 3741 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 2.04 - Compaction | Detail of Activity / Test - Plateau Density Test | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Inspection / Test method - Draft NZTA T/24 (Aug-2024) | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | IDC - RFT Schedule of Price - 3741 | IDC specifications Frequency - NZTA T23 | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Minimum Test Frequency - Prior to each section
2.05 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | 3741 | 5000 m2 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 2.05 - Compaction | Detail of Activity / Test - Maximum Dry Density | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | Inspection / Test method - NZS 4402.4.1.3 | Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | IDC - RFT Schedule of Price - 3741 | IDC specifications Frequency - 5000 m2 | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Inspection / Test method - Survey
2.06 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Stabilising Contractor | — | 3741 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 2.06 - Compaction | Detail of Activity / Test - Degree of Compaction (DoC) | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 5 per 1,000m2 | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth) | Acceptance Criteria - Average DoC ≥ 95% Minimum DoC ≥ 92% | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3741 | IDC specifications Frequency - — | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Acceptance Criteria - Document existing furniture
2.07 | Overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to stabilisation per section | Survey | As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Drawing Showing levels and crossfalls | Stabilising Contractor with Main Contractor | This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. | 3721 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay. | 2.07 - Overlay and check levels | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to stabilisation per section | Inspection / Test method - Survey | Acceptance Criteria - As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls | Responsibility - Stabilising Contractor with Main Contractor | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. | IDC - RFT Schedule of Price - 3721 | IDC specifications Frequency - — | Testing Type - Site Survey | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - DWG File and drawing pdf (Quality Control Testing) | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay. | Record documents (QCP - Quality Control Portal) - Electronic survey files
2.08 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Stabilising Contractor | — | 3721 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² /ton rate for unbound overlay. | 2.08 - Production Plan | Detail of Activity / Test - Plan showing cut lines and sequencing of works | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to each section | Inspection / Test method - Daily Report | Acceptance Criteria - Points covered in NZTA B/5 | Record documents (QCP - Quality Control Portal) - Daily Production Plan | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3721 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay. | Responsibility - Contractor
3.04 | Weather conditions | Material behind stabiliser | M | Prior to spreading | Measurement | Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C | Daily work Log | Stabilsing Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.04 - Weather conditions | Detail of Activity / Test - Material behind stabiliser | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to spreading | Inspection / Test method - Measurement | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilsing Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | Project Specific Notes / Instructions - —
3.05 | Weather conditions | Wind | M | Prior to spreading cement or lime | Local weather stations | Wind speed CHAR(LESS) 25 km/hr | Daily work Log | Stabilsing Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.05 - Weather conditions | Detail of Activity / Test - Wind | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to spreading cement or lime | Inspection / Test method - Local weather stations | Acceptance Criteria - Wind speed CHAR(LESS) 25 km/hr | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilsing Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | IDC - RFT Schedule of Price - 3741
3.06 | Weather conditions | Rain | M | Prior to spreading cement or lime | Local weather stations | No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Daily work Log | Stabilsing Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.06 - Weather conditions | Detail of Activity / Test - Rain | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to spreading cement or lime | Inspection / Test method - Local weather stations | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilsing Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | IDC specifications Frequency - —
3.07 | Spreading of powdered stabilising agent (Cement / Lime) | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | M | every 400 m2 every 150m for a 2.4m width | Weigh mat or tray | ± 0.5kg/m2 of specified rate | Daily work Log | Stabilising Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.07 - Spreading of powdered stabilising agent (Cement / Lime) | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - every 400 m2 every 150m for a 2.4m width | Inspection / Test method - Weigh mat or tray | Acceptance Criteria - ± 0.5kg/m2 of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | Testing Type - Site Survey
3.08 | Spreading of powdered stabilising agent (Cement / Lime) | Compare area spread with weight used for each spreader load | M | On-going measurement by computer/load cells | Measurement each run | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.08 - Spreading of powdered stabilising agent (Cement / Lime) | Detail of Activity / Test - Compare area spread with weight used for each spreader load | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On-going measurement by computer/load cells | Inspection / Test method - Measurement each run | Acceptance Criteria - ± 2.5% of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | Testing Responsibility - Subcontractor (Physical Works)
3.09 | Injection of bituminous stabilising agent (FBS or BE) | Flow meter and operator's display readings | M | Continous monitoring by the operator and the grounds person | Visual display reading | ± 5% of specified rate | N/A | Stabilising Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.09 - Injection of bituminous stabilising agent (FBS or BE) | Detail of Activity / Test - Flow meter and operator's display readings | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Continous monitoring by the operator and the grounds person | Inspection / Test method - Visual display reading | Acceptance Criteria - ± 5% of specified rate | Record documents (QCP - Quality Control Portal) - N/A | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | Paid by - Subcontractor
3.1 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from the stabiiser's PCU) with the measured area | M | Record usage from PCU at the end of each run | Record readings at the end of each run | ± 3% of specified rate | Daily work Log | Stabilising Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.1 - Injection of bituminous stabilising agent (FBS or BE) | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Record usage from PCU at the end of each run | Inspection / Test method - Record readings at the end of each run | Acceptance Criteria - ± 3% of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | Certification Type - Electronic survey files (Quality Control Testing)
3.11 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from delivery docket) with measured area | M | For each bitumen tanker load | Dip bitumen tanker before and after | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.11 - Injection of bituminous stabilising agent (FBS or BE) | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - For each bitumen tanker load | Inspection / Test method - Dip bitumen tanker before and after | Acceptance Criteria - ± 2.5% of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | Comments - —
3.12 | Injection CHAR(AMP) Mixing of Water | In-situ Stabilisation process | M | On-going visual assessment | Visual and hand squeeze test | Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Daily work Log | Stabilising Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.12 - Injection CHAR(AMP) Mixing of Water | Detail of Activity / Test - In-situ Stabilisation process | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On-going visual assessment | Inspection / Test method - Visual and hand squeeze test | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | 2.02 - Pre-hoe, shape and proof roll
3.13 | Depth of stabilisation | Depth of stabilisation | M | Every 200m | Measurement | +15mm / -5mm from specified depth | Daily work Log | Stabilising Contractor | — | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | 3.13 - Depth of stabilisation | Detail of Activity / Test - Depth of stabilisation | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Every 200m | Inspection / Test method - Measurement | Acceptance Criteria - +15mm / -5mm from specified depth | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance Testing | Comments - Allowance to be made when building up a m² for stabilisastion. | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
3.15 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | 3712 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 3.15 - Compaction | Detail of Activity / Test - Plateau Density Test | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Inspection / Test method - Draft NZTA T/24 (Aug-2024) | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - NZTA T23 | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Action (Hold, Monitor, Witness) - H
3.16 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | 3712 | 5000 m2 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 3.16 - Compaction | Detail of Activity / Test - Maximum Dry Density | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | Inspection / Test method - NZS 4402.4.1.3 | Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - 5000 m2 | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Minimum Test Frequency - Prior to stabilisation per section
3.17 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 98% Minimum DoC ≥ 95% | IANZ Report | Stabilising Contractor | — | 3712 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 3.17 - Compaction | Detail of Activity / Test - Degree of Compaction (DoC) | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 5 per 1,000m2 | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth) | Acceptance Criteria - Average DoC ≥ 98% Minimum DoC ≥ 95% | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Inspection / Test method - Use grader's machine control and inspect shape
3.18 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Clegg Impact Value | H | 5 per 1000m2 | — | CIV ≥ 50 | CIV form - ConQA | Stabilising Contractor | — | 3712 | Not mentioned in IDM specs | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 3.18 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Detail of Activity / Test - Clegg Impact Value | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 5 per 1000m2 | Inspection / Test method - — | Acceptance Criteria - CIV ≥ 50 | Record documents (QCP - Quality Control Portal) - CIV form - ConQA | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - Not mentioned in IDM specs | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Acceptance Criteria - —
3.19 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Degree of Saturation, DOS | M | 5 per 1000m2 | NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | aim for DOS ≤ 80% | IANZ report | Contractor | Report only | 3712 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Detail of Activity / Test - Degree of Saturation, DOS | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - 5 per 1000m2 | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | Acceptance Criteria - aim for DOS ≤ 80% | Record documents (QCP - Quality Control Portal) - IANZ report | Responsibility - Contractor | Project Specific Notes / Instructions - Report only | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Record documents (QCP - Quality Control Portal) - N/A
4.01 | Finished Pavement | Crossfall | H | every 20m | Measurement | ± 0.5% of specified crossfall measure 2m apart | Survey | Stabilising Contractor | — | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion. | 4.01 - Finished Pavement | Detail of Activity / Test - Crossfall | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - every 20m | Inspection / Test method - Measurement | Acceptance Criteria - ± 0.5% of specified crossfall measure 2m apart | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - Site Survey | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - DWG File and drawing pdf (Quality Control Testing) | Comments - Allowance to be made when building up a m² for stabilisastion. | Responsibility - Stabilising Contractor
4.02 | Finished Pavement | Stabilised width | H | 1 every 20m | Measurement | -20mm, +100mm | Survey | Stabilising Contractor | — | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion. | 4.02 - Finished Pavement | Detail of Activity / Test - Stabilised width | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 every 20m | Inspection / Test method - Measurement | Acceptance Criteria - -20mm, +100mm | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - Site Survey | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - DWG File and drawing pdf (Quality Control Testing) | Comments - Allowance to be made when building up a m² for stabilisastion. | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
4.03 | Finished Pavement | Surface Shape | H | every 20m | Measurement | CHAR(LESS) 10mm using 3m straight edge | Survey | Stabilising Contractor | Only required if the visual inspection appears unsatisfactory | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion. | 4.03 - Finished Pavement | Detail of Activity / Test - Surface Shape | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - every 20m | Inspection / Test method - Measurement | Acceptance Criteria - CHAR(LESS) 10mm using 3m straight edge | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - Site Survey | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - DWG File and drawing pdf (Quality Control Testing) | Comments - Allowance to be made when building up a m² for stabilisastion. | IDC - RFT Schedule of Price - 3741
4.04 | Finished Pavement | Surface Finish | H | Per Lot | Visual | 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Survey | Stabilising Contractor | ER to be present at pre-seal inspection | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together. | 4.04 - Finished Pavement | Detail of Activity / Test - Surface Finish | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Per Lot | Inspection / Test method - Visual | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - ER to be present at pre-seal inspection | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - — | Testing Type - On site Inspections | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - In house inspection record - Quality assurance testing | Comments - Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together. | IDC specifications Frequency - —
4.05 | Finished Pavement | Roughness | H | Before Sealing | TNZ TM 7003 v1 | 100m rolling average ≤ 75 counts/km | Test Certificate | Contractor | — | 3712 | 1 Test per Site | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | 4.05 - Finished Pavement | Detail of Activity / Test - Roughness | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Before Sealing | Inspection / Test method - TNZ TM 7003 v1 | Acceptance Criteria - 100m rolling average ≤ 75 counts/km | Record documents (QCP - Quality Control Portal) - Test Certificate | Responsibility - Contractor | Project Specific Notes / Instructions - — | IDC - RFT Schedule of Price - 3712 | IDC specifications Frequency - 1 Test per Site | Testing Type - Site Testing | Testing Responsibility - Subcontractor (Physical Works) | Paid by - Subcontractor | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Comments - Allowance to be made under a separate line item for m² rate for site testing. | Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality Control Testing
Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
2.03 - Pre-hoe, shape and proof roll
Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Prior to stabilisation per section
Inspection / Test method - Visual check or Vibratory Roller's response meter
Acceptance Criteria - —
Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
Responsibility - Stabiliisng Contractor
Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
IDC - RFT Schedule of Price - 3741
IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller.
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality Control Testing
Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
2.04 - Compaction
Detail of Activity / Test - Plateau Density Test
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
Inspection / Test method - Draft NZTA T/24 (Aug-2024)
Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
IDC - RFT Schedule of Price - 3741
IDC specifications Frequency - NZTA T23
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
2.05 - Compaction
Detail of Activity / Test - Maximum Dry Density
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
Inspection / Test method - NZS 4402.4.1.3
Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
IDC - RFT Schedule of Price - 3741
IDC specifications Frequency - 5000 m2
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
2.06 - Compaction
Detail of Activity / Test - Degree of Compaction (DoC)
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 5 per 1,000m2
Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
Acceptance Criteria - Average DoC ≥ 95% Minimum DoC ≥ 92%
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3741
IDC specifications Frequency - —
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
2.07 - Overlay and check levels
Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Prior to stabilisation per section
Inspection / Test method - Survey
Acceptance Criteria - As per NZTA Z/16 Minimum: -5mm Maximum: +15mm
Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
Responsibility - Stabilising Contractor with Main Contractor
Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc.
IDC - RFT Schedule of Price - 3721
IDC specifications Frequency - —
Testing Type - Site Survey
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - DWG File and drawing pdf (Quality Control Testing)
Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
2.08 - Production Plan
Detail of Activity / Test - Plan showing cut lines and sequencing of works
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to each section
Inspection / Test method - Daily Report
Acceptance Criteria - Points covered in NZTA B/5
Record documents (QCP - Quality Control Portal) - Daily Production Plan
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3721
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
3.04 - Weather conditions
Detail of Activity / Test - Material behind stabiliser
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to spreading
Inspection / Test method - Measurement
Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilsing Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.05 - Weather conditions
Detail of Activity / Test - Wind
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to spreading cement or lime
Inspection / Test method - Local weather stations
Acceptance Criteria - Wind speed CHAR(LESS) 25 km/hr
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilsing Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.06 - Weather conditions
Detail of Activity / Test - Rain
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to spreading cement or lime
Inspection / Test method - Local weather stations
Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilsing Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.07 - Spreading of powdered stabilising agent (Cement / Lime)
Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - every 400 m2 every 150m for a 2.4m width
Inspection / Test method - Weigh mat or tray
Acceptance Criteria - ± 0.5kg/m2 of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.08 - Spreading of powdered stabilising agent (Cement / Lime)
Detail of Activity / Test - Compare area spread with weight used for each spreader load
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On-going measurement by computer/load cells
Inspection / Test method - Measurement each run
Acceptance Criteria - ± 2.5% of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.09 - Injection of bituminous stabilising agent (FBS or BE)
Detail of Activity / Test - Flow meter and operator's display readings
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Continous monitoring by the operator and the grounds person
Inspection / Test method - Visual display reading
Acceptance Criteria - ± 5% of specified rate
Record documents (QCP - Quality Control Portal) - N/A
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.1 - Injection of bituminous stabilising agent (FBS or BE)
Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Record usage from PCU at the end of each run
Inspection / Test method - Record readings at the end of each run
Acceptance Criteria - ± 3% of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.11 - Injection of bituminous stabilising agent (FBS or BE)
Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - For each bitumen tanker load
Inspection / Test method - Dip bitumen tanker before and after
Acceptance Criteria - ± 2.5% of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.12 - Injection CHAR(AMP) Mixing of Water
Detail of Activity / Test - In-situ Stabilisation process
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On-going visual assessment
Inspection / Test method - Visual and hand squeeze test
Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.13 - Depth of stabilisation
Detail of Activity / Test - Depth of stabilisation
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Every 200m
Inspection / Test method - Measurement
Acceptance Criteria - +15mm / -5mm from specified depth
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance Testing
Comments - Allowance to be made when building up a m² for stabilisastion.
3.15 - Compaction
Detail of Activity / Test - Plateau Density Test
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
Inspection / Test method - Draft NZTA T/24 (Aug-2024)
Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - NZTA T23
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
3.16 - Compaction
Detail of Activity / Test - Maximum Dry Density
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
Inspection / Test method - NZS 4402.4.1.3
Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - 5000 m2
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
3.17 - Compaction
Detail of Activity / Test - Degree of Compaction (DoC)
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 5 per 1,000m2
Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
Acceptance Criteria - Average DoC ≥ 98% Minimum DoC ≥ 95%
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
3.18 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
Detail of Activity / Test - Clegg Impact Value
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 5 per 1000m2
Inspection / Test method - —
Acceptance Criteria - CIV ≥ 50
Record documents (QCP - Quality Control Portal) - CIV form - ConQA
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - Not mentioned in IDM specs
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
Detail of Activity / Test - Degree of Saturation, DOS
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - 5 per 1000m2
Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
Acceptance Criteria - aim for DOS ≤ 80%
Record documents (QCP - Quality Control Portal) - IANZ report
Responsibility - Contractor
Project Specific Notes / Instructions - Report only
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.
4.01 - Finished Pavement
Detail of Activity / Test - Crossfall
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - every 20m
Inspection / Test method - Measurement
Acceptance Criteria - ± 0.5% of specified crossfall measure 2m apart
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - Site Survey
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - DWG File and drawing pdf (Quality Control Testing)
Comments - Allowance to be made when building up a m² for stabilisastion.
4.02 - Finished Pavement
Detail of Activity / Test - Stabilised width
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 every 20m
Inspection / Test method - Measurement
Acceptance Criteria - -20mm, +100mm
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - Site Survey
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - DWG File and drawing pdf (Quality Control Testing)
Comments - Allowance to be made when building up a m² for stabilisastion.
4.03 - Finished Pavement
Detail of Activity / Test - Surface Shape
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - every 20m
Inspection / Test method - Measurement
Acceptance Criteria - CHAR(LESS) 10mm using 3m straight edge
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - Site Survey
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - DWG File and drawing pdf (Quality Control Testing)
Comments - Allowance to be made when building up a m² for stabilisastion.
4.04 - Finished Pavement
Detail of Activity / Test - Surface Finish
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Per Lot
Inspection / Test method - Visual
Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - ER to be present at pre-seal inspection
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - —
Testing Type - On site Inspections
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - In house inspection record - Quality assurance testing
Comments - Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together.
4.05 - Finished Pavement
Detail of Activity / Test - Roughness
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Before Sealing
Inspection / Test method - TNZ TM 7003 v1
Acceptance Criteria - 100m rolling average ≤ 75 counts/km
Record documents (QCP - Quality Control Portal) - Test Certificate
Responsibility - Contractor
Project Specific Notes / Instructions - —
IDC - RFT Schedule of Price - 3712
IDC specifications Frequency - 1 Test per Site
Testing Type - Site Testing
Testing Responsibility - Subcontractor (Physical Works)
Paid by - Subcontractor
Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
Comments - Allowance to be made under a separate line item for m² rate for site testing.