## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Pavement Renewal - Stabilisation | itp |  |  |  |  | ITP - Pavement Renewal - Stabilisation
section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Crushing Resistance
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 10,000 m3
label | Inspection / Test method - NZS4407:3.10
label | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3721 and 3731
label | Testing Type - Material Testing
label | Responsibility - Aggregate Supplier (Quarry)
label | Paid by - Quarry
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Maximum Wet/Dry Strength
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 10,000 m3
label | Inspection / Test method - NZS4407:3.10 & AS 1141.22
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3721 and 3731
label | Testing Type - Material Testing
label | Responsibility - Aggregate Supplier (Quarry)
label | Paid by - Quarry
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Weathering Quality Index
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 10,000 m3
label | Inspection / Test method - NZS4407:3.11
label | Acceptance Criteria - AA, AB, AC, BA, BB, CA
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3721 and 3731
label | Testing Type - Material Testing
label | Responsibility - Aggregate Supplier (Quarry)
label | Paid by - Quarry
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 10,000 m3
label | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
label | Acceptance Criteria - Compacted using NZ Vibe Hammer
label | ○ 4-day soaked CBR ≥ 80%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3721 and 3731
label | Testing Type - Material Testing
label | Responsibility - Aggregate Supplier (Quarry)
label | Paid by - Quarry
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
label | Acceptance Criteria - PI ≤ 5, CI ≤ 3
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - NZTA M04: 2024
label | ○ AP40 - Class 2
label | ○ PI and CI applies
label | IDC - RFT Schedule of Price - 3721 and 3731
label | Testing Type - Material Testing
label | Responsibility - Aggregate Supplier (Quarry)
label | Paid by - Quarry
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Broken Faces Content
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.14
label | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
label | IDC - RFT Schedule of Price - 3721 and 3731
label | Testing Type - Material Testing
label | Responsibility - Aggregate Supplier (Quarry)
label | Paid by - Quarry
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - NZTA M04:2024-Class 2
label | ○ Class 2 in Table 12 for PSD
label | ○ Table 13 for shape control
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3721 and 3731
label | Testing Type - Material Testing
label | Responsibility - Aggregate Supplier (Quarry)
label | Paid by - Quarry
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Blend Particle Size Distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
label | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
label | Testing Type - Design Testing
label | Responsibility - Designer
label | Paid by - Professional Services
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - In this case, professional services contractor to manage this scope of testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Indirect Tensile Strength, ITS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 Optimisation test per aggregate type
label | Inspection / Test method - NZTA T/19: 2020
label | Acceptance Criteria - Testing at 1mm/min:
label | ○ BSM Dry ITS: 175 kPa to 400 kPa
label | ○ BSM Soaked ITS: 150 kPa to 350 kPa
label | Testing at 50.8mm/min:
label | ○ BSM Dry ITS: 210 kPa to 480 kPa
label | ○ BSM Soaked ITS: 180 kPa to 450 kPa
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Designer to advise on binder content(s)
label | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
label | Testing Type - Design Testing
label | Responsibility - Designer
label | Paid by - Professional Services
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - In this case, professional services contractor to manage this scope of testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Unconfined Compressive Strength, UCS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 Optimisation test per aggregate type
label | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
label | Acceptance Criteria - UCS limits set by the design engineeer
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Designer to advise on binder content(s)
label | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
label | Testing Type - Design Testing
label | Responsibility - Designer
label | Paid by - Professional Services
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - In this case, professional services contractor to manage this scope of testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Modified Maximum Dry Density
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Single Point DD vs WC during optimisation test
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - To determine target density
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Required before Stabilisation commences
label | Testing Type - Design Testing
label | Responsibility - Designer
label | Paid by - Professional Services
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - In this case, professional services contractor to manage this scope of testing.
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. BEFORE CEMENT STABILISATION STARTS
checkpoint | 2.01 - Setout section
label | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Document existing furniture
label | Record documents (QCP - Quality Control Portal) - Electronic survey files
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3741
label | Testing Type - sITE sURVEY
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - DWG File and drawing pdf (Quality Control Testing)
label | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe, shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Use grader's machine control and inspect shape
label | Record documents (QCP - Quality Control Portal) - N/A
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
label | IDC - RFT Schedule of Price - 3741
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality Control Testing
label | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe, shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Visual check or Vibratory Roller's response meter
label | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
label | Responsibility - Stabiliisng Contractor
label | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
label | IDC - RFT Schedule of Price - 3741
label | IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller.
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality Control Testing
label | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Compaction
label | Detail of Activity / Test - Plateau Density Test
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
label | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
label | ○ IANZ report when processed
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
label | IDC - RFT Schedule of Price - 3741
label | IDC specifications Frequency - NZTA T23
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction
label | Detail of Activity / Test - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
label | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
label | IDC - RFT Schedule of Price - 3741
label | IDC specifications Frequency - 5000 m2
label | ○ TNZ B/5: Section 7.7.1
label | ○ NZTA B/7: Section 8.1
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 2.06 - Compaction
label | Detail of Activity / Test - Degree of Compaction (DoC)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
label | Acceptance Criteria - Average DoC ≥ 95%
label | ○ Minimum DoC ≥ 92%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3741
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Overlay and check levels
label | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Survey
label | Acceptance Criteria - As per NZTA Z/16
label | ○ Minimum: -5mm
label | ○ Maximum: +15mm
label | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
label | Responsibility - Stabilising Contractor with Main Contractor
label | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
label | — overlay aggregate quality / consistency
label | — moisture content
label | — any concerns with shape and tie in
label | — etc.
label | IDC - RFT Schedule of Price - 3721
label | Testing Type - Site survey
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - DWG File and drawing pdf (Quality Control Testing)
label | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Production Plan
label | Detail of Activity / Test - Plan showing cut lines and sequencing of works
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Daily Report
label | Acceptance Criteria - Points covered in NZTA B/5
label | Record documents (QCP - Quality Control Portal) - Daily Production Plan
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3721
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
section | 3.0. CEMENT STABILISATION OPERATION
checkpoint | 3.03 - Weather conditions
label | Detail of Activity / Test - Material behind stabiliser
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading
label | Inspection / Test method - Measurement
label | Acceptance Criteria - Material after stabilisation:
label | ○ Cement - 5°C, Lime - 10°C, Cement/Lime - 10°C
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.04 - Weather conditions
label | Detail of Activity / Test - Wind
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - Wind speed < 25 km/hr
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.05 - Weather conditions
label | Detail of Activity / Test - Rain
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.06 - Spreading of powdered stabilising agent (Cement / Lime)
label | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - every 400 m2
label | ○ every 150m for a 2.4m width
label | Inspection / Test method - Weigh mat or tray
label | Acceptance Criteria - ± 0.5kg/m2 of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
label | Detail of Activity / Test - Compare area spread with weight used for each spreader load
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.08 - Injection & Mixing of Water
label | Detail of Activity / Test - In-situ Stabilisation process
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going visual assessment
label | Inspection / Test method - Visual and hand squeeze test
label | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.09 - Depth of stabilisation
label | Detail of Activity / Test - Depth of stabilisation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Every 200m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +15mm / -5mm from specified depth
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - On site Inspections
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.11 - Compaction
label | Detail of Activity / Test - Plateau Density Test
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
label | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
label | ○ IANZ report when processed
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
label | IDC - RFT Schedule of Price - 3711
label | IDC specifications Frequency - NZTA T23
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Compaction
label | Detail of Activity / Test - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
label | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
label | IDC - RFT Schedule of Price - 3711
label | IDC specifications Frequency - 5000 m2
label | ○ TNZ B/5: Section 7.7.1
label | ○ NZTA B/7: Section 8.1
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 3.13 - Compaction
label | Detail of Activity / Test - Degree of Compaction (DoC)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
label | Acceptance Criteria - Average DoC ≥ 98%
label | ○ Minimum DoC ≥ 95%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.14 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
label | Detail of Activity / Test - Clegg Impact Value
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1000m2
label | Acceptance Criteria - CIV ≥ 50
label | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | IDC specifications Frequency - Not mentioned in IDM specs
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.15 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
label | Detail of Activity / Test - Degree of Saturation, DOS
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - 5 per 1000m2
label | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
label | Acceptance Criteria - aim for DOS ≤ 80%
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Report only
label | IDC - RFT Schedule of Price - 3711
label | IDC specifications Frequency - ≤ 60% (Table 10: 3710 sub-base compliance amendments)
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
section | 4.0. Testing and Sgnoff
checkpoint | 4.01 - Finished Pavement
label | Detail of Activity / Test - Crossfall
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - ± 0.5% of specified crossfall measure
label | ○ 2m apart
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Finished Pavement
label | Detail of Activity / Test - Stabilised width
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - -20mm, +100mm
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Finished Pavement
label | Detail of Activity / Test - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 10mm using 3m straight edge
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Finished Pavement
label | Detail of Activity / Test - Surface Finish
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Per Lot
label | Inspection / Test method - Visual
label | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | 2. Smaller aggregate held in place by fine material
label | 3. matrix does not displace under normal trafficking and/or sweeping
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Finished Pavement
label | Detail of Activity / Test - Roughness
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Before Sealing
label | Inspection / Test method - TNZ TM 7003 v1
label | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
label | Record documents (QCP - Quality Control Portal) - Test Certificate
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3711
label | Testing Type - Site Testing
label | Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1. The contract rate shall include allowance for mixing, compacting, trimming and finishing, to the specified tolerances, and the first coat seal.
checkpoint-no-status | 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Pavement Renewal - FBS | itp |  |  |  |  | ITP - Pavement Renewal - FBS
section | 2.0. BEFORE BITUMEN STABILISATION STARTS
checkpoint | 2.01 - Setout section
label | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Document existing furniture
label | Record documents (QCP - Quality Control Portal) - Electronic survey files
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3741
label | Testing Type - Site Survey
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - Electronic survey files (Quality Control Testing)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe, shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Use grader's machine control and inspect shape
label | Record documents (QCP - Quality Control Portal) - N/A
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
label | IDC - RFT Schedule of Price - 3741
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality Control Testing
label | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe, shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Visual check or Vibratory Roller's response meter
label | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
label | Responsibility - Stabiliisng Contractor
label | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
label | IDC - RFT Schedule of Price - 3741
label | IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller.
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality Control Testing
label | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Compaction
label | Detail of Activity / Test - Plateau Density Test
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
label | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
label | ○ IANZ report when processed
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
label | IDC - RFT Schedule of Price - 3741
label | IDC specifications Frequency - NZTA T23
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction
label | Detail of Activity / Test - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
label | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
label | IDC - RFT Schedule of Price - 3741
label | IDC specifications Frequency - 5000 m2
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 2.06 - Compaction
label | Detail of Activity / Test - Degree of Compaction (DoC)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
label | Acceptance Criteria - Average DoC ≥ 95%
label | ○ Minimum DoC ≥ 92%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3741
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Overlay and check levels
label | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Survey
label | Acceptance Criteria - As per NZTA Z/16
label | ○ Minimum: -5mm
label | ○ Maximum: +15mm
label | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
label | Responsibility - Stabilising Contractor with Main Contractor
label | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
label | — overlay aggregate quality / consistency
label | — moisture content
label | — any concerns with shape and tie in
label | — etc.
label | IDC - RFT Schedule of Price - 3721
label | Testing Type - Site Survey
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - DWG File and drawing pdf (Quality Control Testing)
label | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Production Plan
label | Detail of Activity / Test - Plan showing cut lines and sequencing of works
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Daily Report
label | Acceptance Criteria - Points covered in NZTA B/5
label | Record documents (QCP - Quality Control Portal) - Daily Production Plan
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3721
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
section | 3.0. BITUMEN STABILISATION OPERATION
checkpoint | 3.04 - Weather conditions
label | Detail of Activity / Test - Material behind stabiliser
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading
label | Inspection / Test method - Measurement
label | Acceptance Criteria - Material after stabilisation:
label | ○ BE: > 20°C, FB: > 20°C
label | ○ and Ambient: >5 deg.C
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.05 - Weather conditions
label | Detail of Activity / Test - Wind
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - Wind speed < 25 km/hr
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.06 - Weather conditions
label | Detail of Activity / Test - Rain
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
label | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - every 400 m2
label | ○ every 150m for a 2.4m width
label | Inspection / Test method - Weigh mat or tray
label | Acceptance Criteria - ± 0.5kg/m2 of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.08 - Spreading of powdered stabilising agent (Cement / Lime)
label | Detail of Activity / Test - Compare area spread with weight used for each spreader load
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.09 - Injection of bituminous stabilising agent (FBS or BE)
label | Detail of Activity / Test - Flow meter and operator's display readings
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
label | Inspection / Test method - Visual display reading
label | Acceptance Criteria - ± 5% of specified rate
label | Record documents (QCP - Quality Control Portal) - N/A
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.10 - Injection of bituminous stabilising agent (FBS or BE)
label | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Record usage from PCU at the end of each run
label | Inspection / Test method - Record readings at the end of each run
label | Acceptance Criteria - ± 3% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.11 - Injection of bituminous stabilising agent (FBS or BE)
label | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - For each bitumen tanker load
label | Inspection / Test method - Dip bitumen tanker before and after
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.12 - Injection & Mixing of Water
label | Detail of Activity / Test - In-situ Stabilisation process
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going visual assessment
label | Inspection / Test method - Visual and hand squeeze test
label | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.13 - Depth of stabilisation
label | Detail of Activity / Test - Depth of stabilisation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Every 200m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +15mm / -5mm from specified depth
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance Testing
label | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.15 - Compaction
label | Detail of Activity / Test - Plateau Density Test
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
label | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
label | ○ IANZ report when processed
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
label | IDC - RFT Schedule of Price - 3712
label | IDC specifications Frequency - NZTA T23
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.16 - Compaction
label | Detail of Activity / Test - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
label | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
label | IDC - RFT Schedule of Price - 3712
label | IDC specifications Frequency - 5000 m2
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 3.17 - Compaction
label | Detail of Activity / Test - Degree of Compaction (DoC)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
label | Acceptance Criteria - Average DoC ≥ 98%
label | ○ Minimum DoC ≥ 95%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.18 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
label | Detail of Activity / Test - Clegg Impact Value
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1000m2
label | Acceptance Criteria - CIV ≥ 50
label | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | IDC specifications Frequency - Not mentioned in IDM specs
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
label | Detail of Activity / Test - Degree of Saturation, DOS
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - 5 per 1000m2
label | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
label | Acceptance Criteria - aim for DOS ≤ 80%
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Report only
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
section | 4.0. Testing and Sgnoff
checkpoint | 4.01 - Finished Pavement
label | Detail of Activity / Test - Crossfall
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - ± 0.5% of specified crossfall measure
label | ○ 2m apart
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - Site Survey
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - DWG File and drawing pdf (Quality Control Testing)
label | Comments - Allowance to be made when building up a m² for stabilisastion.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Finished Pavement
label | Detail of Activity / Test - Stabilised width
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - -20mm, +100mm
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - Site Survey
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - DWG File and drawing pdf (Quality Control Testing)
label | Comments - Allowance to be made when building up a m² for stabilisastion.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Finished Pavement
label | Detail of Activity / Test - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 10mm using 3m straight edge
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - Site Survey
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - DWG File and drawing pdf (Quality Control Testing)
label | Comments - Allowance to be made when building up a m² for stabilisastion.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Finished Pavement
label | Detail of Activity / Test - Surface Finish
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Per Lot
label | Inspection / Test method - Visual
label | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | 2. Smaller aggregate held in place by fine material
label | 3. matrix does not displace under normal trafficking and/or sweeping
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
label | IDC - RFT Schedule of Price - 3712
label | Testing Type - On site Inspections
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - In house inspection record - Quality assurance testing
label | Comments - Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Finished Pavement
label | Detail of Activity / Test - Roughness
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Before Sealing
label | Inspection / Test method - TNZ TM 7003 v1
label | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
label | Record documents (QCP - Quality Control Portal) - Test Certificate
label | Responsibility - Contractor
label | IDC - RFT Schedule of Price - 3712
label | IDC specifications Frequency - 1 Test per Site
label | Testing Type - Site Testing
label | Testing Responsibility - Subcontractor (Physical Works)
label | Paid by - Subcontractor
label | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
label | Comments - Allowance to be made under a separate line item for m² rate for site testing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1. The contract rate shall include allowance for mixing, compacting, trimming and finishing, to the specified tolerances, and the first coat seal. The cost of the supply of bitumen is covered in Item 3211.
checkpoint-no-status | 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Pavement Renewal - Overlay | itp |  |  |  |  | ITP - Pavement Renewal - Overlay
section | 2.0. BEFORE BITUMEN STABILISATION STARTS
checkpoint
label
label
label
label
label
label
label
label
label
label
label
label