## Master List Templates
Id | Type | Name | Values | Prompting Name
ec7948c3-7b89-4ab1-9a90-bd066e43ba05 | checklist | ITP-000 - Pre - Construction Rev1 | itp | ITP-000 - Pre - Construction
506e5e0e-4e8d-414c-bc28-45f44fcfae34 | section | 1.0 - Pre-Construction Checklist
bb1b890f-0cb3-4c5a-a6f5-446b4065d82e | checkpoint | 1.1 - Communication (1)
e6f27722-502f-58c2-b426-2305736b810c | note | ACTIVITY / DESCRIPTION: Community and emergency services
6258feca-81d0-5706-bf01-9d7eed536c8f | date | Date:
4f6316b9-fedf-499d-9762-6cd5cc620113 | checkpoint | 1.1 - Communication (2)
137e7b09-4d54-57aa-9ea8-39c135260c65 | note | ACTIVITY / DESCRIPTION: Emergency response plan
83221d13-ffc0-5de9-bbca-0f2d05b3bb00 | date | Date:
db95abb7-c978-4764-a800-6de2d2b0385e | checkpoint | 1.2 - Approved Construction Documentation (1)
2c70a2e1-e3c5-594a-ad68-52f8fb752c64 | note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
3c20a521-3ae2-5314-8779-3a3f6c5b25f2 | date | Date:
1ed25072-4fcc-4fd4-8ddc-ba434ce7df22 | checkpoint | 1.2 - Approved Construction Documentation (2)
11dbcb17-275f-5dbb-84b8-1ea8d03d3bf7 | note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
18063c05-15b8-58b4-b289-2c22f5bec7be | date | Date:
628a0d05-08b8-4c6a-83d9-70116d2c05be | checkpoint | 1.2 - Approved Construction Documentation (3)
4ce8e019-0bf8-568f-a1a1-9c77a6d5b1ce | note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
5b8904b9-7e7a-5642-9e32-209e001adc65 | date | Date:
d91fe6f8-7fb3-4faf-9207-97bf00c9d4b9 | checkpoint | 1.2 - Approved Construction Documentation (4)
645bf9e9-61d0-551b-8ab2-742fc17952ee | note | ACTIVITY / DESCRIPTION: Quantities / Specifications
a5bd8f41-895a-5c25-a239-ab3a71a6b63e | date | Date:
f4719456-1071-4d3c-9fec-7385ad8384bd | checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
23a39979-2f30-542b-b34f-b8a606c6ecd3 | note | EXTERNAL REFERENCE: Hold Point (HP)
430309b8-514a-5878-a61d-c0b20019dc09 | note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
f3e08c44-dffe-5016-851a-e4bd3ea02bcb | date | Date:
6b04975a-d93d-4e71-9ca6-b5620cd15ce9 | signoff | AUTHORITY HOLDPOINT
12ca0316-e4de-42f3-8da6-662f03ddc498 | checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
7244d7e9-09bc-5133-a337-962e3e7de2e3 | note | EXTERNAL REFERENCE: Hold Point (HP)
08f48c8c-b29b-5bde-a5c0-5db75156e260 | note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
e8d3772c-485d-5d46-9833-578b30de8cd3 | date | Date:
3b40ac63-c535-47f1-8bdb-74def4c4f850 | signoff | AUTHORITY HOLDPOINT
2ebe271c-fc0b-490f-9d92-2bca7c1006f5 | checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
b1161ed9-9fef-5fe8-932d-82e2ed9a07e4 | note | EXTERNAL REFERENCE: Hold Point (HP)
4d1b6287-c606-58af-8dd2-12cff0abd6fc | note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
a42d04c0-ff2c-5436-b2e8-1ee9ecca2e17 | date | Date:
ab37b5a7-57ce-443e-80ad-61c24a6ac789 | signoff | AUTHORITY HOLDPOINT
9e76dc01-ccf0-4e89-bcda-311dc9659e9a | checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
0a20d56b-1eb3-556d-9026-612a8fa504e5 | note | EXTERNAL REFERENCE: Hold Point (HP)
412f68fa-a9c9-598c-b8aa-cfab9f73f067 | note | ACTIVITY / DESCRIPTION: "No Go Zone"
dda313ea-2131-587c-af5d-c4d40276d947 | date | Date:
b76e7864-4c8a-497d-a0bb-715d25c76419 | signoff | AUTHORITY HOLDPOINT
44686010-6df2-4a6f-a41f-fa5f012e3c45 | checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
2b46c0bb-336b-5ab5-b694-14ba8d5d95c0 | note | EXTERNAL REFERENCE: Hold Point (HP)
89ae91b8-c56e-5dd4-bf0b-f12f14621ea4 | note | ACTIVITY / DESCRIPTION: Tourist attraction
1169444e-24c2-53a9-a0d8-1a1c5a55c794 | date | Date:
46976b36-15f5-43a6-9f48-7cdffceaeb5e | signoff | AUTHORITY HOLDPOINT
ece9aae3-7806-4437-9989-b248534b3792 | checkpoint | 1.5 - Protected Environment (1)
232def67-1d5f-56c3-9e6b-a93553ecf3bf | note | EXTERNAL REFERENCE: Hold Point (HP)
5f975cc0-b2ff-5564-9a4a-9869b241de7a | note | ACTIVITY / DESCRIPTION: Flora
1a139fbf-6379-53d4-a909-b1eb5f584d67 | date | Date:
74258bbf-360c-488d-a28a-50eaee22af78 | signoff | AUTHORITY HOLDPOINT
9d211495-a126-4974-92e5-1c9026df4e00 | checkpoint | 1.5 - Protected Environment (2)
2ee6f03e-b2de-58e1-8e08-34073ff0ed93 | note | EXTERNAL REFERENCE: Hold Point (HP)
0ef2076f-8f1b-5547-8c97-07f89b68d45f | note | ACTIVITY / DESCRIPTION: Fauna
935ae3a8-2680-5fcf-bb60-0e80e35c1d84 | date | Date:
3b9d9fef-f609-4eb2-a8db-df35a6280651 | signoff | AUTHORITY HOLDPOINT
8f77462d-ce5e-4bd0-bd70-742f0eec3929 | checkpoint | 1.5 - Protected Environment (3)
8361494e-2ef3-5ef6-9324-99c0d60afdea | note | EXTERNAL REFERENCE: Hold Point (HP)
bb94b0e4-1ff6-5ed6-9518-b52104666749 | note | ACTIVITY / DESCRIPTION: Water bodies
a6320b06-2180-525b-9324-83467fdac279 | date | Date:
0c39cbb8-dea7-4094-82bb-a9dcf68b775f | signoff | AUTHORITY HOLDPOINT
b753e1dd-55d2-4f32-b18b-3b13286788bd | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
4d0e7d85-db70-50b2-a112-4be2c7a2bc40 | note | ACTIVITY / DESCRIPTION: Dial Before You Dig
b9512c41-5e6f-50b4-b302-2b1e86969f05 | date | Date:
d2c13cf0-661d-4123-b565-8bcb0faa0c7b | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
9f9f74aa-fef9-5389-85cf-68a058f0cad0 | note | ACTIVITY / DESCRIPTION: Excavation Permit
fb1b3d1a-ffa9-5c89-84bc-935a0f14c755 | date | Date:
754225c2-8308-4714-9a7c-6fc32c6bc7fd | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
eb0da7a7-b40d-516f-8a21-70da80294ea9 | note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
aa3db215-a525-5952-a488-c96443dc8e40 | date | Date:
024486ff-edc7-40d5-bf72-8850f1e7d2af | section | 2.0 - Pre-Commencement Checklist
73e71e67-a3aa-4ee4-a041-46b45cbc5b32 | checkpoint | 2.1 - Traffic Items (1)
219e153c-34ac-530c-9618-b17528289be5 | note | ACTIVITY / DESCRIPTION: VMS boards
d59c19b3-ab5e-55d6-8f72-65bf2cc933f2 | date | Date:
c1c93cbe-a777-492c-9e6e-0fbf59983d24 | checkpoint | 2.1 - Traffic Items (2)
40537772-448f-5021-b861-346ce535c0ab | note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
bc22d5d7-8d2a-5cf5-95b0-8f1ce1f61d65 | date | Date:
a373fe9c-e74e-40b4-9b65-1682d1557bc2 | checkpoint | 2.2 - Site marks / references (1)
7222e648-5ebb-54d7-a3ee-4f53060f49a9 | note | ACTIVITY / DESCRIPTION: Limit of Works
2ec47ee6-abfb-523f-878d-1e0a376b9c9b | date | Date:
14c7cb9d-f208-426b-8022-f86375318965 | checkpoint | 2.2 - Site marks / references (2)
c4196c09-8497-5e7d-abcb-7084bab05b35 | note | ACTIVITY / DESCRIPTION: Survey control point
97e3fe00-ed0e-5fc9-940e-e4cdbf31cc77 | date | Date:
4dee1a61-622e-41b5-8aa5-fd7c5781f4cb | checkpoint | 2.3 - Services, inspect/identify clash points: (1)
7ba32668-63a5-5faf-8d34-0c6454d68734 | note | ACTIVITY / DESCRIPTION: Sewer, Water
09ec3b17-bf39-5023-b2b6-6f4b1d5d5694 | date | Date:
e54a5eed-5f32-4a1c-ad5e-e8e1766818da | checkpoint | 2.3 - Services, inspect/identify clash points: (2)
71cbea25-cdec-5fe4-b4f0-8072a81257df | note | ACTIVITY / DESCRIPTION: Gas, Electricity
71ff9c9f-86fa-5791-bcb0-7249db27aa35 | date | Date:
312527e0-5e5f-4b4b-bec0-c033036a4b46 | checkpoint | 2.3 - Services, inspect/identify clash points: (3)
9346209e-8d80-5310-af05-a3bae73bcbd8 | note | ACTIVITY / DESCRIPTION: Telecommunication
1bbd0831-b4b7-50da-b126-635c3fdc6f91 | date | Date:
5597bfce-7124-45f5-9cc6-ccc4725e1487 | checkpoint | 2.3 - Services, inspect/identify clash points: (4)
a60de8f4-24d0-5fcd-82ca-c112ab21741d | note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
74d84631-64fd-5ed8-a4b2-61860885b26e | date | Date:
1b77da62-2c91-4b45-9592-2097031f5220 | checkpoint | 2.3 - Services, inspect/identify clash points: (5)
01bcd3e6-26ab-5137-b622-4c9ca69ff619 | textbox | ACTIVITY / DESCRIPTION: Other specify:
1b5693cf-1601-59cc-a48d-f4bb08991699 | date | Date:
a622f273-5f8b-441b-9028-0d4a48324858 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
0c804654-ad59-51f1-ae7d-48e6e9bf0b04 | textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
8b2724e9-7df2-5d6d-908f-87549f86fb0f | date | Date:
c3c63897-0579-4ff8-a8f3-e058ee326284 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
abbda1d3-7c6c-5e6c-af72-571fd4a345d3 | textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
021cf184-01a0-51cf-9446-c83bb22da090 | date | Date:
27221d83-48eb-4d78-b372-5b83bb209154 | checkpoint | 2.5 - SWMSs reviewed: (1)
1eacaf2c-c04e-5ff7-9325-90d9c48cec31 | textbox | ACTIVITY / DESCRIPTION: Site-specific
0bb07632-2f94-5ea7-a558-b820930f1c99 | date | Date:
bc2295c1-f237-404a-8c3b-8ac54367d715 | checkpoint | 2.5 - SWMSs reviewed: (2)
e036ee75-e886-54cf-acd2-e0bbf47e014c | textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
05881025-1e77-5f01-837d-8867dbd8482d | date | Date:
66b75e59-aa24-441c-9afd-c14f48b00ba4 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
028de256-9b8e-54ba-8a3e-7d74d3933972 | textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
b208738c-f16c-5770-af3e-17763ba4a610 | date | Date:
1ee340b3-1ac5-486e-ac75-1a9f45fcfac3 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
1058298f-9ad0-5d19-90b5-7eeef3daea9c | textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
9198d1a5-6aca-5001-bf77-f68519df304c | date | Date:
6995948b-0c19-4f77-8fb1-f3d9472f8178 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
de6ee94b-8e54-525b-9c9b-187403b8d828 | textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
72dd73e5-6cb0-5b64-84ed-1e80acab2035 | date | Date:
0d337ec7-94c9-4562-8598-49a0f5c4f661 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
bd2bf265-6826-5882-8aca-cd6edac5340c | textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
b5dfec9a-0ae6-5ed7-b5cd-13852792b5da | date | Date:
ead8a1f3-7559-4f03-9352-98fc6eaf5c40 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
0afa1408-8f65-5dec-a111-19f431215f85 | textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
f2848b2c-8df4-52d5-af73-65e26d4d1b87 | date | Date:
ef92f9df-7eb2-435d-b79a-c265ddc5f624 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
2d84ae2b-3d7c-599a-86d3-b3e7ebd46e40 | textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
e051b90b-cac2-5bda-8101-6cdcfec749b8 | date | Date:
a393892b-b867-45d1-8c2f-9133392571d6 | section | 3.0 - Construction
f4eb0f64-3d11-4bf2-a816-73172d1b42d5 | checkpoint | 3.1 - Vegetation Removal (1)
1cab15f0-5e7b-5c96-a725-76781f197099 | note | EXTERNAL REFERENCE: Hold Point (HP)
37e5a847-d5ec-5561-ac5f-748f41747f5f | note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
469f7783-cce5-5766-8600-c0ba06b3e33b | date | Date:
e561e711-c152-4d07-b21d-66df85f66441 | signoff | AUTHORITY HOLDPOINT
55e0a9cb-cfce-496f-a205-bbbca7a9f903 | checkpoint | 3.1 - Vegetation Removal (2)
a859cd75-a4c1-54c0-afbc-a300243a2e1a | note | EXTERNAL REFERENCE: Hold Point (HP)
d5b0f6a4-2099-5ae9-87ab-76e906d0d5e9 | note | ACTIVITY / DESCRIPTION: Equipment, Access
923e39d6-c933-5b25-92a2-17a4c7d97360 | date | Date:
797081e5-8338-4e4f-bfeb-98917c58692c | signoff | AUTHORITY HOLDPOINT
1d860393-f8bf-45b7-bf83-f55c7f174e58 | checkpoint | 3.1 - Vegetation Removal (3)
77fc8179-01a8-5de1-be4e-a37535b31a98 | note | EXTERNAL REFERENCE: Hold Point (HP)
87c85ec8-5ae7-5d2a-adc8-98a01d70a7ac | note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
f6aed4ff-758c-5563-aaec-3d02eaf92d2d | date | Date:
b0a58810-0af8-4066-b9fb-a71b31e17b1e | signoff | AUTHORITY HOLDPOINT
b7321300-f332-41f3-a265-1234b410b202 | checkpoint | 3.2 - Contaminated Materials
862c77d5-a076-5349-aa81-bcb31ec4949b | note | ACTIVITY / DESCRIPTION: Contaminated Materials
32e3f890-2c02-52ea-bf37-1a874b0b9ec8 | date | Date:
8aa6e0cc-5d25-4a60-a9d7-6a55fbce6ceb | checkpoint | 3.3 - Traffic Items (1)
3cec7a10-622c-5e33-8373-42a2631396b5 | note | EXTERNAL REFERENCE: Hold Point (HP)
5e1e9cc2-8a6d-5a3c-8cb5-7b5d3b9221ba | note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
59c52f51-46d5-5079-b49c-1171224b7fd4 | date | Date:
6bbd4b82-1dea-409f-9277-9c4bef46ff23 | signoff | AUTHORITY HOLDPOINT
cc6495e2-124b-4074-bf86-4e454507afa5 | checkpoint | 3.3 - Traffic Items (2)
8eb94ed4-6acc-5864-8445-d5fd59ccbc9d | note | EXTERNAL REFERENCE: Hold Point (HP)
15ec0df4-b540-5603-94f9-a7bf4bd688e6 | note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
ba2d424f-e07d-5a9f-803d-32be44fddeaf | date | Date:
ca55ed71-9ef2-41b8-b237-2dcf62379026 | signoff | AUTHORITY HOLDPOINT
4954d163-13e4-4ee9-899b-268a99781b67 | checkpoint | 3.4 - Trenching works (1)
fd7bbf0d-957b-5f55-a51e-1efc04516634 | note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
7593820d-1516-5ada-9470-03e9b001907d | date | Date:
75296157-50a4-447a-b649-98848df5a9ab | checkpoint | 3.4 - Trenching works (2)
a5fa4824-9515-5be5-99c1-6bb10b5e2b94 | note | ACTIVITY / DESCRIPTION: Review ground / water conditions
e3d10731-e374-597a-a285-8c9b94b7f8e3 | date | Date:
bca066ad-6d6e-4587-b58d-491f4dbc743e | checkpoint | 3.4 - Trenching works (3)
c1be90d4-adf0-5abe-8239-6f205b20eeeb | note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
c61d7548-b876-50b5-8132-bd371b837029 | date | Date:
eb267d9b-e897-48e3-82d6-ef9236856089 | checkpoint | 3.5 - Drainage Works (1)
f6dd6785-19a9-5698-9390-35804760059b | note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
15f9c08d-de9c-5eee-bbb8-b51160f6ec31 | date | Date:
a001a3cf-22d2-4c20-873b-1e738cde50ac | checkpoint | 3.5 - Drainage Works (2)
f7e2f46b-d835-57a2-ae6e-10d853f18e72 | note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
67f68621-d3c7-5577-97fd-10a4936f7510 | date | Date:
dcb3d0b2-d044-4e31-bd29-a386ccfb4319 | checkpoint | 3.5 - Drainage Works (3)
0c8e4bb0-500f-5729-9a5b-10e6f778a663 | note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
a255cb4c-8eaf-5175-baf8-816cc0270fa4 | date | Date:
2dc63166-00f5-4cac-ab3e-806aed2ba661 | checkpoint | 3.5 - Drainage Works (4)
479ffa13-c5fd-518b-9d9f-ea8dc618374f | note | ACTIVITY / DESCRIPTION: Review confined space entry
398f8d24-c01b-5cd6-abf4-266f570fad88 | date | Date:
cfdf667c-2ba5-49a4-9408-7a8591fe58a3 | checkpoint | 3.5 - Drainage Works (5)
b9164c3b-7b37-567f-982f-c03c51acb950 | note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
283b5fa8-b68d-50da-a580-5cf7faa7b029 | date | Date:
7f3d683d-f3b5-4086-978c-2a5c63d1252c | checkpoint | 3.5 - Drainage Works (6)
5e6fc178-5be6-51d5-865c-698d223474b8 | note | ACTIVITY / DESCRIPTION: Levels
d2918e5e-86c9-54dc-8127-aab434333995 | date | Date:
bfccd875-e979-42cb-971d-e1f4b3474e3f | checkpoint | 3.5 - Drainage Works (7)
1662e6a7-0386-52bd-8a9f-f566df06206d | note | ACTIVITY / DESCRIPTION: Pit covers / Grates
1da7eb42-be09-58cf-8f39-047f3abc1436 | date | Date:
bec5c66f-230c-4036-9d20-a021e24f4b76 | checkpoint | 3.6 - Structural Items (1)
5bb36a25-8acb-51b9-ba68-3da979928c87 | note | EXTERNAL REFERENCE: Hold Point (HP)
9cf22238-c949-53ac-aa7f-fe054762c153 | note | ACTIVITY / DESCRIPTION: Crown units / culvert
cf184cf2-88a5-52c2-9b80-7670ae16b74f | date | Date:
4ebe9f6f-fc5d-4692-808f-beeee483c5a9 | signoff | AUTHORITY HOLDPOINT
8da2805d-0e6a-4075-b5c2-f70636883660 | checkpoint | 3.6 - Structural Items (2)
7a9ebbed-de21-56c8-a434-272bb7dc3d41 | note | EXTERNAL REFERENCE: Hold Point (HP)
b4ec60d2-620b-5720-adbf-39d8cc1a3f17 | note | ACTIVITY / DESCRIPTION: Retaining structure works
a856f55b-4c73-57b2-8e5e-23f893cf1244 | date | Date:
85aaa81b-691a-4b99-8e28-35b3cce01f9d | signoff | AUTHORITY HOLDPOINT
fab14ed3-3bda-422d-aea0-44462df3aef2 | checkpoint | 3.6 - Structural Items (3)
db904c1f-778c-5ee3-a73a-ecdd449010be | note | EXTERNAL REFERENCE: Hold Point (HP)
ad0a05bd-65a9-5358-be6a-07628591fd3b | note | ACTIVITY / DESCRIPTION: Bridge works
fb431245-769c-5726-bd68-d70cad3c3751 | date | Date:
3256c727-9df6-4346-9a8d-a74be95568b2 | signoff | AUTHORITY HOLDPOINT
b54bd7aa-dd80-475b-a572-b814c27c71df | checkpoint | 3.7 - Concrete kerb works: (1)
4e83a662-87af-584f-8d91-292cab1937d1 | note | ACTIVITY / DESCRIPTION: Alignment / level
9084ffe3-5527-5440-b8d1-8d5d3a1be359 | date | Date:
73ec6383-3102-44c3-91bc-7088f2fe3391 | checkpoint | 3.7 - Concrete kerb works: (2)
ed1dc1f0-117c-5394-96ff-2ad947d3db58 | note | ACTIVITY / DESCRIPTION: profile / finish
ed0df4d6-4539-5db6-9d53-f10d384e2757 | date | Date:
980487b0-24c5-4273-a598-11ff8b37d2d3 | checkpoint | 3.8 - Concrete Works (1)
9cb9c99d-31ff-5065-9de0-5c9efe86cd01 | note | EXTERNAL REFERENCE: Hold Point (HP)
4555486a-0e50-5c78-97e9-5acc7489a8e2 | note | ACTIVITY / DESCRIPTION:
e290765f-51b5-580b-8cf5-66b3be991bb3 | date | Date:
c3488558-a77d-485b-8b94-1f986cdb7522 | signoff | AUTHORITY HOLDPOINT
8ad63936-0e1a-4300-8882-88d2325e3399 | checkpoint | 3.8 - Concrete Works (1)
cbddb7dc-7965-527e-8604-d0f59ed7cf96 | note | EXTERNAL REFERENCE: Hold Point (HP)
79934066-2a33-55b4-b790-32e626d8074d | note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
e10c73aa-244b-56d5-9b3b-677156da6681 | date | Date:
a19049ed-7ac2-418e-a4ff-2c91334bb8b8 | signoff | AUTHORITY HOLDPOINT
ce96ee44-2c12-4fd9-84a8-fd71e6814422 | checkpoint | 3.8 - Concrete Works (2)
df46743f-9e58-5dc9-acce-7c996c1b0db0 | note | EXTERNAL REFERENCE: Hold Point (HP)
c0df993f-67d3-581c-bbf2-47691fed7330 | note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
4ae24711-c212-5c14-a915-8ec828dde90d | date | Date:
4fd4c7a2-690a-485d-b364-dc9f3f3a7441 | signoff | AUTHORITY HOLDPOINT
8fd4143a-d3f5-4d84-96fe-cf55e66e911b | checkpoint | 3.8 - Concrete Works (3)
4b5a48b0-275b-5eaf-a393-1b7bfc67ef83 | note | EXTERNAL REFERENCE: Hold Point (HP)
57b1b11a-1cae-5935-83cf-3a545eba2023 | note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
aebe87c5-1f12-595a-a287-6b3a1be6dac6 | date | Date:
0a043d4e-c975-4545-9181-1f5e5613eba4 | signoff | AUTHORITY HOLDPOINT
cf3f2a86-4e76-4739-82ad-9b20e72ea05d | checkpoint | 3.8 - Concrete Works (4)
46b7835c-3393-50ce-bc2a-ac65a53757e3 | note | EXTERNAL REFERENCE: Hold Point (HP)
a6d0a595-de69-5bf4-8c9c-096947c82311 | note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
adef0c6e-e4a3-5d5e-ae57-f80fcf047b39 | date | Date:
8dafd2b1-8146-46b3-890d-f60a776511f9 | signoff | AUTHORITY HOLDPOINT
4f4404b0-e73e-4c25-a76a-2466a8403eb5 | checkpoint | 3.8 - Concrete Works (5)
42910eff-d18b-5269-87d0-c1ec995729fd | note | EXTERNAL REFERENCE: Hold Point (HP)
d140611b-6ba1-55b0-a7dd-7af3e430efd3 | note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
187420f9-647a-5bc2-8b0e-d53ad848608c | date | Date:
8e4160a3-1bde-4820-998c-a4d4c3ca0f79 | signoff | AUTHORITY HOLDPOINT
9fefc923-eef2-4b1c-a0ed-5b1390fc1a10 | checkpoint | 3.8 - Concrete Works (6)
604bbfa1-4836-5ad2-85b5-9b7006c2ee8a | note | EXTERNAL REFERENCE: Hold Point (HP)
262509b8-ced2-597e-a5cb-a75976506bb5 | note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
3551f2cf-f97b-5556-b09e-1cfc50d7cd5b | date | Date:
2976a003-b4ff-41a8-bb88-682d21cd7e8b | signoff | AUTHORITY HOLDPOINT
42b27439-aae0-479c-96be-f27ab5427ca5 | checkpoint | 3.8 - Concrete Works (7)
cbe630c5-4be8-57e4-a782-def703791116 | note | EXTERNAL REFERENCE: Hold Point (HP)
43422f83-6406-5907-85ae-4d6ef87f137d | note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
b93c9931-f628-5460-8b05-e02bef831907 | date | Date:
0a6f5824-24f1-4b1f-a3f4-d9621dea5785 | signoff | AUTHORITY HOLDPOINT
6118b315-e4d3-485a-bc8a-5fdac3ce0d06 | checkpoint | 3.8 - Concrete Works (8)
a1534231-1814-58fe-8bc9-0bf703c80aa8 | note | EXTERNAL REFERENCE: Hold Point (HP)
3959aebd-efe2-51e1-991c-f987dc9057ac | note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
419da4d6-6b52-5eb8-a145-7761e51949d4 | date | Date:
c405d90e-f0fb-4399-bf7a-b56330b49f5f | signoff | AUTHORITY HOLDPOINT
89c0daa7-7f02-48b7-8bbb-8b3097541cd6 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
9be36065-a1cb-5a8e-ac1d-008886293ed7 | note | EXTERNAL REFERENCE: Hold Point (HP)
93b5a13e-e894-50d5-813b-574ff6463518 | note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
d7ae2396-94a0-5a9e-ad3f-4fc6496cb7f2 | date | Date:
06036741-40d7-4332-b711-9140ce7d4f6f | signoff | AUTHORITY HOLDPOINT
30454fe1-eb90-465c-a078-1336dec66ab1 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
662603f2-d921-5a27-9a6a-8aae01dd1522 | note | EXTERNAL REFERENCE: Hold Point (HP)
dec3ec97-d98c-5dc5-bc16-78aa064e6223 | note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
a928a9c0-b4cf-578b-8b39-287e73f04aa1 | date | Date:
1b279548-1bd4-45e8-ad5f-a0477359a71e | signoff | AUTHORITY HOLDPOINT
773d00cd-66ea-444e-a86d-d6aab077d1a6 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
73d4214b-096b-5466-afed-f123a7ae0be7 | note | EXTERNAL REFERENCE: Hold Point (HP)
637f418b-0705-5ad7-be69-c5eb1b133b14 | note | ACTIVITY / DESCRIPTION: Density results
d17488cc-60b5-52fd-aed6-fa9f858227b3 | date | Date:
a08daee9-f5c0-47bf-9ef2-e68064c69b4c | signoff | AUTHORITY HOLDPOINT
e322bad3-404f-4587-a749-b127f1733122 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
43e8db1c-d6ae-5f22-bf9d-fd7fa721f92d | note | EXTERNAL REFERENCE: Hold Point (HP)
2c6b4a52-154a-567b-83ac-6335e46b90ef | note | ACTIVITY / DESCRIPTION: Proof-roll
4a684b97-6d96-500d-9bab-b42ad14eb5f0 | date | Date:
68e6916d-15a8-4029-9acd-e6ecb75accee | signoff | AUTHORITY HOLDPOINT
361f7507-c152-4740-92f9-9bab00978d3c | checkpoint | 3.10 - Pavement Works (1)
edb85706-5505-58cb-b813-ca93cab573f1 | note | EXTERNAL REFERENCE: Hold Point (HP)
9a7c7cd5-75c1-559f-ad83-297c8eefb6cf | note | ACTIVITY / DESCRIPTION: Density results
a4d15a2b-d3a1-5fab-ba52-8a62234442cc | date | Date:
0ea5c1c2-5872-4eb1-9773-33e6a47a21df | signoff | AUTHORITY HOLDPOINT
dc5002f5-ad85-4d60-8978-9fa1caa01d9b | checkpoint | 3.10 - Pavement Works (2)
6c86a36e-1c2b-5900-9305-a897701fbfaa | note | EXTERNAL REFERENCE: Hold Point (HP)
1de26549-c9bf-5c7a-9eaa-41e96afbb8f8 | note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
3cb70c70-be7c-5660-8cfa-82c5ef680799 | date | Date:
ffd0760a-f76f-4e58-b23c-af422768bd31 | signoff | AUTHORITY HOLDPOINT
1ce26c32-7d5d-4787-8e9b-621b400222e2 | checkpoint | 3.10 - Pavement Works (3)
c4e732d4-e269-534e-b8ff-2075a0067d2a | note | EXTERNAL REFERENCE: Hold Point (HP)
2f8f5c5c-716c-5297-9b78-b3ac06b2af32 | note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
0be33575-9e08-5ec5-b0a7-07e0175b3568 | date | Date:
8799fc49-1764-4723-b282-9a3711007f67 | signoff | AUTHORITY HOLDPOINT
9cda9b78-24d5-45dd-9984-1b4606177db7 | checkpoint | 3.10 - Pavement Works (4)
d7a587fc-196e-5a63-a5c6-212e4e55d1e7 | note | EXTERNAL REFERENCE: Hold Point (HP)
4a7351f6-c346-5c8c-8f1b-9335c2c07056 | note | ACTIVITY / DESCRIPTION: Ball Penetration Test
ff7308a0-2a8f-5b16-95ba-4e268d9cdfb6 | date | Date:
7f24d8c8-60fe-438f-ac2c-3e81bfcab2cc | signoff | AUTHORITY HOLDPOINT
98858a12-4a3c-4ef8-b53b-04c0226f49d1 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
5773b127-b81a-59f2-8961-672edfd9d95d | note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
f189c5a2-7632-58d2-9a88-63c4f15d3a9b | date | Date:
8eaf6c32-b2b7-4e5a-9444-fefe6d20fb66 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
6e5385a5-3b7b-57a5-9e20-4abae3b4dd32 | note | ACTIVITY / DESCRIPTION: Approved equipment for installation
344c5d9e-d7fa-523a-9adc-9342f1201129 | date | Date:
91890935-158e-40b9-aa71-f19066499b7d | checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
351e38af-d749-5dd5-a727-e13be1354ae3 | note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
841cac14-37b0-5904-a230-e2d543a86a05 | date | Date:
af8f1ce1-2ccc-4f1a-bfe2-62237911c846 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
66d4152f-0178-5442-9850-46f8432d38a9 | note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
4bdf3e18-b201-5d17-bc7e-e515011c3707 | date | Date:
6402d019-4706-44f4-819d-e6cb9407f3cd | checkpoint | 3.12 - Pavement Surface Works (1)
ffc06c16-b190-5e53-bc27-6600c528ef48 | note | EXTERNAL REFERENCE: Hold Point (HP)
88072e80-0d0e-54a3-a817-664b21923bf8 | note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
dc023705-525d-5f81-ac0b-6ee6d18d4c1a | date | Date:
2256846d-1f29-4cda-9ada-91c2812e4359 | signoff | AUTHORITY HOLDPOINT
814b5b45-90dc-4ae1-a32b-6fb45003c251 | checkpoint | 3.12 - Pavement Surface Works (2)
701c8aed-f5de-5658-b4a7-e37c6c8d96af | note | EXTERNAL REFERENCE: Hold Point (HP)
2ad4e868-dbe8-5fd4-852f-6d03091b4759 | note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
bbe2ee03-df3f-5846-bab3-63112b143462 | date | Date:
8da7637c-d95f-451c-9b8c-65c644c46282 | signoff | AUTHORITY HOLDPOINT
1189fa11-6530-4708-bc0d-3b9bd96b760b | checkpoint | 3.13 - Landscape (1)
c47bca78-c4ea-5663-9d0a-5df4fb629fb6 | note | ACTIVITY / DESCRIPTION: Seed / Grass
a8ba22b6-cbab-581d-b38d-3879ae33d9b1 | date | Date:
30b90162-863e-4a8e-b5b7-5ffe496c1950 | checkpoint | 3.13 - Landscape (2)
7eeecf5b-d93f-5eb5-969d-45bfd2a14f02 | note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
02ddacd0-cb66-509e-a8fc-991d63944896 | date | Date:
7228ee54-a67f-47ab-ab42-333d14c6f328 | checkpoint | 3.13 - Landscape (3)
978d6ef9-0791-5752-8f9b-d22f16335e00 | note | ACTIVITY / DESCRIPTION: Street furniture
54eff99d-8058-572a-8821-4cf0cc0d27ff | date | Date:
e4261a40-ef24-4c51-a4f7-bc560ddf8099 | checkpoint | 3.13 - Landscape (4)
27f493b8-64d2-54df-89d4-b769b0c5ead8 | note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
6576b4e3-3f41-56b6-8461-793e8f9ab4ac | date | Date:
bd642e35-645a-453b-8f53-a719e45d6db8 | section | 4.0 - Practical Completion
2db86639-1a42-4f81-85a0-4c7259c608a2 | checkpoint | 4.1 - Road Fixtures (1)
43e329bb-76af-5d73-bf31-7d2d1c998a95 | note | EXTERNAL REFERENCE: Hold Point (HP)
895211b8-1959-551b-94f6-1dc94f3edf17 | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
a6b12caf-efb8-5009-8c20-aa99cdac572b | date | Date:
2ffbb314-993b-4819-af5d-58665dab80bd | signoff | AUTHORITY HOLDPOINT
064dae2c-3dd1-49da-be8f-473db404c1e9 | checkpoint | 4.1 - Road Fixtures (2)
1dc0757e-c689-5ea7-b9e6-90022cb23c44 | note | EXTERNAL REFERENCE: Hold Point (HP)
3e5ce256-eb21-50d4-8b3d-b23f076ab26a | note | ACTIVITY / DESCRIPTION: Signs
96ad4902-844e-5471-897c-fd2b53716465 | date | Date:
f16224fc-7bcf-4d79-8783-477672ce87b4 | signoff | AUTHORITY HOLDPOINT
1f9b40f7-9ad9-4b17-addf-4291fa82fe28 | checkpoint | 4.1 - Road Fixtures (3)
811c64f3-46d9-5823-a1ab-4fcb5a84c4c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
df4ddbb5-52d9-5811-9374-e9d912e4ec0f | note | ACTIVITY / DESCRIPTION: Guide posts
44f78845-cdea-5ee0-a1f4-8b3edca7bc64 | date | Date:
3c861e70-53d6-4db0-97e8-5af62e436823 | signoff | AUTHORITY HOLDPOINT
317b0749-52a8-4c74-a9de-638fef256931 | checkpoint | 4.2 - Safety Barrier Works (1)
f07a90d3-e3cb-505c-b092-e69dfea0c102 | note | EXTERNAL REFERENCE: Hold Point (HP)
6ee626b0-c424-5d0d-93a2-5b94acf51dfa | note | ACTIVITY / DESCRIPTION: Guardrail
35fb547a-5a20-597a-b810-a975f004cde9 | date | Date:
752024bc-ebd4-4f2c-a845-25285c5b3594 | signoff | AUTHORITY HOLDPOINT
1aebfb00-53c7-4133-afe7-03a51992cd0d | checkpoint | 4.2 - Safety Barrier Works (2)
92df4c2e-1ae0-5253-8610-51bc4e1b06cd | note | EXTERNAL REFERENCE: Hold Point (HP)
bba34ff1-9ea3-5518-bf6d-8b1ccf5f0a6a | note | ACTIVITY / DESCRIPTION: Wire-rope
383afdcf-e884-503b-9ead-39cc532fcb27 | date | Date:
31f46e23-7fc4-437c-b162-969574f0b050 | signoff | AUTHORITY HOLDPOINT
da547094-b943-4ebf-a00b-878e57be9d33 | checkpoint | 4.2 - Safety Barrier Works (3)
b81129e8-8a67-579f-aeb3-2bcea3ae949b | note | EXTERNAL REFERENCE: Hold Point (HP)
80752d29-196a-59a9-ab60-4e99af91433d | note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
ad117929-0402-5f2d-86fb-edba7ab78eaf | date | Date:
87cbc774-0f7f-47bf-870d-955bd54f22cd | signoff | AUTHORITY HOLDPOINT
0953ff2b-a116-4f0f-8221-861e448041f9 | checkpoint | 4.3 - Fences and Gates
f7230881-6417-504c-b6f7-d940307940be | note | ACTIVITY / DESCRIPTION: Fences and Gates
f2194732-7626-548f-b712-894db3509011 | date | Date:
e6640a44-1781-4873-b1ed-b0259b4af084 | checkpoint | 4.4 - Quality Ride Test
ad48874f-e750-5ab1-9613-8d0376132bb0 | note | EXTERNAL REFERENCE: Hold Point (HP)
9e52f830-712c-5482-ae98-710d53ecb076 | note | ACTIVITY / DESCRIPTION: Quality Ride Test
482837ee-0bbd-5cbd-bc87-72edadbc2dee | date | Date:
3c817810-95c6-4723-8b4c-d1722e2ec43f | signoff | AUTHORITY HOLDPOINT
cfb3a837-b1d3-4291-a6c1-3ff1cdda929b | section | 5.0
7e48ef31-bbd7-4beb-a7d9-94cf9a680775 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
90e9cd06-9135-5896-903d-03da135aeb1c | note | EXTERNAL REFERENCE: Hold Point (HP)
e233111b-ee6a-5d4a-b0c2-9b101957d6ae | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
47998745-5a7d-5116-9432-a3413d86ce66 | date | Date:
d26c3bb2-cc76-4b9e-83c0-1fa5007b8628 | signoff | AUTHORITY HOLDPOINT
247095d1-3765-416e-9524-b97a9a174e2f | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
c189a0ff-90c5-5874-bac6-bbe2f46069f3 | note | EXTERNAL REFERENCE: Hold Point (HP)
d9386149-3c31-5c05-867b-7af66c215c63 | note | ACTIVITY / DESCRIPTION: Signs, guide posts
9be5c458-7cc3-5042-9dce-dfeb281ecd11 | date | Date:
105f7805-cc45-49b8-84b7-ab4b8458fcf5 | signoff | AUTHORITY HOLDPOINT
3c796aa6-9bd5-483b-a646-2aad979b2d84 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
2d90792a-a9ce-5e28-a0ed-3be2b7155639 | note | EXTERNAL REFERENCE: Hold Point (HP)
2744ffa1-f4b8-5f5d-8061-1eb00966f6b4 | note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
ed8a7a46-26b8-5e55-88aa-ab827485b1be | date | Date:
5fe117a1-97d0-46af-bb52-2c048ea625de | signoff | AUTHORITY HOLDPOINT
51fb0002-3d38-43df-9aae-c61344e5f466 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
9a9bab70-3bd7-5a08-b23f-64eed17b403e | note | EXTERNAL REFERENCE: Hold Point (HP)
e4d4a010-81bf-5fce-9136-4be8e73bd139 | note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
9b12f7dd-cdf3-536c-84d4-50e2d4b694de | date | Date:
38ad7416-84d2-430f-b111-2b0da8d53443 | signoff | AUTHORITY HOLDPOINT
eb50e3ba-eb29-4d9a-9cc1-b8698bebf7d3 | checkpoint | Final Inspection
78035bf4-fc43-5262-babb-710b0370407a | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
26bcb08c-94e9-5cef-8014-01480efefa37 | textbox | Print Name:
8770fd6d-e7f8-5a8c-9305-19f1dc660ed9 | textbox | Position:
9eb131b1-9cb4-5da5-b537-9057d2ce48ae | date | Date:
4f75df59-8ec0-41ae-bb5c-778e680816f6 | signoff | Sign ITP
9f6a62e5-d4ec-40bc-9f36-74f33f0647d8 | checklist | ITP-004 - Precast Pit Install Rev1 | itp | ITP-004 - Precast Pit Install
4d06e99b-b490-4d03-839b-4133a64eeeb8 | section | 1 - Preliminary Works
fde1bc23-fefa-4692-9903-11578075a310 | checkpoint | 1.1 - Check for correct documentation
93290235-80e9-5eac-9cc9-da5c5139d09c | note | FREQUENCY: Prior to commencement
4894e7fd-eee3-5ccd-b01d-bd3ac7f7ee25 | note | ACCEPTANCE CRITERIA: All drawings are the latest revision; drawing register is complete and matches site documentation
5748bd8b-f339-5228-86ee-45a084e41dd6 | note | REFERENCE DOCUMENTS: Project Drawings, Drawing Register
64be1367-d068-553d-b48f-3b58e0516a14 | note | INSPECTION/TEST METHOD: Visual inspection
468e1a8c-c570-55c9-8aac-aea5e28326c9 | note | RECORD OF CONFORMITY: Signed ITP
e9e0f082-d52f-5df4-94ac-0f01ba585af0 | note | HP
253f8062-f8e5-5057-956d-ecdc1b239b00 | note | RESPONSIBILITY: Site Engineer / Contractor
46de880c-b290-54cf-84b2-f905e0006320 | date | Date Completed:
62b62bce-d44c-4acd-9ffa-a6da61d9886b | signoff | AUTHORITY HOLDPOINT
12b6d808-dbe6-4f92-90fe-7fc0196435fb | checkpoint | 1.2 - Excavation clearance and bedding
352414ff-acc4-5c3a-b82a-791b5c874e6b | note | FREQUENCY: Each pit
b352f728-4706-577c-8fff-4086d705e6ea | note | ACCEPTANCE CRITERIA: ≥400 mm clearance; bedding thickness: 80 mm (clay), 150 mm (rock); bedding material complies with Section 701
b17664fe-0b94-5538-b729-f306f8dfb06a | note | REFERENCE DOCUMENTS: Sec705.05(b), Sec701
ab9f2e7e-6f78-5902-b1e8-31cde0dfd8a1 | note | INSPECTION/TEST METHOD: Visual inspection
9fd3b80a-01a4-5a03-925c-75e2bb4c525f | note | RECORD OF CONFORMITY: Signed ITP
7918767d-e7b0-5e12-8925-7d6412c6ec5b | note | HP
d76aeade-2fb2-5b39-94c0-b790451b7362 | note | RESPONSIBILITY: Site Engineer / Superintendent
359dd2f4-0de2-5779-b784-c287e54fc581 | date | Date Completed:
0d531173-d721-4a69-8911-c8d0008c0df7 | signoff | AUTHORITY HOLDPOINT
5c0b901b-e046-4128-95d9-ca9e9316d8d0 | checkpoint | 1.3 - Precast pit configuration
8568c9be-d097-5540-ac51-18c298277b52 | note | FREQUENCY: Each pit
675921ba-73a3-5ace-abeb-c3a294fe9f69 | note | ACCEPTANCE CRITERIA: Precast base and riser units match design; knockouts only in required walls; no thinned wall sections
30800a2c-9e87-5d36-b609-a3825cd0c816 | note | REFERENCE DOCUMENTS: Sec705.04(a), Drawings
3629db6d-11a6-5762-b3e0-476d1b2ae8c9 | note | INSPECTION/TEST METHOD: Visual inspection
0b20f526-c862-523b-add6-1df14524a6bc | note | RECORD OF CONFORMITY: Signed ITP
c519e6c4-4df4-5b62-ab8b-eec5f4a9afb4 | note | IP
f680a955-35e9-5eb6-b5d2-dc7287a856e6 | note | RESPONSIBILITY: Site Engineer
5b982e43-7fed-5d6b-8629-c7c83dd6ed16 | date | Date Completed:
94d89deb-0535-45d5-829c-2abbe5b30e07 | checkpoint | 1.4 - Fibre content verification (FRC pits only)
2a0b240b-a591-5c07-b2ff-717ba38f63d7 | note | FREQUENCY: 1 per 5 batches
403d25ee-aa5f-57c6-b051-f6867735c6f7 | note | ACCEPTANCE CRITERIA: Fibre content within ±1% of approved mix design
472cffc4-e8af-5a6c-8bb1-309e0c16ae95 | note | REFERENCE DOCUMENTS: RC 377.01, Sec705.08(d)
d59aba0b-d40c-5ad4-905d-e004dccfc512 | note | INSPECTION/TEST METHOD: Wash-out test
211b3306-f31d-5851-b13c-b834856f3595 | note | RECORD OF CONFORMITY: Test Report
5097b2a6-d3ad-5e62-b9e9-6c08e46cc238 | note | TP
6147388d-ff1a-561b-a0fb-4b2905f57fe3 | note | RESPONSIBILITY: Site Engineer
2393519d-014c-5a7c-b58f-8867ca4e8c79 | date | Date Completed:
9887496d-39a2-4bda-ab42-1c20a2cbc33a | checkpoint | 1.5 - Prototype testing (FRC pits only)
6ed3bd98-995f-5c59-a437-668ea683e565 | note | FREQUENCY: Initial design or major change
a2437769-6cb9-50c9-b5d4-6d816f54d85c | note | ACCEPTANCE CRITERIA: Load test per AS 5100; meets vertical load (210 kN), lateral pressure (≥25 kPa), and reinforcement equivalence (≥150 mm²/m)
ad389801-5c48-5154-82fa-b3fb704cbfa6 | note | REFERENCE DOCUMENTS: AS 5100, Sec705.08(b)
3f0c0a0b-c5f7-5135-951b-f69b1cb4c2d6 | note | INSPECTION/TEST METHOD: Load test
4f670054-7b4a-59f0-ae53-880e2d8e86e2 | note | RECORD OF CONFORMITY: Test Report
1b64d8ff-09c7-5404-952c-08c2429434da | note | TP
d81865fb-03de-596d-8d69-e10a9f5d875a | note | RESPONSIBILITY: Precast Supplier / Superintendent
bba2e9cc-4391-569b-8d7d-05a1acbcae97 | date | Date Completed:
d6f7cbb3-c465-4cea-b26f-2cc54b26168d | section | 2 - Construction Works
6807d285-e40b-4a6a-ac26-f8d392eba80b | checkpoint | 2.1 - Stormwater connection openings
beab9d3b-f535-5097-921b-69bc25bf2dd3 | note | FREQUENCY: Each pit
0b58c923-62f5-5e51-8205-85c1cfa979de | note | ACCEPTANCE CRITERIA: Openings are saw cut only; epoxy coating on exposed reinforcement; hole diameter within 50 mm of pipe
cf1a8e25-6966-5aa3-9a6e-d7939c3d6de8 | note | REFERENCE DOCUMENTS: Sec705.11
e40d4ecd-fb75-52d6-bda4-8d82e465f2d9 | note | INSPECTION/TEST METHOD: Visual inspection
24a2ca01-c2e1-5629-9e9e-4b0e2ab5c5a2 | note | RECORD OF CONFORMITY: Signed ITP
6f098c8e-3c8d-57c4-a46d-d233b7adbf3a | note | WP
b180df78-893a-5711-a4ec-4776204b7f05 | note | RESPONSIBILITY: Superintendent
d06a7664-cb40-5ee9-857a-a2234c034592 | date | Date Completed:
3bc7581a-4bac-444c-9258-fbcefbd45d52 | checkpoint | 2.2 - Segment alignment and rebating
1b9804c2-0089-5215-b537-fc4268e254d8 | note | FREQUENCY: Each pit
f2ca5e2c-13a0-513c-9c85-d8e77f396ee6 | note | ACCEPTANCE CRITERIA: Rebated joints ≥15 mm; alignment correct; no horizontal movement
c2761a93-daff-545b-b1ab-f477716820cf | note | REFERENCE DOCUMENTS: Sec705.09(c)
49b05902-4952-55cc-9a59-53a86f382ce5 | note | INSPECTION/TEST METHOD: Visual inspection
3b174875-40b7-5a87-b922-c7ecf0e636fc | note | RECORD OF CONFORMITY: Signed ITP
94e87180-7434-5978-935a-9d05ac60c4fa | note | IP
6e93a7e1-7f28-519b-8d6e-669704751d5c | note | RESPONSIBILITY: Contractor
8a188474-c828-57d7-93c9-d412e847e2d6 | date | Date Completed:
5b75f64d-7f19-4df3-9a3e-27aff6f7bf72 | checkpoint | 2.3 - Step irons installation (if >1.0 m deep)
29a8880a-02bb-571e-bdd8-f515a3cad056 | note | FREQUENCY: Each pit
14a56304-64bf-5e06-9c60-787e8bfabfea | note | ACCEPTANCE CRITERIA: Installed per AS 1657; positioned to avoid water discharge; epoxy mortared if cast-in
d927bd76-7e3b-56a3-84bd-d838179853ac | note | REFERENCE DOCUMENTS: Sec705.12, AS 1657
297ddac7-3b58-590d-aa77-15f3356b4760 | note | INSPECTION/TEST METHOD: Visual inspection
9e75a0bd-916f-5f65-b181-655fd2e56d6e | note | RECORD OF CONFORMITY: Signed ITP
73b47192-bbf2-5762-aae1-6bc37f1ba970 | note | WP
33b6674a-8bb7-580a-9397-798850b26f21 | note | RESPONSIBILITY: Superintendent
4cb014e9-e5e1-562d-881d-0ac8c38adfb9 | date | Date Completed:
f31fbb8f-15e8-4e49-b604-8ea59e154cf0 | checkpoint | 2.4 - Surface finish and jointing
60e9504d-15e7-5b6a-9a6a-3a30325121ae | note | FREQUENCY: Each pit
bedb07f4-19b9-53df-b006-305daa5d6ed9 | note | ACCEPTANCE CRITERIA: Class 2 surface finish; joints cleaned, wetted, and mortared; cured ≥48 hours before backfill
7a098d98-2742-59cd-9419-fcd17b27bc03 | note | REFERENCE DOCUMENTS: Sec705.14, Sec705.15
7c1059bc-5236-5b4b-97cf-a750be3407c1 | note | INSPECTION/TEST METHOD: Visual inspection
fea39b64-6a98-5052-9527-59b9949b10f0 | note | RECORD OF CONFORMITY: Signed ITP
148a5b22-bb12-5e97-b6fb-bb6bb652b2ae | note | IP
cc1355f3-30a8-590f-bc88-33ed30e6181d | note | RESPONSIBILITY: Superintendent
874e035b-5da6-536f-bb4b-4106cd3303e0 | date | Date Completed:
7b5a879a-4c25-43b0-a608-71c6de79110e | checkpoint | 2.5 - Cover fitting and alignment
354e0b79-a395-5dd2-9f99-b2a2fb546f64 | note | FREQUENCY: Each pit
72f2a3a3-2114-5457-bc0a-9df311a24084 | note | ACCEPTANCE CRITERIA: Covers bedded on 5 mm mortar; level and kerb line within ±10 mm of design
d92dc49e-2fcd-5ce6-85bb-e088e5001396 | note | REFERENCE DOCUMENTS: Sec705.17
0100ea0b-b73f-5f83-8df1-31328c5523a3 | note | INSPECTION/TEST METHOD: Visual inspection
2080bde7-d336-5bc7-9c53-493a3247a78b | note | RECORD OF CONFORMITY: Signed ITP
a75df575-c1a3-59ef-9122-866f27b1f6e7 | note | IP
e33a7d40-ebe2-5806-84ae-c496da2bbf3a | note | RESPONSIBILITY: Contractor
3bfe9f80-b309-5d4c-87a0-13d98d018ae8 | date | Date Completed:
cb301e6e-2316-4113-94a4-5f1f7e761d40 | checkpoint | 2.6 - Backfilling
cd1582fc-0ec3-572c-80b6-7f17a84adf93 | note | FREQUENCY: Each pit
17ef4fe5-b0c0-5e88-8e64-aa5709b95bb6 | note | ACCEPTANCE CRITERIA: Backfill placed in ≤300 mm layers; compacted to refusal using handheld mechanical equipment
acf641a9-ab97-5268-b93f-00b599a7fb9b | note | REFERENCE DOCUMENTS: Sec705.18
c67bda4b-233b-5f50-924c-88cd5a8876bf | note | INSPECTION/TEST METHOD: Visual inspection
3ea4c161-f786-5653-a691-98907321d448 | note | RECORD OF CONFORMITY: Signed ITP
936e3e82-9540-5235-a1d6-c0c81723697f | note | IP
51952829-e3c7-5659-a33c-bd2e4af87292 | note | RESPONSIBILITY: Contractor
8354d9db-39de-5918-8c9a-0591cf3f43d5 | date | Date Completed:
c1d16a02-6c21-420e-9e38-b06295e80de3 | checkpoint | 2.7 - Final inspection and sign-off
3226b5fa-1be6-5bc8-bf5f-177489a76a40 | note | FREQUENCY: Completion
765d66c7-90f1-50d4-806b-a4b4dc3d4991 | note | ACCEPTANCE CRITERIA: All installation elements conform to drawings and specifications; no defects or non-conformities
50510814-d39c-5f46-a0c6-2499746a0513 | note | REFERENCE DOCUMENTS: Sec705
220f113f-7f90-5674-a65e-311b3aba831f | note | INSPECTION/TEST METHOD: Visual inspection
65eab166-6199-5c0a-aec4-4de4ee40c36e | note | RECORD OF CONFORMITY: Signed ITP
58fbc895-59a0-57d8-b683-5b02ce814738 | note | AP
54565775-01c7-5106-8b5d-ea91963bc8ba | note | RESPONSIBILITY: Superintendent
cad81395-e5b9-51e3-983a-b46a90e51660 | date | Date Completed:
584665eb-c3d9-4e88-93ac-2fff7d634d3b | checkpoint | Final Inspection
c7d8f4ba-43ac-5e06-bcc4-a5dd102c07de | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
10ca781b-80c5-52a0-ae03-df8942059e16 | textbox | Print Name:
29938638-0db7-58d0-a1ad-880daec66091 | textbox | Position:
eeca9749-b5bd-5c62-8aac-9b2c454bfdba | date | Date:
80d43600-621d-4715-91d9-9aebe293a88c | signoff | Sign ITP
ad11a893-a1e0-4e7c-9acf-fa344183bd76 | checklist | ITP-007 - Hot Mix Asphalt Rev1 | itp | ITP-007 - Hot Mix Asphalt
8fb2fb16-98bf-426d-88aa-9db02aa770ac | section | 1 - Preliminary Works
ede63562-15a8-49e6-a138-c9d3f73a29b4 | checkpoint | 1.1 - Site Inspection and Base Conditions
3f834e13-2d65-5e96-af44-d4f865b775cf | note | FREQUENCY: Prior to commencing paving.
7f4aaf7d-ea7c-57ae-862c-e3627e1744da | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
9e4d56ea-80ed-5110-80d9-a9d426f88dec | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
e4cb8c23-59aa-5cab-8b37-425285ef37e4 | note | METHOD: Visual Inspection
11317d58-0b46-5641-baea-8de96121e4cc | note | RECORD: Signed ITP
4fcaa443-4c66-550a-9e52-7b572b32ccb5 | note | WP
e1492f32-cbdf-59bd-95a8-41828a70ad2c | note | RESPONSIBILITY: Site supervisor
fc9adb00-4a54-54b6-9a6e-11b5cd0f3f82 | date | Date Completed:
2c2fafc3-517c-4fdf-80c3-5bd1753902ec | checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0051143d-ce08-5377-9528-05e4b1972c38 | note | FREQUENCY: Prior to commencing paving.
966837aa-0136-5210-8593-06168c6e16f8 | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
6f006a6e-5e35-5fcf-8fc3-d53060bd3656 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
ae5e7da2-bf5c-5e6d-b875-4b44eb8e8e78 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
9cbafb4b-c8ec-525c-8c33-94a3fa730f1d | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
ca57b2a5-dad2-5782-a4e7-32283ffa5e27 | note | METHOD: Calibrated thermometer
45862ec1-96d4-5731-992b-7f02222c44c8 | note | RECORD: Signed ITP
059b3ffb-f0bf-5395-ad51-7479c61e2f5f | note | IP
0d976075-3a95-59f7-a325-b6ca869ba998 | note | RESPONSIBILITY: Project Engineer/Site supervisor
29f42c2e-4dd4-5e09-adb2-447cc5eabb58 | date | Date Completed:
f1600b24-630b-491f-9364-aa6f655fb4d8 | checkpoint | 1.3 - Surface Preparation
cc8f3109-166c-567e-8e02-adf6d305eead | note | FREQUENCY: Prior to commencing paving.
26ae563e-922a-597e-892c-dc9981875d68 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
84e6248d-b8c3-588e-9ae3-35c466641c9d | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
cbbb5fe5-43b9-5815-9e1e-b05b303dee39 | note | METHOD: Sweep Clean and Inspect
b6830653-cf9f-549c-8a6d-e3cc94841bd1 | note | RECORD: Signed ITP
eeeaf889-78c7-5e55-8f01-c49552934989 | note | WP
9eb55e7f-b490-5e94-8076-9c8a4d315ce3 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
622dee39-7e2c-5ea9-93e6-a6569bc6efff | date | Date Completed:
7a77a56e-fae2-469d-8f2d-f47c1bae510a | section | 2 - Construction Works
eef53c1c-0d40-4df3-a368-c0c16439a710 | checkpoint | 2.1 - Application of Tack Coat
fcf5daa4-f3ea-5ab6-b11a-f1a94cc7c03b | note | FREQUENCY: Prior to commencing paving
4b752ebb-ceb4-589c-ad09-08a768433de5 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
3bc89894-caed-5119-8884-2e22f06eeb6c | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
41cd073c-3baf-5928-a296-20b1782c6c3a | note | METHOD: Visual Inspection & photo evidence
3b80514f-7697-5158-b438-6bcdb489a786 | note | RECORD: Signed ITP/Spray Record
11ed2dc6-7574-55de-8f5c-4e8740262cf7 | note | WP
5972f22a-ecb0-5d8a-9926-0296cef7f77b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8becd464-895a-54a1-ba77-8bf2510289ee | date | Date Completed:
f09e4948-b94b-45e3-8872-112203ec69c1 | checkpoint | 2.2 - Planned Joints
3d9bebdb-edee-5a9a-a68f-0adbf8d6304e | note | FREQUENCY: Prior to commencing paving
af02af11-ef94-5f87-a84b-bdac1189a08b | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
fbc5289f-cb4a-53e8-a582-347e97402175 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
aa5fb8b1-0a71-576b-bbfc-d95a5f2f107a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
9b218da2-7f8f-5250-84c0-c6b98d7fa4c1 | note | RECORD: Signed ITP/Job Sheet
fbcaadfd-4b6d-52b4-8c64-e48931e2b7ae | note | WP
e763dfe0-392d-52d9-851f-e89373318740 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c2315f14-b51d-52a3-92ad-7b79c663cbad | date | Date Completed:
af3b61a8-064b-4d93-aa39-8dce306aeb93 | checkpoint | 2.3 - Commencement of Placing
ca135723-8dc0-5243-8c56-b5a2df43cc53 | note | FREQUENCY: Prior to commencing Paving
2ea2ac5e-3833-56dd-b966-05315132d7a6 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
d3393fe3-1f59-5b2a-83bd-15caab350630 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
ff5dc533-bd62-5e67-b6ab-91d0dad1356d | note | METHOD: Visual Inspection
95041c7b-7a4e-53e1-bddb-f15632c51634 | note | RECORD: Signed ITP
fac73d84-3b12-5028-8c32-454f9213a515 | note | HP
f310ae5b-7a5e-576d-8055-6094b44a2990 | note | RESPONSIBILITY: Fulton Hogan Project Engineer
a3d16390-796f-588c-b3e1-0a1fae3a6b3d | date | Date Completed:
d0ff0d2c-0dc7-413e-bfea-5ed441febb5c | signoff | AUTHORITY HOLDPOINT
8d367f90-bfe4-4de7-89ee-4a110fc4123d | checkpoint | 2.4 - Delivery of Mix
9f4bc750-2ba5-5940-adfd-a3488a665acc | note | FREQUENCY: Each Load
09e565b9-8176-5a1d-9347-a661bf9ed33c | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
68d368cf-b3ec-5eb3-95b2-058a3d09fb07 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
49ba27b9-3dd7-52f5-bb90-a4c51054ea91 | note | METHOD: Visual Inspection & Delivery Docket
4cdc5a9d-9b87-54c1-bc3f-8ef5150f9a2f | note | RECORD: Signed ITP & Production Dockets
b6011e42-927c-5cc3-9720-48e9c3770919 | note | WP
e652227f-a255-5636-9789-d9abd907dc79 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
1b46a552-1094-5807-a20b-cf811549e602 | date | Date Completed:
3319d752-5fed-47a3-98cd-8c53095a7515 | checkpoint | 2.5 - Traceability
94a90b12-b7a4-5ef0-a739-0e3ddf426627 | note | FREQUENCY: Each Load
5aac4146-087c-5db4-811b-f3831d3f735d | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
2fe90295-67c1-51b0-9f67-378311b9a058 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
b49d7eae-fe9e-5a99-bfd2-172d2bea1dd3 | note | METHOD: Project Engineer/Site Supervisor
b09146e7-6b81-5e6a-833c-63925f07c72c | note | RECORD: Signed ITP & Traceability
125993a2-8284-5075-8cab-060337a2e480 | note | IP
fd05b92a-3e2d-5c75-a0f7-9a98d4503f1a | note | RESPONSIBILITY: Project Engineer/Site Supervisor
35a1cf1c-832c-5fb4-ac13-679cc1fb38c5 | date | Date Completed:
f3916154-dda6-4c51-8f7e-28fc0c0076d6 | checkpoint | 2.6 - Layer Thickness and Level Control
9cf74044-338d-5b2f-8175-8bba3db84109 | note | FREQUENCY: Regularly during paving
30088601-42cf-5572-b3b4-c0bf3b07dec6 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
9027471c-e9c1-52c3-b5fd-9612598dbbcf | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
e38a8591-e198-5e4e-bfe8-0931733c76fd | note | METHOD: Dips, string line, measurements oﬀ kerb
00b0ee1a-5fb0-50d5-bdd0-d773fd2ac078 | note | RECORD: Signed ITP & Traceability
34498218-76ad-5ec1-9f2e-66e0373ec633 | note | WP
9633fc36-56c1-5e3d-b990-f644867ebe76 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c2277a29-bdc0-5e70-b96c-93352691fb46 | date | Date Completed:
03e46b50-2e0b-47f7-afc4-6ef8461cec24 | checkpoint | 2.7 - Paver Stoppages
75f7d136-2ef7-5cb4-a769-10bd53fead2a | note | FREQUENCY: If paver stops
ccb7896b-c309-5658-a86b-49bd76502d4f | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
3fd3c13e-97d2-530b-b6a2-90c271c2232d | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
f3d2b4fb-9579-560a-afdf-6f5370481f26 | note | ○ 40km/h – 20-1
3c87fbc8-e43a-569e-8e6b-fd81912e42b0 | note | ○ 60km/h – 30-1
2548d814-ddbb-54ce-b866-6416396f481f | note | ○ 80km/h – 40-1
f738f555-a562-5e7e-ae72-b352477cae95 | note | ○ >80km/h – 50-1
1d082437-e1fc-5db4-9823-4aaff7c20a3e | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
19f55e99-208b-537b-8428-3baffd692a4d | note | METHOD: Thermometer
0d6c7135-065e-5dc6-9328-094e63c84dec | note | RECORD: Signed ITP & Traceability
f5ef8b7c-a7a7-58ad-9729-caf9a4bd8315 | note | WP
df6ade87-644d-5a45-b572-ec0b6c92483b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
5d4e947a-b8f6-5124-af10-db71353ebb9d | date | Date Completed:
f41e8cda-2392-4608-8910-953ac39cfe02 | checkpoint | 2.8 - Surface Finish of Wearing Course
ea52c2d7-0085-5388-abab-9892adef0110 | note | FREQUENCY: During paving and after ﬁnal roll
241b3cbc-5ebf-5082-8183-92f6585e6b24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
4198cc13-e4fe-5c08-9cb9-b48de680d10b | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
bb53d7f1-6d04-5bde-b4a4-7d09eb83501e | note | METHOD: Visual Inspection
03deb5a0-570c-5a40-8d38-8f8f2a7a1813 | note | RECORD: Signed ITP & Traceability
191f27b6-54bb-5c6e-9b42-52d1934e0871 | note | WP
a2bb6d80-05e2-5379-a77d-fe660b8ae3f3 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c10f9c16-8ba4-51a1-9a7a-6fd169ad38f4 | date | Date Completed:
7f9930b5-a97f-4125-9b92-07df73307d2a | checkpoint | 2.9 - Kerb and Channel
30d44fe1-2b64-5d4c-8bdf-19c3761d47bb | note | FREQUENCY: During paving and after ﬁnal roll
4e694115-e864-5759-8dc0-3c7a1f8bb744 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
59b14065-9094-5100-a4f5-ed3cf0b5f1ec | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
ba054bec-4d36-5f93-ad66-a4e3c0d52b48 | note | METHOD: Visual Inspection & Measurement
eb8c880c-a14f-5917-afa7-9d798987239f | note | RECORD: Signed ITP & Traceability
58424747-707c-5c37-970c-925b94bfba77 | note | WP
e7d0485c-2043-5ee2-978a-a36c0b6b98ee | note | RESPONSIBILITY: Project Engineer/Site Supervisor
4cbde6ac-a031-5147-b9cb-f16210a771cc | date | Date Completed:
a9901a7e-2d10-45b7-bcc0-4648f36119a3 | checkpoint | 2.10 - Alignment of layers not placed against concrete edge
f9b7a7bb-3124-5f75-be18-9e0fed6d4e03 | note | FREQUENCY: During paving and at completion of work
913608e6-d198-5747-ae7c-8932301c8ba1 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
a2d7c24e-091c-593e-a968-36daad056f82 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
20294112-5983-54a1-9da9-a24a8fde2b6c | note | METHOD: Alignment as marked by Surveyor and measured
3e6ffaf1-ccd6-52ce-8fd7-7d55e4f5d385 | note | RECORD: Survey Report
63132329-2f23-5e51-b11d-539677c27072 | note | SCP
3324b555-8393-5383-a273-c383ff42af5a | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
8b930a72-01ed-54b2-9c97-0c76b1483fcd | date | Date Completed:
d184dd7e-cbaa-46bd-ac1a-9906091a6be6 | checkpoint | 2.11 - Width of layers not placed against concrete edge
996eea8e-97b6-58e5-b8b9-e648c1c9e294 | note | FREQUENCY: During paving and at completion of work
dff7e596-edd3-50cf-aafa-be9e414f1208 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5d73ebd1-242b-5f0f-ae3a-9043ec512675 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
605d41af-00ed-5909-ab61-93f4b9f7e5d7 | note | METHOD: Measurement
71cc70d3-fcfb-51ed-b1ce-70e11470dfa1 | note | RECORD: Survey Report
82a3eb0d-e633-520c-a07b-2092c9f49528 | note | IP
c9b84b8a-565f-556d-91c2-1606fc1f57e9 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
941ef6a5-2c0d-5138-8bfd-bdb18e5ace4b | date | Date Completed:
7d720ddb-b79c-432d-a2a8-42c2d8d40f4d | checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
d6cdd5ed-933c-57d3-967d-5de43e92795a | note | FREQUENCY: During paving and at completion of work
530d699c-e7ce-597f-8881-e47553facc80 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
9ec5f66e-f8a9-5945-90e5-ab5bc0b6a837 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
6cc230fa-5735-513b-b121-de5922973e49 | note | METHOD: Measurement or suﬃcient time has lapsed
2a6678cf-3e9d-5b54-91c7-a000014fe5aa | note | RECORD: This ITP
3f82afca-0113-50cd-bef9-c68fdbc02e4b | note | IP
f65f8789-5a61-5265-b02f-f5e78511d78f | note | RESPONSIBILITY: Project Engineer/Site Supervisor
658464a3-fb02-5a7a-b969-cee6831a1e2d | date | Date Completed:
6b239baa-b897-4caf-ac33-eef5790d6617 | section | 3 - Testing Requirements
0497fb4d-7220-442e-95ab-e648b421e16f | checkpoint | 3.1 - Compaction
43da187d-4ee1-52ec-99ae-1d2899dc4708 | note | FREQUENCY: Per Lot (6 shot test)
eea7fdbf-969a-57dc-b602-4ac42c97b06c | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
ac9bedea-dc81-5ed0-8fdf-8ae680322c26 | note | ○ 95.0% or greater Accept lot
c2c78e48-77c0-5afd-a417-29b411bc8c5c | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
94bfa61e-4811-50f0-9c85-491576e4cd57 | note | ○ 92.9% or less Remove and replace asphalt
d20510cb-cbac-5792-b93a-c5ebf1067f8d | note | For layers ≥50mm, if characteristic thickness is:
8d2ee423-6f18-50f4-ba36-e9e6c7445552 | note | ○ 96.0% or greater Accept lot
c5a3d2ea-fb24-585a-abc7-1538b698ac10 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
4cc2da49-7595-5b68-b0cd-66463c829230 | note | ○ 93.9% or less Remove and replace asphalt
893103f3-ff7b-5396-be9b-740f69521e8d | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
d676de8f-24eb-581e-b117-88f510a03ad5 | note | METHOD: Compaction Testing
984973ae-ab1c-52f9-8ef2-0c5b9a897f90 | note | RECORD: Asphalt Field Compaction Report
c32dac89-0182-5655-93ec-1096da5f539a | note | TP
663b4d59-3802-5dc7-bd59-f930269c7625 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
825e9305-7ec9-5a09-bc6b-7521ba06391a | date | Date Completed:
b5647df6-e575-45d3-80a9-c5e6a2bfb0b5 | checkpoint | 3.2 - Surface Levels
e684b7e1-7869-5697-a878-1da3446244e1 | note | FREQUENCY: Each lot as required
13d9f8c8-8077-5c3a-bfbc-ac65c3dd961d | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
d464146f-3121-5560-8c93-3aeb8fac294f | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
509bd4b0-3dda-54dc-a0aa-282686c0445d | note | METHOD: Survey
91c1b990-aede-547a-b0a3-063003ab6ba7 | note | RECORD: Signed ITP & Survey Reports
09beb6dd-3cfc-5a41-818f-cbac6af5c2b6 | note | SCP
18fb2f0c-d5b2-5a5b-b88b-ead251e2d2b7 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
4502068a-2f54-5591-9f3c-17f6d87cab22 | date | Date Completed:
40141e30-1b41-4007-9f0b-f6661b40041e | checkpoint | Final Inspection
c3323dcd-6149-57b6-b5e8-dc3d5a695462 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
d3a06a2d-8fee-5d34-9579-0b6b7ea92a73 | textbox | Print Name:
93e0cf83-857b-5ba4-856e-bceb24078209 | textbox | Position:
7b7b1426-44c6-53a8-b5ad-66c8f08dfa61 | date | Date:
079cfed8-940e-431e-88dc-9effac30299f | signoff | Sign ITP
860dfd61-dd11-4d89-bb82-6e7b0d3b337b | checklist | ITP-008 - Line Marking Rev1 | itp | ITP-008 - Line Marking
237e246a-f20f-45f6-be8f-c9f75ba8fb0b | section | 1 - Preliminary Works
d9467c3e-40cc-42c7-a935-2aec828fae14 | checkpoint | 1.1 - Line marking Conformance
0ffc9ce5-fdc7-57bf-a25d-57d3902893ef | note | FREQUENCY: Prior to commencing any activity
4866c740-3409-58b7-ab94-a061ca278716 | note | SPECIFICATION REFERENCE: 721.A05
2ff8830b-f0fd-535c-ae6e-099adbcbb61c | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
2d196ff3-9eb7-542d-ac72-35f872220eca | note | METHOD: Record Review
16f7c0b5-4fcc-5276-9037-76e8b84afea2 | note | RECORDS: Material sheet
26d8d127-181b-5553-a224-92cbe9eb9fce | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
48e42163-0311-5d29-b7e7-978a4c66c295 | date | Date Completed:
a83a825c-4905-413c-961c-9868f51dad08 | checkpoint | 1.2 - Site preparation
2766b790-4313-5ba0-a449-2de74bb9d9c4 | note | FREQUENCY: Prior to commencing any activity
a8374c38-5c28-5d50-b79e-e8cd3b1d43a2 | note | SPECIFICATION REFERENCE: 721.A06
1a8648cd-7380-5a90-8417-10a396adebef | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
04ccf158-2d4c-5971-9d25-c5ba1532866a | note | METHOD: Visual and photos
eceb05a9-3d7a-50ee-ba6d-95630c5c22c0 | note | RECORDS: Photos
01885bc8-92ab-5b07-a796-446ca64c46c1 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
5adae9f1-d684-595d-a5c8-9aefa011ed07 | date | Date Completed:
e621e62f-1521-4de4-86f2-0589279e9e0f | checkpoint | 1.3 - Set-out of Pavement Markings
a2d34b1f-7548-5e6b-b6c5-92b0e34b6c15 | note | FREQUENCY: Prior to commencing any activity
a4b35e5b-57b3-51b9-914d-671133adcd2c | note | SPECIFICATION REFERENCE: 721.A09
1d2cbe13-7872-5d19-be7c-7f4b817ce566 | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
bee989b5-18ae-5e5f-875f-423a74ee7c8d | note | METHOD: Visual and photos
162bcdf5-4fb7-5369-9f3a-61b885a4a758 | note | RECORDS: Photos
a39e3baf-84ca-52c0-bf03-dd60aa272857 | note | RESPONSIBILITY: IP - Contractor Representative, HP - FH Representative
7b4eb61b-7289-58e2-9a66-069c927f4541 | date | Date Completed:
9c3bb038-2c00-473e-85fe-ac214556750a | signoff | AUTHORITY HOLDPOINT
122605c9-54fa-490b-906a-2df18b2efd65 | section | 2 - Installation
50d83829-cbeb-4eb1-a870-7b03c092ba49 | checkpoint | 2.1 - Line marking Installation
cb1be43d-1296-59d3-ab35-0b4d1ef78730 | note | FREQUENCY: During Construction
ac489085-4a2e-589e-a7f3-fbe5679d552c | note | SPECIFICATION REFERENCE: 721.E01
d7117b9d-814e-521d-9e3b-ca9e05065d42 | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
b03afa3b-dbf7-587f-b7c4-524ac88efae9 | note | METHOD: Visual and photos
047e502f-47d2-5bb7-a306-380f2d2686b3 | note | RECORDS: Photos
e4876d94-e966-5ea4-8bd9-ef70a2e93232 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
055b0990-8940-5205-89a8-0189752f2c2b | date | Date Completed:
1a091473-631a-4722-917e-0bc186130871 | checkpoint | 2.2 - Glass bead Install
0dee327d-3e4d-58dd-b772-39531a5a3b34 | note | FREQUENCY: During line marking works
d30f5856-3b0c-5f68-9fdb-e7ebfbfe867a | note | SPECIFICATION REFERENCE: 721.E01
93de12f7-2ce1-5b4a-af44-cbd9ef369804 | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
c4c1e040-2a84-5fb0-8413-2f624e92a222 | note | METHOD: Visual and photos
597c61c9-d65b-5396-bd5a-688fa6a776da | note | RECORDS: Photos
77645359-f205-5a75-bee0-ed07424ee172 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
f6cffa82-d152-5508-abcc-8667acacfd4a | date | Date Completed:
3f461f9c-848a-4632-b5f5-420064bae601 | section | 3 - Compliance
8d0e1fe8-a18c-4260-a6e7-3cee37398187 | checkpoint | 3.1 - Completion Inspection
6e9e9d42-2c61-540e-b78a-a538f6214923 | note | FREQUENCY: Upon Construction
1fbc4932-7588-53a0-b9c6-9f662d25401c | note | SPECIFICATION REFERENCE: 721.E01
b8c13a98-3405-517d-b0b4-cd17ea559bbd | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
8d981a55-2fd3-58d6-83a2-1a402ff8c72e | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
0ca387a4-14dc-574d-81b6-2c46d7dd75b1 | note | METHOD: Visual and photos
aa56a327-8c10-5212-a673-b568a8304edc | note | RECORDS: Photos
79c0a7e8-a38f-5067-b8e6-ff5119635528 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
2bfd393f-8a77-5d6a-8755-16ad438b33ae | date | Date Completed:
da7db3cf-ecb8-4b92-9b37-f56ecb7858db | checkpoint | Final Inspection
eb97ab66-ca72-5d4e-a87f-e37fae14c102 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
8ede4843-2fc2-55cb-bfca-c5c943071667 | textbox | Print Name:
482720df-f3f2-5040-83e0-39c8be31ccb0 | textbox | Position:
f3ba2c38-8829-5c79-8797-d81944cfa08b | date | Date:
18633851-de57-49be-9b71-7bbe0c335526 | signoff | Sign ITP
41b1572e-b2fb-53b0-8c57-7655a1fefb56 | checklist | ITP-009 - Road Signage Checklist | itp | ITP-009 - Road Signage Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1b96c8c3-d3cb-5511-bdc0-8ad038818b89 | checkpoint | Inspection Checklist Items
dc9b7c6f-a3ed-5493-8998-dbc970ea3834 | textbox | Sign Code & Dimensions
a917188f-ab1a-5f77-b82e-144aef0167e9 | textbox | Chainage Location
c5198dd8-98c3-59ae-a1b4-113408481183 | textbox | Number & Post per Assembly
2477ad5e-17d6-5890-b4ad-005a3ffec528 | textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
98565e99-e225-56ba-bf92-09385b9da396 | textbox | Post Hole Depth (D) (mm)
64db3e30-c50c-5fe8-8663-c497b25407f1 | textbox | Fitting Type and Number of Fitting
dd0678d8-3635-54eb-bb12-b59c577f0e13 | date | Footing and Sign Installation Date
9600558b-1bcf-560a-b940-10cd212b3d9d | note | Photos
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
4c619913-70b2-59b9-8e85-7aa07009facc | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
7c9377e4-e5f8-5220-be1f-c2b39c3c57de | textbox | Print Name:
f6476e10-3a1a-5684-898c-a073d3a3fdf6 | textbox | Position:
bd7fa19e-daa1-5a8b-9ef3-03c4d76e0e2f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
981e7153-3854-5c45-8bbb-2905670016f0 | checklist | ITP-010 - Guardrail | itp | ITP-010 - Guardrail
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
0ec57c45-86f2-5bdc-b58b-a216f96427bf | note | FREQUENCY: Prior to commencing any activity
086cb6b8-35d8-503d-979c-02b0754ff62e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ab817a45-c92b-5e09-af6c-7c7e05ebd0bf | note | – using the correct and complete set of drawings
0e87b665-1836-5f00-8bd9-0aff94e5fb43 | note | – all drawings are the latest revision..
aa50f204-8caf-51f3-b943-d67d410f8d74 | note | REFERENCE DOCUMENTS: Design Drawings
4a0abe65-ea75-56fc-871d-5432bf3fb90c | note | METHOD: Visual Inspection
251f8e93-1153-5553-8544-9e01118b4ab8 | note | RECORD: Signed ITP
03256eb2-10f7-5eb2-acbc-768daed6ab0d | note | IP
82c51713-01e0-5753-b05a-f8bc425c1a90 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
6dcf91aa-ca4f-5cd5-bded-9751eee20558 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
5afcc918-dc4a-558f-aa76-735dfd2c28bb | note | FREQUENCY: Prior to commencing any activity
663cff31-6696-5aa8-af87-521b6453cf31 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
6a2336c7-2787-58be-84c1-3df28befa56c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c37a8318-8c2d-5a69-8c75-a83252fb4bc3 | note | METHOD: Visual Inspection
f341f913-15fa-54c4-97bd-e055ff085002 | note | RECORD: Signed ITP
5742e225-b980-5fa7-b89e-fd6a8e25bfc2 | note | IP
12c453ab-0f00-53a1-9a99-d7a762d45f9b | note | RESPONSIBILITY: Project Manager/ Site Supervisor
179b0df0-6817-59e8-83a9-f173c1ad472a | date | Date Completed:
73920d7e-e2c5-5db3-bfa8-d36b7058a4c5 | checkpoint | 1.3 - Setting Out
4c70ffe9-0fd7-59db-aade-198edbbb95fa | note | FREQUENCY: Prior to commencing any activity
8dd0c908-2af4-5773-b10c-1cdd07379690 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
caac9424-8219-5a49-be8c-0b27d7d96fdf | note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
f0a37273-72f2-5e02-a92c-218a38f5abef | note | REFERENCE DOCUMENTS: Drawings 708.08
a0b2264e-1557-5811-a657-fa658781abaf | note | METHOD: Document Review
25ba3632-56f1-5b5b-b635-2d5d334c04af | note | RECORD: Signed ITP
f9e669d5-a8fc-5868-88b2-85fd11d2861b | note | IP
5f22be86-56b4-51c7-a4f6-77db6d3b4243 | note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
540fad9a-8918-51a5-bfb3-689327283865 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
9579dbba-7fbc-5ddf-a026-c6bd5bf26814 | checkpoint | 2.1 - Supply of materials
07311716-27c3-59bc-8c66-34ff2ec8f1e8 | note | FREQUENCY: Each Delivery
41fd03e0-71a3-5cf0-8d71-d65231baead1 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
8e743b2d-c7ea-5d17-8f27-b941961e81bb | note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
65b15744-9046-51d6-9b49-9c0cb11e31e5 | note | METHOD: Visual Inspection
70bdaa8e-43b7-5dea-8b64-f89f86506728 | note | RECORD: Signed ITP
1e7a1bf2-e8a9-5d1c-bb3b-ec9a92bfb1d2 | note | IP
d5b348f3-513f-539d-9466-d8c71722ef26 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
0c0c4c74-906d-528e-b904-8c78909e065c | date | Date Completed:
a11c7727-374c-58fe-ae54-aad72e43d297 | checkpoint | 2.2 - Installation
85a5de76-58b8-5d60-aee8-b55099377790 | note | FREQUENCY: Each lot as required
8db5e8bf-9e53-5d1f-a2c4-2912b045a9c6 | note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
88f58727-1259-5f70-9b1b-a724f725415a | note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
c5f6a30b-5ebc-515c-b4c2-7a399533416b | note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
5f83d83c-6406-5083-9409-db6c8a43b72d | note | METHOD: Visual Inspection
fe660ed2-bef8-5c2e-9d8f-c860f088952e | note | RECORD: Signed ITP
b2c24674-080a-5153-8c78-959dfae3b2bb | note | IP
01ba80f2-36ab-5720-b70e-1c3e7a2f224c | note | responsibility: FH Engineer/Site Supervisor
cd466e90-8a5b-5335-b067-d55ed355d4d9 | date | Date Completed:
1a622dd6-72db-5c53-b748-bd2deb588d9c | checkpoint | 2.3 - End Treatments
51b415f8-bb9e-5625-823b-01f660682781 | note | FREQUENCY: Each lot as required
57c5859d-5b20-5d54-8805-88afb2bad015 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
0bbb2739-8a95-53a2-ace1-5e372d6aed4b | note | REFERENCE DOCUMENTS: Detailed design 708.08
6ea32cbc-291c-531d-b0a3-17bcdbd44c54 | note | METHOD: Visual Inspection
370fc108-8336-590c-b227-ef32a7bac163 | note | RECORD: Signed ITP
623b922e-10a0-5aee-bbb3-be120111e4dd | note | IP
edfa7fad-f9b0-59fe-badc-78506f6adf76 | note | responsibility: FH Engineer/Site Supervisor
c070f63d-cad9-520d-a077-313ac75e4be6 | date | Date Completed:
7d961610-33b0-5075-8b0b-29fcab9d6e50 | checkpoint | 2.4 - Motorcycle rub rail
4d5697fd-9c4c-5f8f-a59d-ac37aa7b95a5 | note | FREQUENCY: Each lot as required
a748f548-eee9-5b61-873c-7ce62cbd9938 | note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
237b6204-7728-5f89-802a-f6314a444077 | note | REFERENCE DOCUMENTS: Detailed design 708.09
7509c32b-e1e2-562b-b3f5-6ad6425f2f4d | note | METHOD: Visual Inspection
e6c525e7-02f8-56aa-83bc-8a3ea15886d5 | note | RECORD: Signed ITP
54c65d0e-d8a3-539d-a84c-45b0a1bc4744 | note | IP
6ac946d1-567f-5d9d-8b3d-0ce869d45aaf | note | responsibility: FH Engineer/Site Supervisor
29a00349-f5ee-5795-8f98-7a256ef90ccf | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
6ca108b5-1937-510e-89f1-beae553f2df9 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
68028ba3-22e7-5c2e-bfd6-3aaf14cc3eb5 | textbox | Print Name:
d1dbdee0-8b8e-5e3e-80e4-a67262f3bc1a | textbox | Position:
59922202-9206-54e2-84fd-08300ad09ec6 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
03f66bb4-f5f3-461d-b781-a49c242883f1 | checklist | ITP-011 - Sprayed Bituminous Surfacing | itp | ITP-011 - Sprayed Bituminous Surfacing
93fa33f8-7709-4651-a627-7b7c9e2c601b | section | Details
61445f3d-639c-4a8c-8504-0d21de680733 | checkpoint | 1 - Preparation of sealing
cff9242f-fbf8-5414-a073-7c24f2147ca9 | note | SPECS REFERENCE: VR 408.02
d7002269-39bb-5c18-8acb-7d67cb836944 | note | DOCUMENTATION OR ACTION: Constructed to meet specified shape and level requirements Homogeneous and consistent with the material in the pavement base layer
03e69ba4-7cfd-5e10-a787-fc76737e851d | note | ○ Uniform in texture
997ca655-6d14-5f63-ae43-deefda2fe657 | note | ○ Free of tearing and scabbing Free of lamination on or within 75 mm of the finished surface
ee5eb2d6-c6e0-54ac-bd58-9dff98adee76 | note | ○ Level with adjacent sealed areas and edgings at the Joints
07fa5320-f833-52ca-a4d8-56e1d5423a70 | note | ○ A hard dense and tight surface capable of being swept with a rotary road broom or similar
22bec890-726e-545b-869f-9fe06789423a | note | ○ Free of looses and foreign materials
c96b2033-e4df-546e-bac8-fbb7867b0095 | note | ○ Dried back to the moisture content and embedment requirements specified in Clause 310.03
97c6f657-3ea3-5663-a1ba-4581d6e97bba | note | RESPONSIBILITY: Subcontractor
e9f9a715-c5a1-5aa8-b0d9-8eba4fdf9cc0 | date | Date:
53907519-1ab6-4476-9938-2962499da213 | checkpoint | 2 - Preparation Testing
7c634490-6015-538a-a348-f9d2cfe61861 | note | SPECS REFERENCE: VR 408.03
c56e711e-aff9-5a3d-b1ed-07ff2b29065a | note | DOCUMENTATION OR ACTION: Testing Scale B
44652329-ef93-515f-8534-88c1cd58a165 | note | ○ Maximum lot size 4000m2
8644e199-81a1-50c7-ae3b-880e86303553 | note | RESPONSIBILITY: Subcontractor
de0a892a-c892-5f26-b12e-41d9d924a6d9 | date | Date:
65490af4-83a4-4c27-aef5-6be9b8b7fdef | checkpoint | 3 - Commencement of Work
fef1d9b1-725a-5e37-96a4-f394d2fc4cf2 | note | SPECS REFERENCE: VR 408.03
a25ddcf7-7c52-5924-8844-b95750a8813e | note | DOCUMENTATION OR ACTION: HP - Work shall not commence until the contractor and the Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 prior to the work occurring.
1d32c36a-8ed9-5339-8a45-3d003584a501 | note | RESPONSIBILITY: HP VR Rep. AP
ff6d0caa-d896-5f33-8d7a-59f94181363d | note | ○ Site Eng
3b6e8706-a439-5fa4-badd-caae6bf1deea | note | ○ Superintendent
7782d94d-6c9f-564b-b7c9-10c4bd99bf72 | date | Date:
839c7d89-ca80-4cb2-bd8f-cef957b74b57 | signoff | AUTHORITY HOLDPOINT
b4a40e44-a39d-43e3-bf76-36129bdc832f | checkpoint | 4 - Limits of Work
e18accc4-2d19-5919-930f-f409a1b99a0e | note | SPECS REFERENCE: VR 408.04
7e243a63-d5e4-5050-aa9d-5db4b0edc39c | note | DOCUMENTATION OR ACTION: Limits of works shall be marked out as per drawing and table 408.161
2cce2553-e5cf-5d81-8814-5f1f40a8ee4f | note | RESPONSIBILITY: Subcontractor
387ae2b0-c89d-51a1-ba02-f295ab0bb789 | date | Date:
563edd87-7324-4f54-9e4f-fb1fa2a3cee5 | checkpoint | 5 - Materials
6db03085-d758-5c99-a3a4-a58934548ce5 | note | SPECS REFERENCE: VR 408.06 & 408.07
891f46eb-3c91-590e-91f2-325a15392390 | note | DOCUMENTATION OR ACTION: Materials to comply with specification, contractor to confirm materials to be used
64781f3f-a6ac-5604-a58a-f9a8ac13d58e | note | RESPONSIBILITY: Subcontractor
df73da13-cfa5-507a-b8d5-f3fd861f0aa5 | date | Date:
45b6c6a6-c68a-4e35-a8f2-c510f0620819 | checkpoint | 6 - Application
8f6b9b7f-0b2f-518a-a972-5bb9dd0cf155 | note | SPECS REFERENCE: VR 408.10
1a7e132d-8708-59b9-b608-c7a77e215fef | note | DOCUMENTATION OR ACTION: Supply Seal design to superintendent for review prior to application of seal and application rate not to be less than 0.1L/m2 for design
5ff11baa-48fd-572f-9990-0ce0ae2ffbad | note | ○ Minimum air and pavement temperature to e not less than 15 degree C
bf3a2abd-ad0f-559e-825e-5708f3e46793 | note | RESPONSIBILITY: HP Subcontractor
222ce37d-b482-598d-85d0-f9d23d9ab337 | note | ○ HP VR Rep. AP
bc32dd88-2348-57d0-ad19-95308a7838d4 | note | ○ Site Eng
57a265c7-a187-54d0-be46-3cef9c455607 | note | ○ Superintendent
e0022086-b80f-58a5-8ea7-c7ffa8f4bf63 | date | Date:
eeca1da1-4600-4fc1-8b3d-9b7029bf1987 | signoff | AUTHORITY HOLDPOINT
da74c6f9-4421-4d05-a8d4-c06a4df50890 | checkpoint | 7 - Removal of Loose Aggregate
79365212-2431-5aa9-af12-628355a4dd65 | note | SPECS REFERENCE: VR 408.11
eb58a75d-62c5-53eb-8e06-84bc5864fc28 | note | DOCUMENTATION OR ACTION: Aggregate to be removed within 48 hours of application.
11ba391d-064e-5d05-98a4-e0d9439ee920 | note | ○ Road to remain appropriately signed until aggregate is removed.
3a0ba5ad-9765-52d3-9646-aab916ec96ac | note | RESPONSIBILITY: Subcontractor
c9ee018a-9160-5029-9b7f-3344f79d7c27 | date | Date:
a7862975-0bb7-4178-9932-8669feafa809 | checkpoint | 8 - Acceptance of Loose Aggregate
6cdcba82-98f3-5cb4-ae57-8152ab7eb73a | note | SPECS REFERENCE: VR 408.12
93dde1d9-04d7-53ff-8580-4edafe0b6426 | note | DOCUMENTATION OR ACTION: ACCEPTANCE OF SEAL
7c66ee3b-9bd8-5e5d-94d1-0561220aee67 | note | ○ Accepted application rate shall not be 0.1L/m2 less than seal design rate
a9496df0-d14a-50ad-8ead-72b15f418dad | note | ○ Surface texture shall be based on visual assessment
97b29395-f65b-5e70-8a52-19d5e89bb215 | note | ○ Aggregate retention shall be based on visual assessment
acc827c7-f818-5b09-98ea-0c3e99ee1942 | note | ○ The seal shall appear visually uniform.
7e93cd0b-3a5f-5386-8179-375e0355db1a | note | RESPONSIBILITY: HP Subcontractor
48645473-3fca-5301-8600-9dbe96a446af | note | ○ HP VR Rep. AP
9a8b9bae-fc69-535f-8f39-29b0afcaba3e | note | ○ Site Eng
fde1ea6d-a8d3-5e63-a71a-21e8ea979b64 | note | ○ Superintendent
a359a989-ace0-54d9-a870-609bb7380fd8 | date | Date:
729f4191-3252-4a0e-bc0b-a5205e8e1d72 | signoff | AUTHORITY HOLDPOINT
4bbbd276-1409-4b7e-8cc3-003929e7fe06 | checkpoint | 9 - Maintenance of Seals (Repairs to Seal)
5c3eae87-5151-5708-9019-90ba14fcbfc7 | note | SPECS REFERENCE: VR 408.14
37ddc42b-f785-56b9-bfed-9e9f3f88e1cd | note | DOCUMENTATION OR ACTION: HP - Superintenden t to approve the proposed treatment to effect the above work before undertaking the work.
55c29598-be38-5343-ae21-2ba328f3f1cf | note | ○ HP - Where the treatment for protection or repair of a seal involves the application of a further seal coat the Superintenden t shall approve prior.
c2b7714b-6c69-5c9b-8e9d-623eb1cbb504 | note | RESPONSIBILITY: HP Subcontractor
6842f207-63a1-52b3-8781-affd1675d053 | note | ○ HP VR Rep. AP
15f70d05-08aa-5d97-9878-9eb73d7d720a | note | ○ Site Eng
92f41fee-4a70-532b-b1ce-dbad34bbdda3 | note | ○ Superintendent
cd1b0a17-c7fd-5944-b209-f82c5d70fd20 | date | Date:
a282a80b-0bb9-4165-a879-c6c00e36851b | signoff | AUTHORITY HOLDPOINT
0f4d7f4a-48ec-4de1-93ed-bba1db217d39 | checkpoint | Final Inspection
00d6ecf3-5858-5420-94a9-5dbf1851a393 | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
35eaab8e-8b45-586c-ac1d-4c6fb0f8f6ba | textbox | Print Name:
96576342-c889-57f0-8c40-42beab02b0d3 | textbox | Position:
fe9f077d-c8a5-556a-b72b-6bbacf73c5a4 | date | Date:
e55d43e2-7d63-4b95-acde-9602d72b45bd | signoff | Sign ITP
d8c5d0b3-b309-4557-be7e-eb7e696b8d14 | checklist | ITP-045 - General Concrete Paving Rev1 | itp | ITP-045 - General Concrete Paving
ee718103-0f4f-4115-8144-930487f652d8 | section | 1 - Preliminary Works
65c28b11-8c8e-4b11-ae75-09180521d32f | checkpoint | 1.1 - Check for correct documentation
a678cf0b-eee3-5ee2-ba1e-2698419ffd56 | note | FREQUENCY: Prior to commencing any activity
47358bec-9698-578b-b6bf-9c5a1a29faa4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6d64e38c-a22e-55e8-aa72-7a7623804bdb | note | – using the correct and complete set of drawings
dc61fe6c-ce6e-5a56-9988-7d99b813ce4e | note | – all drawings are the latest revision
28e48fbe-703d-574a-b2ec-0872126bc1f0 | note | REFERENCE DOCUMENTS: IFC Drawings
a41eae10-5575-5298-9645-996511f48af3 | note | METHOD: Visual Inspection
d8373706-0733-51f5-812c-2102162f3e95 | note | RECORD: Signed ITP
0efc2203-0b5f-53eb-ab46-905ce5f7ad62 | note | IHP
11a97480-fbec-5a71-aa01-75f72a828b52 | note | RESPONSIBILITY: FH Project Manager
8ec2ed40-c950-5beb-8165-c163be134472 | date | Date Completed:
a16c11bd-94d9-4d2c-8518-603ac09d8372 | checkpoint | 1.2 - Implementation of all measures and controls
73dc78dd-b9f9-5bd2-9c75-227762730a87 | note | FREQUENCY: Prior to commencing any activity
da63006d-c68c-557a-9f4e-8c888a7a0c11 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
956296d5-dd4f-5c52-aa8b-de3deb9875f0 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
04f1d6bf-e310-537e-9c2e-e8f00d4f1671 | note | METHOD: Visual Inspection
54b29d5a-fa22-54c2-a491-e30197a0126b | note | RECORD: Signed ITP
0a79697e-c55c-5de7-8d17-64f5662c12a4 | note | IHP
a9d4c4b7-03b5-5241-8bc4-fc75e86d44e9 | note | RESPONSIBILITY: FH Project Manager
5da36c95-34e2-5278-80f4-8cbd8f07e0e0 | date | Date Completed:
b55f3b7e-fed5-4682-8a4f-c99eab94b3c3 | section | 2 - Construction Works
8945263f-d853-403b-8259-72ad2c65e046 | checkpoint | 2.1 - Survey Set-Out
7143d719-47c1-5eeb-8aad-76b9d6177d12 | note | FREQUENCY: Prior to commencement of excavation.
3dd9ee5a-6b04-590b-8217-adb47393a6a6 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
fa11f811-fde4-519f-b31d-741af12c6f00 | note | REFERENCE DOCUMENTS: Work Procedure
808235a6-9ad0-591c-ad7c-9cc4c46547f7 | note | METHOD: Verify
8e24cc82-5a5f-51a4-9ec0-121d5ea608d5 | note | RECORD: Signed ITP
ef822d52-52c0-51a7-8268-fb8cb9d3a69f | note | IP
50f12078-7ab4-5f5e-bd16-74cb03252efd | note | RESPONSIBILITY: FH Project Manager
1db20acb-4da9-50c5-9bc5-f9ebe0b70cab | date | Date Completed:
d360dd5f-38ab-4df6-858f-ef63a8895896 | checkpoint | 2.2 - Excavation Permit
bf6a906c-0e98-5bfb-aca3-bd33a8420d25 | note | FREQUENCY: Each Lot
ca4ccb1b-73fc-5b85-8f66-4c7559cd490a | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
dca373db-7b05-5d38-aca6-70b5085cf55f | note | REFERENCE DOCUMENTS: Excavation Permit
2f9bd74f-5d2b-517a-9f16-5cf28b103ae1 | note | METHOD: Verify
37e9bd4b-15cf-5442-9b75-9507835523b0 | note | RECORD: Signed ITP
91dc7219-9477-5202-ba77-232f4f6e69b9 | note | IHP/IP
1aba0382-3c61-5941-b76e-4c1d6c5b3cfc | note | RESPONSIBILITY: FH Project Manager/FH SEQ Adviser
0e120987-8a7a-58e5-ae32-f6aae258e285 | date | Date Completed:
1f9327e9-516c-4294-b51d-9ba3bfa20c0e | checkpoint | 2.3 - Formwork
295d85a9-3915-5068-bfb7-a2af9df94fec | note | FREQUENCY: Each Lot
771c2cbd-2e28-54f6-8aae-8bd4c7a682ad | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
ee8bdbe6-3094-5b19-88a9-964a7d45ecb1 | note | REFERENCE DOCUMENTS: AS 3610
7a60bac8-cc48-519d-88d3-e72b39b9c89f | note | METHOD: Site Inspection
100fbb9f-c059-5f79-b7e8-f65a4658d5f0 | note | RECORD: Signed ITP
41cf2064-9ce4-5a04-bf91-677477147041 | note | IP
fc29822f-f5cf-535d-812f-de5ca5dcfad1 | note | RESPONSIBILITY: FH Project Manager
c10ba11f-71ba-5175-9621-bd15ee6b3812 | date | Date Completed:
e660d5f3-3efc-4702-93fb-f55c5d75570c | checkpoint | 2.4 - Reinforcement
4555017e-aeab-5579-861b-24ea9a8736da | note | FREQUENCY: Each Lot
67abc454-3e80-5124-8264-71057ef307ac | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
9dbf8066-1b28-521e-ac19-e32e0afa52aa | note | REFERENCE DOCUMENTS: AS/NZS 4671
bb951a37-1511-5454-a9af-6ea3165a2063 | note | METHOD: Visual Inspection
fe70f0af-3ba7-5d3c-bb7d-da7590a0cc79 | note | RECORD: Signed ITP
36fec6dc-4671-5e7c-bbb5-2680aa9a18d0 | note | IP
bc377710-27a8-5613-859c-c2a8c4b24cbe | note | RESPONSIBILITY: FH Project Manager
dcaffb91-3dee-5b16-bd3c-7f90aefba176 | date | Date Completed:
da2b1b77-169d-4574-ab09-a3f5d5e8a127 | checkpoint | 2.5 - Temporary Drainage Provisions
7a80d2b0-3b43-56c1-85ab-9e32f039607a | note | FREQUENCY: Prior to commencing
63f96b53-70c3-54ae-9dfc-40a497c9e157 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
c3a72674-8de6-52b7-ab74-631d159f7376 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
b431ddb8-8a11-57ec-b35d-4c351a70637d | note | METHOD: Visual Inspection
451eea4a-d34c-53fc-9526-c54b4fca6722 | note | RECORD: Signed ITP
96b6202c-4cf3-55a7-876f-50f52955919a | note | IHP
7b9d281c-46f5-507e-beb9-36c965d0b68b | note | RESPONSIBILITY: FH Project Manager
05f9598b-d35e-5726-a476-a89b72d1f576 | date | Date Completed:
fd81ec31-49f8-4212-994e-42c9e11f0eb0 | checkpoint | 2.6 - Bedding
f8fdcaab-c661-5d4b-8fc6-847b7ccc0be2 | note | FREQUENCY: Each lot as required
f6250143-c792-5a8f-be0c-d6bf3477ad5e | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
b29243b9-b444-5b77-902e-2ffed39af517 | note | ○ Bedding trimmed, moistened, and compacted as necessary
70e200d5-0d2b-5b4e-aded-7ed05ff0b5b8 | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
8f2fe147-9e17-59cd-a828-5e93f44ac856 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
42840c7b-f45b-5e15-962d-a120738d692c | note | METHOD: Site Inspection/ Document Review
a0b4b235-9ac9-5e05-ba77-0e0eae64048c | note | RECORD: Signed ITP
d9518778-070e-5f25-929c-0527b29d66a8 | note | IHP/AP
7f45acf4-66cc-5f39-b47c-673ab0ae844f | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
ecdd2fd6-8b4c-544d-89c1-f26c3d57a9d7 | date | Date Completed:
ce1c4f73-eb1d-4c02-bb48-00a4e27fdff8 | checkpoint | 2.7 - Concrete Placement
1c68cf3a-4740-5ee3-aa79-ee123be169a8 | note | FREQUENCY: Each lot as required
7f706949-1a89-573a-b670-9049f8006325 | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
0ebaf9ef-7b06-58a1-bec4-a57d08eaf184 | note | ○ Comply with requirements of AS1379
9f67beb7-0567-50ab-b93c-f7bf822dfb81 | note | ○ Aggregates to comply with Table 703.051
b9d29c8c-cfeb-55d2-a0f1-34c52ce8f728 | note | ○ Extrusion machines cement content ≥ 320kg/m3
75be63ff-0ab0-53fa-8d55-6369b938a574 | note | ○ Surface pitting < 5mm diameter
c6861856-9520-5926-b2f0-0392b52335f1 | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
fa6f36fb-83f9-540d-90b4-651595d1d7c7 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
8312bdd7-6690-5c3a-a2e0-e1000227e84f | note | METHOD: Visual Inspection
4eddb95c-5ab5-5fce-ab07-5d33103e59a6 | note | RECORD: Signed ITP & Test Reports
f35b47b3-395a-5c56-a6cd-537298fdf2a1 | note | IHP/AP/TP
f3dd9770-ebe8-52d9-b84a-de63cef423e4 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent/External testing Company representat ive
f5c477af-e372-5b4d-89c0-116cb8cb1dad | date | Date Completed:
2073f5ee-3ad7-41f9-966e-6bb3b0e8aa4d | checkpoint | 2.8 - Finish Surfaces
6a2c015c-865b-5735-95ae-fde7814c9bbb | note | FREQUENCY: Each lot as required
029ce11f-2172-5f68-b475-078923ea3231 | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
ded89165-d9b2-58fc-8eff-c4ca576cc40b | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
e22b5289-68ed-5f5e-bded-285c4367ad90 | note | METHOD: Visual Inspection
7b0494e4-d68b-58e2-9266-d327246da3d6 | note | RECORD: Signed ITP & Test Reports
44c318db-ddeb-59ef-b629-a142d56e96e3 | note | IHP/AP
5a31a44a-5147-59ad-bc85-6ba2586dfa81 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
6310e9a9-de3d-5bcd-a206-eed60fb2340f | date | Date Completed:
e76df3a4-290e-40cc-a763-9b0a1b7cb098 | checkpoint | 2.9 - Tolerances
9a93f120-d4e1-5593-a741-e8aae09268ba | note | FREQUENCY: Each lot as required
d1475efb-ff0f-5afc-9db4-40e1fc52bb73 | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
c3d6dcea-f4c4-52e9-b99d-c429f4a1234b | note | Section dimensions:
8a0f9332-07a4-5eeb-b4ba-819847adb333 | note | ○ Within 5mm and 15mm for width; and
e6ff4f09-0479-565b-a2d0-2e08d7d07323 | note | ○ Within ±3mm for dimensions less than 25mm.
3f4d58cd-2d24-587e-85ed-2de6546124ee | note | Concrete footpath:
cc77f7a4-6b60-50b2-ac7c-3fc5e204dd93 | note | ○ 150mm thick
921d43b1-cb50-52fa-9a6a-0b162f0e0f4a | note | ○ SL72 reinforcement
34ebcac8-eae6-5f3b-b299-d16ba8bd5a37 | note | Concrete Surfacing:
143705d7-1780-591e-bbaa-7006a68c765c | note | ○ Type 1 100mm
15a0cc5f-6dd2-5259-8497-c562df302457 | note | ○ Type 2 150mm
222386a7-0786-5ece-899d-8c3ba011f4f4 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
4b265422-316b-546c-b016-e3fb374e6835 | note | METHOD: Visual Inspection
3f16f303-fe92-5636-80db-6f0f47ba5214 | note | RECORD: Signed ITP
044f889f-5161-5edd-91a8-2843da374532 | note | IHP
601979c2-322f-5c62-ad0b-eaa14aae8eae | note | RESPONSIBILITY: FH Project Manager
94be7381-98be-50f4-9de9-6be188f9b923 | date | Date Completed:
9a68e8c7-1760-46a9-beab-bb69f6b979b1 | checkpoint | 2.10 - Joints
739f5244-2600-5330-b4e3-f50218f1cf28 | note | FREQUENCY: Each lot as required
9a54c6d3-35f4-5da4-8c78-18be884f63b9 | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
3ec372bb-1b75-5ab8-a83d-2920df7dbdae | note | ○ Expansion joints at 12.5m regular intervals
c716083c-2261-584d-9511-b5f95c51184f | note | ○ Control joints at 2.5m regular intervals
f2cb709b-314d-5eb9-b658-6cf4458c350b | note | ○ 20mm deep and 5mm wide
dca62a8c-df60-575f-b597-de18c6dab629 | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
bf1330bf-003a-5571-88ad-0a34a4c44291 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
2a3fc51d-81a8-5a7f-9e39-fde0dea01981 | note | METHOD: Visual Inspection
729d21ac-d19b-51d4-869d-7a2f88041b72 | note | RECORD: Signed ITP
46d49ae4-9488-5882-8685-bc37aa268313 | note | IHP
832d053e-8cb9-5ad6-bca5-b7c7e4ed089e | note | RESPONSIBILITY: FH Project Manager
ab414be7-383f-578c-a19d-c8e4ed80518a | date | Date Completed:
7b71b39e-8813-4a9a-a717-b1c86f054fc3 | checkpoint | 2.11 - Backﬁlling
1b3ba207-95ea-5b32-bdc8-9ee7f77015db | note | FREQUENCY: Each lot as required
1c0963be-9f7d-5a91-a98a-30833735d197 | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
8a1c5021-85cd-5d6d-bc31-c6b6d22df184 | note | ○ Width ≥ 300mm behind edging to top of edging
4003e6f2-a6d7-576d-ab45-610f6ce3b96a | note | ○ Topsoil placed after 3 days of concrete placement
4b98ac1b-900f-5b57-bb75-4bcca0d5c4e7 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
03a623f8-6158-54fc-83aa-b407cb5ebf43 | note | METHOD: Visual Inspection
71493979-bcf5-5d26-a27f-9b65f1dbe69a | note | RECORD: Signed ITP
05bd00b5-5f8a-55ae-982e-795e255290af | note | IHP
36647594-ba02-5d5c-befe-65585d23885d | note | RESPONSIBILITY: FH Project Manager
aabf1989-3179-5dbc-a1f9-66d1f87bb6d8 | date | Date Completed:
ebb46c88-1159-4772-93f1-21f11c679723 | checkpoint | Final Inspection
707109ac-fa76-597d-80ad-513a946aa019 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
09db49a6-4811-55a0-a8fd-a15ef120e826 | textbox | Print Name:
644fb0d4-793a-599a-bbac-eabc7f8feaa3 | textbox | Position:
b6180b90-47f1-50fe-87b1-7d62645e6fcd | date | Date:
ea4d1aad-b2a7-4a2d-b185-e8ae23dc8e39 | signoff | Sign ITP
99e3f24f-a60d-451b-8cfb-fb612a715198 | checklist | Proof Roll |  | Proof Roll
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e4b19a51-35ba-4f79-b684-1067444740d8 | checkpoint | Proof Roll
fb379d65-bb79-5f43-82fb-94ee8432e1f5 | note | FREQUENCY - Each Lot
1f80bc96-c1da-540e-85c4-7d53c9b791cf | note | ACCEPTANCE CRITERIA - Stabilised layers shall pass test rolling in accordance with Section 173, prior to acceptance of the layer.
16162740-7f58-51b5-aaad-4be408deb23d | note | REFERENCE DOCUMENTS - VR 307.10
3f723108-0521-5ad2-874b-96b2a53a599f | note | INSPECTION / TEST METHOD - Visual
61da5592-7413-56f7-94a3-05abaa610fdf | note | RECORD OF CONFORMITY - Visual
4209055a-2aaa-5f3a-9c1f-85d07f51c923 | note | HP, WP
c602e713-940e-555e-9b96-35bfe0617239 | note | RESPONSIBILITY - Project Engineer / DTP
4f8230f2-7144-5bb4-aa0c-bc486b1f9dc0 | date | Date Completed:
4c8be00a-c372-4015-8ffe-5567fbf235eb | signoff | AUTHORITY HOLDPOINT

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
ca25c40e-9a05-4435-be1f-e46af8b52a02 | checklist | ITP-001 - Vegetation Removal | itp | ITP-001 - Vegetation Removal
2d2cdfd4-4ccf-409c-bf6e-7782a551920e | section | Vegetation Removal
64fbcb5f-3f2a-400d-baee-f2993f5ee0e1 | checkpoint | 1. - Establish cultural heritage area
54038414-ebed-5174-b90d-17d36132ae79 | note | FREQUENCY: All Areas
b8f7a38e-cd70-5333-8025-2976d0147707 | note | ACCEPTANCE CRITERIA: Bunting around the areas
3c14374a-2ca5-55e9-8e09-f45520654fef | note | REFERENCE DOCUMENTS: Project Drawings
d4ce6b7a-d941-5300-a4c9-03779609730e | note | INSPECTION / TEST METHOD: Visual
08ed8cf5-77f1-5a05-b79e-a8fb7f1bafd0 | note | RECORD OF CONFORMITY: This ITP
c870a17b-7789-5318-9bb0-3a6514badcc9 | note | HP
782be038-9022-55d6-b072-7588301dfe83 | note | RESPONSIBILITY: Supervisor/Surveyor/Environmental Co-ordinator
04f0f57f-4514-5863-a1ba-eacfcf72f739 | date | Date Completed:
ae959018-15a2-4a6b-85c0-50416fe070bc | signoff | AUTHORITY HOLDPOINT
df2d11b3-8688-42a7-b850-343524858973 | checkpoint | 2. - Establish track alignment & clearing limit
dfcef31e-1c8c-5787-b44c-5fe4a4e3aa74 | note | FREQUENCY: Every change of direction of the horizontal alignment
26e8c215-c33e-577a-a07e-dc2bca935ad2 | note | ACCEPTANCE CRITERIA: Survey marks
48ed0161-b135-5b07-962d-609d29d0af9d | note | REFERENCE DOCUMENTS: Alignment Drawings
d8dd0b3e-afaa-5da5-8032-a77a3aec90ee | note | INSPECTION / TEST METHOD: Visual
d88b6689-78e3-5801-9ac0-92db21438998 | note | RECORD OF CONFORMITY: This ITP
0cb49d94-09b0-5d20-bd1a-92dc1c0bce03 | note | WP
ee2c0811-c401-59ce-ac17-8e234bf126c5 | note | RESPONSIBILITY: Supervisor/Surveyor
bae3f2b1-0c4b-5976-a99c-3de6ff9a6928 | date | Date Completed:
0e5d846d-73ec-4700-86ce-0f87f82f78d8 | checkpoint | 3. - Identify trees to be removed
c998a1a1-5ac0-5c1e-a131-b8b52eb2fd23 | note | FREQUENCY: All tress
34a247e8-5647-5efb-8ece-a28f0dc87e1d | note | ACCEPTANCE CRITERIA: Removal marks (Blue “R” or Blue mark for small trees) sprayed on the tree following joint inspection with Principal’s Representative | ACCEPTANCE CRITERIA: Removal marks (Blue “R” or Blue mark for small trees) sprayed on the tree following joint inspection with Principal’s Representative
aa4ff841-989c-5e0f-90fd-329fe3ae1940 | note | REFERENCE DOCUMENTS: Tree Register
39fd5b9e-0dbd-59ba-a75f-8b7b855d8a38 | note | INSPECTION / TEST METHOD: Visual
e200c230-0f61-52e0-98a3-535a7c65e859 | note | RECORD OF CONFORMITY: Completed Tree Register
c8ecd734-dedf-51f9-b224-210dd5c645cd | note | WP
b8782fad-4196-5009-9279-1d635d943e09 | note | RESPONSIBILITY: Supervisor / Environmental Co-ordinator
d942982b-180f-5759-a37e-067e17e04d42 | date | Date Completed:
98773390-0cf8-41c2-b51e-7c57f157de8e | checkpoint | 4. - Identify branches to be trimmed
17d00563-2d6a-53ab-aa8e-8514bb830d91 | note | FREQUENCY: All trees
8ec2e00c-a9b3-59b5-bf51-db510c659c49 | note | ACCEPTANCE CRITERIA: Trimming mark (Pink ribbon) placed around the branches at the trimming location following joint inspection with Principal’s Representative | ACCEPTANCE CRITERIA: Trimming mark (Pink ribbon) placed around the branches at the trimming location following joint inspection with Principal’s Representative
65bc3c05-07e4-5c00-ae47-8c45d117c630 | note | REFERENCE DOCUMENTS: Not Required
ad5780fa-ed2a-533d-a062-3518dd74e5c6 | note | INSPECTION / TEST METHOD: Visual
98d8c61b-764b-5525-b05f-32ac554a685b | note | RECORD OF CONFORMITY: This ITP
00eba4dd-bd50-5aa4-ac7a-00bff0eefa7a | note | WP
57b02a30-1ef0-51c5-b09a-eb9fe2ac77db | note | RESPONSIBILITY: Supervisor / Environmental Co-ordinator
21789f05-65fc-5010-9734-582b0be7b4be | date | Date Completed:
4ff762fc-f694-416d-966e-84d2ebc59a05 | checkpoint | 5. - Weed removal
df66a6fa-37b8-5ee8-b68b-97093a6d533b | note | FREQUENCY: All areas to be stripped
0aaf3dd6-b378-54fd-bef2-42c45659d428 | note | ACCEPTANCE CRITERIA: Removed weeds are deep buried (900mm cover) to reduce the risk of respreading
17b8a55d-be4f-5c7c-b8a5-9356ca33aedf | note | REFERENCE DOCUMENTS: Not Required
089810d5-dbc0-53ec-943f-9ed23f0d27f2 | note | INSPECTION / TEST METHOD: Visual
600d324d-93cc-56e7-9d22-80d67b54c38c | note | RECORD OF CONFORMITY: This ITP
fcc07f70-382e-5b57-9a83-485daddf8e88 | note | WP
7f624030-f2e5-532c-a8c2-6bab6e3df888 | note | RESPONSIBILITY: Supervisor
cb31ea72-49a0-562b-9e47-37d433fa9a40 | date | Date Completed:
e45de0bd-e614-4bef-b813-b8c7012ae2f4 | checkpoint | Final Inspection
5bf7e314-617e-5573-b3b5-e24e9bb71bbd | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality System Procedures and verifies lot compliance with specifications. | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality System Procedures and verifies lot compliance with specifications.
d3bcc43e-3f4f-5ec2-a543-4c812346b35c | textbox | Print Name:
a0f4fb6e-b3e3-5116-8ef6-afc6fb2484d2 | textbox | Position:
e3ba374e-3cad-51e7-81ff-5f39fb253ea3 | date | Date:
1db8058b-d311-40ec-8200-3b89b685fec3 | signoff | Sign ITP
87e72771-493a-4390-89aa-775c9f900c47 | checklist | ITP-002 - Underground Stormwater Drainage BC Rev1 | itp | ITP-002 - Underground Stormwater Drainage BC
413da0d9-71c4-4883-b76e-523165578961 | section | 1 - Preliminary Works
33fc9297-8b38-4fc2-a208-2113f49b4f6a | checkpoint | 1.1 - Check for correct documentation
d2ec157d-6f2f-5e55-9691-cb0132b23140 | note | FREQUENCY: Prior to commencing any activity
1ec12a1c-ee38-59ac-8ac4-ba678f1d44bd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
604bf1ad-bd3f-5f5d-becb-c09b9c5d9045 | note | — using the correct and complete set of drawings
718f8ce5-1b7b-5e2f-af90-97a2d6cb837b | note | — all drawings are the latest revision
8eca52c1-fc3f-5bcd-90d8-4103e6151097 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
dbaef608-851d-54aa-bb3d-105436b1aab4 | note | INSPECTION / TEST METHOD: Visual inspection
a4526cac-e673-54ac-ac62-6a07be361884 | note | RECORD OF CONFORMITY: This ITP signed off
f5c0a924-1ade-5ae2-861c-b0a1b733bc78 | note | HP*
4aa65f9b-1028-5e17-956a-4c8ddbfad318 | note | RESPONSIBILITY: Project Engineer / Site Foreman
285a5b18-1302-51ae-89c8-8eff3710862c | date | Date Completed:
b05518e2-bc2e-4c7a-a783-0eb0692eb62a | checkpoint | 1.2 - Implementation of all measures and controls
cd560598-3e5b-5918-8ce3-1f3dd1d608c2 | note | FREQUENCY: Prior to commencing any activity
c027d0c6-28af-531e-89ce-bc9312e43901 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
7a1483ab-4759-54f6-944e-e571632f2b60 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
92e6b5aa-59ee-5da8-b836-14b5042e29cc | note | INSPECTION / TEST METHOD: Visual Inspection
91f2a618-22b6-5351-be8a-aa3198b61aef | note | RECORD OF CONFORMITY: This ITP signed off
e76e60b4-4c12-5421-b0fd-230856ff43a1 | note | HP*
d2ade016-ac3a-58b8-a759-cf107b853f43 | note | RESPONSIBILITY: Project Engineer / Site Foreman
c8d26829-78ca-5eea-98ea-8b0a38c0f0f9 | date | Date Completed:
002c5c43-4210-41aa-93b2-ed2c7ae64862 | checkpoint | 1.3 - Precast Materials Inspection
89a48b35-b25c-57c0-9c2a-ae8036ff1333 | note | FREQUENCY: Each Delivery
efcad1e0-990e-5f96-8b26-984535fbade6 | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
791e3a56-a53f-56f0-8066-a514c3a26548 | note | REFERENCE DOCUMENTS: 701.04b
3087a607-831c-5b92-ab7f-f21b0f17813d | note | INSPECTION / TEST METHOD: Visual Inspection
4e4b11f8-0886-5e72-8414-0f81d4574bb7 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
828e068d-5652-5787-8e04-4a0b8a5e9fe5 | note | IP
8149219a-e1be-509b-9885-7f34e46825c7 | note | RESPONSIBILITY: Project Engineer
9b48761c-be8c-5389-bde6-588a8a75315d | date | Date Completed:
bef37db3-c55a-4843-9593-1f0dc23e4521 | checkpoint | 1.4 - Precast Pipe Compliance
3daf5e26-fc09-5b7b-9db2-519b164feeaf | note | FREQUENCY: Prior to Commencing
8d00c23d-8f2a-5f2b-807a-d33f517a4247 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
c8497d47-9c37-5583-901d-d913c7fb65c7 | note | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
fcb5097d-42b6-5b09-bf08-95d03cebb9e2 | note | REFERENCE DOCUMENTS: VicRoads Spec.
981c1373-2ce0-527c-9902-83facc9d1bb7 | note | ○ Cl.619
83ae326c-4597-54dd-8747-33811f05a8fd | note | ○ Cl. 701.04(a)
6e65b246-8fe9-520a-8a65-fa64a299f2fa | note | ○ Cl. 701.04(b)(i)
c06bb844-be04-5d32-b1b4-a8535766c6b4 | note | ○ Cl. 705.04(d)
8486f97e-5c61-5fe5-9583-49d3d5be970a | note | ○ Cl. 705.11
ad07c5fe-1cd8-56d6-a523-8cd2ef5d79fa | note | ○ AS4058
2c3187b1-5411-57a3-a01d-2114aa5fbe28 | note | ○ AS4680
acd590e7-d694-5701-ae9c-79a299032611 | note | INSPECTION / TEST METHOD: Document review & Site inspection
f9e4f27e-c705-54f8-bdff-dd6289cdb843 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
def32028-92bd-5c21-8ccf-4091dd873629 | note | IP
b32d3bfa-2629-5223-bdb0-4e9b3a7f1408 | note | RESPONSIBILITY: Project Engineer
e0740e49-18a5-51cd-a22c-2fcdb003b639 | date | Date Completed:
73483ff1-6ca7-435f-9c85-459ab0358bfd | checkpoint | 1.5 - Bedding material classification
57207d7d-8110-540c-b6cf-aed0ae8dc781 | note | FREQUENCY: Prior to start
8f2829b4-5807-52bb-9da2-8c81b9ed4796 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
86bc4de4-0c18-54c3-99de-d0ae300aece0 | note | ○ 100% passing 19mm sieve.
e6c8836f-506a-5cad-a3c1-feffff404d78 | note | ○ 5%-40% passing 0.075mm.
161b213a-c253-5e7a-908c-a49202be7502 | note | ○ PI = 20 max.
9a521d24-a7d5-55b1-af5c-774c8da60e84 | note | REFERENCE DOCUMENTS: 701.04e
acc39550-1f08-5e24-aa73-44fb82703a60 | note | ○ Table 701.041
0a13272b-f657-52b9-9c10-44e1968582a2 | note | ○ Table 701.042
e08d5e33-915d-5f5c-b5e1-0cc768ea16ae | note | ○ Table 701.231
2c2b8dd1-0662-582c-8615-75e65db64a9b | note | INSPECTION / TEST METHOD: Verify
427c694b-8c69-5a5a-84ac-fff6c91ff2b7 | note | RECORD OF CONFORMITY: Test Reports from supplier
cd559f3e-7a72-5c81-ade3-2f74bef750f6 | note | TP
616f8c8c-a824-5c5b-818b-ce8a9ebec2d3 | note | RESPONSIBILITY: Project Engineer
51bfa187-c840-5f91-a416-56111d1de53f | date | Date Completed:
1b55d6d9-569e-4e25-9416-e703bcbf7bdd | checkpoint | 1.6 - Backfill material Classification
4bed7e76-d2c3-5373-91d5-2ebb133f8175 | note | FREQUENCY: Prior to start
04110d4c-1574-5ab3-97f6-b172783c989a | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
195df932-3296-5a94-8600-8b45bd5a3ee3 | note | ○ 100% passing 37.5mm sieve.
9fee6837-b16f-5719-914f-956f23acab6d | note | ○ 5%-40% passing 0.075mm sieve.
38ebed3c-f949-5b1c-815d-a183beac99e4 | note | ○ PI = 20 max.
e5281155-022a-534e-a64c-08c14a514fdf | note | REFERENCE DOCUMENTS: 701.04e
87ec5988-c05a-5237-b8fb-44d6b004e393 | note | ○ Table 701.041
4ee46857-422b-5c14-918a-3537ba2498a2 | note | ○ Table 701.042
b7373e8e-45e8-51a7-bbe2-cb893c7e9850 | note | ○ Table 701.231
51623e79-8b95-5087-bfe6-7cb95c73487e | note | INSPECTION / TEST METHOD: Verify
1747a7e3-b815-5ab2-8a81-60b35a46fe1e | note | RECORD OF CONFORMITY: Test Reports from supplier
ca9df8b4-b52c-54ad-80e5-43bdedc4ae3e | note | TP
3f093500-f91f-59ef-a9f9-8dfe8d106d17 | note | RESPONSIBILITY: Project Engineer
75181d67-006d-5a61-80fa-5ab6080fddc0 | date | Date Completed:
92cc67fd-0c1e-4f89-88bb-a97dd6fec772 | checkpoint | 1.7 - Mortar material classification
d1d0f4e0-5586-56f4-9053-1d23b0229c11 | note | FREQUENCY: Prior to start
b73a3bf5-365e-547d-99fb-59cc4006fcfc | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
d5b34fb8-98fb-5f14-8478-b372baa34b6b | note | REFERENCE DOCUMENTS: 610.33
2b9ce392-52f0-51e3-b06a-0264a28862b8 | note | INSPECTION / TEST METHOD: Verify
5ded7c66-9457-5a77-a7f5-5e97a2d1b47a | note | RECORD OF CONFORMITY: Test Reports from supplier
b53e45db-2624-50c5-9d26-16ec6f7f4eee | note | TP
3a25b7bf-f721-5c77-8cec-4d71754a4bc1 | note | RESPONSIBILITY: Project Engineer
793492d4-2d58-5ed7-b9ae-9f59bf795ce7 | date | Date Completed:
823162d8-7ca7-4666-aba2-a60bb3f3299c | section | 2 - Construction Works
2068ee27-6b7c-45bd-a99e-1f2035c91fb0 | checkpoint | 2.1 - Excavation Permit
0b9f8d62-04ab-517c-a538-ae36d4e3ab02 | note | FREQUENCY: Each lot
e3ff6e62-358b-5a91-a27b-fbd52593394d | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
ed7999ac-37f9-51c0-9736-c2afa44593ae | note | ○ Plant and equipment shall be appropriate for the task.
5c717e19-557c-5e43-8ff2-e8ca6b55e8b2 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
6c55e849-cf60-555a-86fb-3604ff92b5ba | note | REFERENCE DOCUMENTS: Excavation permit
cbe10fd0-e1e6-52ea-adb3-4239381dd431 | note | INSPECTION / TEST METHOD: Verify
781cf752-72b1-5660-9ad7-6e3b21b5344b | note | RECORD OF CONFORMITY: ITP Signed
8c784a0e-8253-57b2-9ad0-17087085ccd4 | note | HP*
855cb483-0162-58a3-9ce8-bd3817307849 | note | RESPONSIBILITY: Project Engineer
9ff57de4-7a66-563a-8c0c-c6da6c3dc9a8 | date | Date Completed:
f227ed69-e28f-46c1-b730-8acd0f1db87f | checkpoint | 2.2 - Set out drainage
aa2cc0c1-8758-52a0-b25e-2b866f6cca7e | note | FREQUENCY: Prior to excavation
cf59fece-f1b9-58d0-83dc-f3fd27b3756f | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
216daf35-3d28-5a23-a7e7-c166a4858281 | note | REFERENCE DOCUMENTS: Drawings 701.10
573a6c55-bfd3-512b-84db-ab8576a24ef1 | note | INSPECTION / TEST METHOD: Visual Inspection
ca38643d-47fb-54b3-bef1-e5f3746f78c1 | note | RECORD OF CONFORMITY: ITP Signed
4b942c95-8b2e-554b-b28a-7837d5abc197 | note | HP
505f2288-4cbb-54ef-b714-4ea6e1c61653 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
91d3268f-f245-59ac-9ee2-b7a860cb8045 | date | Date Completed:
cd6e219c-4bb5-4c9b-83b0-b94b41b796b8 | signoff | AUTHORITY HOLDPOINT
080c66e8-0a74-4ca8-b930-758f32b66d3f | checkpoint | 2.3 - Excavation (pipes)
379398b1-db2b-55f2-890b-2820da12d20a | note | FREQUENCY: Each Trench
9fd9bbf7-3173-567a-8b2e-9c72d3c620f5 | note | ACCEPTANCE CRITERIA: Horizontal clearance between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
54e457d3-2203-56ed-b19e-a18b3e1cd9a6 | note | Depth of trench:
cf6cca8b-7dcf-5c5b-8033-074263e3b06e | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
48635a41-e1f8-5e8e-a134-0f9e7bb78e93 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
3e37a859-dfb5-58ef-bc76-9351ff2f693a | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
fbca1a21-ba57-578f-8fa0-f53950bccd3f | note | INSPECTION / TEST METHOD: Visual Inspection
9437e20d-b3a0-5253-8d59-4a600964cd6b | note | RECORD OF CONFORMITY: ITP Signed
c2b432f3-b297-57b6-bf67-ddf5b530d3dd | note | IP
858f12ee-78f3-5848-9eed-828b92303fbf | note | RESPONSIBILITY: Site Foreman
7e9b9e6a-85ce-59e6-bb4d-d3133718abb9 | date | Date Completed:
e2dfbc7d-ef6d-4933-bac9-f2ff6347ea50 | checkpoint | 2.4 - Compact base of trench
6fde7dfd-8d34-5ddf-8d84-c8db777be399 | note | FREQUENCY: Each Trench
3626cf21-60cf-59b7-b5b4-07abbca23299 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
5d2b933d-ca4e-59a0-a1ce-a0a7c0440faf | note | REFERENCE DOCUMENTS: 701.1
a2cbc347-4380-557e-943f-e89d13357493 | note | INSPECTION / TEST METHOD: Visual Inspection
4438ee95-d0ba-58bc-8f07-9c3968fa3f0c | note | RECORD OF CONFORMITY: ITP Signed
6bff9c8c-b68a-5de0-99ed-d6b22437b64b | note | IP
939ded26-4964-5a07-ba39-a077346c13e4 | note | RESPONSIBILITY: Project Engineer
e9609716-c6c5-5f89-b63d-73e752161e5b | date | Date Completed:
8d144358-3374-42fb-9686-95e7e7ffec7a | checkpoint | 2.5 - Place bedding material & compact
62a13acb-9ac0-5389-a9be-8d286a35dde8 | note | FREQUENCY: Each Trench
b2394288-481d-5b3b-bec8-7d7e848aab9b | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
0d4915e3-6de6-52c8-9916-69f727ec2c68 | note | ○ 100mm under pipes.
8f5214e8-2d6c-5bc5-808a-495e5b42164a | note | ○ 80mm (earth foundation)
41288542-93b9-58a6-aeaf-75ca48678857 | note | ○ 150mm (rock foundation)
ddc5eb44-04ac-5d31-bbc5-642a996cc485 | note | REFERENCE DOCUMENTS: 701.19
aca41d5c-752b-56cc-b7b3-04e42d123a64 | note | INSPECTION / TEST METHOD: Visual Inspection
7d8f9d5b-4657-53e0-aea3-4e641c1d6f80 | note | RECORD OF CONFORMITY: ITP Signed
d70ec50f-85f2-51b4-bf46-c2286f6d1c61 | note | IP
eeb2e979-951d-5e49-912a-1d48d5b2291b | note | RESPONSIBILITY: Project Engineer
50d7e1c6-1af7-5809-bfab-2eec90f66132 | date | Date Completed:
59f0ae6e-8706-48df-8177-da226db3e584 | checkpoint | 2.6 - Place pipes
77af6520-01f9-59da-9831-994383a68705 | note | FREQUENCY: Each Line/Pit
51681b29-1335-57df-8d1d-20a00c9e41e9 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
78ca8680-0e78-5781-81a7-a042d820c842 | note | REFERENCE DOCUMENTS: Drawings 701.17
97da4b22-ee05-5b63-a45f-520afa3d5bd1 | note | INSPECTION / TEST METHOD: Visual Inspection
3bdaa699-8b44-5ce1-959d-7fd63d24a9b1 | note | RECORD OF CONFORMITY: ITP Signed
497ba4b8-3eda-504c-91df-3f077d7ce3cb | note | IP
6e5b7afa-4a7a-5613-bc23-9db5912a93b8 | note | RESPONSIBILITY: Project Engineer / Site Foreman
8c4f5daf-740c-5331-b7a1-066d66e843ce | date | Date Completed:
2c31a780-eb0a-401c-8d0d-2fad7ba3c4c2 | checkpoint | 2.7 - Jointing Box culvert sections
38ace088-b6cf-5bf5-a300-d7441e3e40ee | note | FREQUENCY: Each Line
b37081d1-2d6c-5187-821f-824804f53919 | note | ACCEPTANCE CRITERIA: Consecutive sections of box culverts shall be firmly butted together. The top sections shall be matched to the bottom sections and shall not be lapped over adjoining bottom sections. The contact areas between the top and bottom sections shall be mortared. Multi-row box culverts shall be laid with the sections in each row in contact with the sections in the adjacent rows.
6c253c80-9788-5da9-8168-e77f72db8d20 | note | REFERENCE DOCUMENTS: 701.17
b1b3a526-1fa8-5289-a73b-8ba0e1a104ee | note | INSPECTION / TEST METHOD: Visual Inspection
d7798dd7-c92a-5fcb-88b1-9d9512ee9c65 | note | RECORD OF CONFORMITY: ITP Signed
09f7ad52-a353-52d6-bc2b-704478964aa3 | note | IP
8ce210e0-9443-5b51-ae5a-676740df7f26 | note | RESPONSIBILITY: Project Engineer / Site Foreman
67b53476-ab50-57ba-a3ed-b51354f5db87 | date | Date Completed:
605c772e-4864-4e43-82f3-15f609484294 | checkpoint | 2.8 - Place & compact backfill material over pipes
2796fe9e-dcf5-532a-b417-ef39b7959fce | note | FREQUENCY: each lot
78958c4c-a474-5ec2-9b9b-72f3f0c9f86b | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
6a5f3526-45eb-53e7-8434-e3840735b33b | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
e16e4dcc-495b-583e-bf07-5b1776d0e2c2 | note | ○ Loose layer thickness <= 150mm.
61ebfc3a-ab5d-550f-8262-2aa344bd6ec2 | note | ○ 1 lot = 150mm layer
76c88c39-5cfa-5e6c-87d8-fac31341d679 | note | REFERENCE DOCUMENTS: 701.14, 701.15
d7cfdaa6-7110-58c9-a494-59a7591ff884 | note | INSPECTION / TEST METHOD: Visual Inspection
dbeadb07-9d25-58a6-acc4-817aec00c5dc | note | RECORD OF CONFORMITY: ITP Signed
e1148f24-6032-5e4e-82a8-44af703a75fc | note | IP
471532f8-25e4-569f-8a2e-c2afacb2b6c1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3c92d1a5-bce4-538f-a0dd-9ca9feda947e | date | Date Completed:
7b87592d-653d-4ab1-9bfa-e6efa63012eb | checkpoint | 2.9 - Repairs to damaged pipes
04b9c674-2561-58b2-a33f-83a9c0235657 | note | FREQUENCY: Each damaged pipe
fc551f81-6771-5843-a15f-daf43a4daa38 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
05ea38e1-253f-5ba3-8ee7-a0f8d961b677 | note | ○ All repair procedures undertaken in accordance with Cl 701.25
ae0a86f8-79e1-55e6-8931-a210ee2dd09f | note | REFERENCE DOCUMENTS: 701.31
87e914b1-d1ec-56b9-b1f9-3611a4fc5fd0 | note | INSPECTION / TEST METHOD: Verify
efd5db86-caf2-5976-9654-f135b1bdadbf | note | RECORD OF CONFORMITY: ITP Signed
2626a1ea-7cea-575c-aa1f-eeb7e76f4f9a | note | HP
afef41b5-27d0-57b1-ad0d-db15692556aa | note | RESPONSIBILITY: Engineer / Forman & Superintendent
18b6670b-656e-5225-a040-06ae8cbc7c1f | date | Date Completed:
1554f29a-18de-4507-9213-761deb7809cb | signoff | AUTHORITY HOLDPOINT
8c3f0832-7987-44fb-8fb8-96f2b71f0816 | section | 3 - Testing & Completion
a0eb4abd-cb7f-4f83-b215-f9f9fbc2203e | checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
31f39a62-fe89-545d-b453-82a8e8015d73 | note | FREQUENCY: as required/requested
88595d17-6424-5c7f-868f-f5f964f39c95 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
1f4c8b0b-7530-5b66-bb0b-7989a5faf65e | note | ○ Bedding material shall be compacted using a compaction plated to refusal.
19f2fb97-886c-527d-854d-9f58263e5b7a | note | REFERENCE DOCUMENTS: 701.2
491aebfd-af87-5ce5-aa99-c324b5262d3e | note | INSPECTION / TEST METHOD: Verify
f18a1556-c716-55d9-9aa3-7ae689ac2329 | note | RECORD OF CONFORMITY: Test Reports
05c1c106-f8a2-5609-9f5f-cda57ec4a200 | note | TP
c5a9af06-a40b-560f-8b6c-63aac2c384d0 | note | RESPONSIBILITY: Project Engineer
bfc86594-6d71-52f9-83ab-87653c610e60 | date | Date Completed:
cda53f59-4d8b-4526-9b6a-b1c00d53c81c | checkpoint | Final Inspection
93e861e9-be69-57fb-9f1e-7c7d6c8d7ab5 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d4dba176-e10a-5f5d-9773-3ce27641f272 | textbox | Print Name:
38658a97-1b16-56a8-98a6-b41cd737faba | textbox | Position:
49677f9d-9542-544e-a873-7f1dfbcdedb6 | date | Date:
5f784d38-fd72-4c12-bbf7-69f9da6ebfca | signoff | Sign ITP
a9e770f8-0bfb-417e-a491-217f962864df | checklist | ITP-002 - Underground Stormwater Drainage RCP Rev1 | itp | ITP-002 - Underground Stormwater Drainage RCP
8086dc28-9335-4929-b863-59b5fbea002b | section | 1 - Preliminary Works
6d0e1217-a9c8-4a3f-8f40-5c25bc618c0f | checkpoint | 1.1 - Check for correct documentation
5c2e1191-8f9e-5bdd-ab8d-5b007681f3da | note | FREQUENCY: Prior to commencing any activity
15feb239-a55e-5dfe-8908-08c46c3a7e9e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a0397f45-369f-544c-afae-32357a6019d0 | note | — using the correct and complete set of drawings
6ad89e25-037a-55a3-aa30-ed0f786a1758 | note | — all drawings are the latest revision
31e0531b-1e0a-5081-adcb-a32e16256c80 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1b6da297-6fad-5aaf-ac0c-606210808b04 | note | INSPECTION / TEST METHOD: Visual inspection
adf361ce-06a5-5fc0-960c-f5df5b1ff68f | note | RECORD OF CONFORMITY: This ITP signed off
52285ae7-cd31-5e1b-8941-d30a83f0f0b2 | note | HP*
dbb763a6-215b-57c7-93f6-c03d0c242a12 | note | RESPONSIBILITY: Project Engineer / Site Foreman
beec74e3-d59c-5d86-b4cc-5edb60c7fa0e | date | Date Completed:
6678a957-62ff-47bb-a154-07090d4410b2 | checkpoint | 1.2 - Implementation of all measures and controls
23f37380-a0fd-5135-bf28-14b30747a1b0 | note | FREQUENCY: Prior to commencing any activity
f21c13b9-48c0-51c6-bddf-d97df721d9ce | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
bbb127c4-84c9-5cc8-8d21-8746c8d8eecf | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
31135266-9f9a-51e4-8bea-7d3ed1533425 | note | INSPECTION / TEST METHOD: Visual Inspection
af23dee5-9234-573e-849e-6ad962a15d5e | note | RECORD OF CONFORMITY: This ITP signed off
1d7d5c35-8fa3-5300-b765-e7fac235ede0 | note | HP*
248e9c8c-8e32-5186-842d-ff39aa2e0108 | note | RESPONSIBILITY: Project Engineer / Site Foreman
3020f682-0b16-55b8-aaee-b2d38456672b | date | Date Completed:
ca96901e-8d84-414c-bbd0-f072e5ca9f69 | checkpoint | 1.3 - Precast Materials Inspection
13efefbd-0434-54ab-a6c4-c10c2c131c9b | note | FREQUENCY: Each Delivery
13978eda-a88c-5c5a-a410-da5e9e27298d | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
f86e48f1-751b-5e9a-bfec-31f2bea3b43f | note | REFERENCE DOCUMENTS: 701.04b
64994cd7-9f1e-5314-a1b1-21299527a36b | note | INSPECTION / TEST METHOD: Visual Inspection
f123a90b-1e1c-52b0-8652-f2fadf59d70f | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
3ebed8f6-a339-5ee4-98cc-41b36aabd3f5 | note | IP
5c310105-9d9d-567f-a241-3dc2d5efcec0 | note | RESPONSIBILITY: Project Engineer
77f52b5f-7bc2-55d8-a185-fe22fab24c1b | date | Date Completed:
cfc081cf-09b0-41ad-b9f2-be912fc43691 | checkpoint | 1.4 - Precast Pipe Compliance
8eaf88d4-aa85-5dfa-9e6c-fe05b4355f45 | note | FREQUENCY: Prior to Commencing
de689f79-1dd4-5383-a013-856163fb53d1 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
7a932440-f886-5316-95ae-3c0e389e0ff0 | note | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
41d7c349-c676-56fb-bc3b-373f4c8440e5 | note | REFERENCE DOCUMENTS: VicRoads Spec.
e16e6aed-1dc5-576a-9579-8f0190e90ecd | note | ○ Cl.619
7e27f1ef-e013-5778-b921-a32676518914 | note | ○ Cl. 701.04(a)
d216a6b0-8079-5a91-9d7f-f22b789d4cd4 | note | ○ Cl. 701.04(b)(i)
5232bc59-a231-5313-a9e7-5848521f14cd | note | ○ Cl. 705.04(d)
a9d523ec-2d4e-51fc-89fb-89b032c224f8 | note | ○ Cl. 705.11
dd0f76c4-04ba-5da9-9376-0e5e146d4550 | note | ○ AS4058
62a36426-5420-58a9-b930-b2a69ba82571 | note | ○ AS4680
82417237-2a70-5eb1-b5ed-fc9b050df487 | note | INSPECTION / TEST METHOD: Document review & Site inspection
b6db35b8-c487-5c8f-ba13-66cb37a6f170 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
a7b298ab-1218-5dec-b176-061bf396a89a | note | IP
56430a8c-8bd1-5ac9-876f-73fdba34f91d | note | RESPONSIBILITY: Project Engineer
a9504b08-016d-5064-9b0e-400ce33023ba | date | Date Completed:
f1137f78-1b05-489f-9cc2-aacd3a82d6c1 | checkpoint | 1.5 - Bedding material classification
0a5b37f2-fb41-5ce4-9eae-aa07909a79a7 | note | FREQUENCY: Prior to start
a182f0e4-497d-5d94-a3f4-5b64df04e9e0 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
db3c554e-a01a-5991-a461-599e75a794c4 | note | ○ 100% passing 19mm sieve.
734840d2-4936-5691-a41d-5438b95874df | note | ○ 5%-40% passing 0.075mm.
bdd37174-f063-574f-8026-195e47d634a8 | note | ○ PI = 20 max.
4b145f8d-585e-5dff-8472-81bbb53a7b7e | note | REFERENCE DOCUMENTS: 701.04e
2b2e7451-3748-59f6-adbb-602974f065c9 | note | ○ Table 701.041
889a3358-547f-59fd-a9bc-789f1164dcd8 | note | ○ Table 701.042
0b0ee245-d3f2-557f-b097-b51ae322626b | note | ○ Table 701.231
e18cf5e4-62a6-5352-9674-ab36900c5c1a | note | INSPECTION / TEST METHOD: Verify
869c6a21-1a52-5cdc-89e7-db0963f69868 | note | RECORD OF CONFORMITY: Test Reports from supplier
b06a609f-76d5-583f-ab47-30ce9435c6c2 | note | TP
7698054a-086c-5edd-82cf-0719fd11f5ce | note | RESPONSIBILITY: Project Engineer
76a1fbc8-190a-53f0-afd7-d276a831a31b | date | Date Completed:
82a9452f-94b5-4cf6-9309-57a2460f0a7e | checkpoint | 1.6 - Backfill material Classification
aaef9999-0847-56b2-8e14-d8c5aeced95d | note | FREQUENCY: Prior to start
8a739102-b138-55f1-a7fc-ac39de586797 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
b1c227b3-7be6-5730-88a5-42fe9e1bf134 | note | ○ 100% passing 37.5mm sieve.
65ff4a8f-cb4d-562a-8dcd-d089df4f8111 | note | ○ 5%-40% passing 0.075mm sieve.
69fad59c-8f1a-5468-9fd1-bba0bdf0b076 | note | ○ PI = 20 max.
31388571-2939-5ff5-a1b3-bf264726ae90 | note | REFERENCE DOCUMENTS: 701.04e
0d2b9da9-9528-5d8a-838e-9d146f9e92de | note | ○ Table 701.041
c49c0e7f-3c41-50d6-937d-e7f84dee4935 | note | ○ Table 701.042
e2411a39-274a-5d75-8ca0-87b80acd5599 | note | ○ Table 701.231
3a9c975a-6229-5737-8e38-7408cd4a2860 | note | INSPECTION / TEST METHOD: Verify
4c0f2a81-45e9-51a5-a677-970b6256da50 | note | RECORD OF CONFORMITY: Test Reports from supplier
6432f961-e1ef-513b-b786-0c2b24ce8107 | note | TP
79c3927f-1b17-5d01-b6fd-3c73069228a2 | note | RESPONSIBILITY: Project Engineer
16d9b785-ba92-5414-af73-3b64d18ba852 | date | Date Completed:
921f0650-1a1d-4622-bde6-9d048687387f | checkpoint | 1.7 - Mortar material classification
fb0adc0b-a051-5f39-8f47-d3f0c7d50f7b | note | FREQUENCY: Prior to start
5672dcab-aba7-5ad6-b3db-d8e6715f1c26 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
853b6333-b8ea-546b-aaf7-db173355a84f | note | REFERENCE DOCUMENTS: 610.33
3e788ff0-9a6d-5bdb-8de5-e5a4dbf182d3 | note | INSPECTION / TEST METHOD: Verify
34a0491c-987d-5e28-b6d6-93e592035691 | note | RECORD OF CONFORMITY: Test Reports from supplier
5eb5bb45-fb8d-547a-8efc-bf73c269ea4b | note | TP
b516dbd6-8a3e-565d-8161-59c92bf0824f | note | RESPONSIBILITY: Project Engineer
56c648da-4866-50ae-b571-8611dfefab5b | date | Date Completed:
91c3919f-791a-4046-9ef0-7f3669287862 | section | 2 - Construction Works
38b14121-63b0-4044-b9cc-dd457ed807b5 | checkpoint | 2.1 - Excavation Permit
822109e5-357d-564b-a740-c5045ebb11fe | note | FREQUENCY: Each lot
b3e7dfc3-859a-5141-b2cb-8e8f1c955d78 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
985133b9-b2cb-5e18-84f4-7e65a79a5b05 | note | ○ Plant and equipment shall be appropriate for the task.
ac41f679-35c5-565c-9883-025ec74bd041 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
21fb435d-2d0e-584e-bf3c-8365e4ddd84b | note | REFERENCE DOCUMENTS: Excavation permit
df4c1db0-86ce-5c88-8fae-34b1cefadfb0 | note | INSPECTION / TEST METHOD: Verify
c9d559ba-ef29-529f-8339-043f10eeb39f | note | RECORD OF CONFORMITY: ITP Signed
68a86082-0875-593d-ba8a-19c329046b8b | note | HP*
0510927f-6f79-5101-8616-541bde9acc32 | note | RESPONSIBILITY: Project Engineer
5f4ec42b-e3b2-58e1-a81f-4877b2a29be0 | date | Date Completed:
c0af9c7c-a0b2-4688-b2d0-d5628cd6d7ac | checkpoint | 2.2 - Set out drainage
683b0217-c30c-5c09-a60e-f6a037ba8a6b | note | FREQUENCY: Prior to excavation
44f861e4-f4dd-5eb5-afed-d50cccab35cc | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
3ba9cc23-8de0-5a58-8c66-857894d3027c | note | REFERENCE DOCUMENTS: Drawings 701.10
5bcc6bf9-c6a9-5b26-8bae-7ae3a7a0b1bf | note | INSPECTION / TEST METHOD: Visual Inspection
32393b8e-69d0-5c81-8f74-0d020b2bea1e | note | RECORD OF CONFORMITY: ITP Signed
92eef134-21f8-5927-90b8-15e49022fa1c | note | HP
7a51ad8d-9618-5adf-8228-6d6a95259907 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
07b9a060-0d4e-543c-93b8-eaaca67bb608 | date | Date Completed:
612ce4e4-fc2e-4946-bfef-24d7efc09325 | signoff | AUTHORITY HOLDPOINT
71be1fdc-6abb-4e28-a53b-b24b6c52b2b7 | checkpoint | 2.3 - Excavation (pipes)
05283362-1352-5b5c-82dc-48853ed82dc6 | note | FREQUENCY: Each Trench
667a961f-28f6-5521-bbde-af04f0206a6b | note | ACCEPTANCE CRITERIA: Horizontal clearance between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
45a1d529-824b-5c48-b166-8d85f3a4f509 | note | Depth of trench:
4b30ea40-9616-5fe8-84a3-66cb1569a38b | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
6292e4ae-0b03-5d4d-a811-138948c891c5 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
861be942-092e-55e9-90ce-6369122bb37e | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
a7fcbb74-0f35-50aa-a607-be65463bce25 | note | INSPECTION / TEST METHOD: Visual Inspection
f07c37f0-c653-5ce9-8468-d873e735fcc3 | note | RECORD OF CONFORMITY: ITP Signed
bdeb1ddb-7310-5090-9db4-e6a9f643105d | note | IP
48c57d5e-cc54-5a20-83f1-4bfb7c2a79c8 | note | RESPONSIBILITY: Site Foreman
9b82fde4-88fe-50ce-a7c7-c033afe0b02e | date | Date Completed:
682ad86b-34b1-4767-877b-ca3367adc193 | checkpoint | 2.4 - Compact base of trench
6d928160-0fee-5122-ac01-f42dbe313b86 | note | FREQUENCY: Each Trench
89851bda-9ff6-5f4a-acbf-a5aa8ff370f0 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
09c06de7-a3a0-5109-975a-5137a64a5fc4 | note | REFERENCE DOCUMENTS: 701.1
96ce3cf5-3a26-5744-8f16-4affbc7d921c | note | INSPECTION / TEST METHOD: Visual Inspection
e3dc55b6-0779-5a6f-a5f2-2a770364412e | note | RECORD OF CONFORMITY: ITP Signed
b2283faf-0e30-5365-9a96-6f40e153fac0 | note | IP
6f0902c2-2ba4-5458-aa29-14f286a95d13 | note | RESPONSIBILITY: Project Engineer
a7a81585-665f-5b08-8e62-ab99a6f85098 | date | Date Completed:
8b06f03c-2b66-430c-9284-a5537e8cd04e | checkpoint | 2.5 - Place bedding material & compact
3377e669-7b95-513f-812f-632017c79986 | note | FREQUENCY: Each Trench
5ee79d50-e08a-5928-926a-e001bc95ac80 | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
58b967ca-7bd6-50e8-b4ad-9eeece89dfd7 | note | ○ 100mm under pipes.
8c3caa2d-ef04-53b7-ac35-6d6654515948 | note | ○ 80mm (earth foundation)
6eea8212-e97e-541c-af5b-d97860a99c10 | note | ○ 150mm (rock foundation)
42fa5479-146b-510e-8232-bea10a95ad2c | note | REFERENCE DOCUMENTS: 701.19
e89cf372-554e-5872-a101-fa9191538e78 | note | INSPECTION / TEST METHOD: Visual Inspection
53005bfe-d8a0-56dc-a0c6-42539f1e3ddf | note | RECORD OF CONFORMITY: ITP Signed
1fcbeee7-5021-5c4b-b0a8-9d0e529a0161 | note | IP
b5cf0436-764e-5007-aa9c-40b51ffa88a1 | note | RESPONSIBILITY: Project Engineer
7996f8f2-35a9-57b7-b20c-2c3720ced31a | date | Date Completed:
6a9b4bbe-4618-42f7-99d4-7b1d072e1c55 | checkpoint | 2.6 - Place pipes
a254a7b8-fa57-59f7-91ae-ba5b6f8650d1 | note | FREQUENCY: Each Line/Pit
235ef0db-4834-5d60-9531-93e7b85b0906 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
005fcd8f-56c8-55d2-b822-0e497a4e68a6 | note | REFERENCE DOCUMENTS: Drawings 701.17
b4542aed-385e-56fc-9ae3-72c5a31bb7e5 | note | INSPECTION / TEST METHOD: Visual Inspection
a79c651a-8d91-5ea1-a0f9-c49e5d72a407 | note | RECORD OF CONFORMITY: ITP Signed
d29cbfbd-c5f7-5054-846d-082bf52fe7ba | note | IP
3db17720-2f79-515d-85f3-17cfaa579dea | note | RESPONSIBILITY: Project Engineer / Site Foreman
75ce60cc-9d6b-52cd-b8d2-d35c09681d91 | date | Date Completed:
42647e6b-9098-46a9-954f-16bc1d993793 | checkpoint | 2.7 - Jointing pipe sections
a8a34afd-c0a1-557a-bb82-f42a0910c417 | note | FREQUENCY: Each Line
14c1f9fd-4dce-5638-a29c-30afc2c5f2a7 | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
970ef5a0-80be-5eef-9b59-a86ab3ca7e9d | note | REFERENCE DOCUMENTS: 701.18
a6098052-9e04-56e6-98bd-7a85f55dad3f | note | INSPECTION / TEST METHOD: Visual Inspection
83c4ae67-e651-5db1-8e00-3a4aa72ec022 | note | RECORD OF CONFORMITY: ITP Signed
4b6b7a46-ad5b-5f50-a0db-e5d1c868ded5 | note | IP
6193c0fe-460e-52d8-84e6-31e2e26204f0 | note | RESPONSIBILITY: Project Engineer / Site Foreman
c0b86730-cf6a-5bce-b9cf-e2eae5c45432 | date | Date Completed:
f1a99917-1cfa-48ff-8667-aef7813f13f5 | checkpoint | 2.8 - Place & compact backfill material over pipes
3d6a9369-6183-5fbc-949a-a3b90a68eb52 | note | FREQUENCY: each lot
f94cc357-6984-505d-91bd-be3f3e483040 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
b0082451-5ce3-5577-9a21-d559d7cc9e54 | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
6279a9a7-f667-5fbe-b199-5cbc4709b034 | note | ○ Loose layer thickness <= 150mm.
1d179866-68f9-5ce3-82ae-fbea1e3ab63a | note | ○ 1 lot = 150mm layer
9ac5fe68-229a-5eb8-bb53-abcc478592c7 | note | REFERENCE DOCUMENTS: 701.14, 701.15
495683cd-85d4-5314-951b-c66969b1d2c7 | note | INSPECTION / TEST METHOD: Visual Inspection
c7348977-53aa-56a5-a29c-10f84a5cdf66 | note | RECORD OF CONFORMITY: ITP Signed
333c761c-b730-5431-a136-0bf99ba3a5ec | note | IP
f24202eb-40c6-51bb-9d02-eb1c3bfb9f38 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b93d6205-d1e9-58f4-9567-74c2cc4fcc44 | date | Date Completed:
3cd5d3d1-83a7-4808-a86f-b64f6aec78cd | checkpoint | 2.9 - Repairs to damaged pipes
1f64d4ca-cfff-5ba0-b419-6e6c5b5e44ad | note | FREQUENCY: Each damaged pipe
73c573d5-6218-5d57-8ada-3be16fe5d9f0 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
ed501979-e602-51c7-a036-a1d783237753 | note | ○ All repair procedures undertaken in accordance with Cl 701.25
00bb935e-6360-534d-a8a3-736719e97745 | note | REFERENCE DOCUMENTS: 701.31
d1deacd6-106f-5604-81ee-b2bf81e0f09a | note | INSPECTION / TEST METHOD: Verify
04d177c6-9f2e-594e-8825-a3cc0c15af15 | note | RECORD OF CONFORMITY: ITP Signed
5fddedd4-6156-598d-be98-476fd22b0000 | note | HP
9c39ff88-aa87-54e8-86b5-01862de99b07 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
72cea5d7-61f2-51c1-84c5-42d6c6b2ae7b | date | Date Completed:
ca912454-c8b8-4810-a4af-8bfc8a33c38f | signoff | AUTHORITY HOLDPOINT
db4dcf79-4c86-47bc-9759-f9640e9b6e22 | section | 3 - Testing & Completion
a52bda3e-411f-4d49-b030-8efe0b4ef96f | checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
4ae26404-eaf6-58c4-ae39-1ed88b5a1409 | note | FREQUENCY: as required/requested
7ed75ef8-f3da-506d-9e9c-8bfd9a6dc069 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
b8f32cb7-83a7-579e-88f1-3ff109b28661 | note | ○ Bedding material shall be compacted using a compaction plated to refusal.
5d2bf5eb-ec3c-5c23-8aef-94971225c87e | note | REFERENCE DOCUMENTS: 701.2
4b0a0ad6-7d40-5a5e-a4bd-d407a0d616c9 | note | INSPECTION / TEST METHOD: Verify
bd3b2f14-c023-52de-8e99-28b8d58b15ee | note | RECORD OF CONFORMITY: Test Reports
7a021df3-a921-5ae9-83f2-50683e2444db | note | TP
f89648cb-2948-5cc5-a4f7-e0d829cb15ed | note | RESPONSIBILITY: Project Engineer
8b14fc87-1ce0-5f75-9051-dda74d99ed47 | date | Date Completed:
cc2b0939-9c00-46ef-9e8d-c97fb612faf9 | checkpoint | Final Inspection
7be63313-6ffd-5951-8268-53fcfb7b3fce | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8b7db2d3-aa2b-510d-a47d-76f5f178dd33 | textbox | Print Name:
24045cb3-09d6-55e0-aaba-eacd61191397 | textbox | Position:
0ac4a262-afed-5fcb-a871-72353615e366 | date | Date:
ca2eae9b-a4ee-4ea9-88ca-111d9736cf83 | signoff | Sign ITP
4a227817-456d-44de-86b9-27abcfc342b4 | checklist | ITP-004 - Fill with Material Type A | itp | ITP-004 - Fill with Material Type A
f39b4db7-0e0d-4ccf-a9e4-f8dfe432a523 | section | 1 - Preliminary Works
3a4a3916-c5a5-4dbe-b8bd-6bd647aca502 | checkpoint | 1.1 - Induction
110d84c2-5abb-5c83-ac13-34178432590d | note | FREQUENCY: Prior to Commencing
a86e65ef-5087-554f-9fe4-43a56a321870 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Bellarine Hwy Safety Upgrade
7fee69ed-b18e-553c-b6f4-176961e2fb66 | note | REFERENCE DOCUMENTS: Inductions Register
1acc01d2-dccd-5d2c-a91c-da827166cbcc | note | INSPECTION / TEST METHOD: Document review
29ad3ecd-891a-57eb-af7f-dab2201b28f3 | note | RECORD OF CONFORMITY: Site induction signed.
7b117922-f5e7-5ee2-bcfb-384543022308 | note | AP
4604aa3c-4e44-5248-a945-a8e61f51238d | note | RESPONSIBILITY: Site Engineer / Site Foreman
38ee6f33-7c2a-5863-8db1-5af75efbff35 | date | Date Completed:
3ff83dec-c626-472e-a154-7e9aba5576e6 | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
91d87d29-62fb-5b3d-9e12-9b0ad7ace851 | note | FREQUENCY: Prior to commencing
e2cfa2eb-5eaa-5795-ba70-2363eb6e73e2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
c7ccd849-1049-5e15-b661-fd702af8e6d7 | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
df2bfe88-7e88-538b-a7c2-d65407d980c4 | note | INSPECTION / TEST METHOD: Document Review
6e69847a-dfc4-5629-8056-7151a0c9f276 | note | RECORD OF CONFORMITY: SWMS(s) signed
d22a94c8-a541-5fd3-8559-ca76851c417e | note | HP
91aaae71-ac36-54f7-9e91-c51f18ea2628 | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
951c5735-213a-5b7b-ae6f-6dc0c92d4c05 | date | Date Completed:
80235fad-4eb6-4fc1-b4a3-44599da88da6 | signoff | AUTHORITY HOLDPOINT
3d9a5286-192f-4a76-b7fc-ee3173561a64 | checkpoint | 1.3 - Check that current revision drawings are being used
b5847b83-bf5a-5a14-9b02-c42df9aa007d | note | FREQUENCY: Prior to Commencing
d7afed7c-7719-5986-abc4-5d45e92a53bf | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
036ff425-939b-5932-9741-53a353de9a74 | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
cb8dcad1-8057-52a3-931a-3184c6889245 | note | INSPECTION / TEST METHOD: Document review
e1d23c20-d938-54d6-8d26-eb48e33617bf | note | RECORD OF CONFORMITY: Latest Revision Drawings
6977de1e-e56d-53f0-bfaf-a71aa8ed9348 | note | AP
dc3a2ab8-fd33-58a9-95e2-05d9b480ca90 | note | RESPONSIBILITY: Site Engineer / Site Foreman
498aae79-3ad8-52ac-94fe-5741fa829179 | date | Date Completed:
21753419-cdc3-4354-8323-f9238172ce8e | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
f96219ee-a773-5b33-afdc-13ca515de00a | note | FREQUENCY: Prior to Commencing
c69855ef-a032-5cf5-aef1-56b8e34fc7de | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
6648da67-4cac-5c02-8797-f52545a560ed | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
ba5b20e9-e7c2-59ee-a625-51aefdf79c11 | note | INSPECTION / TEST METHOD: Document review & Site inspection
c932a655-34eb-53a9-9489-226bc3fcbe55 | note | RECORD OF CONFORMITY: Signed ITP
18404777-c130-51ba-a8cd-11a188d0c1d4 | note | IP
55aafc1d-6fb9-5464-ab87-40dcc1022214 | note | RESPONSIBILITY: Site Engineer
bf00b8d8-31fe-51ec-8c83-d2af632fa5d2 | date | Date Completed:
61cf3515-26ed-4494-ac2e-e7632c26a5dc | checkpoint | 1.5 - Excavation Permit issued
d3081c79-7acf-5001-942d-be52d0abcc69 | note | FREQUENCY: Prior to Commencing
07d68c6a-2878-557c-9ece-04208dd9b42e | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
a2ffb93f-1f77-5efa-94a0-62ba92d07211 | note | REFERENCE DOCUMENTS: Excavation Permit
8a870516-2e91-5976-89a2-55093ca575ec | note | INSPECTION / TEST METHOD: Document review
d38b931f-2962-561e-85e0-1272359ba11c | note | RECORD OF CONFORMITY: Excavation Permit #
df96cb4d-35ff-5185-a5f8-99b145e6aaa7 | note | IP
6ad6a9b9-530b-5f37-841c-b4250bfe449f | note | RESPONSIBILITY: Site Engineer
77fcd830-2dcd-589a-99b4-09c9741c2dbe | date | Date Completed:
009b7a86-bfb9-4c96-8277-64a7e53e50ea | checkpoint | 1.6 - Verify Material
e11d5942-b218-577b-b39d-66045514cf06 | note | FREQUENCY: Prior to Commencing
d74e9f2c-a232-58f9-8c89-7986ee297e26 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and FH shall inspect each type of material encountered and subject to verification by appropriate laboratory testing and agree on the category of the material.
578e18fd-44dd-5be2-943e-da3983063e39 | note | ○ Type A material shall be totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel or steel by-products.
160a49eb-2549-5434-884e-4d51dbf23a92 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(c), Cl.204.04(c)
975be414-e16f-5b1a-8490-6461b845132b | note | INSPECTION / TEST METHOD: Site Inspection
deeadcf2-0b34-5099-b1d0-2bc6060aca37 | note | RECORD OF CONFORMITY: Test Results, Material Ctegory agreed with Superintendent
12f94dea-d842-5d40-ac46-79ec46a872ad | note | HP
784e2f4b-cbf4-5283-8ee5-9994d2e8fdea | note | RESPONSIBILITY: Site Engineer & Superintendent
436b1e68-1572-54fa-a1f0-432cbd4f821b | date | Date Completed:
4d6ff2d9-69fd-4055-9465-88d5739c6d70 | signoff | AUTHORITY HOLDPOINT
0dad6af5-f3b7-47e3-a32c-9f6003a64901 | section | 2 - Placing Type A Material
4310a284-110e-4c35-a18b-b5345b8a43a0 | checkpoint | 2.1 - Survey set-out
dd9bb200-3c3c-5ce9-900d-29ca05bdd9a3 | note | FREQUENCY: Prior to Commencing Excavation
6688fd38-79f4-5e32-ad42-a4a3c3e5a3fb | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
ae470f09-bb86-522d-a3f8-30406dec4b92 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
3688e8d7-6407-5f60-90e6-f7f61e51165f | note | INSPECTION / TEST METHOD: Site Inspection
b309cf1f-8cae-51d6-adfa-de6d88dc95d5 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
465f2e3b-5808-5c51-ac6d-6bfd23c8a47c | note | SCP
bba7b3a9-b690-5323-b810-ee54bf6aa171 | note | RESPONSIBILITY: Site Engineer & Surveyor
54c7948b-c2d5-5ef7-8356-ff027e391331 | date | Date Completed:
77c2d7af-4af2-46b2-9624-23c0acd31701 | checkpoint | 2.2 - Fill Construction
bd08ead6-8cef-57ed-8db2-13b84ab78139 | note | FREQUENCY: Prior to Commencing Excavation
dca24449-2a38-5ddc-b393-6a4f23560372 | note | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
74bd9ce9-41fa-5913-99b0-06e05c7ca0d6 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
7e0a0ca3-d951-5d45-9946-998bf3e5e675 | note | INSPECTION / TEST METHOD: Site Inspection
7aef4284-fc03-5887-9b8f-027844184eef | note | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
6e0d4c71-758b-54bc-b9a1-77e512cf6b5e | note | HP
aae2f06c-a1b1-5e0f-a0f8-731e9ce073f1 | note | RESPONSIBILITY: Site Engineer & Superintendent
b35d6cfd-10c8-539c-9370-ec502df2fbfe | date | Date Completed:
19e5c3df-a054-4ea9-b47b-db59ceb2befd | signoff | AUTHORITY HOLDPOINT
946451d7-5379-4de7-b8a2-9b07e2745af5 | checkpoint | 2.3 - Keyed fill layers
03ddb85c-0fa9-5e82-be7c-53eefbfdd470 | note | FREQUENCY: During Excavation
e03ed642-99fc-55ab-8686-c809e0a11b0f | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
6f7601d2-b875-5261-bf64-6c6209f4c2a4 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
97f94694-e342-55d8-b6bd-c0107e15cdbd | note | INSPECTION / TEST METHOD: Site Inspection
c0d011d5-cf47-5e36-93d6-8431faada6bb | note | RECORD OF CONFORMITY: Signed ITP
c9ffe5c0-3f7b-5069-a7f3-7e57d80e9e70 | note | IP
3fd8f67b-855c-5b74-a223-63a13775e8e9 | note | RESPONSIBILITY: Site Engineer
5c3b16e1-dee0-5b0f-a503-d17ad8d1b0d6 | date | Date Completed:
2014a19a-e201-461f-b8f2-9c9eadbed3f8 | checkpoint | 2.4 - Layer thickness
08a6262c-fff4-5b11-af87-faa01f432eec | note | FREQUENCY: During Excavation
5f3d18c4-3f4a-540c-bf4b-a9b272dfa509 | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
bcf7fb4a-f963-5358-a1fd-33939fb22010 | note | ○ A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
fceed6c3-bb29-5e1a-b210-b1996bd638e3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
840be212-9718-5b29-a585-7ebaa8338530 | note | INSPECTION / TEST METHOD: Site Inspection
1c2cc284-e8b5-5096-9cd1-efd5e9305920 | note | RECORD OF CONFORMITY: Signed ITP
530c3f68-0322-54ee-97d1-d38f0e507f43 | note | IP
e762e673-80e4-5c28-9774-122b9f24e538 | note | RESPONSIBILITY: Site Engineer
c7ad2ad2-e09a-59e4-9046-dc3a6d5551e2 | date | Date Completed:
1bf8ada5-f74b-4ea0-8dc9-bd43cc9fb3c2 | checkpoint | 2.5 - Proof Roll
a19fd00d-24a0-53c7-a8f5-976f90abf38e | note | FREQUENCY: Each Lot (one day's production or 5,000m2, whichever is lesser)
9cef4364-0305-5cfb-952f-302348d4c77b | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173.
488f45ce-0bfe-5bf0-93fe-fc440d74dd8e | note | ○ Superintendent to be present during all test rolling.
d33a23c0-ece0-5aee-8ec0-cd5ffff4955d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03
f29ddd19-1d72-5411-8ec2-8718da09d760 | note | INSPECTION / TEST METHOD: Site Inspection
c1db2c9c-6e24-5cfd-9573-6a0ec26bc783 | note | RECORD OF CONFORMITY: Proof Roll Form completed & signed.
3b18579c-617a-5b8e-a4ea-298eb57a06d6 | note | HP
6c268efa-3785-5b03-b237-e96394b608a0 | note | RESPONSIBILITY: Site Engineer & Superintendent
a6a4a53f-3d3c-5b2e-a499-9534aed4724d | date | Date Completed:
ee93e124-99ce-4ec2-9a2d-632091573073 | signoff | AUTHORITY HOLDPOINT
97c8b976-5f32-4b4e-9d4a-dbbb4b685a03 | checkpoint | 2.6 - Preparation of final surface
792fa90e-bfc8-5228-979a-35c902167703 | note | FREQUENCY: Prior to construction of subgrade layer
d206e7de-6017-5e1b-8fe8-ef60fe289213 | note | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
4a213990-af57-58b7-9495-1c0a549aa40c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15, Cl. 204.03(g)
82f0a336-eadf-50ea-8a47-5ff5de79aa36 | note | INSPECTION / TEST METHOD: Site Inspection
33a4d303-b6d8-546f-91a9-3b970d0ecc10 | note | RECORD OF CONFORMITY: Signed ITP
853f984b-c610-58c9-be9d-c1156c366030 | note | IP
0d030b7c-d30d-5aa9-a29e-3b5289ebf02b | note | RESPONSIBILITY: Site Engineer
7c3b302c-b3ca-5b5c-9bdc-fc91b39aee8a | date | Date Completed:
80d142c3-c0ff-4d9f-ac54-e864e3827050 | checkpoint | 2.7 - Conformity with Drawings
9f2a6c20-1625-507d-aadf-bf92cba7abe8 | note | FREQUENCY: Prior to construction of subgrade layer
e7070971-51de-5fd0-91c6-df78e3712de3 | note | ACCEPTANCE CRITERIA: Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
2d9cc6bf-2e26-5acf-bda8-97d679e389c1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.03(f)
d24f2a8f-e6b9-5fe0-add6-ca41aa514915 | note | INSPECTION / TEST METHOD: Site Inspection
68a50c11-80b4-58c5-8395-ef03184f9575 | note | RECORD OF CONFORMITY: Signed ITP
b58132b7-f803-52c7-b055-eaf3468144c0 | note | IP
9037a577-7d9a-5eec-b1fe-058f87c8db00 | note | RESPONSIBILITY: Site Engineer
a86b75e9-f1c4-56c8-8c27-61500f3e7e7f | date | Date Completed:
cefe928b-e861-4386-b773-5b56cdf88262 | section | 3 - Testing
04b93cb3-e568-4469-8d04-dfb38797f6fd | checkpoint | 3.1 - Compaction Testing
720fae7f-a9d1-5fe5-8e8b-cbec1023fb5e | note | FREQUENCY: Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142 of VicRoads must be agreed with Superintendent.
c76cfa2a-8720-5c3a-9959-9a542e0f7c9d | note | ACCEPTANCE CRITERIA: Type A Material placed more than 400 mm below top of Type A Material should be compacted to 97% of MDD. Type A Material placed within 400 mm of top of Type A Material should be compacted to 99% MDD.
3c5c664c-92d3-5caf-8cc1-922c994d56c9 | note | REFERENCE DOCUMENTS: VicRoads Spec.
681f7903-e70a-5ec3-9192-c53259162271 | note | ○ Cl.204.13(a)
20d580a9-84dc-533e-8056-7e4e03a08c85 | note | ○ Cl.204.13(b)
6fec8e20-ada0-56fd-aadd-c7ffe587dc56 | note | ○ Table 204.131
1b616b84-f093-5cda-ac47-c94ce0e5f487 | note | ○ Table 204.142
fd2a814b-d831-58c1-bdbd-da79d58515ca | note | INSPECTION / TEST METHOD: Site Inspection
920b5801-0e7e-5bf7-9f44-cc7dc7701d04 | note | RECORD OF CONFORMITY: Compaction Test Records
1f668686-a201-5caf-9894-0eac221f1ef5 | note | TP
808a8e3f-c40b-5e99-bd2f-40da4e484333 | note | RESPONSIBILITY: Site Engineer
3a4503ce-69ea-50d0-973c-1d63a8afa3ee | date | Date Completed:
369c2a7c-7ad2-49f8-b273-6e140b3b3962 | checkpoint | 3.2 - Maximum Particle Size
c6ffae01-7972-5e85-aab5-85741a2581ed | note | FREQUENCY: Test every lot (one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements.
670d9f58-02ad-5724-89ea-83b4234946c5 | note | ACCEPTANCE CRITERIA: Maximum particle size should be 150mm when soil is within 400mm of the top of Type A soil, and 400 mm at depths greater than 400 mm below the top of Type A material.
7725019c-55f7-5b83-98c0-5132043f90f2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c), Cl.204.14(a)
6ce10a30-3f69-5af4-856b-502cfb4c846f | note | INSPECTION / TEST METHOD: Site Inspection
47d63a3e-4c6b-56f8-a314-6d6aed719ecf | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
67fa0d6c-a3f4-52d1-9052-c3c38f5d7ff6 | note | TP
ff03cc2e-d1c0-515a-b9ea-eb226e3866f6 | note | RESPONSIBILITY: Site Engineer
40a508f1-dc07-5c4b-a7ec-b69d05d881fa | date | Date Completed:
5a369202-3242-4864-95ff-85067cbd0c40 | checkpoint | 3.3 - CBR/Swell
41de7091-301d-512c-87ab-8fd1ff49ab3d | note | FREQUENCY: The initial lot (one day's production or 10,000m2, whichever is lesser). Reduced testing frecuency (every 8 lots) for future lots shall be agreed with the Superintendent
cf7fa50c-1f90-5b66-a26d-c6467debb36d | note | ACCEPTANCE CRITERIA: CBR: ≥ 7%, Swell: < 1.5% swells greater than or equal to 2.5% shall be classified as expansive and approved by the Superintendent).
672cedc7-b53e-5453-986f-f3855a0ae1a7 | note | REFERENCE DOCUMENTS: VicRoads Spec.
fbfbf4c3-b2ce-5b62-9998-602b80124022 | note | ○ Cl. 204.14
16c4b4f3-26e0-5d30-9b15-7756fd7b27f4 | note | ○ Cl. 204.04(c)
89ba6074-4552-5841-917b-ad351d891419 | note | ○ Table 204.141
6896842b-de76-5354-9527-6a8f19391e37 | note | INSPECTION / TEST METHOD: Site Inspection
8d77f755-c0c4-5540-a7e0-5aef6eb2f30d | note | RECORD OF CONFORMITY: CBR/Swell Test Records
6ac632d5-41a3-5c97-978b-7eb0bbbc305b | note | TP
95e31c05-7774-5b38-a4c9-aa432df4bbdb | note | RESPONSIBILITY: Site Engineer
53d0954a-97d0-58cd-a3a1-fe19b153fac4 | date | Date Completed:
2489fc13-f653-424e-bd8e-770de9842cec | checkpoint | 3.4 - Atterberg Limit Tests
30dcafb9-2556-5fe3-9042-4b35bcc0db17 | note | FREQUENCY: 1 Test per 2 lots (each lot is one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. Reduced testing frecuency (1 test per every 4 lots) for future lots shall be agreed with the Superintendent
a0090cbf-2d45-59f2-bd9e-f836c5af0090 | note | ACCEPTANCE CRITERIA: Ensure that soil post-compaction is not classified as silt
9caad686-283b-5eba-9b7d-1bf20a14385f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14, Table 204.141
88f661fa-3d1a-59b1-94f4-76db61c40d3f | note | INSPECTION / TEST METHOD: Site Inspection
0fc31768-9007-5339-bba7-2f2a4197738c | note | RECORD OF CONFORMITY: PI Test Records
60a299c4-c4f3-5c53-b516-70725157978b | note | TP
20b7f75f-e5f9-54f6-b327-49d788a85cf1 | note | RESPONSIBILITY: Site Engineer
f674804d-8831-57ee-b3ff-2df9b6db291c | date | Date Completed:
d59917d4-0dec-4079-bbb6-11ff29070455 | checkpoint | Final Inspection
23850a2f-6d52-5bf4-ae7b-11c3b6d60aaf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ab90d767-0534-59aa-9abc-605ee062f55e | textbox | Print Name:
85086726-9462-5577-8e84-e362566db12b | textbox | Position:
698b7bb9-37ae-5600-ae49-c18a7e09950a | date | Date:
78423a35-f12b-452e-abf6-121211087dd2 | signoff | Sign ITP
7bc08fbc-a678-4b49-9a4f-5da5dd6ab580 | checklist | ITP-005 - Crushed Rock Class 3 | itp | ITP-005 - Crushed Rock Class 3
7c4c1d07-8f6b-4d6b-9c53-70a3be390d24 | section | 1 - Preliminary Works
4d9997c0-725f-41b5-a010-6c5ec338e36c | checkpoint | 1.1 - Crushed Rock Mix design
d09c034f-5289-5666-a829-c32b06f8e899 | note | FREQUENCY: Prior to Commencing Work
dcd13073-a937-57cd-8432-75504a51c9f6 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
f7b8eb5c-7295-5a2c-9f44-6919af681e2a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
b7b85f6a-1fbf-5213-bd78-0248855176c9 | note | INSPECTION / TEST METHOD: Document Review
22b6a37d-5262-52dd-92dd-1e2f0c7f2560 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
478b632e-fdd4-5298-bcec-42b880beaf82 | note | HP*
564d5155-bbe8-51d0-82fa-dd55f62b63b5 | note | RESPONSIBILITY: Project Engineer
e73d2154-8fe2-59bf-ab01-d9551bae95fc | date | Date Completed:
6249ffcd-906c-4631-90aa-f6f739b34b87 | section | 2 - Placing Fill
0dcd1db7-6845-4469-a4ef-7891c2c80778 | checkpoint | 2.1 - Transverse Joints
2e15b12f-5434-5162-a235-9193d34125a0 | note | FREQUENCY: Check prior to placing material
e8db672f-c295-5090-a082-ef7a8c8e99b3 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
88ede262-fc0c-52be-bbb6-a8200abdc3ec | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
a175a8f4-462c-53b5-8a86-19252ac9e131 | note | INSPECTION / TEST METHOD: Site Inspection
583b7aed-294b-5302-8022-7ebf2feec7fc | note | RECORD OF CONFORMITY: Signed ITP
147772a3-03c2-5820-aa84-a647dfb3a7a0 | note | IP
d53bd8de-6ebc-51ca-afbf-2683ec0493ab | note | RESPONSIBILITY: Project Engineer
baa13bfa-b646-5629-be5b-f56ad9e6ed30 | date | Date Completed:
969c71d9-c1a9-47e5-b81d-a270273eced9 | checkpoint | 2.2 - Longitudinal Joints
332e2f59-279e-5488-8c42-7df4d5f8cb53 | note | FREQUENCY: Check prior to placing material
b229db32-897a-52aa-b383-74c1893409cb | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
342680aa-2a85-50a8-9b22-5055a56e93cc | note | REFERENCE DOCUMENTS: VicRoads Spec.
3c9e3164-6b37-5420-8ba6-243a227e9f2a | note | ○ Cl.304.07 (a)
0cccc162-6b41-5f10-99d2-43c88ad48ed4 | note | ○ Cl.304.07 (d)
b2c21526-34be-50a0-9f87-9efb0693eae7 | note | ○ Cl.304.07 (e)
9713ba2d-fcbd-5f1b-a4e2-8814f090d70b | note | INSPECTION / TEST METHOD: Site Inspection
ee1957eb-ef67-5090-b320-e5284701418b | note | RECORD OF CONFORMITY: Signed ITP
deaeac53-9403-57fa-b7cc-115420353ea1 | note | IP
c8bcf51c-5966-5370-a751-f9cf593d82be | note | RESPONSIBILITY: Project Engineer
cefcc237-bc60-5c1a-a753-fe8bb65918de | date | Date Completed:
d07343d6-d417-4901-a292-7440305c3f49 | checkpoint | 2.3 - Lot Size
7bf1017b-8428-5990-90bc-f085bf50700e | note | FREQUENCY: Check prior to placing material
02a7ceee-31a6-5627-901f-246a58dcbb75 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
60acc827-9d80-5e0b-acb8-f43191710d74 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii), Table 304.111
df89f12e-d921-51f1-afba-a69d67f3af54 | note | INSPECTION / TEST METHOD: Site Inspection
1c6ddb56-fbef-5061-b485-33d7c516eab4 | note | RECORD OF CONFORMITY: Signed ITP
0a6cc141-17b2-50ba-b9fe-bf3c91214fdc | note | IP
3e18a40a-4adc-5176-8402-b4f7b2e2b9f6 | note | RESPONSIBILITY: Project Engineer
ed95e48b-597b-5e6d-9961-e73cbdf3f20c | date | Date Completed:
cbbff6d6-e557-4799-9ad3-c8f60be0e0e2 | checkpoint | 2.4 - Proof Roll
0956f347-7c5c-5fa7-a71e-50534a69b241 | note | FREQUENCY: After placing material
abfad506-1bf4-51bf-aa6e-070391f7c5f5 | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
332571d3-77dc-5c1e-991b-d3ef61764122 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
05e02afd-c8f5-56d5-af85-76b497014cf5 | note | INSPECTION / TEST METHOD: Site Inspection
48ad9bd4-8637-598d-9780-1040f06f15b4 | note | RECORD OF CONFORMITY: Signed ITP
843991ec-f603-5a85-8b92-9e66eb347d9d | note | WP
ae056ca6-fd65-5a88-9005-90743faf9b6b | note | RESPONSIBILITY: Project Engineer & Superintendent
5f347f52-acdc-58d0-9a73-6b034273b441 | date | Date Completed:
e0f9a01c-d11d-4b71-bc1f-9df18ea64d62 | section | 3 - Testing Requirements
1d934c3e-3625-487d-975c-5df9e3b542f9 | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
ff5b69f1-a0ed-5c14-ab81-dbf556a46998 | note | FREQUENCY: Prior to Testing
d10e77eb-a49d-5f0a-8ca8-d1dd630c61e1 | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
e80a009e-33e7-5fe4-a712-f2ef80ddb3f4 | note | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
83f676ca-95d9-5173-9c97-e91aef138df6 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
044a789f-5b9f-5c67-9d24-619ee28df798 | note | VicRoads Spec.
f1a575c9-84e2-575c-9148-3b19564bad90 | note | ○ Cl.304.08 (a)
cec4fb24-ab6e-58c3-94df-26ceef25bb91 | note | ○ Cl.304.11 (b)
a3db582d-ac0e-5770-af86-5c356ab6331c | note | ○ Cl.304.11 (c)(i)
f51016f2-8e29-5fab-ab0b-b09e1a270361 | note | ○ Table 304.111
48a2d8a5-a143-58c0-93d6-b797f1e1e070 | note | INSPECTION / TEST METHOD: Document Review/ Site Inspection
b3d8a062-26de-5c67-97b9-d16b5680f660 | note | RECORD OF CONFORMITY: Signed ITP
73d9b90e-8df8-52a3-aae8-b5b909f59fb1 | note | IP
cf23c985-defb-5e36-884a-c5d26a855663 | note | RESPONSIBILITY: Project Engineer
2b78169d-7995-5fce-904c-ff5b1d6f7479 | date | Date Completed:
9a5e5a33-01a3-4be1-82e8-0968e7d1f51d | checkpoint | 3.2 - Modified Compactive Effort
e02f2d82-e278-5e09-917c-5184f40c4349 | note | FREQUENCY: As per 3.1
5551f793-2221-51b4-81b8-071a7a6d439b | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
f47ec4d9-a534-5b85-a2a4-4dd6dd81686b | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
58923a01-0b44-55cd-b9f0-b15bed3da230 | note | INSPECTION / TEST METHOD: Site Inspection
690066a5-81ad-5519-8160-06d91ae27d9e | note | RECORD OF CONFORMITY: Test Records
11a276f3-088b-5a9c-ad7b-67964421a987 | note | TP
2dfd4e4a-0b33-5815-a9a5-42dbca646127 | note | RESPONSIBILITY: Project Engineer
4438296c-f39f-5e01-a33c-66ae91623206 | date | Date Completed:
1a9d87c3-7764-426e-ae56-b29e16dfc304 | checkpoint | 3.3 - Survey Level Conformity
5c783256-991b-5053-b3e0-78a25c76d117 | note | FREQUENCY: At completion
64211472-e6a8-57ea-9bd4-f5fbfee894f9 | note | ACCEPTANCE CRITERIA: Scale B:
8e257929-d7e0-5b23-bbf0-000d28a75c11 | note | — Minimum number of measurements per lot: 40 For Upper
9f9d2d36-9d8d-5181-a2ba-e2cdb6a5928f | note | — Upper Subbase: Mean + 6mm to - 12mm with a maximum Standard Deviation of 8mm
beebbb44-c751-5714-91a6-b4fcb25ed7ef | note | — Lower Subbase: Mean +8mm to -16mm with a maximum Standard Deviation of 10mm.
c4b3eb01-7e43-5908-ac5d-ee2a2bad039f | note | — Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
a4b092e8-128c-527c-ae95-fed9c6d1ab03 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
fc8bcb19-b219-554d-8d93-4cf371a5c4e9 | note | INSPECTION / TEST METHOD: Site Inspection
3e196fbe-8cb8-582b-9e6b-83faa4bcf687 | note | RECORD OF CONFORMITY: Test Records
ac28952b-075c-5f40-b51b-23be361eee88 | note | TP
3df456fa-8c25-569a-971d-e475a17d8a61 | note | RESPONSIBILITY: Project Engineer
4a72f8cf-f127-5386-ae93-14af33af9092 | date | Date Completed:
6c1cab3a-1893-4ad3-8247-5b40a66d9e84 | checkpoint | Final Inspection
ea9b18af-a7d8-564d-8fae-2777057d493d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f1adb6af-52c1-5ded-9ea6-42c5271d5656 | textbox | Print Name:
bd601a8d-a4f5-528a-9d5c-59d6f4ab4666 | textbox | Position:
d4a30e73-6d9d-5141-afaa-5efb068cc899 | date | Date:
fb109e20-f7ef-4cd5-b72b-e61f4449193e | signoff | Sign ITP
70690e5f-43bd-4e79-83ef-237c90c11e79 | checklist | ITP-008 - Cement Treated Subbase Rev1 | itp | ITP-008 - Cement Treated Subbase
a3907e6e-31b3-48b6-a4cc-b3563e7141cb | section | 1 - Preliminary Works
de6bb2f0-2bdf-4253-a39b-1dd376399bcd | checkpoint | 1.1 - Check for correct documentation
8a7333ed-0ad6-5835-bfe9-9a5f64741061 | note | FREQUENCY: Prior to commencing any activity
8bbec951-0357-59c4-8711-74d75fb8f809 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
756aabe9-5b6a-5e62-b024-5589955dcae6 | note | — using the correct and complete set of drawings
e1f61b0c-f993-5b55-9164-ae0a4d6de3ae | note | — all drawings are the latest revision
62b782a2-0e2f-5caa-a4bf-14b687f7f125 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
dd87be3e-6ef7-5c60-8719-5fc0c98c933d | note | INSPECTION / TEST METHOD: Visual inspection
a7876709-60d7-59e1-9ea8-df9abac2a1aa | note | RECORD OF CONFORMITY: This ITP signed
4ff60995-62b1-5468-af33-63f88ad27631 | note | HP*
eea52d97-e073-59f7-960c-3370d15e8c2d | note | RESPONSIBILITY: Project Engineer / Site Foreman
3daa1511-c027-5840-8a5a-0a13ef5a7dbc | date | Date Completed:
18f9935e-ed00-4b37-8e2b-a7f8b50d53e2 | checkpoint | 1.2 - Material Mix Design
f27ea51e-a2ee-5180-a067-5093fb8858de | note | FREQUENCY: Prior to commencing any activity
0955da56-ce7c-5788-b89b-b4556bdd6388 | note | ACCEPTANCE CRITERIA: Material proposed for import for 3% Class 3 CTCR (20mm) meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for approval
9237927e-3df2-5ade-8dde-2e7fb3aecf25 | note | REFERENCE DOCUMENTS: Cl 812.04 Section 820.04 to 820.09 RC 500.02
18ed3da9-cc3f-537e-a2a6-75b91ae57b90 | note | INSPECTION / TEST METHOD: Document Review
8ec84ef8-c449-510d-abcd-8b7f63144136 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval - Quarry Dockets
3943b145-57f9-5145-a70c-50048d544015 | note | HP*
b8ab005d-ef47-5b64-b74c-7c82ee27141c | note | RESPONSIBILITY: Project Engineer
477fac5c-9311-5a37-89cd-85080358be0c | date | Date Completed:
dd44e595-8f79-4338-8a14-d5a46e816a5d | checkpoint | 1.3 - Implementation of all measures and controls
a16cce00-7795-5c59-acdb-03296a71f31f | note | FREQUENCY: Prior to commencing any activity
2af9c9e6-acbd-587b-ac2a-13b0ff0d6022 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
b2c62d15-c72d-5389-93c1-9cb00df4f589 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
d789b216-07e6-5cf4-9e94-5b63d716bcb8 | note | INSPECTION / TEST METHOD: Visual Inspection
89ed7edb-24a2-59f3-a300-7bd717f3e92c | note | RECORD OF CONFORMITY: This ITP signed
e2587e38-5e1a-5b57-8a74-f5323a9fd1ad | note | HP*
5321793e-8bd8-5920-9b5f-2b828b1d4264 | note | RESPONSIBILITY: Project Engineer / Site Foreman
ab0bc0f7-214f-56e0-8794-7779dfe3045b | date | Date Completed:
d92faf96-4181-4114-b77c-33ba00b8a180 | section | 2 - Construction Works
e2b616c1-5300-4c94-95be-492ef6b80212 | checkpoint | 2.1 - Materials
a8b43048-f369-5ea1-865d-bd3ac08072c9 | note | FREQUENCY: Each lot
8a0ae02b-6154-53c4-ad79-063453fe3130 | note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
b3f605de-f7e6-5f9d-b929-a8d0377e652d | note | REFERENCE DOCUMENTS: Cl 306.04
d275e8d6-be0f-58f5-96b8-67f53c4a2bc6 | note | INSPECTION / TEST METHOD: Visual Inspection
49a83875-8af4-54fb-b9eb-211b1be5e28a | note | RECORD OF CONFORMITY: This ITP signed off
dd8d56e9-1b82-5d33-a6fc-8204e55e6b04 | note | IP
b9d64395-4b70-5eed-9c69-4dfcef92f9b7 | note | RESPONSIBILITY: Project Engineer / Site Foreman
bf8b5342-9439-5d22-96c5-cfc34043e6a6 | date | Date Completed:
f8ab2fe1-27b7-487c-aecc-35c8e8bc840d | checkpoint | 2.2 - Moisture Content
9e4c7450-90cc-5a69-ac0c-825d66a2f999 | note | FREQUENCY: Each lot
ed25973b-b0fb-5a3e-b2d2-944413a8f95a | note | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
25b6b4b2-9b72-5eaa-9f34-384d6469f6a7 | note | REFERENCE DOCUMENTS: Cl 306.05
b49ee894-107f-55a3-9e98-a68b44232b1a | note | INSPECTION / TEST METHOD: Visual Inspection
6693c252-0bf2-5da6-81e7-944b52eb3034 | note | RECORD OF CONFORMITY: This ITP signed off
49487340-08f3-57f3-88ad-d7cb8a236904 | note | IP
a62c75fe-1fdb-56d6-93b6-e32c0b2d6039 | note | RESPONSIBILITY: Project Engineer / Site Foreman
c9943959-6bc4-55b2-adac-98e9f24868be | date | Date Completed:
b314ffac-b416-4b8e-8f61-b7aabd438039 | checkpoint | 2.3 - Jointing
68f066ba-5dd4-5236-a2a5-c1e29cd820d8 | note | FREQUENCY: Each lot
a4ce95db-18d2-5007-ac05-fbd118b8433b | note | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
2b5a9705-e737-5c44-8d01-f8b6208f91cb | note | (a) material shall be spread in such a manner as to minimise the number of joints;
2b12f049-73b0-5135-960a-51fd28896765 | note | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
b62f649e-92be-56d3-b4a0-909f70dea6cf | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
7e2007a2-0846-534f-a28a-6d73dd3d48f5 | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
685aeef7-b2ac-5042-80ed-a2901fe831c6 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
23be7340-0296-570d-91be-f876ce04715f | note | REFERENCE DOCUMENTS: Cl 306.08
0865dbe3-4f97-52e7-8b4c-af428fcb2dcd | note | INSPECTION / TEST METHOD: Site Inspection
1daf885a-837c-5de8-a16b-f1df35719dd3 | note | RECORD OF CONFORMITY: Signed ITP
63908e89-92bf-592a-9d21-0ce1f164e631 | note | IP
8d8d3398-5509-5111-8c6f-4865ea9b43bb | note | RESPONSIBILITY: Project Engineer / Site Foreman
5e91bd2f-9f0b-57b8-baf9-0fed1da15d98 | date | Date Completed:
1115b157-b758-4e3a-bfa5-1dfa6201bbd1 | section | 3 - Testing Requirements
2c282b5f-c9c2-41b8-870f-8642189b6c01 | checkpoint | 3.1 - Survey Conformance
03e35307-fc20-5abf-a4b3-e1e0bda4e408 | note | FREQUENCY: Each lot
acf49d52-ba2d-5658-a5ed-7a4098f73f4a | note | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
9c7cc366-fd73-5211-8cc9-a3d56e7fc032 | note | (a) Width and Alignment - The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
95cb79b7-e0b2-5c0e-97ef-cf508f6ea7a9 | note | (b) Surface Level of Subgrade and Pavement - The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.031 and 306.032
cf31f2e1-615d-57b0-ab7d-3500b563f4ec | note | ○ Surface level tolerances: Scale B - Range x = +6, -12mm:
57fd63c0-a313-58a4-844c-401d9c5e917a | note | ○ Scale of Surface level measurement: Scale B - Minimum 40 points per Lot
655119d9-a5c6-52cd-ad73-024a1e9f38c7 | note | REFERENCE DOCUMENTS: Cl 306.031 and CL 306.032
ed1c33c2-e6aa-50b1-b8cd-5e8bd21a0e84 | note | INSPECTION / TEST METHOD: String Sheets
2b28b99a-dd84-590d-affd-f649b92b7907 | note | RECORD OF CONFORMITY: String Report / Visiual and ITP Signoff
617d993c-1d73-5f36-b96d-5b9e67e7126b | note | SCP
39dc21c0-ef30-5cb0-a6c9-66f17993ac33 | note | RESPONSIBILITY: Engineer / Superintendent / foreman
87ccdca9-dd06-56f1-b073-acafef1c4361 | date | Date Completed:
8b2cc32a-6fad-463a-a8cb-277fcb16376c | checkpoint | 3.2 - Compaction
e75ad75a-7661-528c-8dab-c4ced9d0e6c5 | note | FREQUENCY: Each lot
b2bc7116-0d86-5b90-8993-42613b4a4b2e | note | ACCEPTANCE CRITERIA: The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time specified in Table 306.091 depending on the binder type and the time of year the subbase is being placed.Except for the purpose of curing, no water shall be added to the cementitious treated material.
324cb0d9-e639-529a-8100-8588b2029db9 | note | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
401410a8-1a24-5c20-937b-b77368d9e7af | note | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent.
08a1c1cb-dbb6-543a-9227-b97f476fd167 | note | REFERENCE DOCUMENTS: CL 306.09 and 306.031
2af0c5aa-4bcf-5e89-9297-8a7fd82432e6 | note | INSPECTION / TEST METHOD: Compaction test and Visual
90281ae6-e8b5-55f1-964a-bddb695b438c | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
e903489f-a85f-5f9c-83c9-cd05e24485b6 | note | TP
a6b8fb7c-087b-557c-bc77-42cb46ba44ab | note | RESPONSIBILITY: Engineer / Superintendent / foreman
9f0f6861-7fe2-5486-b23b-098ce566f590 | date | Date Completed:
aefbb4c4-7491-4cb0-a0cf-8b2949bb864d | checkpoint | 3.3 - Curing
1f27c00f-f2e6-51d6-bb34-a9f9446070dc | note | FREQUENCY: Each lot
0853456e-4b99-5a94-811e-e54411beadd2 | note | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
d71341e0-3f7a-5318-bc93-7230aa93cecb | note | ○ The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
93304400-1f0a-5155-8d66-8c31d223b564 | note | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
2f039c53-3ae7-5f8e-8815-7d80de34e315 | note | ○ The subbase shall be kept in good order and condition and free from contamination.
4b5b4eb5-055d-5198-a9e7-d183ac0d27c6 | note | REFERENCE DOCUMENTS: Cl 306.11 and 306.06
3b36acd3-39ed-513b-90fb-22cd695c3525 | note | INSPECTION / TEST METHOD: Compaction test and Visual
977cd768-d676-5972-981e-a84c31ff1d38 | note | RECORD OF CONFORMITY: This ITP signed off;
5ef5def2-1071-56a8-915b-acc5ce4c9bf1 | note | IP
3bb8a0ec-759e-54ef-b8c8-50d1fa18d018 | note | RESPONSIBILITY: Project Engineer / Site Foreman
4869e17c-a25f-5730-90dc-0ce2389cfffe | date | Date Completed:
ab3f75a5-419a-454d-a0a4-d408fadcc660 | checkpoint | 3.4 - Test Rolling / Proof Rolling
8122cf1c-d6f6-5361-905b-69e4b868273c | note | FREQUENCY: Each lot
17e5cf04-8496-5551-b984-97429bcd3a2f | note | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
954b2787-bc38-58c0-9636-ccf27fd546f6 | note | ○ Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification. Proof roll will need to withstand test rolling without visible deformation or springing
5d71910d-f616-5ca0-a02e-7a7144a25638 | note | REFERENCE DOCUMENTS: CL 306.09
8f899ea2-9711-5f5a-9ce3-bbd6955bc2f3 | note | INSPECTION / TEST METHOD: Visual inspection
6a5f5179-163d-5599-bfc9-429ff05e4789 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
a977c90d-ab41-5ef2-aabe-700222271bde | note | TP
f3097763-6863-57e7-9871-2ecaee992ae2 | note | RESPONSIBILITY: Engineer / Superintendent / foreman
95990ef3-a9c2-5c95-8082-0b449733a1be | date | Date Completed:
b41baa1e-96a0-4083-882c-d38965e58fce | checkpoint | 3.5 - Dockets
d7558b2d-3f7e-56fe-ace5-25a75b409b04 | note | FREQUENCY: Each lot
a7de8089-85c7-5813-8fcd-e1e153baff9d | note | ACCEPTANCE CRITERIA: Where material is measured by other means and for Lump Sum Contracts, the Contractor shall make delivery dockets available for inspection on request.
bf35ade0-2d46-510c-86fb-35df4a1e6d64 | note | REFERENCE DOCUMENTS: CL 306.07
9fb9f4a0-8d38-5d23-86e4-d4e26a2897dc | note | INSPECTION / TEST METHOD: Visual inspection
84e37b46-fc75-574f-a878-bce74847e837 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
c7d72116-e71b-5fc2-a471-e7b4ac5e465e | note | TP
85f8bf16-5c34-5aa4-aac5-7ccde397fb65 | note | RESPONSIBILITY: Engineer / Superintendent / foreman
bb5929b2-68a5-5837-a34e-04df44eb9f33 | date | Date Completed:
65370c78-fb36-4306-9b0a-27b9299213c3 | checkpoint | Final Inspection
f6b47ed7-f67a-562c-9b63-ffe3bd54b682 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
168fa81f-e57b-54a8-b140-f96da3d70038 | textbox | Print Name:
4129e511-f9ef-5d48-b614-c24c6bb4271f | textbox | Position:
a0e9095f-f6af-5427-87a9-785b0c6c738b | date | Date:
6535309f-cf0b-4d23-9c13-62df4d3569b6 | signoff | Sign ITP
032e87fd-f2dc-4eb1-b395-513ac61aa248 | checklist | ITP-009 - Cement Treated Crushed Rock Subbase | itp | ITP-009 - Cement Treated Crushed Rock Subbase
e752dc01-9e35-4348-99ea-08eedd0dec5a | section | 1 - Preliminary Works
aef77b8c-e26b-4c90-b239-0c57c52e8ac0 | checkpoint | 1.1 - Check for correct documentation
d79aa1a1-4e82-5249-8821-42072f6baa8b | note | FREQUENCY: Prior to commencing any activity
245b3946-c13d-5682-b7af-3f899d58fa86 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
87d4031f-6a9b-56c4-b1e1-f187daedf494 | note | – using the correct and complete set of drawings
6eb40224-efb4-5fc1-8987-17bc7ed47da2 | note | – all drawings are the latest revision
178d0736-3921-55e0-bf8a-e85e3e123c88 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f693c311-fe7a-51c8-8544-1391cea12a1b | note | INSPECTION/TEST METHOD: Visual inspection
03924224-aaf6-5f3a-a176-822fd33b4317 | note | RECORD OF CONFORMITY: This ITP signed
eb36ef35-0e39-5bdd-8873-eba4ac745683 | note | HP*
47fb0840-1b71-5989-8fd1-d75ce1987a53 | note | RESPONSIBILITY: Project Engineer / Site Foreman
5c491d0e-92f2-5203-805f-1ef2981afcbb | date | Date Completed:
c6200872-7fee-43fa-8e35-e832205b2824 | checkpoint | 1.2 - Material Mix Design
e913d7f5-791b-5758-92f6-cb4f4e69096b | note | FREQUENCY: Prior to commencing any activity
7b0c44ea-0bf5-5716-bb40-6f194902fd2d | note | ACCEPTANCE CRITERIA: Material proposed for import as Class 3 sub-base material meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for review
73c1bd03-57b6-519c-8d2d-538b866562de | note | REFERENCE DOCUMENTS: Cl 812.04, Section 820.04 to 820.09, RC 500.02
e9126599-f15d-58f6-a07f-ecd32d613447 | note | INSPECTION/TEST METHOD: Document Review
908e9a7f-4a02-52cb-9203-692a467f07ec | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval - Quarry Dockets
0237d1e5-83f7-5c6d-ade1-282ccacab932 | note | HP
a5a24840-0869-5702-85ad-bd933a4fab58 | note | RESPONSIBILITY: Project Engineer /Superintendent
6b2b2794-ad50-5d01-ae94-2c1d63db705a | date | Date Completed:
8c18763e-7716-4c93-9dd9-a55ac5cc91e7 | signoff | AUTHORITY HOLDPOINT
748bf7cc-a8f6-4f32-af3a-af40ce83450c | checkpoint | 1.3 - Implementation of all measures and controls
9bc47587-95eb-5867-8c36-52b742870be8 | note | FREQUENCY: Prior to commencing any activity
534517a3-d6a6-59d9-a527-3915727b13e7 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
22831eb7-8d61-521c-8043-3d87c7231e13 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e86e892b-b642-5762-bf88-600e699c3c87 | note | INSPECTION/TEST METHOD: Visual Inspection
0a6c4705-03b0-56c6-9b51-365fe9a909ef | note | RECORD OF CONFORMITY: This ITP signed
bc6a7cd0-b39b-5b32-87ec-dcab49c68163 | note | HP*
9ded7d8e-33d2-50c1-b63f-ee65559f6b38 | note | RESPONSIBILITY: Project Engineer / Site Foreman
beb6f2d9-f619-5691-9f0e-41702e05ffec | date | Date Completed:
4021b9b9-a67a-490f-986f-8c026ba84af7 | section | 2 - Construction Works
2a857292-9021-4da0-bbdf-1bde05ac8ac5 | checkpoint | 2.1 - Materials
f9fbf718-9d55-5819-85ca-d6d268905195 | note | FREQUENCY: Each Lot
26e54934-7a99-5800-b405-f61e000deb67 | note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
4e25cd06-1a98-5771-abc9-92735d6f4652 | note | REFERENCE DOCUMENTS: Cl 306.04
7fefe578-df48-517f-8309-b93def3779f3 | note | INSPECTION/TEST METHOD: Visual Inspection
34475d76-5528-58cd-b5b9-8ae55dd4b754 | note | RECORD OF CONFORMITY: This ITP signed off
a59fa404-7d3e-55ac-8d79-43dd1287122a | note | IP
4f35b5df-d857-5de4-8453-11390b7ad8ce | note | RESPONSIBILITY: Project Engineer / Site Foreman
3709d1da-b396-5929-948d-c29b79cad52d | date | Date Completed:
cfc4dbff-0c98-40ed-b226-eea1854165a1 | checkpoint | 2.2 - Moisture Content
feb54ebb-ae8b-5544-838d-400a03d174fd | note | FREQUENCY: Each Lot
376cef3c-cfc5-5036-831d-8a4f592c34b4 | note | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
7783a3a5-07b0-55b6-851d-6c7c3a8e1a33 | note | REFERENCE DOCUMENTS: Cl 306.05
c30721d1-8aee-5071-8250-b1bd244aff67 | note | INSPECTION/TEST METHOD: Visual Inspection
8abcff09-a3dc-5440-9e3f-ee6a0280db1e | note | RECORD OF CONFORMITY: This ITP signed off
95989450-cde0-5716-8893-08450e12b022 | note | IP
b662ccd8-dbd5-54f4-8e75-8b692b88a6ca | note | RESPONSIBILITY: Project Engineer / Site Foreman
691c425f-787a-5a10-8bce-c9d103c82c86 | date | Date Completed:
48135044-4cb2-49a0-91b8-4f1e9d6c32fb | checkpoint | 2.3 - Jointing
4978fd38-c084-530b-99e0-2b85b66a3c63 | note | FREQUENCY: Each Lot
7fa6e4b6-7bd6-5d57-9791-b5cd4c263843 | note | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
6f85e817-11df-5d61-9b2e-1a4101443b5b | note | (a) material shall be spread in such a manner as to minimise the number of joints;
ba1378a2-6d07-5a1e-9c11-91b2e6b55656 | note | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
faa754c0-e8db-523d-a357-0bb5ac57d66d | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
c4f2bf2b-2959-5573-a40b-4967bb42bccf | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
d00bc6f7-219b-5e92-9e83-69d65e2b7815 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
b2046f2e-2e9c-51f2-bee8-69599a2ca375 | note | REFERENCE DOCUMENTS: Cl 306.08
fcf92ce8-0bc6-52ba-a930-abde0e626d1d | note | INSPECTION/TEST METHOD: Site Inspection
4513a93f-4854-55e9-9444-4c9d04e47cd1 | note | RECORD OF CONFORMITY: Signed ITP
fed3bdab-52e8-54eb-a93e-daba46708d04 | note | IP
e975aafa-a9f6-5cfd-a0f7-cdc351a863bf | note | RESPONSIBILITY: Project Engineer / Site Foreman
9f3963b4-bc2b-56f9-a9d2-bd367ca840f2 | date | Date Completed:
f7daaa7a-e9ae-4147-8677-173e884bfc0d | section | 3 - Testing Requirements
5bb6a45c-7472-4b2b-910a-e2641e925044 | checkpoint | 3.1 - Test Rolling
3a89ccd6-42d1-5b03-9b35-fed8bdbe52df | note | FREQUENCY: Each lot
958af3bc-c472-5458-9216-d308ec39a7aa | note | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
01eca82f-d516-5d19-94c0-b72360dd4711 | note | REFERENCE DOCUMENTS: CL 306.09
08743265-bbc3-560e-97b6-b5dc3f63a325 | note | INSPECTION/TEST METHOD:
dd2f0f12-6cda-5bd8-8bee-67a9649fee03 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
76ee8a77-00ee-5358-8f22-a0a9cff30a95 | note | TP
f1443a83-3ee0-5576-80d8-85d438e460a5 | note | RESPONSIBILITY: Engineer / Superintendent / foreman
bc5bba11-e6c9-5a0c-9e79-f4f7b2d99c58 | date | Date Completed:
6ec6c206-8688-41d1-9151-a7299a4f16d6 | checkpoint | 3.2 - Compaction
d67c59bc-4bbe-54c9-8ea3-8d6c6935d3b0 | note | FREQUENCY: Each lot
b42f7fb3-3f5e-5a23-bd7d-c90895da5215 | note | ACCEPTANCE CRITERIA: Testing and Acceptance of Compaction
8f9d7ad3-b090-530b-b0a5-56a6664bf9c5 | note | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
969d9708-dfbf-5a36-881e-578c07de3850 | note | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent. Alternatively, the Superintendent may accept the work at a reduced rate calculated using the formula:
fd1a2aee-dfe7-5256-af58-331570013795 | note | REFERENCE DOCUMENTS: CL 306.09
7ea25365-ed63-5e70-ab0c-5d9e39af75fd | note | INSPECTION/TEST METHOD: Compaction test and Visual
350baff6-587e-5c87-8e4f-f9af2ee1b295 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
050e87ca-b188-5f8e-b0a6-6ed921264f18 | note | TP
0df83388-fa73-5548-a4df-3713819b93bc | note | RESPONSIBILITY: Engineer / Superintendent / foreman
986ceef1-4bbe-5429-a7d7-6d3d6042d611 | date | Date Completed:
e9e322db-52fb-4fb1-83c5-156d2885bf18 | checkpoint | 3.3 - Survey Conformance
5ba50551-4633-5c33-af64-b386c721ec39 | note | FREQUENCY: Each lot
72d08c92-f847-58e4-99b6-55edc966590c | note | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
27e55447-6355-5ab9-975e-1d86eb2fb288 | note | (a) Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
4de13669-92b7-50c8-b103-8bdd297da6b2 | note | (b) Surface Level of Subgrade and Pavement: The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.12.
fd977c0a-345f-5220-a7f6-e6f0e0778edc | note | ○ Surface level tolerances: Range x = +6, -12mm
d3d3609f-80e7-5993-9e63-57f13b37cc83 | note | REFERENCE DOCUMENTS: Cl 306
12037a08-4df7-5ffd-b8b4-5524e8331d62 | note | INSPECTION/TEST METHOD: String Sheets
57b419ea-2fd0-5780-bca3-cc2a29477cfe | note | RECORD OF CONFORMITY: String Report / Visiual and ITP Signoff
b82202e9-f42f-5fb0-b192-f7ed818f0842 | note | SCP
6aadafaa-0c8c-5786-bd06-b48ddf36cb4c | note | RESPONSIBILITY: Engineer / Superintendent / foreman
4ef7afa1-e4a2-5363-8531-78b55722057c | date | Date Completed:
673a896e-9b26-405b-8989-661271598fb2 | checkpoint | 3.4 - Curing
26683241-3be5-5514-9e71-1eeef1df494d | note | FREQUENCY: Each lot
7514ecfd-c252-5d49-9eab-ae1c1c6ee70e | note | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
8ea50291-4877-5d28-b013-ffa5ce123162 | note | ○ The surface of each compacted layer shall be kept moist for a period of seven days 1-3 days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
af71b51e-2465-54b9-ac16-86c9a2c5c81c | note | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
3d10bde7-eecf-5178-a08e-05019b686f70 | note | ○ The subbase shall be kept in good order and condition and free from contamination.
2a5af582-bf06-5375-a577-bcc6e7dc0ae2 | note | REFERENCE DOCUMENTS: Cl 306.11
c94384f2-2268-592b-beb8-b098609723e3 | note | INSPECTION/TEST METHOD: Compaction test and Visual
c08868a5-787e-593f-a99f-775d9b4b84f4 | note | RECORD OF CONFORMITY: This ITP signed off;
d7dcaa23-bce9-53b7-bd48-393bbb95651d | note | IP
a968c262-fdbd-52c6-8934-e95bf5f4414f | note | RESPONSIBILITY: Project Engineer / Site Foreman
49b6d928-6b4e-5fb3-a361-5533d6a339be | date | Date Completed:
47f0792d-fd2c-4168-aea6-678a46a0ed5a | checkpoint | Final Inspection
814e6863-6c18-5ae8-b7bf-2573874ff4f9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1c1de43f-5632-5d98-a5b5-098c86f3a9de | textbox | Print Name:
d0621a5f-fb58-5bdc-8572-dcc43ab3bb7f | textbox | Position:
b638d7fd-75ab-5830-8d10-70e16499af1a | date | Date:
aad7c14b-d1e2-4cee-b75f-b15049dbc676 | signoff | Sign ITP
7cf4a807-5850-4cea-9f4d-2c7e06d85471 | checklist | ITP-011 - Guardfence Installation Rev1 | itp | ITP-011 - Guardfence Installation
a819700b-539b-4281-8b0f-8553daf45d14 | section | 1 - Preliminary Works
fd080f99-0bce-42ac-b8ca-745afec38ae9 | checkpoint | 1.1 - Check for correct documentation
8f161134-9733-5eda-a15e-dabb646d0760 | note | FREQUENCY: Prior to commencing any activity
b29632fe-053b-5d5f-9b50-6700c9885f4e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
8a4ee0cf-c98c-581f-94a3-78b708f54d58 | note | REFERENCE DOCUMENTS: Design Drawings & Drawings Register
dd1a8a74-663a-5673-b8af-640022f92d9f | note | INSPECTION / TEST METHOD: Visual inspection
a6cd7f41-a0cd-5788-bac0-597482aab24f | note | RECORD OF CONFORMITY: ITP Signed
a996eb6d-541f-5120-8172-e267ac360f95 | note | HP*
cf2e66aa-67a2-5e63-b321-828060c5266f | note | RESPONSIBILITY: Project Engineer/ Site Foreman
74c43411-0d23-5170-85ff-25adf3f05301 | date | Date Completed:
4b553935-7419-4b0c-8a92-90b4c6e26886 | checkpoint | 1.2 - Materials
44ffd655-7fad-5578-ba5b-e7bf2e257d1f | note | FREQUENCY: Prior to commencing any activity
cd1a0d75-9817-5291-b06a-f6a1eaacc43a | note | ACCEPTANCE CRITERIA: All materials are to be used must be on VicRoads current accepted products list (RDN06-04) and confirm with the detailed design.
14d93395-7d8f-5a1b-8f8b-0644d97cb800 | note | ○ The contractor shall submit to the Superintendent all test certificates related to the supply of steel for the works at least 14 days prior to commencement of installation.
f68ab597-fa28-54b2-9cbb-7de986e05245 | note | REFERENCE DOCUMENTS: VR Section 708.04 & 708.05
f8806f60-c12b-59ae-ab14-fafac7870285 | note | INSPECTION / TEST METHOD: HP
5b94a656-ede2-5847-907e-86fbb6d2f902 | note | RECORD OF CONFORMITY: ITP Signed, Certificate of Materials
1c488ba0-da7b-52f9-8d6f-e9783c8555f0 | note | HP
ea2bb19d-465a-5eae-8f93-7d8feb46b9ad | note | RESPONSIBILITY: Project Engineer/ Superintendent
2bb4048d-a720-5a70-99aa-2ccbd7be5e14 | date | Date Completed:
132f5e6f-b7b4-4caf-ba46-c162bd9c6bdd | signoff | AUTHORITY HOLDPOINT
47d1c14b-f245-42f0-900d-a9344b7d9004 | section | 2 - Construction Works
ad9e9453-4cca-41fd-bd19-798da5830ce5 | checkpoint | 2.1 - Identification of Services
1b8f07f7-d9b4-5226-aa47-058fe18e5182 | note | FREQUENCY: Prior to commencing any activity
7ccd0dfe-78f1-5cac-8dd8-fdcd31a76648 | note | ACCEPTANCE CRITERIA: Ensure any locations have been identified and marked on site. Ensure any approvals are in place with service providers prior to commencing install.
94d83162-bf3c-5b8b-90b4-63fd83595ddf | note | REFERENCE DOCUMENTS: DBYD
3084fd6d-1d37-5036-a694-2fe7e4199e57 | note | INSPECTION / TEST METHOD: Witness Point
edf1eeee-10ba-5ef2-9bda-d5086bc48bf4 | note | RECORD OF CONFORMITY: ITP Signed
3a0bae28-b566-5196-b570-5752568d9edc | note | HP*
357a2265-fe4f-5e81-8118-1ae42fdf0fed | note | RESPONSIBILITY: Project Engineer/ Site Foreman
aa65df10-b46b-55e5-8e3d-6973da0b1f9b | date | Date Completed:
47802e1a-d08a-4d7a-ab21-aebbdbe68589 | checkpoint | 2.3 - Setout
a984ee0f-4df5-5bb5-8cc0-1f853a278d3a | note | FREQUENCY: Prior to commencing any activity
e9f86fc9-c64c-56b9-9e16-124839a6aab8 | note | ACCEPTANCE CRITERIA: Contractor to confirm with the superintendent the required location and length of all guard fence alignments.
8d6f4a20-8da5-53e4-922a-b3bb32655d31 | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 708.08
2d11409e-cd08-5092-bc4c-6ea79477cfbf | note | INSPECTION / TEST METHOD: Visual inspection
44bc623a-4844-56cb-9784-c182de1bf05c | note | RECORD OF CONFORMITY: ITP Signed
90133a43-a9bd-55e9-86df-32f8707c0a2d | note | HP
4b8a61f9-c1ff-54c6-86aa-79cb774ddc3f | note | RESPONSIBILITY: Project Engineer/MRPV Superintendent
973cdc7e-a415-5ec9-80eb-cf6fcfc99366 | date | Date Completed:
1fce2886-1060-4633-b47b-c4787778c717 | signoff | AUTHORITY HOLDPOINT
ec2fb8e1-770c-468b-9b20-5144ddde366b | checkpoint | 2.4 - Installation
d9857a1d-6878-5230-86d4-48c5fcdfbf1f | note | FREQUENCY: Each Lot
d75becf6-f5a9-5b0d-aefb-f52f2bf45a5a | note | ACCEPTANCE CRITERIA: Guard fence system to be installed in accordance with design drawings, manufacturer guidelines, and within tolerances set out in VicRoads Standard Section 708.07 (d).
1f9b8d7f-efa1-5c21-8c84-7517033319f0 | note | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
ec98b593-eb58-5de9-a157-6a0ef5cb0f2a | note | INSPECTION / TEST METHOD: Visual inspection
2b574ea9-be7d-502f-8b45-cc68e4c90d86 | note | RECORD OF CONFORMITY: ITP Signed
dbfe1bf0-7730-50a8-8fea-65a38031154f | note | IP
5cb9cf7f-59a3-5157-8990-5a632c53d11b | note | RESPONSIBILITY: Project Engineer/ Site Foreman
532c5830-b808-5d73-b6cf-029c010cd2bf | date | Date Completed:
98f6165d-4bdd-480d-8020-b3b15d117b44 | checkpoint | 2.5 - End Treatments
62c3ba95-8fdd-5c5b-9d9f-d036390d0399 | note | FREQUENCY: Each Lot
d353a272-6bf4-5b3b-b576-68b7c6ad131c | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed in accordance with design drawings, manufacturer guidelines, and specifications.
5003e1d0-dd08-5faf-8c3b-71624b53aba5 | note | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
10f97a1b-2039-5330-abb0-19fdc90c0476 | note | INSPECTION / TEST METHOD: Visual inspection
d84de9e2-3e82-5d3b-bdba-274b99f8dbb8 | note | RECORD OF CONFORMITY: ITP Signed
be713cf0-6504-574b-8d6c-51f428486c52 | note | IP
33f2193c-7167-598b-867b-d135509d153b | note | RESPONSIBILITY: Project Engineer/ Site Foreman
9a567a31-def4-557f-84b1-ec47ff51068a | date | Date Completed:
522e9458-c440-4091-a326-255664069cd1 | checkpoint | 2.6 - Installation of Delineators
c3d56d90-e422-5c8d-8149-a384b43ceb4f | note | FREQUENCY: Each Lot
ca41f711-86c8-5df3-87e3-2efd92d200e8 | note | ACCEPTANCE CRITERIA: Contractor to supply and fasten delineators on left hand side (red) and right-hand side (yellow).
63154d3d-a992-59d9-bb87-180133664c24 | note | REFERENCE DOCUMENTS: VR Section 708.07
e698d792-c5e8-56f0-9aa2-889af303ef89 | note | INSPECTION / TEST METHOD: Visual inspection
1dcd3cb4-3367-5c93-b5ff-89a0110e5e1f | note | RECORD OF CONFORMITY: ITP Signed
f1d5f4c1-54b0-5422-bb80-1cf1bb1ecdf6 | note | IP
7ed7e7a3-149c-53f7-a92a-02161c4f42b6 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
192b4be6-9185-568f-8f30-c8695b4a0026 | date | Date Completed:
fccf89e4-9560-4cb1-b60b-4bfd5c084141 | section | 3 - Testing and Quality Control
de77b2ba-4404-449e-b885-45d7e0b88e13 | checkpoint | 3.1 - Submission of Certificate of Compliance (CoC)
42ff4f86-daa2-5449-825b-d9d7a08bac16 | note | FREQUENCY: Upon completion of install
9f552046-8857-5707-ba02-7fed390aefbe | note | ACCEPTANCE CRITERIA: Contractor to submit the CoC to the Superintended from guard fence supplier.
a413b3f6-77d8-5233-a99e-72eb99be7642 | note | REFERENCE DOCUMENTS: VR Section 708
df6cf7fe-d787-5bf3-a997-12d8843a40b1 | note | INSPECTION / TEST METHOD: Test Point
dbfd74bb-5313-527c-bc9f-8786b4dc470f | note | RECORD OF CONFORMITY: ITP Signed
a5ffc13c-4461-53e8-bb93-eb861502ff96 | note | TP
4d8f04dc-5bc3-5671-be79-feb0e9711bb4 | note | RESPONSIBILITY: Project Engineer/ Superintendent
ae16b383-34ac-5505-975a-a8bcc338f9d1 | date | Date Completed:
7126a108-5f79-4f45-a4e7-bb86781cada0 | checkpoint | 3.2 - Submission of Material Test Certificate
94c89a49-c3ed-5039-8f67-903d05de043a | note | FREQUENCY: Each Lot
7516bb4e-533b-5294-9ce5-716d9029ab3e | note | ACCEPTANCE CRITERIA: Contractor to submit test certificate to superintendent from guard fence supplier.
87f512f5-d4b8-5036-8930-0748d735c61c | note | REFERENCE DOCUMENTS: VR Section 708
b107a8e8-93ef-575b-b3c5-96dcf48ad6f0 | note | INSPECTION / TEST METHOD: Test Point
0fd2d68b-4d0f-5a56-832d-f5ddb2f1771d | note | RECORD OF CONFORMITY: ITP Signed
6847c595-1b70-5fe3-92b0-cc3deb4683eb | note | TP
d6ecc218-1d65-5512-b8c9-f0788f00f02b | note | RESPONSIBILITY: Project Engineer/ Superintendent
9d516dc2-9dfb-5cdf-8a2c-17ea751cc589 | date | Date Completed:
35c67d06-442f-4042-91e3-de5bee071ee1 | checkpoint | Final Inspection
15f4315b-4516-5d09-afb5-cd038e02d490 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e79552c3-2518-516e-abf4-94221fbb1ef5 | textbox | Print Name:
52d9eda8-060b-5376-be86-4d3bfb213aec | textbox | Position:
b44e2bc9-c16e-56eb-ad41-99f3f92c81a0 | date | Date:
2649bd53-b0fc-45e0-9b7b-3363ac2c8e0a | signoff | Sign ITP
2def68c3-1df9-4bc2-af04-8f8864e05ee8 | checklist | ITP-012 - Subsurface Drainage | itp | ITP-012 - Subsurface Drainage
a25e0643-18d9-4731-a8ad-79a676fc3dd3 | section | 1 - Preliminary Works
f7885df9-7cb9-4551-93b4-590fe538df34 | checkpoint | 1.1 - Check for correct documentation
0920e470-64c7-5478-92d6-cc4a49080046 | note | FREQUENCY: Prior to commencing any activity
6dc79816-e8cd-58ce-994b-a28db1cbd503 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
87e72ed0-9009-5c7b-862c-d2cbcd01cb27 | note | – using the correct and complete set of drawings
784aef8f-b71c-5d74-8a88-102b1bcf87d3 | note | – all drawings are the latest revision
dbe548a0-9e04-5289-a4f9-d961ba15272f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2f0da3d3-830a-5f02-b05f-30a125b10d18 | note | INSPECTION/TEST METHOD: Visual inspection
36d73d02-c12a-5db4-811c-ee195e8ab504 | note | RECORD OF CONFORMITY: This ITP signed off
86747c95-0bf7-5a6c-ada4-250f2c2f29eb | note | HP*
a08c8414-9752-5e2d-a9ee-1b6d40af9a44 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3a759b2f-a211-5661-9fc6-7bf43e47f114 | date | Date Completed:
e564f0da-151b-4aff-9fb8-5772d4fc7872 | checkpoint | 1.2 - Implementation of all measures and controls
1bd74be9-eb53-5bd9-bbd0-46e6294d5e51 | note | FREQUENCY: Prior to commencing any activity
a53e40ad-9646-5daf-a28b-00128c98ae18 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, ERA, SWMS
5b291697-2058-550d-a2ad-ef6bb3007c94 | note | REFERENCE DOCUMENTS: QMP, EMP, ECP, ERA, SWMS
3dadae19-73dc-5c41-a904-d97cb0f6acd1 | note | INSPECTION/TEST METHOD: Visual Inspection
9f719a1a-8da5-5150-9aaa-64ee515c0103 | note | RECORD OF CONFORMITY: This ITP signed off
14bc5054-bf1a-5cbb-8bef-07522cff02b9 | note | HP*
548345f6-871b-5b38-a477-6df5e80f2cb4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
53fe5ba3-ddb4-59e1-b4dd-8fe4fab7c599 | date | Date Completed:
d3aee803-74a4-4fb0-adde-83c3343ea655 | checkpoint | 1.3 - Placement of no fines concrete
e551bcee-0e9f-5682-9e79-0cd1aadb0079 | note | FREQUENCY: Prior to works commencing
b4c374b2-6236-5464-92f2-a2573e9cc431 | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
cbb8539f-427e-5f13-8a5e-8ae8fcf43513 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
35b1db8e-8c87-5f17-b5b3-2426bdf63d94 | note | INSPECTION/TEST METHOD: Verify
acd1a1ae-c59d-5d28-af73-64e92b7ac78b | note | RECORD OF CONFORMITY: This ITP signed off
2d35d639-0967-5ea4-8b23-7585afd13e0b | note | HP
ce5c508b-5015-560a-84c7-ff228776711b | note | RESPONSIBILITY: Site Engineer/ Superintendent
fa8fd634-6f67-516f-83b3-ca36cbcaa83f | date | Date Completed:
5a8a9155-f87d-4c0d-beaa-ccd2d147f09d | signoff | AUTHORITY HOLDPOINT
35a98514-7e38-440b-8667-d7f9cfd8fcc0 | checkpoint | 1.4 - Material Classification
0e8eb69f-a497-54d1-b6dc-e6e5851f47ca | note | FREQUENCY: Each Lot
3fd643b8-79a1-554f-81ad-3d50f972572f | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
6297a6ca-c168-528a-873c-5332bc25b8a5 | note | ○ Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05
5d7fa7b4-cb74-56f0-9996-8d713e323e28 | note | ○ Geotextiles: Shall comply with Cl 702.06.
4c9bd30a-6fbb-5c28-aea9-3e7b8c21f155 | note | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
d705094f-ce68-52a8-8672-3b1cf955e7b3 | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
9a68362b-4bfd-5fa1-b8de-1f2dbf05dcd3 | note | ○ Flushout risers: Constructed to the detail of SD 1631
aaf734d7-1050-537b-b4a2-34d96517b69a | note | REFERENCE DOCUMENTS: VicRoads Spec 702.04, 702.05, 702.06
d8ef9aa4-83a6-5503-bf97-ccf9f6ce88c3 | note | INSPECTION/TEST METHOD: Verify
a4f02bc5-f2cf-57bc-bb96-08280886cac9 | note | RECORD OF CONFORMITY: This ITP signed off
c317ca78-37a0-5e1d-bac1-27fc5cd29d38 | note | WP
26ea11d8-d39e-56ab-b266-5c652304ce2b | note | RESPONSIBILITY: Site Engineer
4fa93a6d-b6a8-510d-b8c6-fb0d4177c736 | date | Date Completed:
758b20f9-ad1e-440b-9fa1-6ae50cf65f5c | section | 2 - Construction Works
04231730-82a4-454d-9070-3325b938e46f | checkpoint | 2.1 - Excavation Permit
bc0f557b-c119-5b17-80c7-2d2b6c1496c5 | note | FREQUENCY: Each lot
69fdbf2e-8ae1-582c-a7e7-77c27d4aebef | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
24d840b2-491f-5d7a-9c38-280922f18372 | note | ○ Plant and equipment shall be appropriate for the task.
b2828df7-83b2-5a96-82ba-85fa4dab61aa | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
d240aa68-2f58-57dc-b46e-34dabb28a9cb | note | REFERENCE DOCUMENTS: Excavation permit
0379cb63-6553-5649-bb85-8e13c9df2559 | note | INSPECTION/TEST METHOD: Verify
6921539b-22c5-59b9-9cd7-0af88822b9ed | note | RECORD OF CONFORMITY: This ITP Signed Off
77506840-1850-5778-82b0-137219f188df | note | HP*
c26b9800-2bd5-504d-9ec6-cb779ed54890 | note | RESPONSIBILITY: Site Engineer
f6f8c516-9ba6-5482-b0ac-f946c281d44d | date | Date Completed:
380f0c1b-011a-4afe-a147-312e826d7051 | checkpoint | 2.2 - Excavation of Trench
9f16f3ce-6b19-5fbb-bdb0-7eff06b00687 | note | FREQUENCY: Each Lot
594a4450-9e37-5f2e-a6ae-2e7c068765f6 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
d2c20505-91e4-5efa-8a6e-45c33b565397 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.08
8d04595e-2810-5085-8648-e01e84119eb1 | note | INSPECTION/TEST METHOD: Visual Inspection
204bdcc5-af16-57a4-b4d4-ed001c1e61a7 | note | RECORD OF CONFORMITY: This ITP signed off
5de54893-a1e6-5425-aa94-eda4fadcb4bb | note | HP
156db5fe-4fcd-5295-84f6-b367bae0b9bf | note | RESPONSIBILITY: Site Engineer/ Superintendent
c9c1d5db-11c6-50c1-879b-8cfcbd37083c | date | Date Completed:
4dd0b22c-49b7-4615-bfa0-97780695ba64 | signoff | AUTHORITY HOLDPOINT
a14f58f0-b420-4a67-91f5-12f3d299ac69 | checkpoint | 2.3 - Placement of bedding
a472b4b8-f9a2-5507-95de-a025fdbf8c9c | note | FREQUENCY: Each Lot
ce686d95-91e1-5558-8147-d4835e320539 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
8dd43890-0189-583c-8d2c-82f8ceaed60d | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (c )
07760cde-146f-5b73-827a-049d2c2bfcdb | note | INSPECTION/TEST METHOD: Visual Inspection
4bf3c946-a310-5be0-875c-2242cad1efdc | note | RECORD OF CONFORMITY: This ITP signed off
134a8244-febb-586c-88e5-c0507d54e1e3 | note | IP
392cde47-52d8-5050-8345-cd1f83e541e4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c4875aba-cfa5-5a66-866c-857fc7fbbed8 | date | Date Completed:
12ce4e19-dfab-42de-9518-8b08f29cda5d | checkpoint | 2.4 - Placing pipes and geofabric (if required)
03a6fe25-e6ea-568a-81bd-2fe4a25b9402 | note | FREQUENCY: Each Lot
91af4394-5d2f-57d5-93f1-e8fd42b098e0 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
5cc1dc76-f97e-5958-b2a5-20c2c7d9b4a5 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
7488dd18-a6dc-5aa9-8ede-98fdaf2ef1cf | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09
5add63d2-ca5a-5ed1-a0d7-f110419b0006 | note | INSPECTION/TEST METHOD: Visual Inspection
e6c65eed-e632-5142-807b-81ec98e34770 | note | RECORD OF CONFORMITY: This ITP signed off
0a02e3ee-acf3-540b-a417-99a6b6da86a8 | note | WP
953cdac1-cc90-5d26-83a0-11170cf7f157 | note | RESPONSIBILITY: Site Engineer / Site Foreman
7c5d2e94-821d-5669-bf19-47e84f8c4caf | date | Date Completed:
b10aaf4a-f907-432b-9d1f-920e52bf1c6e | checkpoint | 2.5 - Placement of backfill
bac4c5cf-cd62-54bd-8c8f-8491ec7fe1e9 | note | FREQUENCY: Each Lot
5e9b261b-9486-52d4-a32d-d2e1b673f45c | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
abec7f07-ffd3-50b1-a1cf-dd9fa5e01f66 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
dc87dd17-ffc0-5e49-9620-274bde3d33ec | note | INSPECTION/TEST METHOD: Visual inspection
d12ae72f-a9d8-542f-92bb-fca89d552f22 | note | RECORD OF CONFORMITY: This ITP signed off
84ac7847-8e17-5d46-b16b-c8bed35d9c6b | note | IP
faa184b5-2436-5883-8955-280bf1ba5dcb | note | RESPONSIBILITY: Site Engineer / Site Foreman
c0ec21ba-93b0-59d0-99bd-a4f233f4b446 | date | Date Completed:
b8cc487b-395a-49d5-9ab7-901a84f27230 | checkpoint | 2.6 - Install Pits and Flushouts
68488bd8-20f3-5be9-af59-1de22ef991a1 | note | FREQUENCY: Each Lot
da435315-7a83-54ea-a67a-43a1f19430b5 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
adc572a6-8b31-533b-85e7-ba6fdb669707 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.1
7168e7c0-294d-5cd1-9652-2ebc65f78073 | note | INSPECTION/TEST METHOD: Verify
b9c9e89b-00d5-52e7-be1c-07c6db086185 | note | RECORD OF CONFORMITY: This ITP signed off
dd1f3471-a678-507e-9335-3f75f3c8e507 | note | WP
d4c204cf-ed05-50b9-a8ba-9b1dffbb2c44 | note | RESPONSIBILITY: Site Engineer / Site Foreman
7a65bec4-1431-5972-ac0e-eb520f77f7e3 | date | Date Completed:
1a08a36d-1fbe-43aa-9e32-6817dc92a335 | checkpoint | 2.7 - Flushing Test
b4a297ad-d2dc-5de0-99f8-d62ad6e843e8 | note | FREQUENCY: At completion of stage
f49911f2-aa09-597a-9f46-54f00b3f758e | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
6d71a83e-b412-57c6-91d9-70cc9951981f | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09(h)
6e1bcdb9-1a21-549c-9d8c-d0fd652d3ef7 | note | INSPECTION/TEST METHOD: Site inspection
d60e7cec-81d0-5d64-868a-cb689f36f327 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
c54ab05d-d434-51df-bc7a-83f6091c501a | note | WP
ceaee312-6e30-5138-a3de-67e8808db300 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a8dffcd2-1f09-543c-b383-eb885102a5ba | date | Date Completed:
1e30d00c-40cd-4dba-80d5-d22faae31d9e | checkpoint | 2.8 - CCTV
439ba6c5-0c60-58b7-87d8-f9b4fc603a05 | note | FREQUENCY: At completion of stage
f3c0dfd4-959c-5d8a-b91f-9646668a87b9 | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
b7d10f55-009a-5aad-9b11-3db6a1a9e361 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09(i)
625e0e5d-34ae-5c25-9032-a3ef440e68a5 | note | INSPECTION/TEST METHOD: Site inspection
073bc112-a1dc-5623-997c-e9bf54d7d9e2 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
a5920a15-e4f6-563c-a65d-225aeee13b8d | note | HP
74e50b86-49b8-5a52-81ee-de76ad388f60 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a0f6181e-d6ef-56f6-b679-84e52842c18c | date | Date Completed:
3c913c1f-3f06-4d8e-ae3c-a7999ccdc570 | signoff | AUTHORITY HOLDPOINT
8868433d-7384-44c3-909f-47e7a55d7d01 | checkpoint | Final Inspection
14233df8-8916-5ce5-b0f3-59d46f0eec3b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ab779906-48db-5ccc-a260-3c4164abcb86 | textbox | Print Name:
bdc2045c-bc21-5d7d-a1b0-03a517ae877e | textbox | Position:
a349b428-ad82-5fd6-91d1-6fe43af2c297 | date | Date:
b62f6c8e-3e8f-4030-99e1-b18147524090 | signoff | Sign ITP
612fb065-9500-4366-ab24-7fed5821376f | checklist | ITP-015 - Construction of Concrete Paving Rev1 | itp | ITP-015 - Construction of Concrete Paving
c4bc0189-87e6-4047-99aa-f458e9703b59 | section | 1 - Preliminary Works
db3eb685-5902-480a-92a2-f92572a7330b | checkpoint | 1.1 - Check for correct documentation
7c4443e2-4f31-548d-a93a-ddcb6beda133 | note | FREQUENCY: Prior to commencing any activity
33d09738-ab6a-5f74-99fd-21785ddf0fee | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
d0ee8c02-3dac-55fc-adb5-0c7bde535a58 | note | — using the correct and complete set of drawings
3348ca10-19d2-5c30-bf9c-b9456b8125e9 | note | — all drawings are the latest revision
62a18d84-5ca1-5b2c-a301-a5fa9f7eab95 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
225d3703-dc27-55e0-b47b-1b02816c14f3 | note | INSPECTION / TEST METHOD: Visual inspection
286cce81-7ca0-51fb-9c2c-4585fa590621 | note | RECORD OF CONFORMITY: ITP Signed
8a3abe39-4346-5c46-8560-3bfe6eff9058 | note | HP*
97507966-395c-5384-82eb-867e672a84c9 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
7fce0086-d093-5fb9-b657-ac27e53e4340 | date | Date Completed:
8d3aa515-66a1-4efc-b8b7-049b46779b23 | checkpoint | 1.2 - Implementation of all measures and controls
919dd8f1-bc35-580e-9c1f-2d26c920aec5 | note | FREQUENCY: Prior to commencing any activity
bcbb0e1c-429a-5de0-a23d-825a306822ee | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
734e4c78-798b-50c4-95c6-06d789e27b97 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
5735b7b9-b1af-568b-8995-29beaf3d1ccc | note | INSPECTION / TEST METHOD: Visual inspection
e5bb21a7-20f7-525b-a18c-a97f7bf652d5 | note | RECORD OF CONFORMITY: ITP Signed
ab3dc359-093a-504c-b5d6-fe22708e2681 | note | HP*
99f6cff5-b53a-506d-bf25-a12877ce259c | note | RESPONSIBILITY: Project Engineer/ Site Foreman
17f22835-3a2e-56c3-81b4-73e54fddf53c | date | Date Completed:
33a39c64-3c5c-4e75-bb1a-d0e80093463c | section | 2 - Construction Works
5f585d21-2663-4ccd-94d1-07feb47b1d5c | checkpoint | 2.1 - Setting Out
90d88ce6-d4db-5fc5-9f2c-d196a3b3b892 | note | FREQUENCY: Prior to start
84ee2793-b16d-5159-bf59-d5343901bc15 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
8be422c1-8588-599b-9b7c-5c25d7bf8dff | note | REFERENCE DOCUMENTS: 703.17
e0ba5892-680f-516a-a42f-7c278fce5a26 | note | INSPECTION / TEST METHOD: Verify
7d0446a9-961f-5068-9bbd-e53ac4604450 | note | RECORD OF CONFORMITY: ITP Signed
3ac8952a-f1bd-519f-9cd0-b03848aeb049 | note | HP
0e8e36d1-8b50-55b7-8767-5d19e88fa1cd | note | RESPONSIBILITY: Project Engineer/ Superintendent
c7273e88-b013-591e-b7ea-76492c8797e6 | date | Date Completed:
8f559996-8c9d-4eeb-83f9-f1a0529fe957 | signoff | AUTHORITY HOLDPOINT
c86a52f0-ed2d-459a-a25d-b4c8c012f1e9 | checkpoint | 2.2 - Temporary Drainage Provisions
1864071b-bb43-55d3-99d3-a6056526c175 | note | FREQUENCY: If Required
499b998d-7c5c-5a3b-bbfd-f00c84bf46f6 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
6d246564-9719-5319-ba43-c498d2dc83d4 | note | REFERENCE DOCUMENTS: Cl 703.18
46f58d58-2146-51c5-8d56-4b7cbbae0eb2 | note | INSPECTION / TEST METHOD: Visual inspection
d0573967-a8d2-58a4-ac12-fdf473cc1217 | note | RECORD OF CONFORMITY: ITP Signed
e10ba839-3a0d-53e6-b2bc-57dd2e89b1e3 | note | WP
d1056c80-b9b5-5be6-9678-c1b0c9cc72af | note | RESPONSIBILITY: Project Engineer/ Site Foreman
7dd1361b-11a8-5ba4-8e69-872e7ac50ed6 | date | Date Completed:
d49a5cc5-a7b6-4909-9b3e-65982c775c28 | checkpoint | 2.3 - Bedding
b92f120c-ae2c-53c4-a349-ae1327f4124a | note | FREQUENCY: Each lot
f40d7aaa-53b7-5df5-8d8f-add001630ad7 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
c064f1ec-ffb2-5304-85ab-a2904573cd42 | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
6afa44e3-8b13-58b6-b6d1-2e5af8b1eadf | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
16193a39-96fa-5fe5-a86b-ff57ef45fbad | note | REFERENCE DOCUMENTS: Cl 703.21
35010627-d44c-5355-b2b9-79e46e912f51 | note | INSPECTION / TEST METHOD: Visual inspection
3106b183-ccc2-5352-8fc0-c406844ac1c0 | note | RECORD OF CONFORMITY: ITP Signed
97f4c0cb-3e9d-5207-8844-a93e50531c03 | note | WP
5a3f4898-c1b3-54fc-b34a-37ef366968fb | note | RESPONSIBILITY: Project Engineer/ Superintendent
5165f498-e7ea-52f5-bcee-7ca4e66f5111 | date | Date Completed:
6c22e134-9471-44b5-a3b8-09bd753752ab | checkpoint | 2.4 - Pre-concrete check
cbbd88fb-75ab-5475-b267-93f96267ab51 | note | FREQUENCY: Each lot
73d6bc26-8bac-5a3b-89be-d93d43edfe80 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
c5534de2-f35f-511a-bf03-95420b307c0d | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
e6dd8aa6-c25e-5ae7-b8eb-1bb21bbf799e | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
708d7be7-6c3c-5533-b411-f61635c13320 | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
6e1adf9b-a38b-5195-a1d5-4d406bcccf97 | note | REFERENCE DOCUMENTS: Cl 703.08
5f38a89b-ec02-5a7a-8314-3be6a0f9c9a3 | note | INSPECTION / TEST METHOD: Verify
d2f21172-6cc4-5897-8f72-d08d7fe57b48 | note | RECORD OF CONFORMITY: ITP Signed
b4d89a27-a8d9-570b-8d09-b28a921b0a6d | textbox | Ambient Temperature |  |  | °C
bb57d65e-f9e3-5e9a-8a63-fca07a0732ad | textbox | Concrete Temperature |  |  | °C
08cfdc11-a483-5a4d-94ed-116ca437971b | note | HP*/ WP
ef0a89c9-2003-5123-b6ce-5967c72dd48a | note | RESPONSIBILITY: Project Engineer/ Superintendent
b4a09f11-8666-56a7-822b-f5db2fe881af | date | Date Completed:
59eca5b8-278e-4ad0-bd22-862bca5dbe8e | checkpoint | 2.5 - Reinforcement
255b5d80-d8cd-5ebd-a7d4-234f4246223c | note | FREQUENCY: Each Lot
7075ac66-4b62-52aa-9eda-10df91d1a486 | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
340f6e07-e4cf-5040-8a0e-fcb09467267f | note | REFERENCE DOCUMENTS: AS/NZS 4671
c5f1000c-34e6-5647-b585-29b3dcdea92a | note | INSPECTION / TEST METHOD: Visual inspection
c3ce0ed9-f859-5c58-863e-e2a378ac1444 | note | RECORD OF CONFORMITY: ITP Signed
44dc0fff-0f5d-5229-9377-2b8a8ffb4e69 | note | IP
5d16e2ad-2027-53be-8ff1-831d82544d45 | note | RESPONSIBILITY: Project Engineer
541ed279-ea6c-5820-804a-357b95c2b764 | date | Date Completed:
94b0414b-01bf-4675-9bcf-23a8a35a4209 | checkpoint | 2.6 - Concrete Placement
bdbdd5d0-b67a-523d-a120-610eb4491424 | note | FREQUENCY: Each lot
fd5bec57-cbff-560a-bc97-332793d64be9 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
32798cec-aaca-5eeb-878c-09011c31d4cf | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.23
da202262-f654-5756-be4b-aad703cbed6c | note | INSPECTION / TEST METHOD: Site Inspection
7242a7f3-43c2-5946-a236-67b52c15d6a1 | note | RECORD OF CONFORMITY: ITP Signed
dd4db02a-6601-5a60-9c17-8c9a1d01d055 | note | IP
27d75278-9f34-53ef-8fd5-1936e3c2f190 | note | RESPONSIBILITY: Project Engineer
88e696a7-d9b7-52fa-96b8-ec00455e350a | date | Date Completed:
bca39e3f-e5e2-49ef-963c-d68a2009e4dc | checkpoint | 2.7 - Finish Surfaces
187994f1-67df-53b7-a408-c270d4002494 | note | FREQUENCY: Each Lot
044fad3b-a44d-564c-a092-4b37ff8c8ae9 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
7f884de2-6f07-5473-8c7a-b0183238b791 | note | ○ Concrete to have a neat appearance and uniform colour
aee3b6b4-5b40-5717-85fd-da5c73a0add8 | note | REFERENCE DOCUMENTS: 703.25
e9860695-b5a7-56cd-996f-49eac535db59 | note | INSPECTION / TEST METHOD: Visual inspection
e02202cf-b910-5ead-94a8-6d52b539a840 | note | RECORD OF CONFORMITY: ITP Signed
dbcc03aa-5d01-5983-bf29-165b20d4803f | note | IP
f9982201-b25b-5169-aa4d-c80a0829df44 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
919f44ba-9686-5dc8-9ad6-79c7bf353aa4 | date | Date Completed:
88a410a1-de97-49a1-b661-24fad5f152a9 | checkpoint | 2.8 - Joints
7e824f1b-cf4d-5acb-9fa8-5d94fe34e28e | note | FREQUENCY: Each joint
30365102-5729-5758-a867-8df7f5e3acec | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
3a279801-e935-5425-b174-b89de07f0d99 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
f3b2dbdd-8663-5e5b-a516-85f8703702aa | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
732787bc-d7b1-5a3c-970d-5fbd42e2cf18 | note | REFERENCE DOCUMENTS: 703.26
40c59041-bcc4-52f6-9734-7a639066ea96 | note | INSPECTION / TEST METHOD: Verify
442dbf6e-42cb-563d-b3a5-0384a53d4cb6 | note | RECORD OF CONFORMITY: ITP Signed
fb86b29f-15d4-5d48-8760-d13025376178 | note | IP
cfd90c53-01a1-5c96-968c-78c67b24c7e7 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
d08c4452-3133-5e43-b17b-9915fb8c8931 | date | Date Completed:
a4a90db7-3313-41ea-ab33-6ee5abd6139f | checkpoint | 2.9 - Backfilling
0ddeec91-e01f-5c9e-9149-17b2773feb3f | note | FREQUENCY: Each Lot
b995ad1c-e70e-5d18-a875-559eeca569f8 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
3bebefda-a2c9-55f6-991a-b9856bcae66e | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
43e5169e-0986-54b7-8ade-de0c42c90f2d | note | ○ Layers shall not exceed 150mm compacted depth
5cefc896-f19c-5875-ac49-9e8b0cc5f0db | note | REFERENCE DOCUMENTS: 703.29
d3295652-337b-5caf-95d7-a7682191fb8a | note | INSPECTION / TEST METHOD: Verify
cfe3a797-0309-5f10-9521-dbe4095dc293 | note | RECORD OF CONFORMITY: ITP Signed
dbfb5e98-0786-587d-9c4a-410c5da8d519 | note | IP
abb377cf-a41b-51dd-b852-e82c6a338276 | note | RESPONSIBILITY: Project Engineer
cbc26540-1634-52b2-a9e2-64d7b35e50f4 | date | Date Completed:
d8acea1b-0dc7-4a10-9586-df48d8fa5e2d | checkpoint | Final Inspection
592106fd-9382-56be-9cbd-225fc066ad4a | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
49536b01-c2aa-53db-a73f-58b4f1b87072 | textbox | Print Name:
ff952a7e-fa5d-5a4b-82a8-2826c9b8aa78 | textbox | Position:
3c6a15d8-fbc1-59d2-bd67-da84e146597f | date | Date:
a27af9d5-6815-4b37-bf1e-60f4ef5f8272 | signoff | Sign ITP
198f725c-b5e0-43a0-b06b-13bdf30ec78f | checklist | ITP-015 - Construction of Kerb and Channel Rev1 | itp | ITP-015 - Construction of Kerb and Channel
59534cff-7b16-4dd0-94ba-f17f446a5a62 | section | 1 - Preliminary Works
6aabdf79-8ff1-4809-ade9-8ee13fdc5c75 | checkpoint | 1.1 - Check for correct documentation
bc177a1c-2496-5a0c-8d4b-f9de71bca0e7 | note | FREQUENCY: Prior to commencing any activity
ff9095cc-9fe8-5bee-8ccd-a68415da63e3 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f41497d5-7de0-5622-b893-05987150815a | note | — using the correct and complete set of drawings
fef635bd-50ca-525f-9d13-79f450132592 | note | — all drawings are the latest revision
7f515a1e-c2ec-5edf-8111-c4ab7cae466b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
05d4d1c4-c341-52a1-8bb0-6361c16b0c99 | note | INSPECTION / TEST METHOD: Visual inspection
c0dc4b76-3cd6-5352-968f-e11c7de643d4 | note | RECORD OF CONFORMITY: ITP Signed
2cfb68ad-1109-5c4a-8c9d-70b9917b6273 | note | HP*
1ec3a44c-02d9-58eb-b38c-93d4731a0d59 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
398b5df6-15a2-5089-9065-c57f77af2b17 | date | Date Completed:
72ff73cc-df3e-40c0-866a-297ea567e6d8 | checkpoint | 1.2 - Implementation of all measures and controls
7559e71b-73cc-55a8-bd66-c19b4c97ca77 | note | FREQUENCY: Prior to commencing any activity
aac0869d-fe49-5802-9d1b-34681318fb88 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
c8a426fc-46b9-5fa3-887d-a174cc5c6c27 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
f5a5116b-b124-51ba-9974-c8f2bb5acd3c | note | INSPECTION / TEST METHOD: Visual inspection
04f2b0ca-4b64-5a33-82b7-93fb8bcfcdbc | note | RECORD OF CONFORMITY: ITP Signed
36be77ed-dd55-5fda-b763-dcfd8149d653 | note | HP*
e14e4850-e564-595f-8ce0-54c9e5f5c5f2 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
9c79b5a5-8495-5a97-8a44-0b02e055acbe | date | Date Completed:
dd49573e-980e-4411-a728-11c8791ac731 | section | 2 - Construction Works
f52d2505-6105-495b-925d-fb95492ba7bc | checkpoint | 2.1 - Setting Out
a36791b2-8b4c-5844-acd1-c49c50bd1b01 | note | FREQUENCY: Prior to start
bb73ebbd-c501-562c-9d69-3750f10a6cb4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
c679602f-6ff1-5a46-965d-b25566e06489 | note | REFERENCE DOCUMENTS: 703.17
00d12307-d785-54d1-a5ef-bbcbef9eda64 | note | INSPECTION / TEST METHOD: Verify
506d4f2b-6e44-5804-bf84-20eb4d07a742 | note | RECORD OF CONFORMITY: ITP Signed
bee7bb44-156b-5bea-bb12-2b61b2e96124 | note | HP
2231fd77-4d33-5a6f-bf7c-ffc5205c6050 | note | RESPONSIBILITY: Project Engineer/ Superintendent
edc0e9eb-99bd-5ecc-8a2b-92bd4f2d7fbe | date | Date Completed:
0eeb9c75-2aae-49de-9028-97419a2070fc | signoff | AUTHORITY HOLDPOINT
86d49bf2-64bd-4a71-926b-87d99bf7429e | checkpoint | 2.2 - Temporary Drainage Provisions
b5e2d715-ddf8-5c00-bfd9-d914a3eae456 | note | FREQUENCY: If Required
88909feb-0c98-5e01-a62e-7b41f4b1dc1e | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
ca24c87f-668e-57ae-ac3e-3f22a88cd10d | note | REFERENCE DOCUMENTS: Cl 703.18
b419ce17-f984-5112-af41-44660446a04b | note | INSPECTION / TEST METHOD: Visual inspection
f640f94c-f186-5b40-8229-72757d08a6cf | note | RECORD OF CONFORMITY: ITP Signed
de7eaded-3807-5e07-99c2-630aff3efc6d | note | WP
2663f687-cd30-5902-a6dd-a9997850f49f | note | RESPONSIBILITY: Project Engineer/ Site Foreman
080baced-2f04-53f7-8674-22a567ab2767 | date | Date Completed:
b5113345-acc0-438f-9789-724fcc895c7a | checkpoint | 2.3 - Bedding
df753cd4-47f6-5362-8990-32b5e4b18079 | note | FREQUENCY: Each lot
925cee56-8b21-5cd9-a77b-3909944f07ad | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
07af76a9-dbe5-5854-81f3-a5e36153b37e | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
7ea2c31e-cd9d-5705-bcea-f848148cded2 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
970c4c3b-2de0-55e2-8b5f-39fbbbfda979 | note | REFERENCE DOCUMENTS: Cl 703.21
93be65c5-f5ff-5280-ad67-0bffa6ed3b81 | note | INSPECTION / TEST METHOD: Visual inspection
379a7980-b363-544d-a74c-9405fc3f1129 | note | RECORD OF CONFORMITY: ITP Signed
f569d85e-57e9-52a4-aa15-1f2aeda710e0 | note | WP
9b0ff26d-744e-5523-89c1-23289e8e782e | note | RESPONSIBILITY: Project Engineer/ Superintendent
0d746583-41d0-52b9-a8e5-e4f80326af69 | date | Date Completed:
0d22c40c-8600-41d5-b7b3-93795ef34081 | checkpoint | 2.4 - Pre-concrete check
8080e455-0280-5473-8a5e-aabd631bab60 | note | FREQUENCY: Each lot
ec1c7b89-4a6b-5f62-a63e-8e599498c905 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
7a395298-caac-5a69-8613-c48e99383670 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
9c02247d-20fd-5717-8148-f15136040c13 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
7de776ef-4670-524d-b97c-939004d447b4 | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
e6fa052b-3437-5fd2-a22d-78f9ba2d488a | note | REFERENCE DOCUMENTS: Cl 703.08
37bd5a8d-a641-56d6-8952-10848dc67d81 | note | INSPECTION / TEST METHOD: Verify
5c8a9927-cba3-5e12-bf07-022916b4d098 | note | RECORD OF CONFORMITY: ITP Signed
9f2b4276-abf4-5bd0-89cf-544600a3a57e | textbox | Ambient Temperature |  |  | °C
df8b527d-cbd5-566d-85b4-541b5c71b8c9 | textbox | Concrete Temperature |  |  | °C
c744638c-7d70-54e4-ba23-5f390f477f27 | note | HP*/ WP
44917d28-b9c5-51d6-aa4c-364c7732d92d | note | RESPONSIBILITY: Project Engineer/ Superintendent
45a801d3-c952-546d-b767-69f4e31d8fda | date | Date Completed:
3d5d147e-492d-4c5a-b6d3-f5a5c2770ca7 | checkpoint | 2.5 - Concrete Placement
14472d90-82f0-5e4b-a1c2-934ddcfcf3a6 | note | FREQUENCY: Each lot
d7a01919-c829-538b-bff3-4f79cbf6ae0f | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
0acde323-fdbc-5d36-80cd-1f6886bf6002 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.23
8d2ea503-fcff-55ce-bb26-3d198241cc76 | note | INSPECTION / TEST METHOD: Site Inspection
8265aa14-3d65-597e-91b8-33390ec5a054 | note | RECORD OF CONFORMITY: ITP Signed
717d7aba-a507-528f-9cff-18090f74d574 | note | IP
3ab981d1-d32c-5c24-9385-830a323e7920 | note | RESPONSIBILITY: Project Engineer
696a19bf-9e45-58f0-b3f3-78e645e99b2e | date | Date Completed:
ac0df04b-e75b-48a7-94dc-b2abc98d1778 | checkpoint | 2.6 - Finish Surfaces
6c35b123-acfd-53a3-bc6d-e396f5e02ae0 | note | FREQUENCY: Each Lot
857765af-2ace-5020-a693-67d3ec85abd0 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
5a6a20a2-c1ad-56cc-9193-bab88bbf6168 | note | ○ Concrete to have a neat appearance and uniform colour
1ddf3bc8-d057-59d4-a0a0-f1c29a9695a8 | note | REFERENCE DOCUMENTS: 703.25
f077ef9b-961b-56ad-a0dd-eba1769f18a7 | note | INSPECTION / TEST METHOD: Visual inspection
41786aad-572f-5063-8629-950a46d58a63 | note | RECORD OF CONFORMITY: ITP Signed
f7aa0200-c9c6-5f40-ac25-b748670b5f9b | note | IP
9a741b2f-fd24-5cf6-8ac1-5586af9123f6 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
5e1a3775-a3ba-5191-b2cb-265504372373 | date | Date Completed:
34648163-294d-4ac4-8c77-6bd6cb353758 | checkpoint | 2.7 - Joints
78c4aed6-4cc1-58c5-8763-ddd9ebccc74b | note | FREQUENCY: Each joint
470676ca-1077-5512-9d59-c74d1fcc9b80 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
4562f28e-9d86-5a7b-bdce-20cd4df56ad9 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
96a31d2d-ca4b-5221-b48b-60f19e16361e | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
2f95b4f5-b29e-5fc1-9bc2-74cf9e075ef2 | note | REFERENCE DOCUMENTS: 703.26
8a6f4d29-3f4a-5589-913d-f9cee7f40993 | note | INSPECTION / TEST METHOD: Verify
8a53fbb8-5e6e-5ca4-b35e-a2d7f0ef738f | note | RECORD OF CONFORMITY: ITP Signed
e1e89a53-e688-5404-a871-ce1e29ed34a3 | note | IP
be2493ac-f1b1-5acc-91bd-6714166a75a4 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
e350bbe0-cfa9-5330-b7a0-10dd302344e8 | date | Date Completed:
b8cdb21c-2825-49a7-a10d-ef49c04b152a | checkpoint | 2.8 - Backfilling
4d4b34b6-7468-53b9-950b-29869a68dede | note | FREQUENCY: Each Lot
76434503-bcef-57d3-81cb-411e4adec959 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
1f8f79a7-a7ee-552c-a6cd-c0874f0fc522 | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
83e24fba-d39d-52ba-8c34-0dd79403b5ea | note | ○ Layers shall not exceed 150mm compacted depth
7ab32a72-98a5-5fa5-897b-dc744de65ef2 | note | REFERENCE DOCUMENTS: 703.29
5b38c557-b12d-53ac-99b6-dfaae45405e2 | note | INSPECTION / TEST METHOD: Verify
e58dddd3-1bdd-5257-94f0-c8b0a02bd4fd | note | RECORD OF CONFORMITY: ITP Signed
057cc33b-8a7b-5b66-bc59-22d6840bb0a0 | note | IP
fb2826df-1700-5303-ae64-fb06aa116de2 | note | RESPONSIBILITY: Project Engineer
f8d7e62a-628c-586d-af05-3531705bfa44 | date | Date Completed:
508a15ab-9d72-4143-a514-e7ce7422fa80 | checkpoint | Final Inspection
bfbade20-eeae-5ea3-a478-147f917f5d46 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5de603c9-b244-5d35-95ec-8b9d29149f4b | textbox | Print Name:
e3c16b4d-18b4-5db4-97d8-38b302ddd293 | textbox | Position:
b73ecd59-3e62-5de4-9ed6-2a03afd4af10 | date | Date:
b410e64a-4320-4bb5-b4a6-7b6ce2cb61ee | signoff | Sign ITP