## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Rock Fill VicRoads Section 205 | itp
section | Hold Points (HP)
checkpoint | Clause: 205.04(d)
label | ACTIVITY: Oversize Rock
label | HOLD POINT DESCRIPTION: Approval for use/disposal of oversize rock exceeding Type B fill specs
label | RESPONSIBILITY: Contractor
label | RELEASE AUTHORITY: Superintendent
holdpoint | HOLD POINT
checkpoint | Clause: 205.06
label | ACTIVITY: Trial Section
label | HOLD POINT DESCRIPTION: Review of first lot placed as trial section for grading, mixing, watering, and rolling routine
label | RESPONSIBILITY: Contractor
label | RELEASE AUTHORITY: Superintendent
holdpoint | HOLD POINT
section | Test Points (TP)
checkpoint | Clause: 205.05(b)
label | ACTIVITY: Placement & Compaction
label | TEST DESCRIPTION: Compaction trials with track rolling, monitored along the alignment
label | FREQUENCY: Each trial section
label | ACCEPTANCE CRITERIA: Effective refusal and compliance with level tolerances
section | Witness Points Inspection
checkpoint | Activity: Rock fill and CL3 Layer Level Control
label | DESCRIPTION: Visually check rock fill layer conformance at 350mm and CL3 layer at 100mm
label | METHOD: Visual
textbox | TOLERANCE:
checkpoint | Activity: Geofabric
label | DESCRIPTION: Confirm rock layer is wrapped in Geofabric
label | METHOD: Visual
textbox | TOLERANCE:
checkpoint | Activity: Geogrid
label | DESCRIPTION: Confirm geogrid placed under rock layer
label | METHOD: Visual
textbox | TOLERANCE:
checkpoint | Activity: Proof Roll completed Soft Spot Repaired
label | DESCRIPTION: Proof roll over repaired area prior to placement of Type A layer
label | METHOD: Visual
textbox | TOLERANCE:
checkpoint | Activity: Subgrade level conformance
label | DESCRIPTION: Survey conformance of subgrade repair
label | METHOD: Survey conformance
textbox | TOLERANCE:
checkpoint | Activity: Compaction testing of CL3 layer
label | DESCRIPTION: Compaction testing
label | METHOD: Compaction Testing
textbox | TOLERANCE:
section | Supporting Documentation
checkpoint-no-status | Supporting Documentation