## Master List Templates
Id | Type | Name | Values | Prompting Name
be0821af-0812-4143-86b0-6054e6508cd9 | checklist | ITP - Chipseal | itp | ITP - Chipseal
7f202172-5a75-413d-8312-99ce30488a1c | section | 1.0 Pre-Commencement Activities (Design suitability)
401fe3c3-072d-4e98-988c-143de632d238 | checkpoint | 1.1 - Surface texture measurement (1)
44f8b73e-1cdc-5cd2-baba-73a12c0c7589 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03
3ba0de5f-6cdd-59da-924d-1881bd9d294c | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P03
2d7e62e1-fc17-54c2-a82b-0e7b8457f8a9 | note | Higgins (Comment) - NZTA P03 (First Coat seal) and P 04 is client provided designs
dd498689-f034-5d12-8ef2-2656865afb81 | note | Frequency - As per NZTA P03
ac69a977-c833-5807-9f03-57d29dd0506e | note | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
90ae79a9-db0e-51d6-8eba-7f7ccc8135dd | note | Contractor - H
dff87a0a-9802-5726-b81a-6d953b98d3a8 | note | Records & Remarks - Tabulated worksheet
a81dbb7f-1dfb-4b56-a46a-e85b28b2480b | signoff | HOLD POINT
3742517c-5eb9-48cc-914e-3683100987e6 | checkpoint | 1.1 - Surface texture measurement (2)
26ab086d-21be-5fc7-bc6c-aa14d3a28270 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P04
9cfae3e9-7a74-58d3-ba82-8907ff029128 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17 4.3 Surface Texture
015cfdfc-ab5d-54f9-b507-0de5a94bda75 | note | Higgins (Comment) - NZTA is contractor supplied
3b31c665-02ce-53e2-98a5-25a6a02e019c | note | Frequency - As per NZTA P17
642df900-b7da-5ab4-b0e7-334bb5d7ce99 | note | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
12a9c09e-2cbe-5168-a8e8-4d4e589c9083 | note | Contractor - H
44d2b816-ebfa-5fd6-9bb0-f4cbb0766058 | note | Records & Remarks - Tabulated worksheet
bbd8c135-c8f4-4656-8a73-a3e388412677 | signoff | HOLD POINT
3725f305-b0f4-492f-b2f3-b7167a46231e | checkpoint | 1.2 - Treatment selection confirmed
cb18585f-2b03-57c4-a18d-6c7ce06817d9 | note | Frequency - Pre site works
e5709b76-db27-5b50-a86e-60a0c17cffa7 | note | Criteria Notes - Principal agreed treatment selection
cd7fc413-3481-5daa-86e6-f847bd7a278f | note | Contractor - H
b871b2a1-bcca-5151-8ef7-b9c70ea313c7 | note | Records & Remarks - Records of Contractors Design
0fe0a0ee-a2b3-4389-86f8-8e1ff68c3ede | signoff | HOLD POINT
ba6e2a8f-863b-4c94-b809-652917b2edd2 | checkpoint | 1.3 - Chip skid performance
368663d2-ec62-5214-811b-7595d26d5424 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA T10
b8758f49-d3d6-531d-bc59-b085976a03bf | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA T10
71e256e6-6a17-5fc3-9652-dc3938f70b6f | note | Frequency - Pre site works
85ea9332-2e84-54b7-b4a8-35c97103b40e | note | Criteria Notes - Aggregate Peformance Report submitted & accepted by Principal.
7f5c7f83-d197-5ef4-bde8-27ea3e7caa33 | note | Contractor - H
7b08822a-e684-5a57-8f0f-ed4fbe52567c | note | Records & Remarks - Included in chipseal design report
7d86faae-aade-4b7b-b527-33931bd92ad3 | signoff | HOLD POINT
d29c2946-5fce-49ef-9098-751e58b07956 | checkpoint | 1.4 - Chipseal Design
b5d5962d-4246-51d0-a2ed-44044ed9c2ad | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P18
e261c45a-8eaa-5f47-b724-623ad4202e2b | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
348857e3-b1ce-54a6-acb6-b86926d74c41 | note | Higgins (Comment) - NZTA P18 is principal designed
d7b3b2bc-70b4-5c97-8926-4b3f76c45b0b | note | Frequency - Pre site works
fccbab16-e275-5049-8d3c-705d0d6bf64d | note | Criteria Notes - Design meets contractual requirements
3ff5aa86-14e5-5661-bb22-c4c90b015570 | note | Contractor - H
c99f631a-cdbb-545c-b7aa-a73f7f1f504a | note | Records & Remarks - Seal design provided to principal
79128254-dcdf-4c02-a963-ed04a6208d83 | signoff | HOLD POINT
55812aed-072a-4d1a-ae30-237a1496297e | checkpoint | 1.5 - Multilayer compatibility
6bea49a6-70ba-5aa8-a989-a1bf96133c00 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P18 Fig 1
8c1ddf60-dac2-5556-97b6-3722a9417e52 | note | Applicable Standard & Acceptance Criteria (Higgins) - Chip seal NZ
b444d6a0-74f7-5b1e-aeaa-1b82adb7101b | note | Higgins (Comment) - NZTA P18 is principal designed
6777585b-d77a-5432-a855-b809a0cdb1df | note | Frequency - 1 per design
20549f5d-7758-55f5-8787-33a4fd40de61 | note | Criteria Notes - Both ALD results identified on graph
333369f3-0a8a-566b-aa68-c4ae12f2ee54 | note | Principals Rep - W
abd6a840-96e8-5e7c-ad4d-5342f2639c07 | note | Records & Remarks - Included in chipseal design report
8af8d99e-912f-45e3-8f5c-385c6fce0549 | checkpoint | 1.6 - Renewal Quality Plan
c8130edc-7179-55c1-81d9-81008a59af89 | note | Frequency - One overarching for all reseal sites
c11c7823-3c87-57d0-ba33-c77cd7e1b563 | note | Criteria Notes - RQP Approved
4e05552b-ca4b-5172-a21e-4d974a6906d5 | note | Contractor - H
11f92868-9f76-5ecf-a7a7-85d8562563fc | note | Records & Remarks - Principal approval signature
0f24fe9c-d5f2-4be7-b5fa-c0f36c7353d7 | signoff | HOLD POINT
3d729f2b-2cf2-436c-aba6-e784c0302aab | checkpoint | HP – Chipseal design verified for site commencement
0eff4e7f-6935-5e99-be3b-d6e0976c85d7 | note | Criteria Notes - Contractor checklist copied to Principal
690dda18-92db-57d6-9914-16749b06aab9 | note | Principals Rep - W
ff1532db-c0b9-5d6a-8b69-3c018fb24786 | note | Records & Remarks - Pre-commencement checklist signed and filed
6169331e-878e-42be-8863-75f862209cd6 | section | 2.0 Material Compliance
2244b4ea-a143-4172-aae8-b89a6ef006da | checkpoint | 2.1 - Bitumen compliance
6f383f08-1270-5936-9c57-1e86bab02716 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M02, P03, P04
778a37e7-81f2-5992-9bb3-52de4c2d3c9e | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M1
68f6e75f-6017-5115-abcf-fb6c98654264 | note | Higgins (Comment) - Currently all seal is completed with Cut Back Bitumen as per M01
81cdca0c-b8c8-5bf6-b467-23fbda152442 | note | Frequency - 1 test certificate per bulk shipment
a47bf167-58f2-598e-ab67-b57eb868e971 | note | Criteria Notes - Lab Test Report
945a83d6-1883-50e5-ba42-5fa1f9bd13fc | note | Principals Rep - W
aac9c3b0-ebc9-560c-86fa-e36eda0f2712 | note | Records & Remarks - Property Test, NZTA M01
71a23fe0-67d8-4478-8c22-8487ba6e3c83 | checkpoint | 2.2 - Chip source property compliance
d23942f7-93ee-5d1c-90fd-5cd7b0913b39 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M06
b2a5c9b2-98c4-5c85-9bf2-8b62daf47a77 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M06
30321e1f-c0ac-5c25-b0e0-9369a54c8a95 | note | Higgins (Comment) - same
6a31a041-6e08-53c7-a89a-9c7e87681378 | note | Frequency - Annually for each source
72e58981-0fc1-59f2-ae0d-d80431217950 | note | Criteria Notes - Lab test results
89330110-5d79-5546-be09-a5bc2ae62278 | note | Principals Rep - W
cc794aff-6b9c-55d3-ae49-c2479e8343d9 | note | Records & Remarks - Source property checklist: PSV, CR, WR
bfd15eac-8a7d-430f-9b6e-90e22d481a1f | checkpoint | 2.3 - Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from)
d84c6460-a1b4-5f3b-a806-8385443f28bc | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M06, P18
e5323749-fc22-5328-a821-4e78ff431f74 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M06,
0a6146fa-4f71-5bb4-bb2f-1aa94f82d71d | note | Higgins (Comment) - same
4fa56a07-c9e1-5f5c-8bca-e3dd1dfae324 | note | Frequency - < 100m3, minimum 1 sample
c374e499-33ec-521c-af2e-c53bf23cb06d | note | ○ 100 - 500m3, minimum 2 samples
268dfe80-c28b-5b81-b7b7-d04ea764e81d | note | ○ >500m3, minimum 3 samples
7520bc98-8150-51b5-89d0-17d4f714fa14 | note | Criteria Notes - Lab test results
5b34f2cc-98d0-588d-85b8-ac31fab71b0d | note | Principals Rep - W
9c2ca1ef-d5b4-502f-a6ad-491d2c8beb09 | note | Records & Remarks - Cleanness (Grades 2 – 6); Sealing chip size & shape; Broken faces (if reqd); PSD
432b9b91-9ea4-4844-b729-c725039b606a | checkpoint | HP – Material compliance confirmed (binder, source & production properties)
d235d724-c653-52d1-b068-5c3067051516 | note | Criteria Notes - Material compliance checklist copied to Principal
75c754a1-068d-565b-b432-2d22cc8e3af9 | note | Principals Rep - W
aa2f5408-a424-591f-a076-836a202c038c | note | Records & Remarks - Material compliance checklist signed & filed
a36bc2df-4a58-4642-ba2c-09b0c481cd98 | section | 3.0 Seal construction
cf8e2e0d-362c-42c4-9c19-5520ebf4a663 | checkpoint | 3.1 - Pre-Seal Site Checklist (week prior)
e8dcf7d1-7ff9-5443-823c-7c150b25c8f8 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - Confirming site is ready for sealing
f49dbe14-2c80-5ea4-8907-ab584a2a9898 | note | Applicable Standard & Acceptance Criteria (Higgins) - Confirming site is ready for sealing
2ea0a7a8-7553-53ef-8477-8d05ffcc7383 | note | Higgins (Comment) - same
027cf52c-c164-55ad-81aa-61d2327132b3 | note | Frequency - Following ALL pre seal works
32899384-2706-54b5-b9ed-5ef33b476c3e | note | Principals Rep - H
1af4f703-247d-5364-9d12-08262ed7884c | note | Records & Remarks - Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records
d91bf495-5da0-4008-a6ef-790223d288eb | signoff | HOLD POINT
455d839d-9c55-47be-bfa3-ea218a3325d7 | checkpoint | 3.2 - Bitumen Distributor
e7f5c21f-6e83-5997-b21c-84c9d5de85a5 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - BPG 02
212b7ff3-88a0-530a-a38e-878bfc9df84b | note | Applicable Standard & Acceptance Criteria (Higgins) - E2
c32ce549-7f27-5481-8100-29e777baa8f9 | note | Higgins (Comment) - Bitumen Distributor is certified under NZTA E2
d375d4af-3b18-5413-8789-8b9aad3276b6 | note | Frequency - Annually
0d4afa9d-3d74-559c-8240-7eff7f973539 | note | Criteria Notes - Speed Test, Dipstick Test, Distribution (Pad)Test
3e82f10f-af82-5b2d-8818-3ff716133476 | note | Principals Rep - W
f43fe886-ed26-55e5-ba72-7c18bd7c2e5d | note | Records & Remarks - E2 Certificate
39dae4de-3931-4064-8239-e67645adc37b | checkpoint | 3.3 - Go/No Go Checklist
792ff0a2-c3af-580d-95f7-94d8aa423f70 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
ca885309-e6a4-53e5-bac7-ee94118519fd | note | Applicable Standard & Acceptance Criteria (Higgins) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
869d6da5-e135-5dbe-8f54-d6db22caaa31 | note | Higgins (Comment) - same
3bc9e252-f67a-5ed5-a586-e34bbdd87100 | note | Frequency - Prior to sealing on each site
9a12d0e5-6635-5b53-84e3-3272eef45232 | note | Criteria Notes - Visual on site and check list sign off
f9944dc3-d7e3-50f6-8db8-d5b1d87bcf91 | note | Principals Rep - H
9427f621-8f21-592d-bec8-2da72159cfa0 | note | Records & Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
c6c6165a-41f5-4969-97b3-ba72f4f1ccb7 | signoff | HOLD POINT
7d15f2ef-acb3-440d-9885-58351e84c942 | checkpoint | 3.4 - Spraying – site measurements
30e84a88-2308-58ab-b0d5-cf1968d5edea | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
4cd53e1c-ba2d-5b34-a592-69c9aa1b63eb | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
79ee306a-7db2-52b8-a017-08fd2bf1fdc5 | note | Frequency - Per Site
3ee515e6-4dc5-5dca-b8f3-caef33ac5c93 | note | Criteria Notes - Application rates within design & tolerances + or - 5%
351087fe-99a8-57be-a8f0-0d3e5af1f22c | note | Records & Remarks - Spray sheet
6ac06cfe-4d52-4c1d-b672-7e8a48d3af2f | checkpoint | 3.5 - Geotextile reinforced seals (GRS )
155fd4a3-a58e-5bf4-b4dc-e3338f0b6fa3 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - As per P18 & specific design requirements
f6c4af35-bb21-554c-bb50-d93f9f1e4b5a | note | Applicable Standard & Acceptance Criteria (Higgins) - As per specific design requirements and P17
cf78d7e4-f7d7-537d-ad50-39b12132b880 | note | Frequency - Per Site
d34faefa-c1e4-55e8-90b4-8f52559281b2 | note | Criteria Notes - Accurate RP start/end location & offset
471a22ed-1c88-5c00-a02a-3ab6b3b6e833 | note | ○ Application rates within design & tolerances + or - 5%
c8d8f5ad-99c1-5719-bed1-3afe4c392207 | note | Records & Remarks - Spray sheet
111c5272-ff4f-49fc-9fae-21ab2b00dc36 | section | 4.0 Clean-up
c2accdaf-4139-4d37-9210-507333745e38 | checkpoint | 4.1 - Post-seal (exit) inspection
084c5822-587d-5ef6-8514-23889115b54d | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
7fa6be6a-fe15-56db-a737-926afd68139c | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
da4a461c-96da-5ab6-8cbe-c36338425560 | note | Higgins (Comment) - NZTA P17 Notes section 18
614f846e-9685-588d-bbff-5c8b5bac9cca | note | Frequency - Per Site
1f3648c6-b1eb-58d7-a928-5607b6709b09 | note | Criteria Notes - To open for trafficking
34fe6b98-59f4-5463-be4e-83fe8413e716 | note | Records & Remarks - Chip Sealing Quality and Site Checklist
e1b01149-b9f7-480d-86a3-9e39dc1b4553 | checkpoint | 4.2 - Removal of surplus chip
675a14b0-e580-5d87-baea-682f4fba9e89 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
72732a36-6a89-583e-9f25-a62e277742ad | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
272aa5a2-64c8-527c-b057-7f01be9375c3 | note | Higgins (Comment) - NZTA P17 Notes section 22.2
7eb94d07-e16f-512d-8479-0bb38664ba1e | note | Frequency - Per Site
ac079a4c-bd1f-508c-97b0-ec131c90e986 | note | Criteria Notes - Loose chip complies with P03 or P04 as appropriate
cc9bdf6a-5a5c-5379-af3e-22ef9c6cc312 | note | Records & Remarks - Chip Sealing Quality and Site Checklist
0b0db315-7d6d-44c8-b91a-0f289d4f31e5 | checkpoint | 4.3 - Post-Seal Site Management
7761b3c2-2dca-5d3d-8dd8-18846cdd26d1 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
29225741-d2d8-5357-afb7-c3a05713b487 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
2a4f4259-a575-5fe7-a31c-041902ac667f | note | Higgins (Comment) - NZTA P17 section 7
db38c504-6b9b-55cf-bacd-81adc74d265d | note | Frequency - Per Site
bb3c9d3c-6779-568a-8e8f-7222474beaf5 | note | Criteria Notes - Implementation of positive traffic control when loose chip quantities pose a risk to public safety
072ac084-3f9f-4eb9-90ae-df68aae0345c | section | 5.0 Post-construction
e3ba8413-039d-4cb4-abc3-c06c9d443b6c | checkpoint | 5.1 - Post seal inspection (Final TTM Removal)
436cdd59-d094-5ce7-98ce-1c38950a573b | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
5999de2f-593a-5a03-8727-3d2b46d96e35 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
b95a0b85-9972-55c8-9150-4093c5f393d5 | note | Higgins (Comment) - NZTA P17 section 7
0ca80fad-9181-506a-96fd-5aa747db0298 | note | Criteria Notes - On completion of roadmarking Surplus chip to be removed
4354dc3e-fafc-5d0e-87b2-ab63a788ea86 | note | Principals Rep - W
c1fc3e58-31f4-55f2-9d54-af54453fd69f | note | Records & Remarks - Chip Sealing Quality and Site Checklist
b6f0ba1f-5b1d-4206-86b2-ee160be77518 | checkpoint | 5.2 - QA Handover
f47d9e36-e8f9-5a57-b1d2-49528c520256 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04 or P18 and contract drawings
5ee19e32-da77-5533-98d5-d8cbd7218b7e | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17 and contract drawings
6aa5a02a-bb49-5529-82d0-7c07e03cd840 | note | Higgins (Comment) - Quality Plan
ecfcfe6f-80c7-5c0c-bfa6-70f10be98725 | note | Frequency - For each site on the project
505c05e0-13fb-55dc-bc77-e85bd4eb7ade | note | Criteria Notes - Materials, construction compliance and extents
0719065b-b3cd-590f-9166-5adefea19d71 | note | Principals Rep - W
8617c01c-7c9e-541a-9c13-430e7defdfb1 | note | Records & Remarks - Evidence provided demonstrating full compliance with specified design
4aaa23bc-5196-4dc8-b16a-f7f7042b5a3a | checkpoint | 5.3 - RAMM update
efea4322-1b07-5072-abee-1ee109cf4e38 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - RAMM updates completed
20da98da-49c3-50e3-b40e-7bc5509be5d0 | note | Applicable Standard & Acceptance Criteria (Higgins) - RAMM updates completed
d684471e-dc16-5bfc-a145-dad1a822eb62 | note | Criteria Notes - Review of RAMM update and confirmation
9fd38f79-29b1-5ff4-8184-5f46a24e7752 | note | Principals Rep - W
a1493e08-becb-5291-8fdf-e6d7fedfda71 | note | Records & Remarks - Site records of RAMM update to be reviewed and confirmed
553acd8a-f7fc-42de-a9b8-1af67b680450 | checkpoint | Quality Record Close Out:
81321d32-9817-5ba9-a531-36e149d9d96c | textbox | Quality Manager Name:
df098857-d598-56cb-9afc-8bdadf3490c7 | date | Date:
d38a9420-fa12-4b7a-8325-9ccda2378e96 | signoff | Add Signature
7141f147-bdae-47a0-a6d3-96a7acdc3702 | checklist | ITP - Pavement Rehab - SH 05 - Boundary Road South | itp | ITP - Pavement Rehab - SH 05 - Boundary Road South
1ca59300-19c4-4fc2-b0af-836585e3df2c | section | 1. Procurement - Design
bd7fcf88-4b1c-4fb3-b4d1-4940bd82e15d | checkpoint | Geometric Design
644e3ac6-3586-587c-8a9d-99ca424d1460 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
5689a434-e18b-532b-b864-6ffe63fa8700 | note | Acceptance Criteria - Principal Approval
ea74fb7f-c4c5-57af-bc0d-7e5019c30332 | note | Inspection or Test: Method - Contractor and Principal peer review
b13d6d09-975c-5b99-85bf-08f0e53c5aa7 | note | Inspection or Test: Frequency - per design revision
d395d79f-8013-51a3-a35c-417460232816 | note | Inspection / Test Authority: Conduct - C or S
3075736e-2075-5cd3-a91c-5d0647b58d77 | note | Inspection / Test Authority: Produce Record - C
8f0ebc64-cd62-57fb-bf08-2525192a70d6 | note | Inspection / Test Authority: Approval - E
a4db01f1-48db-5327-a92e-2076e7413c99 | note | Hold Point - Y
c68ed9ab-76f6-4520-885c-85a315a27fad | signoff | HOLD POINT
04dea26e-18cb-4615-8b7e-be2f9b3293fa | checkpoint | Pavement Treatment Design
be6cdff8-2b4b-525b-8a46-3bd366b8716f | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
21d514a8-689d-5e39-99c4-18c0a1698f84 | note | Acceptance Criteria - Principal Approval
2674da28-650f-521e-9b2e-1d8fc99a5810 | note | Inspection or Test: Method - Contractor and Principal peer review
4faf0964-43bd-51f8-9982-5990dfd3ed87 | note | Inspection or Test: Frequency - per design
e1f94d6c-8b78-5380-861e-efb2eca9fc53 | note | Verifying Document - Pavement Rehabilitation Design Report
f4ac2c10-9947-50c0-bcdc-b9e222924bf5 | note | Inspection / Test Authority: Conduct - C or S
def6f7da-1005-5ccc-b9c8-21c454868f13 | note | Inspection / Test Authority: Produce Record - C
d7c57b7f-310a-51de-93b5-b5570c268503 | note | Inspection / Test Authority: Approval - E
a784b15e-5f7b-5392-af11-c218e7915ea9 | note | Hold Point - Y
3fe384fb-0f47-4eac-bc29-005bf9b30ea1 | signoff | HOLD POINT
2b8ff648-cbcb-4820-ac0c-99b0c0594e93 | section | 1. Procurement - Materials: GAP 65 Pre-treatment Material
88a81b6c-507a-4b0e-bb5d-77d99efa1145 | checkpoint | Aggregate Sampling
e46eb6bf-2419-5517-b28c-bbbde041a086 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
c49942d2-6e94-5b3b-bec8-db7454d1bdfe | note | Verifying Document - Sampling Worksheet
9d02eca7-8f49-5d04-8124-102625c7953a | note | Inspection / Test Authority: Conduct - C or S
914c89b6-5f4c-5f6d-a50f-1aca10821c17 | note | Inspection / Test Authority: Approval - S
4ca99cff-dd5c-5cf0-82ed-e9b6e7e4bf80 | note | Hold Point - Y
36cd797d-e9cd-4085-b122-e188d25721ac | signoff | HOLD POINT
28e5e609-a40d-4598-bcb9-3c238e957246 | checkpoint | Source Property Test
eddcb733-8330-58b5-be48-c32181a9c50b | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
0ea24809-27be-54e4-80c0-218f20b37471 | note | Acceptance Criteria - Soaked CBR ≥ 40
aed9dff9-126b-5447-bbd2-f93b8759b94e | note | Inspection or Test: Method - Soaked CBR test (NZS:4407:2015:3.15)
da0a1205-746c-533e-94e0-c2a685e1214a | note | Inspection or Test: Responsible Person - Supervisor
7a0eec26-0ac5-5924-9227-3676a3229838 | note | Verifying Document - Test Report
ff5b4f41-4323-56ce-8c3b-d8e09dd44064 | note | Inspection / Test Authority: Conduct - Sp or C or S
c2afbad5-657c-552e-ad64-c200bbc57991 | note | Inspection / Test Authority: Produce Record - Sp or S
900d6b93-fd81-50ac-bfe2-4d1ebb47bf28 | note | Inspection / Test Authority: Approval - E
35388427-391a-59aa-9bbf-d3559243c51a | note | Hold Point - Y
819ffd33-5010-43ab-9f78-0af2e4c38577 | signoff | HOLD POINT
44313984-a6b6-4607-9195-4d48e13dfe07 | checkpoint | Production Property Test
1e863c8a-725f-52f0-b2f0-2310305ccf72 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
d94ba8fb-4b77-55ac-bd4f-9c922608497c | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
bce953aa-6b5e-5e9a-97c2-762c1ef2b1b2 | note | Inspection or Test: Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
d3d6df69-9dd7-5092-ba61-ea43b2f9fb6f | note | Inspection or Test: Responsible Person - Supervisor
d5cad12d-c11f-5b63-be7e-279fec3d2db1 | note | Verifying Document - Test Report
445f68f6-34d9-5782-983f-5d1aa621660d | note | Inspection / Test Authority: Conduct - Sp or C or S
b493c031-f4d0-5715-8e89-b4d4017c6cc5 | note | Inspection / Test Authority: Produce Record - Sp or S
23e593a1-d33d-552c-985a-ffac8f57098a | note | Inspection / Test Authority: Approval - E
1cce4bf4-529d-5862-af4f-974f4c17110b | note | Hold Point - Y
7e30db38-b44b-4023-b864-ac684b7b40a2 | signoff | HOLD POINT
09917c79-7948-4245-b506-bbc19fc960a7 | section | 1. Procurement - Materials: M/4 AP40 Basecourse Material
64061b33-e35b-49f2-a856-c342d24f2077 | checkpoint | Aggregate Sampling
f8d15460-ee22-5b9b-8ebf-21073a0858b5 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
522cf364-40fe-5806-a6f5-f086691bec70 | note | Verifying Document - Sampling Worksheet
01f991e2-af96-4c34-ab03-d311471e7329 | checkpoint | Source Property Test (1)
8c08e66b-8ea6-5cd2-8aae-0ef2a4cf31ce | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
3a1e2c93-074b-54c3-a1d4-ba96675601d3 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
483729de-b976-53d1-a519-1c7ea9ef542e | note | Inspection or Test: Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
663c089f-5570-5637-b38f-59b0f0fd27c0 | note | Inspection or Test: Frequency - One test for every 10,000m³ of source material
21641231-e072-506b-8d3e-06fc0cdcc0d0 | note | Inspection or Test: Responsible Person - Quality Controller
b19bf9d9-82a6-568d-a43c-b914774bdc5a | note | Verifying Document - Test Report
efa03311-bb38-5260-bc76-ada5c839c2d0 | note | Inspection / Test Authority: Conduct - Sp or C or S
999a8755-5f28-56d6-b58b-9791fa34bbfb | note | Inspection / Test Authority: Produce Record - Sp or S
2c6e7063-0166-5e6d-8b88-63e1dd62d48f | note | Inspection / Test Authority: Approval - E
005afb9a-e392-561b-95a4-6313b639c0ca | note | Hold Point - Y
7d81d958-48d9-4a0c-8235-76dafb4a86bb | signoff | HOLD POINT
572c7212-833b-4d7c-ae65-8cbde1551c59 | checkpoint | Source Property Test (2)
4fcb3abd-14c9-53bd-a63e-9f94d3be3f66 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
6fac0ec7-ed1c-56d4-a545-5d07bbda8702 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
1f70a493-c219-5be2-9bd9-b2f6bf8db1b2 | note | Inspection or Test: Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
18d4955d-5e7a-5ef6-8f45-2d087bb720a1 | note | Inspection or Test: Frequency - One test for every 10,000m³ of source material
3215aa32-47d1-595f-bf6b-9d0e83e893cc | note | Inspection or Test: Responsible Person - Quality Controller
14c61c05-262a-5fc4-9c97-077bf0aff004 | note | Verifying Document - Test Report
e19367fe-f376-5363-a28f-58db6a4b41bf | note | Inspection / Test Authority: Conduct - Sp or C or S
93e99849-bd95-5909-9481-043d360fb0a0 | note | Inspection / Test Authority: Produce Record - Sp or S
5723478e-f976-5066-a6c9-2fd66b6e72c2 | note | Inspection / Test Authority: Approval - E
3fec80c9-dfb8-5bc7-af31-7f68ea25c02a | note | Hold Point - Y
851816c9-b3db-4286-b313-6f79c43d57ac | signoff | HOLD POINT
5320ea7c-0739-41a8-93d0-3aa03a16dc52 | checkpoint | Source Property Test (3)
f12d146c-2865-55bb-b885-2a2f58a1cea4 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
94c3f813-7a19-5695-b4fd-84f62639aace | note | Acceptance Criteria - Soaked CBR ≥ 80%
b442fa7c-229f-5a9c-8a7d-fc3a7750c5e8 | note | Inspection or Test: Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
57fe9aa5-ecc7-5d7a-a17f-8b0bee1e2571 | note | Inspection or Test: Frequency - One test for every 10,000m³ of source material
6d246341-edb5-5fb5-9dba-8c3b9d73869c | note | Inspection or Test: Responsible Person - Quality Controller
4197f54e-ea4b-53ff-996f-4f3b7f3d52ee | note | Verifying Document - Test Report
71524b41-ccfb-5a18-ab6d-1d2159c3c579 | note | Inspection / Test Authority: Conduct - Sp or C or S
13e5b23e-6871-53dc-900e-95ef513aa4be | note | Inspection / Test Authority: Produce Record - Sp or S
8cdbf66e-300a-5dbd-a5ca-686837175bec | note | Inspection / Test Authority: Approval - E
8ad2f6c1-4a47-5a7b-8c5b-cc26e02db608 | note | Hold Point - Y
5869aaa5-f7ff-4419-b7c0-d064702f10e5 | signoff | HOLD POINT
3c75b259-7847-4556-9694-84c97033c7bc | checkpoint | Production Property Test (1)
88b883cc-5f4c-590e-83c2-2cbe635e63fe | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
95c1f342-e73f-574a-a3e0-4468793bcda5 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
7494071d-e7c8-5ee8-8e49-796ad0154051 | note | Inspection or Test: Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
70ca0057-6cf7-5392-9024-4d2a4fbff3ef | note | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
549c10df-c6be-5234-8bcf-656275720524 | note | Inspection or Test: Responsible Person - Quality Controller
4392f738-d467-5d6b-93c9-6af3af140303 | note | Verifying Document - Test Report
fa88403a-4244-5477-8d96-372c59930e52 | note | Inspection / Test Authority: Conduct - Sp or C or S
597082e5-36c3-5730-a5b4-914909fd5a82 | note | Inspection / Test Authority: Produce Record - Sp or S
41c20a97-9272-5aec-9dc6-a84599e9cb19 | note | Inspection / Test Authority: Approval - E
e36a33f0-68e2-5c18-a0a7-b1c22a37158f | note | Hold Point - Y
a9d5e131-767e-4a86-8baf-50e5e82b1384 | signoff | HOLD POINT
b9ef8cba-14c4-443f-9740-6f0f886ceffc | checkpoint | Production Property Test (2)
f56c6664-594a-5130-9928-5caa139a2759 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
12beec12-67ff-5b47-9cde-6cccc277ca79 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
71f6d433-cc95-501c-8500-4dc7b251fd12 | note | Inspection or Test: Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
c376d471-38ea-5785-8e7b-2e4278a48090 | note | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
55f460af-8641-5d6c-8e13-ada2dc4c9bbd | note | Inspection or Test: Responsible Person - Quality Controller
48e25f10-7daf-5a23-95cf-57e6d634386e | note | Verifying Document - Test Report
92a240b6-d539-5fd8-9af5-cc1544663d2a | note | Inspection / Test Authority: Conduct - Sp or C or S
1d2bb745-98b5-57a1-b8c2-b436b3f7b50c | note | Inspection / Test Authority: Produce Record - Sp or S
4fc5a503-e11f-529e-91aa-fae116d697b8 | note | Inspection / Test Authority: Approval - E
188e771f-37a8-5788-8c5a-6b1ba705f4db | note | Hold Point - Y
0aa65d22-05ee-43fb-9848-5768076b6192 | signoff | HOLD POINT
33e491dd-d442-4362-92c0-d151cc82328d | checkpoint | Production Property Test (3)
47350bc5-823c-586e-8614-ea9fc0f8c958 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
34f650cf-0c33-501b-b46f-c9151d765568 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
d75a3d0c-2b9b-5b82-8da4-93dbcbe46b7d | note | Inspection or Test: Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
d1c5232f-56f7-5449-8716-9c7bf46b98fa | note | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
15987af6-8c07-5803-8c9a-c08d9cb5a444 | note | Inspection or Test: Responsible Person - Quality Controller
d63d3d8b-bdf4-58b7-a0e7-bb5fc694e672 | note | Verifying Document - Test Report
87071bdb-d92a-5534-94cc-a1d1768362c4 | note | Inspection / Test Authority: Conduct - Sp or C or S
14943f2e-cfcc-59b2-8c61-9017fe78f337 | note | Inspection / Test Authority: Produce Record - Sp or S
20addf6f-e270-5780-be52-311bec24c925 | note | Inspection / Test Authority: Approval - E
a547be7b-8132-5422-a24f-37f22d509411 | note | Hold Point - Y
9e31adfa-e0bc-49e7-8898-b811763a57de | signoff | HOLD POINT
e2407041-8657-4f92-a295-c28b6e17402d | section | 1. Procurement - Materials: Cement
9b5668cb-25b5-4fd9-9e95-d102c89d15d2 | checkpoint | Stabilising Agent Selection
0aa6d8f4-54c5-54d3-8fde-b609c0b3ab99 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
67ba4dc8-2bbb-5339-b431-5e4d41ad543b | note | Acceptance Criteria - GP
0920d8e6-c50d-5f33-9aba-5a3b1b3c41a4 | note | Inspection or Test: Method - Visual inspection of supplier docket
b298e778-f98f-5215-903b-38f2d57faa4c | note | Inspection or Test: Frequency - per truck load
d41baeba-a5f6-53ef-bf87-7ee256e55888 | note | Inspection or Test: Responsible Person - Quality Controller
0ff1dcb5-cbda-5bf2-bae0-fdc515422b94 | note | Verifying Document - Supplier Docket, Supplier Cert
c7abac1b-d4fd-5040-b375-8b4b50267e59 | note | Inspection / Test Authority: Conduct - Sp or S
6475cbb6-173f-50f2-8fbd-96a7d12f800b | note | Inspection / Test Authority: Produce Record - Sp or S
5a3ad44b-8c3e-58cd-a434-f5fab6b20dcc | note | Inspection / Test Authority: Approval - C
da76d8c5-0087-50d6-85c6-22c4437275d1 | note | Hold Point - Y
1cee98e2-9786-4e0b-982b-0735bfd773dd | signoff | HOLD POINT
059fdd03-6161-477b-9727-660f5ff10ea9 | section | 1. Procurement - Materials: Water
16390631-c340-41c9-9eff-8bb372d136b8 | checkpoint | Water draw for stabilising
cbde19f1-4834-54bd-bdda-19d0cf1e9225 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
6081c591-5e94-5b89-97b3-3dea930bf85e | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
f3a8cff0-0370-54b8-bdcf-cc27b06e0e4a | note | Inspection or Test: Method - Visual inspection
ce5e70a1-fe9f-50ec-bec2-54de5a9c1766 | note | Inspection or Test: Frequency - per truck load
43838bbe-213d-5a72-9ac6-63cfc598f169 | note | Inspection or Test: Responsible Person - Quality Controller
3c4c3c8d-a6a6-571d-af4f-0d451129c78e | note | Verifying Document - Hydrant use form
fcdcc0ff-27c3-5636-9ab2-eb2a7b8b3c10 | note | Inspection / Test Authority: Conduct - Sp or S
802a80e8-703b-5cee-84d3-a640a17c418a | note | Inspection / Test Authority: Produce Record - Sp or S
61d2cebd-0220-5f06-ad3e-34f9a781eca2 | note | Inspection / Test Authority: Approval - C
3b603bfe-3318-50b5-a105-25c22ffe93ae | note | Hold Point - Y
0688bd32-6209-4f8d-ad80-8e9262a554d6 | signoff | HOLD POINT
4ed52922-49a6-4086-8630-8695e260a49c | section | 1. Procurement - Materials: Geotextile
642701d2-8ecc-4c43-b363-d2d380cabfc2 | checkpoint | Geotextile (Strength Class C) A29 or greater
bddcaad8-6fd8-5ef2-94e4-87bb0f24155b | note | Controlling Documents - TNZ F7 Specification
95a5e8b6-c362-59c2-8d41-6ee6c9391d77 | note | Acceptance Criteria - Details on Docket
26fcf9e3-8401-5b93-8ef0-e22b4082b7cb | note | Inspection or Test: Method - Visual inspection
7f810466-642b-5249-99a1-c6ff8e2f2434 | note | Inspection or Test: Frequency - Per Delivery
8ef2c27b-96d6-5e0f-b0a0-879194d65972 | note | Inspection or Test: Responsible Person - Quality Controller
93b20ba1-a607-5243-8f14-cc4306b1ea55 | note | Verifying Document - MDS
a5834265-017b-51dd-a470-0d86647d37c9 | note | Inspection / Test Authority: Conduct - Sp or S
1e4beec2-18b9-5668-8c6d-1ce9285ed78a | note | Inspection / Test Authority: Produce Record - Sp or S
a2f750c9-846b-56a0-91ea-5dec96dc99f3 | note | Inspection / Test Authority: Approval - C
73d4524f-606e-5f06-8a05-676cebeeea34 | note | Hold Point - Y
07addb33-014b-4499-a123-11ffc722f700 | signoff | HOLD POINT
79e69efc-89be-4525-a7df-8d4c344cc0de | section | 2. Pre-Implementation
2d76ac9b-6370-453a-85ac-ad3b07aa4530 | checkpoint | Production Testing of stabilised material - OMC/MDD
5a7ff710-153d-5785-8e0b-5d32fd5967a7 | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
78c5d242-10a6-57d7-9e8a-e35483f0ebbe | note | Acceptance Criteria - To obtain OMC & MDD
933111ca-6c52-53a2-b83a-980e9e4db7b5 | note | Inspection or Test: Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
2a9d2068-bf6b-5ff9-91b3-6315038025d5 | note | Inspection or Test: Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
b44bbad0-2d33-56f8-995b-09a48758bf32 | note | Inspection or Test: Responsible Person - Quality Controller
7ed29be6-76d6-5f87-8cc6-c0434c05130d | note | Verifying Document - Test report
cae1af9e-8ca4-5b12-bfcc-3098a1398991 | note | Inspection / Test Authority: Conduct - C
e4e9fcde-7e57-58a3-a50a-35a3051ea913 | note | Inspection / Test Authority: Witness - C
52c90e5f-a0ea-5a14-9638-b0db2ab8f709 | note | Inspection / Test Authority: Produce Record - C
5b9bf473-dc55-5451-8bff-97c73eb030a4 | note | Witness Point - Y
fe70af60-9cdc-44a2-af0f-54c5dccb8a4a | checkpoint | Production Testing of stabilised material - Solid Density
a7ec8cd2-0891-557c-8995-317bbc4cf6c5 | note | Controlling Documents - TNZ B/5 section 7.7
919473b8-11c1-54c7-92b9-89dc9218ec06 | note | Acceptance Criteria - For info. and use in MDD calculation
d309796d-03a4-5926-b163-443282b36da5 | note | Inspection or Test: Method - NZS 4407; test 3.7.1
4f3ac400-eff1-5ab3-a9f3-3f3c19175390 | note | Inspection or Test: Frequency - Once on commencement and if any materials change
584a8b72-cbf5-5312-969e-474aaa8fd0b7 | note | Inspection or Test: Responsible Person - Quality Controller
59e7a533-fb1c-5d8f-b6fa-308e5630c420 | note | Verifying Document - Test report
0717a634-6e73-5e99-8230-897e12830a8b | note | Inspection / Test Authority: Conduct - C
76a791e4-52dc-5eff-bc50-968828f64e40 | note | Inspection / Test Authority: Witness - C
35bfe780-fd2b-590d-8a22-ae99e8d2d47d | note | Inspection / Test Authority: Produce Record - C
30cfd67d-27af-5c0d-b950-62a82ffc5897 | note | Witness Point - Y
73f9b8b7-8edf-46bb-8a3a-7bf7bfef6cea | checkpoint | Project survey setting out
15963842-2722-52cc-8619-313faec1c2e6 | note | Controlling Documents - Reference from Project Drawings
787de435-1a7f-5adc-bbe5-c68886fd809c | note | Inspection or Test: Method - Survey/Mobile Roads, Marks with Dazzle
4ae2fed7-54b1-5f44-b8c2-9db675705c59 | note | Inspection or Test: Frequency - Chainages for every different pavement sections
b45ed9f3-a2c8-5a6e-84a7-ac763b9d1932 | note | Inspection or Test: Responsible Person - Subcontractor/ Engineer
5108bdae-60ea-547b-990c-5875940a70ea | note | Verifying Document - Construction drawings
a411a29d-9421-5e52-85f0-5c395e392f37 | note | Inspection / Test Authority: Conduct - C
c7a99bd7-9778-5aed-a409-1a46ac1f44b5 | note | Inspection / Test Authority: Produce Record - C
2bd95e1b-4591-5ff3-baac-67d0244db7b5 | note | Witness Point - Y
d8916ed7-c7f9-4696-9de5-b1857971d3be | section | 3. Construction - Pre-treatment Digouts
e9eb0ebe-0e55-4140-a360-a9845deed337 | checkpoint | Pre-treatment Repair Method Selection
bc720e0b-5d5b-5781-8e34-f75ad9c58059 | note | Controlling Documents - Site specifics to be confirmed
e6ee788a-89e7-5ab1-ab80-c745ee61fd32 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
d0bcef0d-8c36-5bcc-87e1-e549f6be4825 | note | Inspection or Test: Method - Scala Penetrometer on Excavation Floor
5b897e3d-d2bb-567f-a988-4c8e2016b8b0 | note | Inspection or Test: Frequency - As required
c93a57ad-d9b6-5257-989a-48fcb52a03ec | note | Inspection or Test: Responsible Person - Quality Controller
0c28b6c1-26f4-57b0-a286-dd653d32e2b7 | note | Verifying Document - Agreed treatment plan
b2f01738-be58-50f5-9662-7d08f2ecfa00 | note | Inspection / Test Authority: Conduct - S
cbb36196-1194-5959-aff0-7003568f6da2 | note | Inspection / Test Authority: Witness - C
3ffeee03-efeb-517a-b435-351beec9caef | note | Inspection / Test Authority: Produce Record - S
b4d851ca-d8f0-5478-94e4-f1cba356f1b2 | note | Inspection / Test Authority: Approval - E
75d8fc2a-ed6d-5aaf-bc6a-f92bae36d172 | note | Witness Point - Y
335d3639-8714-4322-a80f-4d2df7eabc5d | checkpoint | Digout of Patches to repair
6ed0e819-33a8-5084-9416-1c7e93af177e | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
89e68fef-8be5-5d22-bc4f-f9dbdc14546c | note | Acceptance Criteria - 250mm deep unless specified
a3362b65-b8c1-5aa4-9312-0c3aa7913c2c | note | Inspection or Test: Method - Visual inspection
47b8b782-d72b-5e36-914d-826901108561 | note | Inspection or Test: Frequency - As required
a0142372-87de-5923-b50f-62c9a7c943c8 | note | Inspection or Test: Responsible Person - Quality Controller
f90bc3f1-cf97-5f69-9752-a348c75634ea | note | Verifying Document - Dig out site records/ Asbuilt
0aefc4ab-0595-5f30-b09c-5c2dee102dd8 | note | Inspection / Test Authority: Conduct - S
02cb198e-caca-5d17-94a5-b3e85029437c | note | Inspection / Test Authority: Witness - C
5cb76fff-b57a-57eb-8f31-5597ae03314e | note | Inspection / Test Authority: Produce Record - S
85e161c2-57a0-5788-b768-be6c76729085 | note | Inspection / Test Authority: Approval - C
8cc45a22-efe8-5ef9-b08c-c329592da976 | note | Witness Point - Y
69188968-ca2c-461c-9973-a2a1098c5305 | checkpoint | Subgrade material hardness, Check base of excavation
b76c499d-0af4-5a87-bc36-613b55412255 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
3c5f3ec7-7e91-5a51-8e6f-b967bb5720f8 | note | Acceptance Criteria - Scala > 3 blows per 100mm
9f20d644-2c18-5b0c-b179-4ce9a5cc12b8 | note | Inspection or Test: Method - Scala Penetrometer test on base of digout
12a24390-aa0e-5f83-b6bc-5d040b15b8d8 | note | Inspection or Test: Frequency - As required depending on size of digout
9b3aac9c-94a2-5a0e-8082-91b1e72a412d | note | Inspection or Test: Responsible Person - Quality Controller
39664e24-880d-587d-a175-a27be8053d36 | note | Verifying Document - Test report
acf4c6df-2ce8-581d-ad85-2eb633840596 | note | Inspection / Test Authority: Conduct - S/C
f5e763d4-d300-5fc3-8b90-dad7ce42831a | note | Inspection / Test Authority: Witness - C
18d07528-1f37-5c43-bb3f-ca5b9e0f9cc0 | note | Inspection / Test Authority: Produce Record - S/C
f4647f02-17d9-5e39-867e-504c7698a732 | note | Inspection / Test Authority: Approval - E
f7cf5b80-5409-503d-8474-3afa9ac938a6 | note | Witness Point - Y
c7e4be82-e94c-4c20-af68-b6a1bf73d44f | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
b68abe2e-4817-5aef-9429-fb8a0c40b135 | note | Controlling Documents - TNZ F7 Specification
fc466622-c51f-53a3-8d36-d9f43d7f0a2c | note | Acceptance Criteria - Meet TNZ F7 Spec.
171c553c-a7b2-5d17-9f3e-0c68c729dd2e | note | Inspection or Test: Method - Visual inspection
bd456fdd-cb87-582e-ac75-614ff92fd99f | note | Inspection or Test: Frequency - Per Delivery
a0057325-be54-5399-9074-b47e34bdec78 | note | Inspection or Test: Responsible Person - Quality Controller
c6cffbd4-e20b-5eb0-acdc-81cadc3dc63f | note | Verifying Document - Certificate of conformance
4c2be017-7a5f-5c78-866b-0653f50e4805 | note | Inspection / Test Authority: Conduct - Sp or S
7e2d8d4f-215d-598d-87e5-48773922746a | note | Inspection / Test Authority: Produce Record - C
cd25dca0-867f-50e7-9a01-2bcbd434668d | note | Inspection / Test Authority: Approval - C
a9026e3f-2938-58a8-83e6-e897ee60844b | note | Witness Point - Y
c6e97265-97ec-4d89-b45c-4dc1022f6841 | checkpoint | Place and compact GAP65 in digout area
fc81e680-67b0-5cdd-8e61-d3e2ea9f3af3 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
4f635bfd-a887-5994-98ca-d70b351163c5 | note | Acceptance Criteria - Clegg value > 45
724ca453-ec0c-55bf-8819-757ddb5b27f0 | note | Inspection or Test: Method - Clegg Test
756dde66-fb29-5075-a449-b7ac93e20b25 | note | Inspection or Test: Frequency - Min. 2 per digout
54786702-4513-542e-8249-5b1c33742e96 | note | Inspection or Test: Responsible Person - Quality Controller
5f756737-cd04-5edc-8c98-a72f5698265b | note | Verifying Document - Test report
4faaf34f-8c2c-5419-8e1d-61d121ef249a | note | Inspection / Test Authority: Conduct - S/C
284bcbee-bee1-5841-b1a4-5b548b220cf2 | note | Inspection / Test Authority: Witness - C
acceeee3-938a-5b70-b668-a390bb6af816 | note | Inspection / Test Authority: Produce Record - S/C
4a759cf0-5bb1-5768-8c20-023863721102 | note | Inspection / Test Authority: Approval - E
9b599195-0397-57aa-a047-ece94fa8c87d | note | Witness Point - Y
5d1a73bb-d6f8-4dff-8eeb-e1139530420e | section | 4. Construction - Granular make up and In-situ Modification
da3f02a2-9c60-4d25-92b5-74061f19321a | checkpoint | Place M/4 AP40 Basecourse Material
18d9d13d-292d-5555-ac39-7afe18b21a5d | note | Controlling Documents - TNZ B/5 (section 7)
de307442-bf34-58cf-ad51-9da3f08dc607 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
42af3aed-8fda-5ae3-8c95-6344ff76b889 | note | Inspection or Test: Method - Visual Inspection
3e4876e6-e864-5288-bb2b-b5b72ff93a2f | note | Inspection or Test: Frequency - On completion of placement
c2d0bc91-b1b6-59ff-8b53-16b4f7928c02 | note | Inspection or Test: Responsible Person - Quality Controller
3894f64a-d94b-5b60-b210-19210f9b2b8d | note | Verifying Document - Photographs and Daily Site Record
a1082260-227d-51eb-97ce-9dc42b1c2303 | note | Inspection / Test Authority: Conduct - S or C
3d5e92b5-b735-5b87-a97d-8d10753615aa | note | Inspection / Test Authority: Produce Record - S or C
73ad62e0-b67f-5ac1-b88e-7e29d997f7dd | note | Inspection / Test Authority: Approval - C
8cbb59bb-6723-5283-b259-a303dd2c0bec | note | Witness Point - Y
58aacd56-8bf8-4af4-a53d-7e41cb3ff84c | checkpoint | Spreading of Cement
77cf1189-4b4a-58d2-ad6a-801870821b99 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
ba99140f-2ec5-513c-8652-17b2e9f6b1cc | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
0b0527bb-b078-58e3-b400-5dc960d6668e | note | Inspection or Test: Method - Mat test (1m² canvas) and Average Usage Test
7d4c57f8-8d17-5ff6-bada-8435eaab96f1 | note | Inspection or Test: Frequency - per 400m² and upon emptying the spreader
b13029a9-e5c8-5f81-badf-f8a3619bdafc | note | Inspection or Test: Responsible Person - Quality Controller
08c8d381-d7dd-5763-a8b6-6dd82c09f565 | note | Verifying Document - Mat Test Form and truck dockets
88640ed6-ede3-5e6b-8c3f-bae1c7cd5910 | note | Inspection / Test Authority: Conduct - S or Sp
f23de8f9-2096-535f-8276-9a53f3ebbefb | note | Inspection / Test Authority: Witness - C
804974fa-fc2e-562e-8791-1f1480da9ad5 | note | Inspection / Test Authority: Produce Record - S
31916213-5679-569d-b7a3-2f3e109d48d0 | note | Inspection / Test Authority: Approval - E
20ec9f0d-c9df-507c-9d30-25c3de2eb466 | note | Witness Point - Y
2d58b073-ee8f-4b6b-bb6d-46c315a2ae3c | checkpoint | Addition of Water
b2d4c0ec-9918-5184-b665-2a74ccb501af | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
6dad7a3e-9b22-5936-a15c-f57e4b6411cb | note | Acceptance Criteria - 90-100% OWC
6dd732a1-ffc8-535b-a1bc-adc169117918 | note | Inspection or Test: Method - Nuclear Densometer Testing prior to Stabilisation
4d636e1e-daa3-56dc-8d3b-5b83618eb59b | note | Inspection or Test: Frequency - ≥1 per 1000m² lot
1fd31863-4c79-5e04-b912-b9da97573261 | note | Inspection or Test: Responsible Person - Quality Controller
23466adf-7b89-5c04-ab35-7560cbf6e135 | note | Verifying Document - NDM Record
ab9cec8d-6733-5da7-b158-58af66111f18 | note | Inspection / Test Authority: Conduct - S
7674fa0f-11ca-58e4-9b4f-9520721788e7 | note | Inspection / Test Authority: Produce Record - S
04a6aa83-ef0e-57e5-b089-cd587d8ad3de | note | Inspection / Test Authority: Approval - C
e748fc05-3194-50c4-a33d-700e4b12670b | note | Witness Point - Y
57c0442f-529a-4b23-8090-5f2ad6dd44bd | checkpoint | Cut Depth
10b59058-9b94-5260-a464-311036c990d6 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
21e29e63-ed94-54da-b8cb-9c7b808ba923 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
37b7090d-0f48-5d8f-827e-ce1906100efd | note | Inspection or Test: Method - Physical Measure and Visual Record
2b5b1271-f582-58f0-8aa4-84604225f1db | note | Inspection or Test: Frequency - ≥1 per 200m of cut length
ac3b45a4-7f68-5e54-92a3-4b93e66dbae9 | note | Inspection or Test: Responsible Person - Quality Controller
3ae0b16b-6a41-58d0-af29-f4e51229ee1b | note | Verifying Document - Photographs and Daily Site Record
2bd20a74-cda0-5d23-bcce-a70b37abff82 | note | Inspection / Test Authority: Conduct - S
4bfd326a-44d8-52dc-ad8a-c9ff6a27591e | note | Inspection / Test Authority: Produce Record - S
c1fb8c8c-a652-53f8-8c42-2e6adedf2c77 | note | Inspection / Test Authority: Approval - C
93d0287d-85dd-5f7b-af70-d5d7a5132467 | note | Witness Point - Y
6acfe076-37d5-4ba0-a5e4-7136509ec839 | checkpoint | Longitudinal Joints
cb638e2a-d091-5d70-b63a-f6f6c4fabd12 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
689abe89-81ff-5cb2-b447-06fde0154bae | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
5e3066e7-1d15-5805-a40f-dafb3092f6e9 | note | Inspection or Test: Method - Visual Record
dacc1727-ec3b-505b-ba92-3b656bd18e96 | note | Inspection or Test: Frequency - per sucessive cut
4f5d5c5f-99ea-516d-9ae3-5ff26a44c5f6 | note | Inspection or Test: Responsible Person - Quality Controller
d52c9675-08bb-5dda-8f8f-7714db25cec5 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
140ae0a9-d9df-54bc-804f-5ec85c359af0 | note | Inspection / Test Authority: Conduct - S
d3c388c7-ad7b-58b7-b191-be4a6c4873f2 | note | Inspection / Test Authority: Produce Record - S
14cc2442-94f3-5bc8-b69c-93ccf1e382e4 | note | Inspection / Test Authority: Approval - C
7cd5f047-e336-51a2-84f7-5529b25a66e9 | note | Witness Point - Y
33af1c63-9b8e-4165-805d-2637e6c7da25 | checkpoint | Continuity of Layer
ecb69365-0bf7-55f9-9953-2fc640a5d8b2 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
979a8767-6b8a-5485-bbc4-ca901640f1c5 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
a5c44a5c-102e-5cbe-9481-19ead2bd79ef | note | Inspection or Test: Method - Visual Record
097a5e20-6a95-52d4-9d2d-b5f99d8d57b4 | note | Inspection or Test: Frequency - per sucessive cut
5e44be84-d3ad-5329-b378-c4862a5cdbe2 | note | Inspection or Test: Responsible Person - Quality Controller
33cac8eb-3edd-57b9-9916-d04cbc41a89e | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
e3954323-d4fb-5fba-bc02-9311c82208ae | note | Inspection / Test Authority: Conduct - S
c0946171-296b-5067-9db2-812373d2cc74 | note | Inspection / Test Authority: Produce Record - S
c9b5e02a-4171-5e59-a377-5ca661cb7220 | note | Inspection / Test Authority: Approval - C
acb7b73e-e7b5-5f96-814f-c829745506f6 | note | Witness Point - Y
bf55b511-840a-43c9-b803-fd30477183bd | checkpoint | Stabilised Material Particle Size
a90c6629-06e0-5f4f-bda3-90230456efb5 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
4a013ab8-0390-51b8-9dab-95dbf6afea06 | note | Acceptance Criteria - No excessive breakdown of stabilised material
7be13453-31a2-5717-8200-4beb14f4c4ea | note | Inspection or Test: Method - Visual Record
e700bfc5-d5b0-594e-8e48-a9bc3621ef45 | note | Inspection or Test: Frequency - within 20m of each section and then regularly based on material variability
c1883c9f-92f8-56b7-85aa-79c1cadab749 | note | Inspection or Test: Responsible Person - Quality Controller
ee401d88-898d-50a1-b24a-0cd71434d928 | note | Verifying Document - Photographs
92883e7a-3192-5ca4-85a6-cb16ebe6cd0e | note | Inspection / Test Authority: Conduct - S or C
c38ecd5c-acf1-5e44-b9d2-9300d9920da4 | note | Inspection / Test Authority: Produce Record - S or C
9ea334b8-00ed-5545-b61b-3c46c0ab55bd | note | Inspection / Test Authority: Approval - C
d043f73f-67d7-5f0e-9bff-2e7cf44dcace | note | Witness Point - Y
07948c37-fc51-49d9-9696-b7cd4d46b0e5 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
d2002ada-63f1-5620-94d9-a8788fe90f63 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
3f6e70c7-ba0a-5d5a-9b70-976c8e1ce035 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
c1ca89bc-ab98-5669-94db-cb325d5b2f74 | note | Inspection or Test: Method - Plateau Density Testing
16147299-24cc-585a-ac94-34c9cac94cd3 | note | Inspection or Test: Frequency - 1 time, or additional tests when material changes visually
5932e08c-0f02-5dad-b715-7dd20de8522d | note | Inspection or Test: Responsible Person - Supervisor
cc29d40a-a710-5164-9e2e-0d885f1f887e | note | Verifying Document - Test record
3a3c9e11-d3f3-51b6-ad75-b4ca5426d3a4 | note | Inspection / Test Authority: Conduct - S or C
bbb5c031-91c5-50e6-a130-bd9310712298 | note | Inspection / Test Authority: Produce Record - S or C
9e42a3bc-3e6a-5b61-8221-d070b3d0ed64 | note | Inspection / Test Authority: Approval - C
16e7500a-d39b-54a3-b868-28435332ed3a | note | Witness Point - Y
1a9c48ed-175c-4db4-b2f8-9b2b01822a80 | checkpoint | Establish Compaction Target
7121a32d-2776-56d5-a71b-9be768f310d4 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
77538ae0-1f57-5834-a492-e1df265bc35f | note | Acceptance Criteria - To provide MDD for NDM testing
71cc9a63-7a00-5d5c-94d2-262d4fcfa01c | note | Inspection or Test: Method - Plateau Density Testing
5cd16ac6-da13-59a1-b96f-dd23fc59e0ce | note | Inspection or Test: Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
215f74b9-85d2-59c8-878d-657f5919f095 | note | Inspection or Test: Responsible Person - Quality Controller
a282520a-3302-5375-ae45-69d420c9b2fd | note | Verifying Document - Test Record
5afe7002-0233-598f-b5aa-f7a968e00b33 | note | Inspection / Test Authority: Conduct - S or C
666d3f51-74dc-5b3a-9787-212cb28d0955 | note | Inspection / Test Authority: Produce Record - S or C
8a831c28-e8bd-50d0-8822-6e3d2074869b | note | Inspection / Test Authority: Approval - E
5c6571ef-3170-530d-84bb-ba3d5b056c2d | note | Witness Point - Y
7981a93d-7094-41df-a953-62dbe001ed1d | checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (1)
4ee2010a-a735-575d-980f-d60e3a0c8090 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
3fd600cb-3e60-5a73-a5ef-b9f1a08d2376 | note | Acceptance Criteria - To provide MDD for NDM testing
a478e7d3-f873-585b-a84b-16ad8e253c48 | note | Inspection or Test: Method - Laboratory MDD at OMC NZS 4402 test 4.1.3.
b76a5d90-c7e5-55a8-bc40-b4c85a7e1da5 | note | Inspection or Test: Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
3c850e66-0c60-56dd-9530-2b28ea3967f4 | note | Inspection or Test: Responsible Person - Quality Controller
08722ad6-7f81-50c7-a8f2-fac0da28571d | note | Verifying Document - Test Record
8a6797f6-d816-5382-b20c-c5333853350f | note | Inspection / Test Authority: Conduct - S or C
478af0bf-69cf-5428-b36b-aae21b2b890a | note | Inspection / Test Authority: Produce Record - S or C
e1df8f1a-81ea-5614-93a7-8d8b4c391679 | note | Inspection / Test Authority: Approval - C
d6ae9bca-5e4f-5246-89da-313e4e37f1e8 | note | Witness Point - Y
72ec71fa-d409-4523-ad66-ee7a17962fa9 | checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (2)
52a4ed2d-9f0f-583e-a737-5dd15b239edd | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
999b95cc-bce0-58d7-986a-e969d7991701 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
02b7e7fc-264d-5f38-b350-8026343ed518 | note | Inspection or Test: Method - Plateau Density Testing Lab. MDD
6766d45e-a95b-511f-adc5-3050c4c1ed44 | note | Inspection or Test: Frequency - At commencement of construction and whenever materials change
69c44744-eaf4-5e16-8375-a4df9e9f65a3 | note | Inspection or Test: Responsible Person - Quality Controller Engineer
c96571bb-707f-5ef4-b09a-1b8e0d343055 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
edab5a01-096b-5fff-b3b0-657cbb37bc23 | note | Inspection / Test Authority: Conduct - S or C
ccca77a6-6ccb-53a2-993c-599eb7456793 | note | Inspection / Test Authority: Produce Record - S or C
1d9a1be5-7722-57fc-91fb-c7c907791cfc | note | Inspection / Test Authority: Approval - E
0f8d3083-45b6-540c-b07a-c6c8c09bd9f3 | note | Witness Point - Y
92b14b99-7aa0-462f-b283-7c0f0de2918d | checkpoint | Compaction Acceptance
d5eda3d9-87cc-5367-a278-511bf89ee34c | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008,
07ceaea9-04e7-5939-8f0f-b4461f52435a | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
7e968d91-aed8-5f86-8087-5417dcdbfab8 | note | Inspection or Test: Method - Nuclear Densometer Testing
379da687-ba57-50eb-a92c-f00a1e35cd81 | note | Inspection or Test: Frequency - ≥ 5 tests per 1000m² lot
396d8071-777a-5930-92c2-a1d73b2d521f | note | Inspection or Test: Responsible Person - Quality Controller
3341d6d9-e240-5e73-abfb-ec2fb18d0f0a | note | Verifying Document - NDM Record
3f17535e-de55-5228-8ac6-6ac804f40d3c | note | Inspection / Test Authority: Conduct - S or C
776682f3-690b-55e6-8062-25945fa86dc6 | note | Inspection / Test Authority: Produce Record - S or C
e714a92a-50e3-5fe1-b5f9-002fdd7c4eb9 | note | Inspection / Test Authority: Approval - E
b53293f7-6d97-5efd-bd8b-de897b054405 | note | Hold Point - Y
6f49f8c5-2dc2-42ca-8735-85028b64c7b3 | signoff | HOLD POINT
d05012e7-0325-49dc-a020-f04a7ed86efb | checkpoint | Control Testing (if required)
32c65757-7103-5dd2-bf73-32daad73e735 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
bc9e3026-fc9a-5c18-82ca-43e3d4e2a29a | note | Acceptance Criteria - Nil
c37efe73-c678-513e-bd32-caaffd81856b | note | Inspection or Test: Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
48e2cb48-066f-58c0-8fc2-38a911cc10e0 | note | Inspection or Test: Frequency - when agreed with the Engineer
8ddda0fb-550d-5b0a-8fbc-135eabc5e3f6 | note | Inspection or Test: Responsible Person - Quality Controller
1646518a-0bbf-568a-9aa1-ccef8e5da359 | note | Verifying Document - Test Report
6853c4cc-8fcb-5f7b-8f24-36c91a5571c5 | note | Inspection / Test Authority: Conduct - S or C
67fe362c-7495-5ed3-bb37-70b9ab9769ea | note | Inspection / Test Authority: Produce Record - S or C
7c73a1d6-83c9-5bb9-a061-8765a6acb6f3 | note | Inspection / Test Authority: Approval - E
15ff7386-1dc2-5046-b791-b16c759b9856 | note | Witness Point - Y
5dbcb3ac-7b9e-4282-be5d-3f8708f13615 | checkpoint | Surface Smoothness
82896ab8-e039-573f-b10e-c1d3b9413ce0 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
16bc41f7-1c4a-5f6e-82ff-a3401d75faeb | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
e988f056-5b5d-532c-bb42-8f7a215eb173 | note | Inspection or Test: Method - 3m Straight Edge
62f98971-c420-5abc-9113-fbe18c1ca026 | note | Inspection or Test: Frequency - during construction and prior to seal
5981ed23-a84f-5c05-a52f-6ea18f95e4ac | note | Inspection or Test: Responsible Person - Supervisor
b794e721-7d85-54df-99fc-502928765119 | note | Verifying Document - Photographs
f5a2fd35-6b29-5254-b5b5-10607231fb7b | note | Inspection / Test Authority: Conduct - S or C
130544c7-321e-57a1-905f-bdb5f5f3522b | note | Inspection / Test Authority: Witness - C and E
0051c1cc-db67-5f71-97a0-3eed1ae244f1 | note | Inspection / Test Authority: Produce Record - S or C
4f27457f-f179-5699-8e0d-e9bf0b805b33 | note | Inspection / Test Authority: Approval - E
ae3fc963-9bdd-50f1-8142-ec24c11ab806 | note | Witness Point - Y
a1089b5f-24e6-40d7-bccc-2f932222ed48 | checkpoint | Surface Shape
04aa4e94-27e6-5c71-b7e0-9503bf157a72 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
6cd2ad0d-039a-5e7c-8f09-9565dcba0947 | note | Acceptance Criteria - Between -5mm and +15mm
d8c31755-562e-5001-a54b-82d70e6e413b | note | Inspection or Test: Method - String lines or Survey Asbuilt
8f2662d6-d153-59a3-aad5-80d026c0e627 | note | Inspection or Test: Frequency - during construction and prior to seal
58551138-8769-5432-b3c5-3cda83ad831b | note | Inspection or Test: Responsible Person - Supervisor
6e648dc5-443c-511b-808f-234e646e0bf3 | note | Verifying Document - String Sheet/Survey Asbuilts
af8e6d6e-f754-517b-9b50-fb9a285efbe8 | note | Inspection / Test Authority: Conduct - S or C
ace3b349-d1a8-5d39-9b11-14fdf2b8a152 | note | Inspection / Test Authority: Witness - C and E
1799f3a2-6ded-5589-96b1-7b8df4a90ad2 | note | Inspection / Test Authority: Produce Record - S or C
cec4d15e-14cc-57ec-b882-21e34f45eab6 | note | Inspection / Test Authority: Approval - E
a53013ee-126c-5bcd-aaed-49b0ecbe3b4c | note | Witness Point - Y
41912605-7475-4ab2-9f4e-b85bf7d6ff66 | checkpoint | Cross Fall
c73290f5-0d4b-5078-8a19-4e365c5b5689 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
08b31051-4299-5c40-a013-8a403467d520 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
017fddb2-19b0-5aa6-91a3-c24d5afca260 | note | Inspection or Test: Method - 3m straight edge or Survey Asbuilt
3b37e7d2-c5bb-5b86-85dd-41b9b650537c | note | Inspection or Test: Frequency - during construction and prior to seal
bd0ece61-2047-584d-aa71-ef158599e43b | note | Inspection or Test: Responsible Person - Supervisor
86a7196e-1e82-59f4-bed8-47ce86bd8681 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
fe334129-2f8b-5eaf-9a0f-ec1b8987647c | note | Inspection / Test Authority: Conduct - S or C
eb9240e4-95b6-5f22-90bc-6c72b6447b1f | note | Inspection / Test Authority: Witness - C and E
35793324-15f7-5d6b-9541-4dc75743cd74 | note | Inspection / Test Authority: Produce Record - S or C
cadba572-fa87-5bcb-9352-ec82aa68cc7e | note | Inspection / Test Authority: Approval - E
785cdcc5-9638-5afb-a4b2-06d4d67084a1 | note | Witness Point - Y
78dc6aab-773a-408e-bb35-b042318bae4a | checkpoint | Surface Finish
86141e7c-ff1f-576a-bc1c-95e2d9ba215b | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
14cfd44d-8d14-551b-9ab3-1af1ce1890d1 | note | Acceptance Criteria - Tightly bound matrix post sweep
7fffa3bd-40fc-5972-9bfe-5a948c8273c5 | note | Inspection or Test: Method - Visual inpsection
0daff8f2-305e-53dd-be67-9a943f0c3041 | note | Inspection or Test: Frequency - prior to seal
faadedd5-015b-5912-879b-4ef699046637 | note | Inspection or Test: Responsible Person - Supervisor
bee99316-02b1-5724-b8eb-0eff892dff54 | note | Verifying Document - Pre-seal inspection sheet
4871ef9d-c788-5c0a-a06e-006b31e540bc | note | Inspection / Test Authority: Conduct - S or C
b3143059-34b8-574b-91df-12a797f0998f | note | Inspection / Test Authority: Witness - C and E
4e02ad59-2da9-5c75-b96e-0642c32aef07 | note | Inspection / Test Authority: Produce Record - S or C
4cf25520-a648-58d0-9e6c-84b02958569a | note | Inspection / Test Authority: Approval - E
22bdca25-fa47-5aaa-b9cb-19e0cb6db4d1 | note | Witness Point - Y
ef02b4bc-fdfd-4cf9-bd72-c61b42f85e27 | checkpoint | Degree of Saturation, DOS
3a91868d-691f-5412-a523-3856b300d678 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008,
8b8f9189-db6b-5427-ac03-a4f76d38893f | note | Acceptance Criteria - ≤80%, however 65% is ideal
98ac4788-5aa5-5f40-b344-e61ad640d6c7 | note | Inspection or Test: Method - Nuclear Densometer Testing
9e5cb5a5-07c3-5c15-9b21-45f5e778627d | note | Inspection or Test: Frequency - ≥5 tests per 1000m² lot
8e63e8a3-a6c5-58a9-acf2-206ca0865554 | note | Inspection or Test: Responsible Person - Quality Controller
c19d8323-3132-5298-951f-40406110693f | note | Verifying Document - NDM Record
8ea7f97e-f977-553c-9897-86feb94a63d0 | note | Inspection / Test Authority: Conduct - S or C
cf6d3c17-af79-5e6b-9a32-4b7eb3866a8c | note | Inspection / Test Authority: Witness - C and E
d5ba5d34-0655-5f27-804e-ba956cbf5df2 | note | Inspection / Test Authority: Produce Record - S or C
57da92fb-a361-54d3-80bc-b987dcb60db6 | note | Inspection / Test Authority: Approval - E
0a844d12-d677-50ee-81f3-6b54bde301d6 | note | Witness Point - Y
9786d472-a243-4666-b28b-1b377789bf52 | checkpoint | Roughness (NAASRA)
d796ea33-393f-5f3b-afde-c653cb984530 | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
ed668dee-71b5-50d0-9f52-482e2e2bca85 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
4ae74ee6-26d2-5ca2-80e1-5d1cc14f2aa2 | note | Inspection or Test: Method - NZTA Maintainence specification section 6.1.2
41c6c7db-0698-5de5-87a0-3ea6d2858cb9 | note | Inspection or Test: Frequency - Average of three replica runs for each lane reported at 20m intervals.
27956184-8a8b-514b-abc5-47c1238bb659 | note | Inspection or Test: Responsible Person - Quality Controller
0b9b3298-f615-51de-bb23-41aafe1c6405 | note | Verifying Document - Test Records
15eb6a92-dd66-5fa4-9dae-75f35b3006e6 | note | Inspection / Test Authority: Conduct - S or C
bf1f05a6-fae7-5ac6-8bf5-0b672bbd0e02 | note | Inspection / Test Authority: Witness - C and E
a61c8b1d-2483-535a-ae45-a69a050896e0 | note | Inspection / Test Authority: Produce Record - S or C
71fffa68-f4a5-5f2d-9fd0-c24a4f1a66fa | note | Inspection / Test Authority: Approval - E
ace6fa68-17a0-5c7e-82de-fcbde72e0ccd | note | Hold Point - Y
3e81dfae-f06f-463e-9092-43ba3d721041 | signoff | HOLD POINT
01ce564f-7fc2-4e46-acb8-a1f9a0e20d45 | section | 5. Chip Sealing - 5.1. Procurement - Chipseal Resurfacing
97d66873-8dc3-4054-9b4e-e10b7368de76 | checkpoint | Binder - Penetration Grade
be0ffe82-94ca-5d8d-b209-f2f808644768 | note | Controlling Documents - TNZ M/1
fcacae7b-f1c9-5055-a4c3-2a2055230ec1 | note | Acceptance Criteria - Table 1
04795652-c384-56c7-916f-254807d4ec76 | note | Inspection or Test: Method - Property Test
7bba96df-889d-51fa-b7e6-124412aee5a4 | note | Inspection or Test: Frequency - Annual
6996d93a-9ae1-5dbd-bbc5-2830477d5762 | note | Inspection or Test: Responsible Person - Bitumen Supplier/ Surfacing Project Manager
73a9b140-daba-5bad-a26b-7f0c06db0f96 | note | Verifying Document - IANZ Report's
309c0823-79c0-5c5c-9e74-552ed1de902d | note | Inspection / Test Authority: Conduct - C
fbadaf17-0315-52ae-84a4-fad94569b257 | note | Inspection / Test Authority: Produce Record - C
4961b918-4c60-5049-883b-af19cc11ca28 | note | Inspection / Test Authority: Approval - N
fa453e15-84d6-50d4-a5d5-ae8bb5eaf3b6 | note | Witness Point - Y
94d1a831-bfad-45a9-a8b7-c5788c7d88e9 | checkpoint | Binder - Polymer Modified Emulsion
aae6ba43-3077-5fdb-9937-00e9c6bdb1c6 | note | Controlling Documents - Higgins Internal Specification
b2ac592d-9261-5736-9961-0af6241399fc | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
e1a422f3-cea9-56ab-90a8-1ad1c6bef7a8 | note | Inspection or Test: Method - Property Test
c5b0623e-8f1e-585f-905b-360c30864b14 | note | Inspection or Test: Frequency - 1/100,000 litres supplied
662cdb05-f89a-5846-8af1-188d06695fb8 | note | Inspection or Test: Responsible Person - Bitumen Supplier/ Surfacing Project Manager
78af65fe-13f6-54ab-b5fa-5d1f0238357c | note | Verifying Document - IANZ Report's
041b000b-ad92-592d-8607-a2f030546b4d | note | Inspection / Test Authority: Conduct - C
c7f880ed-8a38-51c3-b3d6-69916f435703 | note | Inspection / Test Authority: Produce Record - C
cd3836de-bef4-584c-ae47-5930266f94aa | note | Inspection / Test Authority: Approval - N
eb76e85a-8321-540c-93ff-ceed92ef0b98 | note | Witness Point - Y
fb9e3171-a444-4a06-91d3-0c3f7e2e4179 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
c7619db3-b484-5046-9db7-e141271dfb75 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
7cc49a18-6d08-546d-8135-6b9eb4912abb | note | Acceptance Criteria - <10% fines under 230kN minimum
9d0781ea-8341-5393-95af-3b5faea6d78c | note | Inspection or Test: Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
5dc443b7-2e26-5dd9-9fe3-b21ef2d65e42 | note | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
2b1afbdd-557f-5797-9b86-74e7468d5c72 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
c2e0dc5a-7d48-5e7a-a55a-3e8cd59888a5 | note | Verifying Document - IANZ Report's
5c81e38c-82dd-51b1-b48c-677ba98813f6 | note | Inspection / Test Authority: Conduct - C
64ace29f-c731-5543-bb51-e0ceb41f680a | note | Inspection / Test Authority: Produce Record - C
e1f3221b-91ee-5f2f-8c52-4fe50cf45e07 | note | Inspection / Test Authority: Approval - N
18036ad4-d233-5b03-8bde-16ad264aaeb2 | note | Hold Point - Y
00ca298f-dfd6-51c9-9bac-fe3b5dc9b65e | note | Witness Point - Y
ac8931d2-8d9a-4246-9a30-b58f657687aa | signoff | HOLD POINT
e979db6c-0f2b-42ac-943c-0047f9c5a0d2 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
f30b011d-4ed6-5fc4-bdc3-64dc404e0c40 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
f562cf46-016d-551b-b60a-1f891f443da9 | note | Acceptance Criteria - AA or BA
66294c43-1c37-5955-9fee-97a5032034ee | note | Inspection or Test: Method - Weathering Quality Index NZS 4407 Test 3.10
91ec6d54-b0ce-5585-9e7d-06692a326997 | note | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
f9bb378b-fd39-5cd1-b8bb-fab15dc4c1d0 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
b825d853-79ff-5c28-b3ae-9aec3a278aa4 | note | Verifying Document - IANZ Report's
f1b25657-6866-5c36-9f84-acad0e796bae | note | Inspection / Test Authority: Conduct - C
b9a8ff62-572c-5db6-8d63-aae2a8b377f8 | note | Inspection / Test Authority: Produce Record - C
0027537b-5400-5125-9bec-85e12f675e36 | note | Inspection / Test Authority: Approval - N
939a6901-c8b9-530d-afa2-b4caf151fc89 | note | Hold Point - Y
c208c3ea-b58b-590e-b3f3-cd1045291fc5 | note | Witness Point - Y
30ccddb0-6f94-44d2-9226-87a624c98fc6 | signoff | HOLD POINT
7a8c8333-b78b-4f63-ba11-19a2ded2194f | checkpoint | Source Property - Skid Resistance
53f23cec-d46f-5574-8fa7-367879863c9d | note | Controlling Documents - NZTA T/10
a0438c9f-d70e-5e92-abe3-921059b62b8d | note | Acceptance Criteria - Meet Skid performance Requirement
a9e64036-55b8-528a-8eed-477316b70f1e | note | Inspection or Test: Method - Aggregate Perfomance Method TNZ T/10 section 12.3
75d28255-4d5d-54b5-93c4-2074b05f0a7f | note | Inspection or Test: Frequency - Each Site
d680da33-f163-5e99-99d0-5712ea61cd55 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
a9bf04e2-1eb4-558f-88f7-d0191cb8bfaf | note | Verifying Document - IANZ Report's
f3706845-c70b-5e1c-8589-cfceadca60aa | note | Inspection / Test Authority: Conduct - C
be6f65d1-2a54-5cad-9d7a-1aa4b9d767b2 | note | Inspection / Test Authority: Produce Record - C
7b5c6bc1-6542-52da-986c-024b14ae8a4c | note | Inspection / Test Authority: Approval - N
ea86ecd8-671c-5029-ad1d-481da58a09b4 | note | Hold Point - Y
43e899aa-3535-5b5b-a37d-2805ec001946 | note | Witness Point - Y
12cffd5c-5eaf-4ad4-a534-96dfbc6b5eba | signoff | HOLD POINT
62dc205f-3aa7-47e3-b9c5-137f45c62ef5 | checkpoint | Production Property - Cleaness Value
71ade3f1-c566-520e-a8a9-df41f45d2617 | note | Controlling Documents - NZTA P/17, M/6
c832ca80-7634-5d7d-a321-7f8f97d481cd | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
45bfc635-e68c-5078-a4cd-8e9ac8fce28a | note | Inspection or Test: Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
c4d658e5-1d7f-5ef7-adda-250ad7a6b8f0 | note | Inspection or Test: Frequency - Per Stockpile
5da5083b-3e24-541f-ab31-959e57fbcca3 | note | ○ <100m3 - 1 Sample
e2a2b1cb-fa80-50ba-aaec-4e9c8a8c5af4 | note | ○ 100-500m3 - 2 Samples
49c68e14-ccdb-5279-a606-aca9cd3549ce | note | ○ >500m3 - 3 Samples
7de23b40-200f-57ab-8dff-cde8158a75c2 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
b9b5f2e3-04a0-50cf-91b5-8f58c21452ec | note | Verifying Document - IANZ Report's
8b44cf80-ee0e-5a7a-866f-a8754629e68a | note | Inspection / Test Authority: Conduct - C
91727578-a604-5b32-b764-d8d983da7588 | note | Inspection / Test Authority: Produce Record - C
8b988ccc-f9fd-53c6-af20-20a0f7a9116d | note | Inspection / Test Authority: Approval - N
657c25a4-b7f5-5e66-9bfd-0e4b742dd1b5 | note | Hold Point - Y
b6f4da06-f6ae-57bd-ad61-fcd7758c28b2 | note | Witness Point - Y
bb2e732a-87f1-4214-92ef-b707a3f800e8 | signoff | HOLD POINT
c31952e6-ec48-45b7-b46e-dff897a01363 | checkpoint | Production Property - Particle Size/Shape
12dc22d9-38af-574a-876c-20cdec930d2b | note | Controlling Documents - NZTA P/17, M/6
07b847b7-f43f-5709-9a69-0263e71ac702 | note | Acceptance Criteria - As per Table 3 NZTA M/6
d47620ea-6830-547c-9276-fea99f058c00 | note | Inspection or Test: Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
87e4c356-f667-5301-a09c-41464f35f4f8 | note | Inspection or Test: Frequency - Per Stockpile
f0bac8cc-a45a-5d19-b8bb-0384bc331cc7 | note | ○ <100m3 - 1 Sample
3cafee66-79e3-50d6-9e1f-495d8203b576 | note | ○ 100-500m3 - 2 Samples
cdf8f64d-d556-5f68-b638-7dee5ebfb5a1 | note | ○ >500m3 - 3 Samples
3ff17c2d-8578-552d-baf4-cb14382aef68 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
04c811f2-ba37-5402-a0ee-16eee7156054 | note | Verifying Document - IANZ Report's
50170345-554f-5ee2-9c4e-c4518ebc5205 | note | Inspection / Test Authority: Conduct - C
630216fb-e25c-5486-9712-2e7182b85a96 | note | Inspection / Test Authority: Produce Record - C
d20bd9d5-ccd4-55d4-8656-2fbd80ac8f06 | note | Inspection / Test Authority: Approval - N
6ef3be3a-06f6-5e6f-8e44-479aca4c7a24 | note | Hold Point - Y
fc36a0b7-829b-5ee4-987f-b5c68eda943c | note | Witness Point - Y
8407ed70-7caa-450d-9fdb-04ce5de0a18e | signoff | HOLD POINT
3dea09fd-4e32-41c0-85a2-dbdd4d4fe455 | checkpoint | Production Property - Broken Faces
6a90846d-d559-5a9e-9c7a-d4d045cccec9 | note | Controlling Documents - NZTA P/17, M/6
fc8cca34-b414-50ce-9d3e-254b80932b63 | note | Acceptance Criteria - Min. 98%
6b975901-cc18-5b5f-8da4-da35cc03c3c8 | note | Inspection or Test: Method - Sample Test - Broken Faces NZS 4407 Test 3.14
11027f80-0de5-554b-87fc-9fd51e093417 | note | Inspection or Test: Frequency - Per Stockpile
dfbabb83-f3eb-5aab-b9e9-46a5afb812e8 | note | ○ <100m3 - 1 Sample
05a70086-8a24-5750-a2f6-dc72286c2823 | note | ○ 100-500m3 - 2 Samples
f4c0283f-50a7-5cad-a876-05a23436fe27 | note | ○ >500m3 - 3 Samples
270b70fb-3958-5f17-ae24-2ec6495a42d9 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
d22e5e94-1be7-5623-bedf-d5bfcea12550 | note | Verifying Document - IANZ Report's
1d3a3052-741e-5ce2-9ee1-e6ad7a36f693 | note | Inspection / Test Authority: Conduct - C
5fa47e63-844d-5d0f-821e-ff23a1c7d321 | note | Inspection / Test Authority: Produce Record - C
5a0a8ee6-4083-5ea4-a08f-98c6932452e4 | note | Inspection / Test Authority: Approval - N
ff2252f9-7ac9-5b75-b26a-45e5173d2b98 | note | Hold Point - Y
c7c01d37-ddd9-52f9-9e0b-4844e13ce861 | note | Witness Point - Y
32a8c764-09e4-47ff-a920-79f7e1bc00d6 | signoff | HOLD POINT
4e235870-1a58-4c09-bf3f-7d9b40ae5b07 | checkpoint | Chipseal Designs
c4b8b458-07ea-5e79-9dd5-7807b70c69ab | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
7365a8e0-5d19-5549-a26a-154768d663f3 | note | Acceptance Criteria - Client Approval
450faa8b-afb1-5171-985e-b3af9a13524c | note | Inspection or Test: Method - Review
be5bfec8-97df-5fb0-9051-1db890e5d1a9 | note | Inspection or Test: Frequency - Annual
3a7f83ec-a8ec-5c53-96dc-c980a8b7eb5a | note | Inspection or Test: Responsible Person - Surfacing Project Manager
506f901d-c7f6-5e07-ad49-ea99bb99b80a | note | Verifying Document - EBOP NOC Design Report Acceptance
ef87014e-f7c5-5017-8ee0-25b5a45506c3 | note | Inspection / Test Authority: Conduct - C
ca4d36cd-fc28-5da3-976e-660ed67ddf00 | note | Inspection / Test Authority: Produce Record - C
076132c2-2985-5df0-adbb-2eabaf29fb7c | note | Inspection / Test Authority: Approval - N
de0a611e-8de5-57b9-9328-be29d7986345 | note | Hold Point - Y
99f6d730-016e-50b6-a038-eaee3019a89d | note | Witness Point - Y
4a180e14-826d-4b05-84b0-057475095d48 | signoff | HOLD POINT
de106dc7-c1fc-480e-a8cf-397be20dbe09 | section | 5. Chip Sealing - 5.2. Construction - Chipseal Resurfacing
9768388b-27cd-4d8d-a2b6-c2b3d05e36b9 | checkpoint | Ensure limits of site are marked
974eaf39-5dcc-58a7-9e05-09507c808e2d | note | Controlling Documents - EBOP NOC Design Report
942fafb0-0d21-561b-bc69-45199a76930d | note | Acceptance Criteria - Visual Inspection
5dadb68a-052c-5fc7-bdac-68e3d0918552 | note | Inspection or Test: Method - Visual
a9009499-b5a9-5305-948f-9de3c2b3e9fe | note | Inspection or Test: Frequency - Prior to start sealing each site
675f4096-ef16-5a5a-b9fa-da5f2c79a38c | note | Inspection or Test: Responsible Person - Surfacing Supervisor
52849465-5cbb-51ca-bea0-f87c18784502 | note | Verifying Document - Chip Sealing Quality and Site Record
fc4777c5-047a-5508-b74e-794f4f5050be | note | Inspection / Test Authority: Conduct - C
f24880ea-9b0b-55ac-9fc1-0915e505d8ef | note | Inspection / Test Authority: Produce Record - C
1fff19f7-c28d-5989-951b-ce80629e2d07 | note | Inspection / Test Authority: Approval - C
99a98b8a-4d9b-5d9d-9907-20a2c37072b7 | note | Witness Point - Y
ef1cf6b2-b042-402a-b588-04a786cf7b04 | checkpoint | Sweep surface clean of deleterious material
bee14dbe-bc14-50b2-9096-9f2c51cd5881 | note | Controlling Documents - P/17
6ec1ae29-29d3-51a1-a86d-3cbdc871e2f7 | note | Acceptance Criteria - Visual Inspection
2d9b5f5b-8767-566f-9416-c8b82052fa2e | note | Inspection or Test: Method - Visual
7462c0bc-1a11-52b1-b8fc-5cccfdc38270 | note | Inspection or Test: Frequency - Each site, prior to start of sealing
fff0818a-6997-584f-bdcb-b44df8b65b84 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
1febdb2b-7419-5072-8081-2132c458e299 | note | Verifying Document - Chip Sealing Quality and Site Record
9a8b0a81-049f-5d15-99d9-e8b0a4aa34f1 | note | Inspection / Test Authority: Conduct - C
c0d08d68-e348-5a59-abc9-81e4c8f9434b | note | Inspection / Test Authority: Produce Record - C
103b8291-6dc6-5ec4-9148-c4bab291c459 | note | Inspection / Test Authority: Approval - C
f9ceb3e0-90a7-5c58-8e24-0355b2d4f165 | note | Witness Point - Y
adc658d0-b3a2-4ed7-bd29-b1f052f3e8c5 | checkpoint | Record ATP's on site
b020e3c3-409e-59b6-aaac-2660efb6758d | note | Controlling Documents - N/A
24b268ed-5983-54dc-b753-139b628eed5b | note | Acceptance Criteria - Visual Inspection
5d55c2a9-743d-5ee3-8e8d-49072f4b0625 | note | Inspection or Test: Method - Visual
85a5ea62-d013-5dec-9949-962aad069711 | note | Inspection or Test: Frequency - Each site, prior to start of sealing
dec6fa38-a71c-5191-9ed9-b055ad77c9a4 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
15ab2b6d-7d7c-5989-bd6e-95428f87bf87 | note | Verifying Document - Chip Sealing Quality and Site Record
77eb6323-03e8-5471-9777-ee4bff63de92 | note | Inspection / Test Authority: Conduct - C
88c86052-e7a3-5e0d-bec8-9c047d875de6 | note | Inspection / Test Authority: Produce Record - C
dd001849-bfab-5bd5-9a2b-195176820b75 | note | Inspection / Test Authority: Approval - C
32e5b7b9-7da0-52d5-81ea-1d209fdd0bf5 | note | Witness Point - Y
4d676fd4-3d40-4ce3-94d4-1b0de7b3fa78 | checkpoint | Confirm correct treatment(s) and chip
c4ee5018-2603-5b86-bd7e-9e3734db09ae | note | Controlling Documents - EBOP NOC Design Report
13f08974-9f64-52b8-a95f-376083d6874c | note | Acceptance Criteria - Details/chip correct
f649c9bb-c977-56ab-a60f-aa9abc287b72 | note | Inspection or Test: Method - Visual
5c508923-a58b-5d1b-846e-d64fcdbaffc7 | note | Inspection or Test: Frequency - Each Site
ea023d2e-a51f-536e-980c-8b968d2d50c1 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
d695141e-a885-522e-bcd4-0cc7e27d0d03 | note | Verifying Document - Chip Sealing Quality and Site Record
beff456f-1ddc-5cf1-8460-fb07a70e1f72 | note | Inspection / Test Authority: Conduct - C
c2f1049e-a561-521b-bd36-93a0db63b494 | note | Inspection / Test Authority: Produce Record - C
091e4260-8398-5fe6-a188-f712f806ed7e | note | Inspection / Test Authority: Approval - C
061d5a44-9037-51f4-8148-9bb522ddd901 | note | Hold Point - Y
6fa9ffd7-77d3-45c9-9db6-6668e546fbc1 | signoff | HOLD POINT
2088b9d8-4a83-4588-92c4-a5983b230a79 | checkpoint | Cutback Bitumen Blend
acaa9300-b755-5fe0-aa39-2c0a47768889 | note | Controlling Documents - RNZ 9803_0513
cf2ce8fe-6b89-5adf-acc0-bdf865575c23 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
54da722e-a077-56f0-aae6-5de0c08f5bc6 | note | Inspection or Test: Method - Sample and test
8df2adb5-3e34-5afd-8a40-a24984131150 | note | Inspection or Test: Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
55e68613-2c74-51fa-a11b-ee1dfb34dd00 | note | Inspection or Test: Responsible Person - Surfacing Project Manager, Surfacing Supervisor
feaa8160-7eae-578a-ada6-5f483a360aae | note | Verifying Document - IANZ Report's
4a81c43a-e4b3-5fa2-8eff-ce7551530680 | note | Inspection / Test Authority: Conduct - C
7356dbb5-070e-56e0-ad14-a41d04c97ceb | note | Inspection / Test Authority: Produce Record - C
e1065d15-d50a-5183-9027-9768eb9c18f4 | note | Inspection / Test Authority: Approval - C
9149dc9e-6377-50c8-aa3c-1370a68a30ea | note | Witness Point - Y
670c799d-3efe-4a4e-b163-69b8a651412b | checkpoint | Bitumen Application Rate
1d769371-60f4-533e-8fff-deaf10440ecc | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
9fe0ea53-8872-5c62-b5e6-e884104f2a17 | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
18070342-ab9a-5176-8c39-a567cbae4e82 | note | Inspection or Test: Method - Test, Review
af092809-78b7-57b1-b309-f6f5a19c10f7 | note | Inspection or Test: Frequency - Per Sprayer, Per Site
cb353c2c-c550-54cf-ade2-ec6a94d04e77 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
a1d8dcd7-630e-5eb5-a675-d8500d971705 | note | Verifying Document - E/2 Certificate. Spray Sheets
94d6ac3b-912f-50d9-b11b-0534fa2607f8 | note | Inspection / Test Authority: Conduct - C
0e5ae226-8c0c-5e28-9401-b194ff04688d | note | Inspection / Test Authority: Produce Record - C
470019c7-b686-5057-9d9c-bfda58b7088c | note | Inspection / Test Authority: Approval - C
90e25c87-b8a1-5c42-8d74-922d1f9b4a74 | note | Witness Point - Y
b3db02ae-969f-4691-b202-f8ee6c09af39 | checkpoint | Chip Application Rates
c3004fe6-7584-5fee-b464-85d2aa187fae | note | Controlling Documents - Chipsealing in NewZealand
46fa3574-5c1d-5f6d-9334-f6293c205e89 | note | Acceptance Criteria - As per Chipping Guide
174b0647-98e0-5092-acaf-9583651f46ad | note | Inspection or Test: Method - Visual
50a6c5f7-c4af-50df-848f-818674bd8176 | note | Inspection or Test: Frequency - Each Site
bdedeb94-5e77-540f-b88e-a474bd30f9cb | note | Inspection or Test: Responsible Person - Surfacing Supervisor
ed89b6e7-3c5b-54a8-b801-5046a184050a | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
9fd19b26-40de-52ca-b020-450a75f77600 | note | Inspection / Test Authority: Conduct - C
089146ba-01b7-5d1c-9b7a-4f4df664eb7b | note | Inspection / Test Authority: Produce Record - C
61b38901-1615-5b9e-9ebb-080604f082f2 | note | Inspection / Test Authority: Approval - C
2dca0b58-7c60-5b87-88dc-4d67a81ce7d7 | note | Witness Point - Y
990e5adc-1da6-4132-8f29-4d9c51ec8cf6 | checkpoint | Rolling
060f8246-b1c3-54df-9f9a-4d5cd8bca86e | note | Controlling Documents - Chipsealing in NewZealand
57dd87b1-07aa-571e-bc8b-acfa41f6ac7b | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
0f70b86b-aef3-5b0d-af05-56ed834ce353 | note | Inspection or Test: Method - Visual
b53e5b9d-ddea-521c-a44f-f3becb2466b0 | note | Inspection or Test: Frequency - Each Site
84220542-5a77-55f9-90a1-2ff6b50a2977 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
4a701846-39f4-5d5e-9066-8a595f14dad9 | note | Verifying Document - Chip Sealing Quality and Site Record
25b19d6d-6847-5ed5-918a-7b3ad25791ec | note | Inspection / Test Authority: Conduct - C
0b612aac-54d9-5beb-bd45-217170c4494e | note | Inspection / Test Authority: Produce Record - C
dbbc91f5-6a42-524c-9ab0-a3ee8b1b0be1 | note | Inspection / Test Authority: Approval - C
7af83484-6af0-5674-87c6-4dcceb50610d | note | Witness Point - Y
23361e86-4272-4c72-b1dd-2d91552bbc9c | checkpoint | Cleanup
c13a8cef-2f64-50c4-9b13-a0c4764023f8 | note | Controlling Documents - Chipsealing in NewZealand
a9009601-aba5-58d5-a522-f10e3b11ae04 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
21e04dfa-e7f7-54d6-8068-b17ab5a30bf8 | note | Inspection or Test: Method - Visual
61c7ac6c-072b-5c96-a3cd-273233ec5e66 | note | Inspection or Test: Frequency - Each Site
cba87b6e-4e29-5297-8c51-8c008e3019c1 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
4fb8e0a8-862e-5197-a4e8-47a2b8fa7db9 | note | Verifying Document - Chip Sealing Quality and Site Record
a11cbb86-3735-57a5-8c13-80c68ac5b834 | note | Inspection / Test Authority: Conduct - C
4d518479-dae7-58a1-92e2-a326a50489c4 | note | Inspection / Test Authority: Produce Record - C
afae2ad7-0596-51c7-bbbb-fa0427749a32 | note | Inspection / Test Authority: Approval - C
1e72c7ca-3d03-514f-838d-e6a63ff11582 | note | Witness Point - Y
9472dd57-1a18-4c17-8dc9-542ec3adb1c1 | checkpoint | Post Sweeping
86d61f42-6b3f-5e38-9d35-f4057c818f4a | note | Controlling Documents - Chipsealing in NewZealand
1cc735ce-dd91-5f81-af7a-45fe365b57fb | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
e14f80b6-f4a3-5fe9-8d16-998f864c3d01 | note | Inspection or Test: Method - Visual
1620f932-8087-5217-81d3-7e18f994423d | note | Inspection or Test: Frequency - Each Site
a8fa2b71-4a11-5e11-8e13-f2303a8f05f3 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
ed9aab1c-5310-51ec-876f-014fd8f94707 | note | Verifying Document - Site Record
2e7953a4-4d9a-5ebf-9adc-c7c9d6a34b5f | note | Inspection / Test Authority: Conduct - C
d3fad9ca-4f90-5b03-b6d1-da9693e24a39 | note | Inspection / Test Authority: Produce Record - C
da38be39-23c3-59f6-aec3-6bb994bb1321 | note | Inspection / Test Authority: Approval - C
024b01ea-c09b-5cf4-beb5-840f247d9ddb | note | Witness Point - Y
eb48e1be-b7ca-4e64-9802-351cc5750159 | checkpoint | Linemarking and RRPM Reinstated
f38e37ff-15a5-58a0-85a5-af1f3595dc34 | note | Controlling Documents - MOTSAM
5f291c9f-70d9-5db7-ac7d-f1c80bda337e | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
c80bb205-057d-5b36-8604-0a47a009208d | note | Inspection or Test: Method - Visual
3085da5b-032d-5076-99e9-506fe3ac0733 | note | Inspection or Test: Frequency - Each Site
9ad00148-843e-5aec-9be0-13bbaabf5cb4 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
02cb1f04-323e-5ee5-b0c6-449080b0b5f2 | note | Verifying Document - Site Record
5f0e9d40-fc0c-59a3-9cc7-7300f65907c9 | note | Inspection / Test Authority: Conduct - C
ef544a30-5ab6-5add-abe9-e7e11a883029 | note | Inspection / Test Authority: Produce Record - C
1c5b8443-3b78-5336-aa20-63a80ac467df | note | Inspection / Test Authority: Approval - C
31eae5e2-81df-5b4c-bf05-585b6c24ac48 | note | Witness Point - Y
94d3198b-6cbc-4694-a7be-398daf38c4a7 | section | 5. Chip Sealing - 5.3. Post Construction - Chipseal Resurfacing
4a2a9081-e432-4b31-bbe4-30b3f4d38fc8 | checkpoint | Post Construction Walkover
1bc92217-6cc9-5695-b19f-498e0b89f92d | note | Acceptance Criteria - Formal Agreement
335b9e90-d22a-53c7-9ec7-ca03ffa5d10a | note | Inspection or Test: Method - Visual Inspection
3890ded1-2f8b-5452-9075-b80eec89a662 | note | Inspection or Test: Frequency - Post seal sweep
8157b7cc-08be-550e-945e-c575a225ea13 | note | Inspection or Test: Responsible Person - Quality Controller, Supervisor and Engineer
6934802c-a1b6-5f75-9272-0d032923e399 | note | Verifying Document - Meeting Minutes
d2a5e754-c1ec-577c-b8e2-147abb8ad112 | note | Inspection / Test Authority: Conduct - C
a9d2bd7d-302a-559c-ae48-83e4d359c601 | note | Inspection / Test Authority: Witness - C, S and E
718b14a0-f822-5781-8978-1324d4978a11 | note | Inspection / Test Authority: Produce Record - C
1d253630-5682-5632-91d5-0b01939563e0 | note | Inspection / Test Authority: Approval - E
6132893f-fe2c-59ef-9cb7-0438f8f2631d | note | Hold Point - Y
e4269e17-6e74-48a3-a027-4a550de231bb | signoff | HOLD POINT
6adac9f6-a530-4581-9ae0-3148699a198a | checkpoint | Resurfacing Construction Completion report
a1b99809-52f1-520c-ad02-47827f4d6dfd | note | Controlling Documents - NOC; MS 6.1.3
d6642fb8-82f4-511b-b66c-37cd58a2e2a0 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
d6812163-6413-5ec3-9e6c-46f897c3606e | note | Inspection or Test: Method - Record
cbe3804a-549c-5a5e-a913-17c2ab397afe | note | Inspection or Test: Frequency - Within 2 months of completing the annual resurfacing programme
b9647098-18e9-5c29-8515-212229de11cb | note | Inspection or Test: Responsible Person - Surfacing Manager
ab1b27fe-d848-588b-9bf3-0239199104bf | note | Verifying Document - Construction Completion Report
59b01f2d-995f-5741-a799-c159db8043d1 | note | Inspection / Test Authority: Conduct - C
06d4c7ce-4ec5-5fb6-8241-b6a63028e5fb | note | Inspection / Test Authority: Produce Record - C
b3ced148-1839-5116-ab1e-9449fbaecb31 | note | Inspection / Test Authority: Approval - C
82744643-ea27-5109-9a94-b981173517d2 | note | Hold Point - Y
c59477eb-2e15-4351-8091-52c1fbd64883 | signoff | HOLD POINT
29ea31d0-5b41-4a6c-a93f-f73dbb2d836d | section | 6. Close Out
101f5f8c-1fd1-472e-9342-86a4b4a472bf | checkpoint | Pavement Rehabilitation Construction Completion Report
ff2e451a-94f0-51c7-930b-6b037da83123 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
a4b00e92-5aa3-57d1-a297-14ec824c878a | note | Acceptance Criteria - Engineer Approval
0570cef6-266c-531c-88d4-fef5ca3906d1 | note | Inspection or Test: Method - Visual Inspection
303031b3-3c8d-5154-af55-1285faf20389 | note | Inspection or Test: Frequency - ≤2 months of 1st Coat Seal
d55ca7ab-c198-5410-8247-3d30d298c190 | note | Inspection or Test: Responsible Person - Quality Controller/ Contract Manager
fbee4ba4-6d7a-5da6-b76e-3f1ab8c87862 | note | Verifying Document - Signed Report
2daaac08-bd30-5296-85b1-4966bad3d7c1 | note | Inspection / Test Authority: Conduct - C
1c6e4988-188d-54a8-ad5e-ac79ae6cbd02 | note | Inspection / Test Authority: Witness - C, S and E
3b6b15ef-1043-5b81-9f44-518bac7bc4ee | note | Inspection / Test Authority: Produce Record - C
5ee73653-b9e7-5e2e-93e3-fa5f0f343746 | note | Inspection / Test Authority: Approval - E
6c513263-ee5e-5f17-873f-ff8e95c0508e | note | Hold Point - Y
ded96e93-cbd2-4631-9d6a-d160ce7334b8 | signoff | HOLD POINT